## Sheet1
Project Name | Start date | Status | No Of Days | PM Notes | Action Date
Mansha Agencies | 2026-06-05 | Yet To Start | 4 | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week.
Muktangan Education Trust | 2026-06-05 | Active | 4 | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week.
Vivan Associate | 2026-06-04 | Active | 5 | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead.
CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | 2026-06-01 | Yet To Start | 8 | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday.
MANJUSHREE INNOVATIONS PVT. LTD | 2026-05-27 | Yet To Start | 13 | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well.
BFMS FACILITY MANAGEMENT PVT LTD | 2026-05-26 | Active | 14 | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review.
MULTI ORGANICS PVT LTD | 2026-05-25 | Yet To Start | 15 | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team.
AMAL EMBROIDERIES PVT. LTD | 2026-05-19 | Active | 21 | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same.
AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 2026-05-19 | Active | 21 | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know.
EMPREO PREMIUM PVT LTD | 2026-05-18 | Active | 22 | Live Salary Processing Planned for this Month
EMPREO WHEEL PVT LIMITED (MG) | 2026-05-18 | Active | 22 | Backend working is ongoing, training & implementation is planned.
SHREEKHETRA AUTOMOTIVE (TATA) | 2026-05-18 | Active | 22
CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | 2026-05-06 | Yet To Start | 34 | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority.
NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | 2026-05-04 | Active | 36 | Live Salary Processing Planned.
TRIO JEWELS PVT LTD Contractual | 2026-05-01 | Yet To Start | 39 | Same
GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | 2026-05-01 | Yet To Start | 39 | Ajit Ji to send correct updated files to Nagesh
VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | 2026-04-22 | Yet To Start | 48 | Feedback is positive, plan for live processing from June.
TRIO JEWELS PVT LTD | 2026-04-09 | Active | 61 | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license.
RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | 2026-04-07 | Active | 63 | Feedback is positive, User to resolve internal issues and plan for live processing from June.
SHRI JANARDAN SWAMI HOSPITAL (SJS) | 2026-04-06 | Yet To Start | 64 | Pranit to coordinate internally and align the implementation, team to coordinate for further activities
SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | 2026-04-02 | Active | 68 | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching.
STORM FINANCIAL SERVICES | 2026-03-28 | Active | 73 | April Salary Processed, Review Meeting
PANKAJ FASHION PVT LTD | 2026-01-09 | Active | 151 | Onsite Visit planned for 15th June
SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | 2026-01-05 | Active | 155 | Final Review on 11th June
FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | 2025-11-26 | Active | 195 | License has expired and on grace. Had asked for an extension of 10days, they would be paying the amount. Feedback is positive, User to resolve internal issues and plan for live processing from June.
NAIK MOTORS -GOA LOC | 2025-11-13 | Active | 208 | Live Salary Processing Planned for this Month
NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | 2025-11-13 | Active | 208 | Live Salary Processing Planned for this Month
WHISTLING WOODS INTERNATIONAL | 2025-10-01 | Active | 251 | PMS Implementation Ongoing
MEDIPULSE HOSPITAL | 2025-09-09 | Active | 273 | Live Salary Processing Planned for this Month