## Sheet1
Project Code | Project Type | Project Name | Received From | Start date | End Date | Priority | Status | PM Note | Risk Identified | Employee Count | Product | Assigned Engineer | Team Leader | Marketing Executive | Client Type
5001 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Schedule | 2025-01-07 | 2025-10-28 | Low | Completed |  |  | 1270 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost |  |  | 1100 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal
5003 | Escalation | Maharashtra Book Manufacturing | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Shubham Gurav | Nagesh Tiwari | Giriraj Birendrasingh Tomar | Normal |  | 35/79(100)
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 35 | NX | Paras Mahesh Ladva | Viral Panchal | Anuj Kumar Ganga Prasad Tiwari | Normal | 100% | 5/5(35)
5005 | Allocation | Bengal Energy_Staff | Schedule | 2025-01-08 | 2026-03-30 | Low | Completed |  |  | 550 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium |  | 2085/2085(2100)
5006 | Allocation | Bengal Energy_Worker | Schedule | 2025-01-08 | 2025-06-30 | Low | Lost |  |  | 1100 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium
5007 | Allocation | Parbhani Medical College | Schedule | 2025-01-13 | 2026-01-28 | Low | Lost |  |  | 500 | NG | Sushant Thombare | Shreyas Karkera | Jayesh Mojidra | Normal
5008 | Escalation | Aquaair International Frieght Services | Schedule | 2025-01-13 | 2025-04-25 | Low | Completed |  |  | 45 | NX | Nagendra Poojary | Viral Panchal | Jigar Rupani | Normal |  | 45/45(45)
5009 | Escalation | Hardcarb Technologies Private Limited | Maketing | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 250 | NX | Tejas Rajesh Baragade | Prathamesh Mandavkar | Amarprit Kaur | Normal |  | 162/180(180)
5010 | Allocation | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Schedule | 2025-01-14 | 2025-07-17 | Low | Completed |  |  | 125 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Ankur Yewalekar | Normal |  | 111/111(125)
5011 | Allocation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Schedule | 2025-01-14 | 2025-10-28 | Low | Completed |  |  | 350 | NX | Probian Biswas | Probian Biswas | Aparna Santosh | Premium |  | 234/255(300)
5012 | Escalation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Schedule | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Amit Krishnakant Tiwari | Shreyas Karkera | Ankur Yewalekar | Normal
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed |  |  | 270 | NX | Goraksha Pawar | Prathamesh Mandavkar | Amarprit Kaur | Normal | 100% | 178/182(270)
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Santosh Yadav | Prathamesh Mandavkar | Aparna Santosh | Normal | 100% | 29/29(30)
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 55 | NX | Hardik Panchal | Ganesh Jadhav | Pragnesh Panchal | Normal |  | 41/41(50)
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed |  |  | 80 | NX |  | Hiren Bhimani | Manisha Paradia | Normal | 100%
5017 | Escalation | Cartfire India | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 26 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal | 100% | 22/22(26)
5018 | Escalation | Sky Prints | Schedule | 2025-01-25 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Nagesh Tiwari | Viral Panchal | Manisha Singh | Normal |  | 53/60(100)
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed |  |  | 500 | NX | Vikas Yadav | Prathamesh Mandavkar | Pragnesh Panchal | Normal | 100%
5020 | Allocation | S K Traders | Schedule | 2025-01-31 | 2025-06-30 | Low | Completed |  |  | 25 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Premium
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 132 | NX | Darshit Pithwa | Hemanshu Wadia | Nikhil Solanki | Normal | 100% | 93/111(140)
5022 | Escalation | Infexn Laboratories | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 200 | NX | Shubham Gurav | Ganesh Jadhav | Nirbhay Kumar | Normal | 100%
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost |  |  | 70 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Normal
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed |  |  | 42 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Aparna Santosh | Normal
5025 | Allocation | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Schedule | 2025-02-18 | 2026-02-27 | Low | Completed |  |  | 465 | NX | Rahul Ankush Dalvi | Akshay Shinde | Sanket Gosalia | Premium
5026 | Allocation | RADIX ELECTROSYSTEMS PVT LTD | Schedule | 2025-02-18 | 2026-03-30 | Low | Completed |  |  | 630 | NX | Aditya Pathak | Probian Biswas | Pragnesh Panchal | Normal
5027 | Allocation | MARU CONSULTANCY SERVICES | Schedule | 2025-02-19 | 2025-06-04 | Low | Lost |  |  | 150 | NG | Ruchit Shailesh Patel | Probian Biswas | Manisha Singh | Normal
5028 | Allocation | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Schedule | 2025-02-24 | 2026-01-28 | Low | Completed |  |  | 300 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Manisha Singh | Premium
5029 | Allocation | APLAB LIMITED (FOR STAFF LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 165 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal
5030 | Allocation | APLAB LIMITED (FOR CONTRACT LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 251 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal
5031 | Escalation | NPSE AUTOMATION PVT. LTD | Schedule | 2025-02-12 | 2025-04-25 | Low | Lost |  |  | 55 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Amit Arjun Sawant | Normal
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed |  |  | 125 | NG | Vinay Kareliya | Vinay Kareliya | Tejas Kareliya | Normal
5033 | Allocation | KARVY TECHNOLOGIES PVT LTD | Schedule | 2025-03-03 | 2026-03-30 | Low | Lost |  |  | 130 | NG | Tejas Rajesh Baragade | Vinay Kareliya | Vaishali Ramniklal Puj | Normal
5034 | Allocation | QUALIGENS PHARMA PVT. LTD | Schedule | 2025-03-07 | 2025-10-28 | Low | Completed |  |  | 400 | NX | Ruchit Shailesh Patel | Probian Biswas | Giriraj Birendrasingh Tomar | Normal
5035 | Allocation | MADURA INDUSTRIAL TEXTILES LIMITED | Schedule | 2025-03-10 | 2026-04-28 | Low | Completed |  |  | 287 | NX | Varun Rajbhar | Vinay Kareliya | Jayesh Mojidra | Normal
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed |  |  | 700 | NG | Sahil Gadhave | Sahil Gadhave | Santosh Bhoja Shetty | Normal
5037 | Allocation | STEAM PULSE INDIA PVT LTD | Schedule | 2025-03-25 | 2025-10-28 | Low | Completed |  |  | 140 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal
5038 | Allocation | STEAM HARBOUR LOGISTICS PVT LTD | Schedule | 2025-03-25 | 2026-01-28 | Low | Completed |  |  | 60 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed |  |  | 1250 | NX | Sachin Thothawala | Sachin Thothawala | Tejas Kareliya | Normal
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed |  |  | 850 | NX | Kajal Inchanalkar | Saurabh Pednekar | Mehul Patel | Normal
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed |  |  | 60 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active | Mail received from NSCI, they have agreed with changing the salary cycle to 25th to 24th and implementation and training has been requested for 13th July, Team to plan the same. |  | 450 | NX | Mihir Navnath Mungekar | Vinay Kareliya | Sanket Gosalia | Premium
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed |  |  | 400 | NX | Amol Takkar | Amol Takkar | Tejas Kareliya | Premium
5044 | Allocation | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Schedule | 2025-04-01 | 2026-04-28 | Low | Completed |  |  | 1000 | NX | Kunal Joshi | Sahil Gadhave | Jayesh Mojidra | Premium
5045 | Escalation | SAI SANKET INDUSTRIES PVT.LTD | Schedule | 2025-04-01 | 2025-05-25 | Low | Completed |  |  | 410 | NX | Dakshesh D Nadkar | Viral Panchal | Nirbhay Kumar | Premium
5046 | Escalation | LOTUS TEXCOM INDIA LLP | Schedule | 2025-04-04 | 2025-07-23 | Low | Lost |  |  | 51 | NG | Prathamesh Mandavkar | Prathamesh Mandavkar | Sandeep Ashok Joundal | Normal
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed |  |  | 185 | NX | Probian Biswas | Viral Panchal | Tejas Kareliya | Normal
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed |  |  | 205 | NX | Vikas Yadav | Prathamesh Mandavkar | Nikhil Solanki | Normal
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed |  |  | 60 | NX | Supriya Waghmare | Hemanshu Wadia |  | Normal
5050 | Escalation | BASANT OVERSEAS | Schedule | 2025-04-25 | 2026-03-30 | Low | Lost |  |  | 1454 | NG | Yash Pankajkumar Shah | Akshay Shinde | Jayesh Mojidra | Normal
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost |  |  | 100 | NX | Rahul Ankush Dalvi | Viral Panchal | Aparna Santosh | Normal
5052 | Allocation | SNAPWORK TECHNOLOGIES PVT LTD | Schedule | 2025-05-03 | 2026-02-27 | Low | Completed |  |  | 360 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Normal
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 630 | NX |  | Hiren Bhimani | Rushabh Dinesh Shah | Normal
5054 | Allocation | BRIGHT BROTHERS LTD. / BRITE | Schedule | 2025-05-27 | 2026-02-27 | Low | Completed |  |  | 520 | NG | Rahul Ankush Dalvi | Akshay Shinde | Anuj Kumar Ganga Prasad Tiwari | Normal
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 45 | NX | Mayur Pendhari | Akshay Shinde | Manisha Singh | Normal
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed |  |  | 151 | NX | Shreyas Karkera | Shreyas Karkera | Vaishali Ramniklal Puj | Normal
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost |  |  | 25 | NX |  |  | Sanket Gosalia | Normal
5058 | Escalation | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-08-30 | Low | Completed |  |  | 51 | NX |  |  | Nirbhay Kumar | Normal
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 495 | NX | Amol Takkar | Amol Takkar | Sanket Gosalia | Premium
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 300 | NX | Mukeshkumar Shojiram kumavat | Nagesh Tiwari | Aparna Santosh | Premium
5061 | Allocation | GNG ELECTRONICS LIMITED STAFF | Schedule | 2025-06-01 | 2025-10-28 | Low | Completed |  |  | 250 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost |  |  | 750 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal
5063 | Allocation | ALLIED INSTRUMENTS PRIVATE LIMITED | Schedule | 2025-06-01 | 2026-03-30 | Low | Completed |  |  | 500 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Premium
5064 | Allocation | MESPACK INDIA PVT. LTD | Schedule | 2025-06-09 | 2026-04-28 | Low | Completed |  |  | 50 | NG | Pooja Vikas Shinde | Akshay Shinde | Sandeep Ashok Joundal | Normal
5065 | Allocation | UNITED AIR EXPRESS | Schedule | 2025-06-20 | 2026-04-28 | Low | Completed |  |  | 2550 | NG | Shubham Gurav | Nagesh Tiwari | Nirbhay Kumar | Normal
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost |  |  | 200 | NG | Santosh Yadav | Vinay Kareliya | Giriraj Birendrasingh Tomar | Normal
5067 | Escalation | ISA Logistics Private Limited | Schedule | 2025-06-19 | 2025-07-23 | Low | Completed |  |  | 200 | NG | Mihir Navnath Mungekar | Vinay Kareliya | Ankur Yewalekar | Normal
5068 | Escalation | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Support | 2025-06-27 | 2025-07-23 | Low | Completed |  |  | 250 | NX | Pritesh Barot | Viral Panchal | Nikhil Solanki | Normal
5069 | Escalation | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Schedule | 2025-07-12 | 2025-08-30 | Low | Completed
5070 | Escalation | CONTENDRE GREENERGY LIMITED | Schedule | 2025-07-15 | 2025-08-30 | Low | Completed
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed
5072 | Escalation | ROYAL EMBROIDERY THREADS PVT.LTD. | Schedule | 2025-07-17 | 2025-08-30 | Low | Completed
5073 | Escalation | V ALLIANCE NX | Schedule | 2025-07-18 | 2025-08-30 | Low | Completed
5074 | Escalation | UNITED AIR EXPRESS | Schedule | 2025-07-18 | 2025-08-21 | Low | Completed
5075 | Escalation | ESCON ELEVATORS PVT. LTD. | Schedule | 2025-07-23 | 2025-08-30 | Low | Completed
5076 | Allocation | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Schedule | 2025-08-02 | 2026-04-28 | Low | Lost
5077 | Allocation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Schedule | 2025-08-06 | 2026-04-28 | Low | Lost
5078 | Escalation | FFSERVICES PRIVATE LIMITED | CR | 2025-08-12 | 2025-11-28 | Low | Completed
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost
5080 | Allocation | SETHWALA FOODS LTD | Schedule | 2025-08-21 | 2026-05-26 | Low | Completed
5081 | Allocation | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Schedule | 2025-08-01 | 2026-01-28 | Low | Completed
5082 | Escalation | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Schedule | 2025-08-14 | 2025-09-24 | Low | Completed
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed
5084 | Escalation | VABA | Schedule | 2025-08-04 | 2025-10-28 | Low | Completed
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed
5086 | Escalation | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Schedule | 2025-08-22 | 2025-09-24 | Low | Completed
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 |  | Low | Active | User will be processing parallel salary for few months
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active | 2 Days Session to be aligned for query resolution
5093 | Escalation | DRS EARTHWORK PRIVATE LIMITED | Schedule | 2025-09-24 | 2025-11-28 | Low | Completed
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost
5095 | Escalation | PISCES CONTAINER LINES INDIA PVT. LTD. | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5097 | Allocation | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Schedule | 2025-10-08 | 2026-04-28 | Low | Completed
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed
5099 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active | PMS Configuration has been done
5101 | Allocation | VIVID ELECTROMECH LTD. / VIVID GROUP | Schedule | 2025-10-30 | 2026-04-28 | Low | Completed
5102 | Allocation | SREE METALIKS LTD | Schedule | 2025-11-11 | 2026-04-28 | Low | Completed
5103 | Escalation | NAGRIK CONSULTANCY SERVICES | Schedule | 2025-11-10 | 2026-02-27 | Low | Completed
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed
5109 | Allocation | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Schedule | 2025-11-26 | 2026-07-31 | Low | Completed | June 2026 Salary Completed with Attendance W26jul873.
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed
5111 | Allocation | NIKIKA ENTERPRISES LLP | Schedule | 2025-11-29 | 2026-05-26 | Low | Completed
5112 | Allocation | PRIJAI HEAT EXCHANGERS PVT. LTD. | Schedule | 2025-12-10 | 2026-04-28 | Low | Completed
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed
5114 | Allocation | PANKAJ FASHION PVT LTD | Schedule | 2026-01-09 | 2026-08-11 | Low | Lost | Client is not interested and said won't be renewing
5115 | Allocation | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Schedule | 2026-01-16 | 2026-04-28 | Low | Lost
5116 | Escalation | GNG ELECTRONICS LIMITED STAFF | Maketing | 2026-01-19 | 2026-01-22 | Low | Completed
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed
5118 | Escalation | Seventy Seven Entertainment Pvt Ltd | Schedule | 2026-01-19 | 2026-03-30 | Low | Completed
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active | Discussion done with Probian, he said they are providing support to the client and about the payment part, Roopa will be visiting the client next week for closing the same.
5120 | Allocation | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Schedule | 2026-01-31 | 2026-04-28 | Low | Completed
5121 | Allocation | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Schedule | 2026-02-09 | 2026-05-26 | Low | Completed
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed
5126 | Escalation | Elixrr Industries Pvt. Ltd. | Maketing | 2026-02-10 | 2026-04-28 | Low | Completed
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed
5128 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2026-02-25 | 2026-03-30 | Low | Completed
5129 | Allocation | STORM FINANCIAL SERVICES | Schedule | 2026-03-28 | 2026-07-31 | Low | Lost | Client is not responding and is not interested, mail has been shared and an Onsite visit scheduled along with Mukesh
5130 | Escalation | CIRCLE RESOURCES PRIVATE LIMITED | Schedule | 2026-03-12 | 2026-03-30 | Low | Completed
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active | Discussion done with Sheetal Ji, she said everything is aligned and progressing properly, they had some internal work and hence there is a little delay from their end they would be coordinating with Atul Ji post internal discussion for further plan of action.
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active | Review Call done with Sadhana, she said sorry and due to internal work processes she does not get time for spine. Tired to understand her processes, salary processing involved Accounts team, so informed her to let us have a common meeting to discuss the roles and accordingly segregate and start the training and implementation. Sadhana to discuss the same internally and arrange for a review meeting.
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | Review Call done with Siddhi, she said everything is streamlined, she highlighted mobile app related login issues informed her basic pratices like clearing the cache and app data etc and if it still doesnt work to raise a ticket, about the payment part she said she has already submitted it to the team for approval, and it will be cleared by the next week.
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active | PMS discussion has been done, May salary processed
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active | Akshaya is coordinating with the user, he has sent the updated data, but the integrated employee codes does not match, schedule has been aligned for the same.
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed
5137 | Escalation | VIPUL ORGANICS LTD. - STAFF | Schedule | 2026-05-01 | 2026-05-26 | Low | Completed
5138 | Allocation | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Schedule | 2026-05-04 | 2026-08-31 | High | Lost | Live Salary Processing planned
5139 | Allocation | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Schedule | 2026-05-06 | 2026-08-31 | High | Completed | Everything is aligned and leave configuration and live salary processing on going
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed | Live Salary Processing aligned
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active | Review Meeting done along with Partner Team, New HR has joined in, highlighted all the challenges and progress of all the 3 licenses, He said he will discuss and review the same internally and revert on the same.
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active | Payroll training completed, including **April, May, and June** salary processing. The payroll was processed and tallied successfully.
5146 | Escalation | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Schedule | 2026-05-19 | 2026-07-31 | High | Completed | Live Salary Processing
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost | Reminder sent to the user for data and further plan of action
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active | July Salary Processed, PMS Training on going.
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active | Discussion done with Stuti, everything is aligned properly, salary process done, HRMS training on going, Go-Live Planned for 15th July.
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active | Discussion done with Amey, Saloni is coordinating with the user, she said due to monsoon she is unable to connect as she stays at Karjat. Schedule to be planned for next week.
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active | Leave Module implementation planned
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed | The management has decided not to proceed further and is not willing to continue.
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active | Discussion done with Gajadatta, coordinated with Rishikesh ji, he has agreed for onsite training. Informed Gajadatta to coordinate with Amey for engineer's availability and plan onsite session accordingly and complete the implementation and training in one go.
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active | July month processed with new user Ms. Taniya
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active | Discussion done with Probian, Mayur is coordinating with Narendra for datafiles. From our end installation, key activation and document signing and confirmation has been done. Datafiles to be received by 15th July.
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active | Attendance Integration has been done successfully
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active | Implementation & Training Session has been aligned
5159 | Escalation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Schedule | 2026-06-23 | 2026-07-31 | High | Lost | Discussion done with Amit (Director), explained the current situation, he said Rajesh will coordinate and close the same. Discussion done with Probian, he said coodinated with Rajesh and resolved pending items and processed salary as well and about the payment they would be processing the same in a day or two.
5160 | Escalation | ANS NG | Schedule | 2026-06-24 |  | High | Active | Implementation & Training Sessions are ongoing.
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 |  | High | Active | Salary Processing Session planned
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 |  | High | Active | Discussion done with Amol Ji, he said datafiles explaination done sucessfully, client is not ready to share data until NDA. Client has shared NDA Form and will only proceed after NDA. Forwarded the same to Riddhi from Accounts team, informed the same to Amol Ji.
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active | Training and implementation ongoing
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active | Review call done with Rahul, he said everything is proper, he was busy in payroll and Archana is connecting properly. He said initial training is done, he will now verify everything and again connect with Archana and plan for login roll out as well.
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active | Datafiles Received
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active | Payroll implementation and training ongoing
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active | Payroll, workflow setup and Attendance Integration has been done successfully, training ongoing.
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active | working on data files.
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Yet To Start
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Yet To Start
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active
5176
5177
5178
5179
5180
5181

## Go Live Followup
Project Code | Project Name | Status | Completed Date | Client Interaction Date | Vists / Call | Remark | Feedback | Scope of UpSelling
5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Completed
5003 | Maharashtra Book Manufacturing | Completed
5004 | PLASMA RESEARCH TRUST NX | Completed
5005 | Bengal Energy_Staff | Completed
5008 | Aquaair International Frieght Services | Completed
5009 | Hardcarb Technologies Private Limited | Completed
5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Completed
5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Completed
5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Completed
5013 | Metafab | Completed
5014 | Texple | Completed
5015 | ERMELLI PRIVATE LIMITED | Completed
5016 | Helen Keller Institute for Deaf & Blind | Completed
5017 | Cartfire India | Completed
5018 | Sky Prints | Completed
5019 | Cogencis | Completed
5020 | S K Traders | Completed
5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Completed
5022 | Infexn Laboratories | Completed
5024 | Emmay Entertainment | Completed
5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Completed
5026 | RADIX ELECTROSYSTEMS PVT LTD | Completed
5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Completed
5029 | APLAB LIMITED (FOR STAFF LICENSE) | Completed
5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | Completed
5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Completed
5034 | QUALIGENS PHARMA PVT. LTD | Completed
5035 | MADURA INDUSTRIAL TEXTILES LIMITED | Completed
5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Completed
5037 | STEAM PULSE INDIA PVT LTD | Completed
5038 | STEAM HARBOUR LOGISTICS PVT LTD | Completed
5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Completed
5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Completed
5041 | TATARIA HARDWARE INNOVATION | Completed
5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Completed
5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Completed
5045 | SAI SANKET INDUSTRIES PVT.LTD | Completed
5047 | BRILLIANT POLYMERS PVT. LTD | Completed
5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Completed
5049 | TAO AUTOMATION SERVICES PVT LTD | Completed
5052 | SNAPWORK TECHNOLOGIES PVT LTD | Completed
5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Completed
5054 | BRIGHT BROTHERS LTD. / BRITE | Completed
5055 | ARMITA INDIA SHIPPING PVT. LTD | Completed
5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Completed
5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Completed
5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Completed
5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Completed
5061 | GNG ELECTRONICS LIMITED STAFF | Completed
5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | Completed
5064 | MESPACK INDIA PVT. LTD | Completed
5065 | UNITED AIR EXPRESS | Completed
5067 | ISA Logistics Private Limited | Completed
5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Completed
5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Completed
5070 | CONTENDRE GREENERGY LIMITED | Completed
5071 | ILEAF RITZ BANQUETS | Completed
5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | Completed
5073 | V ALLIANCE NX | Completed
5074 | UNITED AIR EXPRESS | Completed
5075 | ESCON ELEVATORS PVT. LTD. | Completed
5078 | FFSERVICES PRIVATE LIMITED | Completed
5080 | SETHWALA FOODS LTD | Completed
5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Completed
5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Completed
5083 | FUJIYAMA POWER SYSTEM (UTL) | Completed
5084 | VABA | Completed
5085 | KISHAN LAL PAWAN KUMAR JAIN | Completed
5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Completed
5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Completed
5088 | POLMOR STEEL PRIVATE LIMITED | Completed
5089 | ACEY ENGINEERING PVT. LTD | Completed
5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Completed
5093 | DRS EARTHWORK PRIVATE LIMITED | Completed
5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Completed
5096 | AUROUS JEWELS LLP | Completed
5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Completed
5098 | RENMAKCH INDIA PVT. LTD. | Completed
5099 | GNG ELECTRONICS LIMITED FACTORY | Completed
5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | Completed
5102 | SREE METALIKS LTD | Completed
5103 | NAGRIK CONSULTANCY SERVICES | Completed
5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed
5105 | ANUH PHARMA PVT. LTD NX | Completed
5106 | NAIK MOTORS -GOA LOC | Completed
5107 | PPKG AND CO | Completed
5108 | DOSHI MEDICARE PRIVATE LIMITED | Completed
5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Completed
5110 | COSMOS IMPEX INDIA PVT LTD NG | Completed
5111 | NIKIKA ENTERPRISES LLP | Completed
5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | Completed
5113 | parvathyhospital | Completed
5116 | GNG ELECTRONICS LIMITED STAFF | Completed
5117 | Talib and Shamsi Constructions Pvt. Ltd. | Completed
5118 | Seventy Seven Entertainment Pvt Ltd | Completed
5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Completed
5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Completed
5122 | Procon RMC | Completed
5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Completed
5124 | SUNRISE FOODS BANGALORE | Completed
5125 | NOTCH INDIA PROJECTS | Completed
5126 | Elixrr Industries Pvt. Ltd. | Completed
5127 | GUARDIAN CASTING PVT. LTD | Completed
5128 | GNG ELECTRONICS LIMITED FACTORY | Completed
5130 | CIRCLE RESOURCES PRIVATE LIMITED | Completed
5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed
5136 | Navio Shipping | Completed
5137 | VIPUL ORGANICS LTD. - STAFF | Completed
5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Completed
5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed
5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Completed
5153 | Vivan Associate | Completed
5165 | Navio Shipping | Completed