## project_master.xlsx
Client Code | Project Code | Type | Client Status | Client Name | Priority | Class | Co-ordinator | Team Leader | Project AC Date | Implementation Engg | DI/CH | Support Partner Type | Support Partner | Project MKT | Project Team Manager | Project Manager | Client Type | No. Emp | Amc Date | Project Start Date | Project Installation Date | Project Implementation Date | Project Managed By | Project Close Date | Title | Type of Product | Balance Flag | Achived Percent | Project Product | Status | Project Mode | Project Remark | Project Update | Project Balance Payment | Bal Pay Month | Last Processed Year Month
SPA111958261609 | 9736 | New | Account Activated | ALSHIFA MULTISPECIALTY HOSPITAL | Premium | E | Ritika Dilip Singh | Shreyas Karkera |  | Gaurav Karmokar | Channel |  |  | Jayesh Mojidra | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 330 | 2027-01-31 | 2026-09-16 |  |  | ENGG |  | NG, ESSM, TAM, LV | Fresh | 1 | 0 | Spine NG | Pending For Milestone | Online | #16/09 - eng - Client will share the data by 18th, Planning to do the further working by 19th / 21st, and will start trng from 23rd sept. (rcvd project delivery file) |  | #excess amount to be adjusted while client pays the implementation amount. | 0 | 0
SPN111933260109 | 9705 | Conv | Account Activated | NAVKAR CORPORATION LIMITED NG | Normal | E | Ankita Bankar | Akshay Shinde |  | Yash Pankajkumar | Direct |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 1000 | 2027-02-28 | 2026-09-17 |  |  | ENGG |  | Con NG,LV,TAM,ESSM | Fresh | 1 |  | Spine NG | Pending For Milestone | Online | Welcome mail done - 17th Sep |  | #Received total module cost +18%GST on that cost deducting 10%TDS on that amount #remaining DMC +server setup cost Payable within 10 days from the date is installation | 0 | 0
SPM111927263108 | 9702 | New | Account Activated | MAHATMA PHULE CHARITABLE TRUST | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 325 | 2026-11-30 | 2026-09-05 |  |  | ENGG |  | NG,ESSM,LV,TAM | Fresh | 1 | 0 | Spine NG | Pending For Milestone | Online | Engineer connect client will proceed for datafile and corp id |  | 50% of total cost and its GSTreceived The balance 50% and its GST will be received after 60 days of implementation or 3 months of live payroll, whichever is earlier | 0 | 0
SPS111926263108 | 9698 | New | Account Activated | SURANA CHARITABLE TRUST | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Tejas Rajesh Baragade | Direct |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 117 | 2026-11-30 | 2026-08-31 |  |  | ENGG |  | NG,ESSM,TAM,LV | Fresh | 1 |  | Spine NG | Pending For Milestone | Onsite | Engineer said user princy said will connect on wednesday and till friday will share the data. #17/09 - eng - workflow & policy pending from user, else we rcvd all datafiles |  | 50% of total cost and its GST received Balance 50% and its GST will bewill be received after 60 days of implementation or 3 months live payroll whichever is earlier |  | 0
SPS107604233107 | 9669 | Conv | Account Activated | SAI SANKET INDUSTRIES PVT.LTD. NX | Normal | E | Ankita Bankar | Amey Telge |  | Vijay Bugde | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 251 | 2027-07-31 | 2026-08-27 |  |  | ENGG |  | CONVNG, EXP | Conversion | 0 |  | Spine HRMS | Pending For Milestone | Online | Welcome mail done - 28th August User is processing salary internally of August month & will share us downtime tent. @ 7-8 sep for conversion user is busy in processing & will let us know the dates for conversion - 8th Sep As per discussed with user, we have started pre-conversion working from 16th sep |  | NA | 0 | 0
SPJ111881261908 | 9644 | New | Account Activated | JIET MEDICAL COLLEGE HOSPITAL | Premium | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 800 | 2026-11-30 | 2026-08-19 | 2026-09-15 | 2026-09-15 | ENGG |  | NG,ESSM,LV,TAM,ONBO,OFFBOR,EXP | Fresh | 1 | 0 | Spine NG | Active | Online | As discussed with salman ji he said we are still in discussion with partner as we bot were busy so not yet discussed will discuss soon and let you know there is no much difference in data and I am only the spoc for this license too. |  | 100% subcription cost against the commercial and its GST - received 100% server setup and its GST will be paid after installation | 0 | 0
SPF111878261308 | 9636 | New | Account Activated | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY | Normal | E | Ankita Bankar | Shreyas Karkera |  | Tushar More | Direct |  |  | Ankur Yewalekar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 300 | 2027-08-31 | 2026-08-13 | 2026-08-17 | 2026-08-24 | ENGG |  | NG,ESSM,LV,TAM,EXP | Fresh | 1 | 84 | Spine NG | Active | Online | Welcome mail done - 13th August Datafiles expalantion done on 14th Aug Datafiles rcvd & checking is going on - #E26aug4289 Online traning started from 24th August We have completed spineNG payroll HRMS & mobile Application training. July month processed & tallied SMTP configuration done. - W26aug9351 we have processed salary for the month of August 2026 and tallied - W26sep2575 |  | 50% of total cost and 50% implement charges and full GST receivd Balance 50% of the total cost and implement charges will be received after 2 salary processes. | 0 | 0
SPC111844263107 | 9596 | New | Account Activated | CREATIONS BY SHANGAR | Premium | E | Ankita Bankar | Akshay Shinde |  | Yash Pankajkumar | Direct |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2026-10-31 | 2026-07-31 | 2026-07-31 | 2026-08-21 | ENGG |  | NG,ESSM,LV,TAM,OB | Fresh | 0 | 76 | Spine NG | Active | Onsite | Welcome mail done - 31st onsite kick-off done - 3rd August Installation done As per dis done with user, will share us data by 10th August tent. user will share us data after 15th August Datafiles followup - W26aug5008 Employee master rcvd & checking is going on Working started from 21st August due to changes in data yet training not started, engineer will visit onsite from 11th Sep to start payroll training of one by one location |  | NA | 0 | 0
SPV111792261307 | 9538 | New | Account Activated | VISHWAKARMA FOUNDERS (I) PVT. LTD. - STAFF | Normal | E | Ankita Bankar | Shreyas Karkera |  | Archana Ramesh Pawar | Direct |  |  | Manisha Singh | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 101 | 2027-08-31 | 2026-07-13 | 2026-07-21 | 2026-07-28 | ENGG |  | NG,ESSM,LV,TAM,PMS,TS | Fresh | 1 | 73 | Spine NG | Active | Online | Welcome mail don - 13th July Kick-off done on 14th July EMP master file rcvd Working started from 28th July Online meeting started from 4th august Traning & Implementation of Payroll is completed along with June month tallied - E26aug1816 training for the Staff HRMS & Employee Individual Login module. Training for the Worker module will continue next week. - 20th August July month salary processed - E26aug4362 August month attendance regulatization is going on & will conclude till 10th Sep September month live salary target |  | NEFT Received as on 10/07/2026 Full GST received, 35% payment received, remaining 65% will be paid in August after salary is processed | 0 | Jul-26
SPV111791261307 | 9537 | New | Account Activated | VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | Normal | E | Ankita Bankar | Shreyas Karkera |  | Archana Ramesh Pawar | Channel |  |  | Manisha Singh | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 100 | 2027-07-31 | 2026-07-13 | 2026-07-21 | 2026-07-28 | ENGG |  | NG,TAM | Fresh | 0 | 9 | Spine NG | Active | Online | Welcome mail on - 13th July Kick-off done on 14th July Working started from 28th July Online meeting started from 4th august Traning & Implementation of Payroll is completed along with June month tallied - E26aug1816 training for the Staff HRMS & Employee Individual Login module. Training for the Worker module will continue next week. - 20th August August month attendance regulatization is going on & will conclude till 10th Sep September month live salary target |  | NA | 0 | Jul-26
SPA111227263101 | 9521 | Add Mod | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Disha Kiran Kargutkar |  | 2026-08-07 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 660 | 2027-02-28 | 2026-07-07 | 2026-07-07 | 2026-07-07 | OS | 2026-08-07 | TS | Fresh | 0 | 0 | Spine NG | Go LIVE | Online | Training done Client is live processing. Time sheet module also live. |  | RECEIVED |  | 0
SPH111773260307 | 9514 | New | Account Activated | HELL ENERGY PVT LTD | Normal | E | Karuna Rajaram Sandim |  | 2026-09-02 |  | Channel |  | MIRACLE TECHNOLOGIES | Sanket Gosalia | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 550 | 2027-06-30 | 2026-07-03 | 2026-07-10 | 2026-07-28 | PARTNER |  | NG, ESSM, LV, TAM, EXP,PMS, ON-OFF BOARD | Fresh | 0 | 85 | Spine NG | AC | Onsite | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) |  | 100% payment rcvd to partner | Jun-26,Jul-26,Aug-26 | Aug-26
SPA111771260207 | 9512 | New | Account Activated | AKRITI PHARMACEUTICALS PVT LTD | Normal | E | Ankita Bankar | Sahil Gadhave |  | Ankush Rampyare Rajbhar | Channel |  |  | Bhavin Nitin Naik | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 310 | 2027-07-31 | 2026-08-03 | 2026-08-17 | 2026-08-20 | ENGG |  | NG,ESSM,LV,TAM,off-boarding | Fresh | 1 | 96 | Spine NG | Active | Online | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance |  | 55% received with full GST extra amount received to be adjusted with the pending 45% of the balance, which will bereceived after implementation or 60 days, whichever is earlier | 0 | Aug-26
SPA111227263101 | 9465 | Add Mod | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Disha Kiran Kargutkar |  | 2026-09-12 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 660 | 2027-02-28 | 2026-06-25 | 2026-06-25 | 2026-06-30 | OS | 2026-09-12 | exp | Fresh | 0 | 0 | Spine NG | Go LIVE | Onsite | training done expense explaination also given |  | Billing to vincible, 50% of yearly subscription + 50% gst pending to be paid whithin 90 days from the date of purchase (Note - Pending with client Client paid 40% oftotal cost which is 40% of subscription + 40% of SS + 40% of IMPL + 40% gst)(received) |  | 0
SPC111708261806 | 9442 | New | Account Activated | CKIM PROMOTERS LLP | Normal | E | Disha Kiran Kargutkar | Amey Telge |  | Ankita Gupta | Channel |  |  | Swati Sangani | Viral Panchal | Vasu Mohan Dusa | SAAS | 120 | 2026-12-31 | 2026-06-18 | 2026-07-03 | 2026-07-07 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 92 | Spine NG | Active | Online | PayrollNx trainig completed. HRMS Training done Attendance Integration completed-E26aug1380 Employee trng done queries and hrms confirgurations is going on Aug salary will be parallel as few employees has not done a proper regularization for their attendance. so sept will be target for FC. Aug salary in 2 days with attendance |  | Full payment receive | May-26,Jun-26,Jul-26 | Jul-26
SPV111703261706 | 9436 | Add Mod | Account Activated | VED INDUSTRIES | Normal | E | Ritika Dilip Singh | Sahil Gadhave |  | Dhanashree Dalvi | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 300 | 2027-06-30 | 2026-06-17 | 2026-06-19 | 2026-06-19 | ENGG |  | NG, TAM, HR | Fresh | 1 | 42 | Spine HRMS | Active | Online | handholding done queries are getting handled #3/08 - eng - everything is sorted, awaiting for salary calculation, today she is on off, will connect her tomorrow. #4/08 - eng - today calculation configure done, trng for payroll processing will be provided as per user's availability. #19/08 - user is out of town, will connect only after monday. #25/08 - eng - user will connect on thursday #17/09 - As discussed, there office is closed today, we asked for his avaialbility he disconnected the call. later i tried again, but no response, so i dropped a msg in our whatsapp.. |  | Extra amount of first 70% balance to be adjusted with the balance 30% + full GST, which will be received by next month. | 0 | 0
SPI111677260206 | 9398 | New | Account Activated | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | Normal | E | Ankita Bankar | Amey Telge |  | Ankita Gupta | Channel |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2026-08-31 | 2026-06-09 | 2026-06-15 | 2026-06-17 | ENGG |  | NG, ESSM, LV, TAM, EXP,ELC | Fresh | 0 | 48 | Spine NG | Active | Online | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion |  | NA |  | Jul-26
SPS111671263005 | 9392 | New | Account Activated | SACRED HEART HOSPITAL JAL | Premium | E | Disha Kiran Kargutkar | Amey Telge | 2026-09-11 | Mayur Pendhari | Channel |  |  | Jayesh Mojidra | Viral Panchal | Vasu Mohan Dusa | On-Premises | 801 | 2027-05-31 | 2026-06-10 | 2026-07-02 | 2026-07-27 | ENGG |  | NG,ESSM,LV,TAM,ELC,MOBHR | Fresh | 1 | 88 | Spine HRMS | AC | Online | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul | #50% Payment along with full gst received #30% payment will be released once the implementation will start, till tan welcome email will be on hold till 10th June. #20% Payment will be done after completion of implementation and salary processing | NA | NA
SPC111653263005 | 9374 | New | Account Activated | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | Normal | E | Ankita Bankar | Vinay Kareliya |  | Santosh Yadav | Channel |  | SOFTCORE SOLUTIONS PVT. LTD. | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 550 | 2027-05-31 | 2026-06-02 | 2026-06-10 | 2026-06-24 | ENGG |  | NG,ESSM,LV,TAM,PMS, Help Desk, Off-Boarding, & On- | Fresh | 1 | 54 | Spine NG | Active | Online | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NX & live target month for processing is August month |  | 80% payment rcvd to spine with full GST remaining 20% rcvd after first salary process. | 0 | Aug-26
SPM111635262705 | 9354 | New | Account Activated | MANJUSHREE INNOVATIONS PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Amey Telge |  | Mayur Pendhari | Channel | SA | Data Crown Computer Consultancy. - SA | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 370 | 2027-05-31 | 2026-05-27 | 2026-06-02 | 2026-06-15 | ENGG |  | NG,ESSM,LV,TAM,ELC,PMS,RCT | Fresh | 0 | 70 | Spine NG | Active | Online | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. aug live payroll will try. |  | NA | May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPA111591261305 | 9304 | New | Account Activated | AMAL EMBROIDERIES PRIVATE LIMITED | Premium | E | Disha Kiran Kargutkar | Amey Telge | 2026-08-04 | Vijay Bugde | Direct |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1200 | 2027-04-30 | 2026-05-19 | 2026-06-02 | 2026-06-04 | ENGG |  | NG,ESSM,LV,TAM,PMS,Off-Boarding & OnBoarding,RCT | Fresh | 1 | 91 | Spine NG | AC | Onsite | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. |  | #we received the 75% of product cost + Full server setup + Full gst on whole amount #the excess amount of first 75% balance needs to be adjusted with the balance pending #Balance 25% of License cost Payable after 30 days or 1 month payroll live whichever is earlier called for feedback but unable to connect dropped msg on whatsapp but they have seen but no reply on it. | July-25,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPA108616242604 | 9283 | Conv | Account Activated | ANS NG | Normal | E | Ankita Bankar | Amey Telge | 2026-09-07 | Aditya Mazire | Direct |  |  | Vaishali Ramniklal | Viral Panchal | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2026-05-04 | 2026-05-14 | 2026-05-20 | ENGG |  | Conv NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | AC | Onsite | Welcome mail on - 4th May Installation done & conversion done Onsite training aligned on 25th May Database Handholding confirmation - E26may9526 Traninig of Payroll is completed - E26may10825 HRMS training & Impementation is done - E26jul3101 | salary based on attendance from August 2026 onwards. | NA | 0 | Aug-26
SPN111575260205 | 9280 | New | Account DeActivated | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | Normal | E | Ankita Bankar | Vinay Kareliya |  | Mihir Navnath Mungekar | Channel |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 400 | 2026-07-31 | 2026-05-04 | 2026-05-11 | 2026-05-26 | ENGG | 2026-08-05 | NG,LV,TAM | Fresh | 0 | 85 | Spine NG | Lost | Online | Project Lost -Mr. Ravi informed us that they will not be renewing the software due to low utilization by their staff & a lack of acceptance of automation within the organization. He appreciated our software and support; however, management has decided not to continue with the renewal. Welcome maild on 4th May Project delivery rcvd Training & Implementation of Payorll is completed along with April month tallied - HRMS modules Training & Implementation is done Attendance integration is done Logins rolled out to employees - E26may6183 Live salary with attednace proceed of June month for some employees | July wth attendance | # full advance payment received |  | Jun-26
SPB111573263004 | 9276 | New | Account Activated | BSA CORPORATION LIMITED | Premium | E | Divya Bhide | Amey Telge |  | Nagendra Poojary | Channel | SP | SHRADDHA INFOSYSTEMS | Rushabh Dinesh Shah | Viral Panchal | Vasu Mohan Dusa | SAAS | 1000 | 2027-05-31 | 2026-06-08 | 2026-07-22 | 2026-06-19 | ENGG |  | NG,ESS,LV,TAM,ON,OFF | Fresh | 1 | 20 | Spine NG | Active | Online | onboard training done- additional field req-E26jul9751, payroll training 4/8 july tallied, bio int done 1 plant, sql not in our format, payment pending - add emp | Icici integration discusson ongoing | 20% payment received. ---- 40% upon the processing of the second salary 40% upon the processing of the third salary | Jul-26 | Jul-26
SPC111560263004 | 9261 | New | Account Activated | CAM TOOLS INDUSTRIES PVT LTD | Normal | E | Ankita Bankar | Shreyas Karkera | 2026-08-13 | Harsh Dilip Ashar | Direct |  |  | Tejas Kareliya | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 315 | 2026-10-31 | 2026-05-05 | 2026-05-06 | 2026-05-20 | ENGG | 2026-09-11 | NG,ESSM,LV,TAM | Fresh | 0 | 110 | Spine NG | FC | Onsite | Project Live- Training & Implementation is done along with April month tallied - W26may10013 Attendance inetgration is done Logins rolled out June month with attednace done & July month processed with attedance Leave policy is pending from client's end, they will share as per their convience- E26sep4961 processed Live salary for the month of August- E26sep3629 | NA | NA |  | Aug-26
SPM111555263004 | 9257 | New | Account Activated | MULTI ORGANICS PVT LTD | Normal | E | Ankita Bankar | Vinay Kareliya |  | Mihir Navnath Mungekar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 350 | 2027-04-30 | 2026-05-23 | 2026-07-17 | 2026-07-25 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 1 | 95 | Spine NG | Active | Onsite | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out | NA | 80% of the total cost and Full GST received Balance 20% will be received after successful implementation | 0 | Jul-26
SPG109930253101 | 9242 | Conv | Account Activated | GNG ELECTRONICS LIMITED STAFF | Normal | E | Ankita Bankar | Nagesh Tiwari | 2026-07-15 | Nagesh Tiwari | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 370 | 2027-04-30 | 2026-04-28 | 2026-06-11 | 2026-06-12 | ENGG | 2026-08-14 | Conv NG | Fresh | 0 | 110 | Spine NG | FC | Online | Project Live - Conversion to NG is done & Handholding confirmation - E26jun4559 Online Training is completed - E26jun6574 JUN (E26jul1005) & JUL (E26aug3785) Month salary processed from system | NA | NA |  | Aug-26
SPV111527262204 | 9224 | New | Account Activated | VOGUE N HYDE PVT. LTD | Premium | E | Ritika Dilip Singh | Vinay Kareliya |  | Akshaya Patil | Channel |  |  | Aparna Santosh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1000 | 2027-04-30 | 2026-04-22 | 2026-04-27 | 2026-05-25 | ENGG |  | NG, TAM | Fresh | 0 | 94 | Spine NG | Active | Online | training and impl confirmation- W26may10964 E26may10665 they process salary on weekly basis client is opting 500 employee count post implementation if the same they will process may integration done logins not going to roll out july targetted as salary with attn #29/07 - eng - worker salary register is pending from user end. else everything is done. #30/07 - regarding his few queries, he tried connecting akshaya today, but she was quite allocated on another call, user told, he is available tomorrow we can connevct him. #3/08 - ENG - we're working on staff salary, once it is completed then will proceed with worker too. #6/08 - eng - will do with attendance salary for the first time with july, they are working on attendance regularisation and then will connect for salary processing by 10th. today we'll create and share the attendance report to user. #27/08 - eng - as user is on leave today, they will connect tomorrow for dummy salary #3/09 - as discussed with user surojit, salary configuration is done, they will recheck and update us, will process salary with attendance by 10th sept. #10/09 - eng - attendance regularizing is going on, but not completed bcoz of MD's unavailability, once he approve, they will proceed with the same, by tomorrow. #17/09 - eng - user has raised a requirement related to salary register, will complete it by tomorrow. | July with attendance | NA | 0 | Aug-26
SPT111503260904 | 9192 | New | Account Activated | TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-05-21 | Mukeshkumar Shojiram kumavat | Direct |  |  | Vaishali Ramniklal | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 151 | 2027-04-30 | 2026-04-09 | 2026-04-13 | 2026-05-13 | ENGG | 2026-08-13 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Payroll training completed-E26apr9978 Hrms training completed-E26apr11242 April salary processed and tallied-E26may4682 May salary done-E26jun6874 contrctual attendance will be by uploading June salary processed. july salary processed | NA | NA | Apr-25,May-26,Jun-26,Jul-26 | Jul-26
SPT111502260904 | 9191 | New | Account Activated | TRIO JEWELS PVT LTD | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-07-17 | Mukeshkumar Shojiram kumavat | Direct |  |  | Vaishali Ramniklal | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 301 | 2027-04-30 | 2026-04-09 | 2026-04-13 | 2026-04-24 | ENGG |  | NG,ESSMLV,TAM,PMS,RCT | Fresh | 0 | 91 | Spine NG | AC | Onsite | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. We are available to initiate the process next week. Please let us know a suitable date and time to take this forward. |  | NA | Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPS111486260104 | 9164 | New | Account DeActivated | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Premium | E | Disha Kiran Kargutkar | Probian Biswas |  | Bhavika Gite | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 251 | 2026-06-30 | 2026-04-04 | 2026-04-13 | 2026-04-29 | ENGG | 2026-08-06 | NG,ESSM,LV,TAM | Fresh | 0 | 50 | Spine NG | Lost | Online | Payroll training done hrms training done april tallied may salary process june salary process integration is pending As per the user's update, due to heavy rainfall, our Director is not present for renewal discussion and therefore the vendor has also not visited. We will update you on mail. Lost- Payroll & HRMS training completed, and June salary was processed. Only biometric integration remained pending. Earlier as informed by Director Amit to Swati Ji that already their existing biometric device did not support integration and a new device was required. Despite multiple follow-ups and discussions, the client did not respond and later informed us they would coordinate with another vendor. Due to delays from client side the integration remained pending and the client ultimately decided to discontinue the software. | Attendance Integration issue | Full payment received | Apr-26,May-26,Jun-26 | Jun-26
SPR111468263103 | 9146 | New | Account Activated | RUPA SOLUTIONS PRIVATE LIMITED | Normal | E | Ankita Bankar | Sahil Gadhave | 2026-05-09 | Ankush Rampyare Rajbhar | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-09-30 | 2026-04-07 | 2026-04-08 | 2026-04-16 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 110 | Spine NG | AC | Onsite | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744 |  | NA | 0 | Aug-26
SPS111464263103 | 9142 | New | Account Activated | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | Premium | E | Karuna Rajaram Sandim |  |  | Riddhi Pramod Sutar | Channel |  | AMALAN TECHNOLOGIES - PUNE-SP | Utsavi Setu | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 650 | 2027-04-30 | 2026-04-02 | 2026-04-03 | 2026-05-20 | PARTNER |  | NG,ESSM,LV,TAM,ELC,PMS,RCT | Fresh | 1 | 0 | Spine NG | Active | Online | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) |  | Payment will be received in 1-2 days ----- 93% PAYMENT & Its GST WILL BE RECEIVED IN ADVANCE, 7% & Its GST WILL BE RECEIVED WITHIN 90 DAYS. ( 85% of the total cost with GST already rcvd) 15% of the total cost with GST will be paid within 90 days | Apr-26,May-26 | Jun-26
SPR111446263103 | 9121 | New | Account Activated | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | Escalated | E | Disha Kiran Kargutkar | Sahil Gadhave |  | Vikas Yadav | Channel |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-09-30 | 2026-04-04 | 2026-04-08 | 2026-06-30 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 1 | 10 | Spine NG | Active | Online | Basic payroll training has been completed. W26jul9046 vikas is connected with gyatri and other user for employee code. Client is occupied in a full-day meeting today. They will share the shift details and confirm the training schedule after checking with the Accounts Team. As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. | Imp in process, no proper response | 55% payment received | Mar-26 | Mar-26
SPS111411262803 | 9081 | New | Account DeActivated | STORM FINANCIAL SERVICES | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-05-15 | Mukeshkumar Shojiram kumavat | Channel |  |  | Utsavi Setu | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 410 | 2026-06-30 | 2026-03-28 | 2026-03-30 | 2026-04-01 | ENGG | 2026-07-10 | NG,ESSM,TAM | Fresh | 0 | 100 | Spine NG | Lost | Onsite | Completed Payroll training and also processed February 26 payroll and matched.-E26apr3050 completed all the training, also provided login access to employee-E26apr3347. completed with March Salary process for 391 employees.-E26apr4776. April month payroll has been processed, and payslip has been published for the employees. -E26may5873. Held up-As per the discussion with the client during the onsite visit by engineer mukesh the client is not ready to continue with the Spine. They have decided to develop and implement their own in-house software. | Another Software | Full payment received | Feb-26,Mar-26,Apr-26 | Apr-26
SPM111405262703 | 9075 | New | Account Activated | MANSHA AGENCIES PVT LTD | Escalated | E | Disha Kiran Kargutkar | Amey Telge |  | Aditya Mazire | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 260 | 2027-03-31 | 2026-03-27 | 2026-04-30 | 2026-06-22 | ENGG |  | NG,LV,TAM | Fresh | 0 | 75 | Spine NG | Active | Onsite | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied user said june we will upload As per amey client said july salary structure has some changes and need payslip with changes so once the approval from mangement and data shared will share you till then we will ask for atten integration. session aligned on 3rd sept for query and salary heads. | User is hospitalized so that’s why data files are received late & implementation is delayed | 60% received along with full GST 40% of total payment pending will receive after implementation( FULL PAYMENT RECEIVED) | May-26,Jul-26,Aug-26 | Aug-26
SPE111306262702 | 8958 | New | Account Activated | EMPREO WHEEL PVT LIMITED (MG) | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  |  | Swati Sangani | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 150 | 2027-02-28 | 2026-04-16 | 2026-05-25 | 2026-05-28 | ENGG |  | NG, ESSM, LV, TAM | Fresh | 0 | 65 | Spine NG | Active | Online | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. | 3 license single user, will take time to Go Live, as user is unable to process | 25% after 3 month payroll processed 25% after 4th month payroll processed (Received) | 0 | Apr-26
SPS111305262702 | 8957 | New | Account Activated | SHREEKHETRA AUTOMOTIVE (TATA) | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  | TRISTAR SOFTWARE & SOLUTIONS PVT. LTD | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2027-02-28 | 2026-04-15 | 2026-06-09 |  | ENGG |  | NG,ESSMLV,TAM | Fresh | 1 | 4 | Spine NG | Pending For Milestone | Online | Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 50% payment pending to partner after 1st payroll process | 0 | 0
SPE111274261802 | 8919 | New | Account Activated | EMPREO PREMIUM PVT LTD | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  | TRISTAR SOFTWARE & SOLUTIONS PVT. LTD | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 105 | 2027-02-28 | 2026-02-18 | 2026-03-25 | 2026-03-25 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 80 | Spine NG | Active | Online | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. | 3 license single user, will take time to Go Live, as user is unable to process | 50% received 25% after 3rd month payroll processed 25% after 4th month payroll processed (Received) | 0 | Mar-26
SPV111249260602 | 8886 | New | Account DeActivated | VED INDUSTRIES POC | Premium | E | Mansi Singh | Sahil Gadhave | 2026-06-24 | Dhanashree Dalvi | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-04-30 | 2026-02-06 | 2026-02-11 | 2026-03-06 | ENGG | 2026-06-24 | NX, TAM, HR | Fresh | 0 | 58 | Spine HRMS | Go LIVE | Onsite | employee master uploaded attn was there priority attn integration done currently their main focus in only on attendance mail lic follow up ongoing ankur and vasu will co-ordinate with client opted on premises lic |  | NA | 0 | NA
SPF107062230902 | 8880 | Add Mod | Account Activated | FFSERVICES PRIVATE LIMITED | Normal | E | Ankita Bankar | Shreyas Karkera | 2026-02-12 | Harsh Dilip Ashar | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 220 | 2026-09-30 | 2026-02-05 | 2026-02-05 | 2026-02-10 | ENGG | 2026-02-14 | PMS NX | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - PMS CONF (E26feb3272) Training & Implementation is done of PMS module |  | Full GST pending (Received) | 0 | NA
SPA111227263101 | 8860 | New | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Mansi Singh |  | 2026-03-15 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 660 | 2027-02-28 | 2026-01-31 | 2026-02-02 | 2026-02-03 | OS | 2026-03-31 | NG, ESSM, LV,TAM,ELC,CLAIMS,PMS,RCT,Add On | Fresh | 0 | 0 | Spine NG | Go LIVE | Onsite | live- training and impl done feb processed from spine |  | Billing to vincible, 50% of yearly subscription + 50% gst pending to be paid whithin 90 days from the date of purchase (Note - Pending with client Client paid 40% of total cost which is 40% of subscription + 40% of SS + 40% of IMPL + 40% gst) (Received) | 0 | Feb-26
SPG109937253101 | 8831 | Add Mod | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2026-02-05 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2026-01-29 | 2026-01-29 | 2026-01-30 | ENGG | 2026-02-10 | RCT NX | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | NA |  | NA
SPS111195262301 | 8821 | New | Account Activated | STERLING LIFESTYLE LLP | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | 2026-05-15 | Aarati Subhashchandra Yadav | Channel | SA | KESHAV COMPUTER PVT LTD - SA | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 75 | 2027-01-31 | 2026-01-23 | 2026-01-27 | 2026-02-12 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 110 | Spine NG | AC | Onsite | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms As per project update Our team is connected with client as new hr has join payroll hrms training completed today regularisation and assistance require in july salary. | NA | No data | Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPP111159260801 | 8782 | New | Account DeActivated | PANKAJ FASHION PVT LTD | Premium | E | Divya Bhide | Amey Telge |  | Aditya Mazire | Channel |  | SA-LANSAR | Deepak Choubisia | Viral Panchal | Vasu Mohan Dusa | SAAS | 1001 | 2026-06-30 | 2026-01-08 | 2026-01-13 | 2026-01-28 | ENGG | 2026-08-20 | NG,TAM | Fresh | 1 | 88 | Spine NG | Lost | Online | "10th, 15th, 25th" 110 emp- E26jan8973, payroll hr set up done, training done, int done, logins done, meeting done- workers not stable hence unable to share accurate data, meeting done may target, later will share data ot policy pending W26jun7203, contractual basic- change- card assign Director has not confidence on his user, Client LOST- Director dont have confidence on his user, meeting done onsite but not productive. Director has stopped receiving calls, client deactivated | Resource Problem | Remaining 50% will be paid in 90 days or after implementation, whichever is earlier | Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26 | May-26
SPM108453242903 | 8778 | Add Mod | Account Activated | MUKTANGAN EDUCATION TRUST. NX | Normal | E | Ankita Bankar | Amey Telge |  | Aditya Mazire | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 608 | 2026-09-30 | 2026-01-06 | 2026-01-06 | 2026-04-18 | ENGG |  | LV,ESSM,ELC,TS,RCT,PMS | Fresh | 0 | 93 | Spine HRMS | Active | Online | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly." | NA | 0 | NA
SPS111112253012 | 8729 | New | Account Activated | SUVARNA DURGA GROUP | Normal | E | Divya Bhide | Amey Telge | 2026-06-12 | Ankita Gupta | Channel | SP | BRILLIANT TECHNOLOGIES_Silver - SP | Roopa S | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2027-01-31 | 2026-01-05 | 2026-01-12 | 2026-02-06 | ENGG |  | NG,ESS,LV,TAM,ON,OFF,RCT | Fresh | 1 | 96 | Spine NG | AC | Online | payroll set up & training done, hr set up & training done, bio int done, rct,on,off std training done, logins done, meeting 2/6 for balance payment n pending points, new user of rct has requirement july done, client specifically wants to meet Roopa, impl details shared with her, meeting done, PM meeting done, rct requirement, aug co wise will be processed, |  | remaining 50% of product cost +server setup + implementation cost +full GST yet to be payable after the implementation or 45 days whichever is earlier . | Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPB111113253112 | 8728 | New | Account Activated | BFMS FACILITY MANAGEMENT PVT LTD | Escalated | E | Ankita Bankar | Shreyas Karkera |  | Amit Krishnakant Tiwari | Channel | SA | KESHAV COMPUTER PVT LTD - SA | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 500 | 2026-12-31 | 2025-12-31 | 2026-01-05 | 2026-01-13 | ENGG |  | NG, TAM | Fresh | 0 | 100 | Spine NG | Active | Onsite | Implementation and Training session aligned from 13th Jan E26jan1479 W26jan5503 Bfms Payroll Training and December Salary confirmation BFMS will not process with Attendance - W26mar1378 the salary of compliance section is not yet decided (in discussion) post that they will process march on monday team will update the company is shifting to pvt ltd hence they are bsy client not responding properly The client mentioned that they have employees such as delivery personnel working with platforms like Zomato, Swiggy, and Urban Company. These employees typically work for only 4–5 days and then leave the job after comparing their earnings with other platforms, stating that they are being paid less. Due to this high attrition and short working duration, salary processing becomes challenging. We also asked why they opted for the software despite this situation. The user responded that it was a management decision. as per vasu's meting client will be providing data post salary processing of june had a call with user to make her undertsand that all isue can be handled through spine which she is having but she seems not interested (E26aug6724) Project Held Up - Despite our continuous efforts to support and resolve queries and concerns, we have not received the required response from client | Mr. Bhau Sawant has assured management support for streamlining the process. Vinantee will coordinate with the team and inform us once the data preparation is completed. Post confirmation, an onsite visit will be scheduled to review the data, finalize the implementation plan, and align the next phase of activities23/06 Client will not shared the Calculation Yet, Multiple Followup - Vinanti | na |  | Feb-26
SPS111104252912 | 8720 | New | Account Activated | SUNRISE FOODS BANGALORE | Escalated | E | Disha Kiran Kargutkar | Shreyas Karkera |  | Tushar More | Channel |  |  | Roopa S | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 50 | 2026-12-31 | 2025-12-29 | 2026-01-14 | 2026-01-17 | ENGG |  | NG,TAM | Fresh | 0 | 76 | Spine NG | Active | Online | Payroll Training completed Mobile training and logins need to be roll out today then HRMS. clienmt shared the data july month salary processed and tallied. As per engineer tushar client is not using attendance module they are not taking interest.will followup for aug salary Not responding | Client is not Responding - GodFrey | No data | 0 | 0
SPE111097252312 | 8713 | New | Account Activated | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | Escalated | C | Divya Bhide | Hiren Bhimani |  | Komal Kanadiya | Channel |  | TAPASH SOFTWARE-SP | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | Hosting | 1400 | 2026-12-31 | 2025-12-23 | 2026-01-05 | 2026-01-07 | PARTNER |  | NG | Fresh | 0 | 100 | Spine NG | Active | Online | "25,10"emp master uploaded, salary structure and register recd, working started, E26jan8008 - engg from spine for assistance, master recd, updated feb salary register, jan feb done, training done, will not do march, directly april from software. calculation changes are there after that salary will be processed. "15" 100 grade - salary structure changed |  | Received | Jan-26,Feb-26 | Feb-26
SPR111093252212 | 8709 | New | Account DeActivated | RAJESHWARI INFOTEL PVT. LTD | Normal | E | Karuna Rajaram Sandim |  |  | Riddhi Pramod Sutar | Channel |  | ACQUIRO BUSINESS | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 1200 | 2026-03-31 | 2025-12-22 | 2025-12-31 | 2026-01-08 | PARTNER | 2026-05-12 | NG,ESSM,LV,TAM,ELC,EXP | Fresh | 0 | 56 | Spine NG | Lost | Online | payroll hr set up done, jan tallied, payroll hr training done, onboard impl going on- client lost report as per their req not possible, had taken on trail basis, they will continue with TCS | Another Software | NA | Dec-25,Jan-26,Feb-26 | Feb-26
SPN111014252911 | 8623 | New | Account Activated | NIKIKA ENTERPRISES LLP | Normal | E | Mansi Singh |  | 2026-05-14 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 175 | 2026-12-31 | 2025-11-29 | 2025-12-04 | 2025-12-03 | OS | 2026-05-19 | NG,ESSM,LV,TAM,EXP | Fresh | 0 |  | Spine NG | Go LIVE | Onsite | go live - training and impl done april processed |  | FULL PAYMENT RECVD | 0 | Apr-26
SPP111012252911 | 8619 | New | Account Activated | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | Normal | E | Ankita Bankar | Sahil Gadhave | 2026-02-12 | Goraksha Pawar | Direct |  |  | Amarprit Kaur | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 400 | 2026-11-30 | 2025-12-10 | 2025-12-15 | 2026-01-02 | ENGG | 2026-03-11 | NG,ESSM,LV,TAM,HD,PMS,RCT,ON,OFF | Fresh | 0 | 100 | Spine NG | FC | Onsite | Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system |  | Received |  | Aug-26
SPF110994252511 | 8600 | New | Account Activated | FEATHERTOUCH LEARNING PRIVATE LIMITED | Normal | E | Ritika Dilip Singh | Saurabh Pednekar | 2026-07-14 | Sunita Yadav | Channel | SA | KALYA TECHNOLOGY INNOVATION PRIVATE LIMITED-SA | Roopa S | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 500 | 2026-09-19 | 2025-11-25 | 2025-12-03 | 2025-12-30 | ENGG | 2026-07-15 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Online | welcome mail done #3/12 - eng - Corp ID done, datafiles awaiting #22/12 - no response Non Payroll Master Data received and uploaded. Salary Calculation received and configured. #19/01 - eng - salary processed, shared register to client for verification, waiting for reply Payroll Training and Implementation Completed W26jan4046. Mobile HR Training Completed W26jan5841. 19/01 - User is on leave and will connect on 21/01 for salary processing. SMTP Configuration Completed #W26jan7987. Location Configuration Completed #W26jan7983. HRMS Training Completed #W26jan8122. December 2025 Salary Completed #E26jan11453. January 2026 Salary Completed #W26feb6498. 08/04 - February processed and tallied, awaiting confirmation. User is too busy in internal work. Attendance Policy changes done. User will process salary by 15/04. #10/4 - busy February 2026 Salary Completed E26apr9176. Roll Out Completed E26apr9176. 24/04 - As per discussion, user not able to process March salary due to license count exhausted. In April as well count is exceeded. User is in discussion with management to increase the license count. User will discuss internally and will update. March salary will be processed post license update. #14/05 - eng - Non payroll employees april processed. Payroll employees configuration is completed and client will process salary in few days #1/06 - eng - in last schedule, they processed may salary with attendance. #W26may11974 - may salary conf. #25/06 - eng -All configuration done and training completed. Till May salary done but May confirmation not received as the Payroll user left the organization so coordinating with another user for all the processes. Now user have shared some changes in the calculation for Payroll category employees so we are finding a way to configure this. From June month user will process the salary with attendance data as they have some internal issues with the attendance. June 2026 Salary Completed with Attendance W26jul873. #10/08 - feedback good and positive |  | FULL PAYMENT RECEIVED | Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPG109937253101 | 8572 | Add Mod | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-11-22 | Utkarsh Sanjay Chavan | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2025-11-19 | 2025-11-19 | 2025-11-21 | ENGG | 2025-12-10 | ELC (NX) | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training & Implementation of ELC Module is completed - E25nov7072 Logins rolled out for ELC module |  | NA | Dec-25 | NA
SPN110948251311 | 8547 | New | Account Activated | NAIK MOTORS - RATNAGIRI LOC | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2026-08-10 | Aditya Mazire | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 180 | 2026-10-31 | 2025-11-13 | 2025-11-25 | 2025-12-22 | ENGG |  | NG, ESSM, LV,TAM, ELC | Fresh | 0 | 196 | Spine NG | AC | Online | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also." | The balance amount of first 70% and pending 30% will be paid after 1 month salary process Also full GST pending which will be received by 1 month salary process (Received) | Jul-26,Aug-26 | Aug-26
SPN110937250811 | 8531 | New | Account Activated | NAIK MOTORS -GOA LOC | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2026-07-14 | Aditya Mazire | Channel |  |  | Sandeep Ashok Joundal | Viral Panchal | Vasu Mohan Dusa | SAAS | 410 | 2026-10-31 | 2025-11-08 | 2025-11-20 | 2025-12-17 | ENGG |  | NG, ESSM, LV,TAM,ELC | Fresh | 0 | 88 | Spine NG | AC | Online | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn |  | The sum amount of first 60% and pending 40% will be paid after 1st salary process. ( Received) | Jul-26,Aug-26 | Aug-26
SPS110901253110 | 8487 | New | Account Activated | SREE METALIKS LTD | Premium | E | Divya Bhide | Sahil Gadhave | 2025-12-22 | Nandadeep Mhatre | Channel |  | TAPASH SOFTWARE-SP | Sumit Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 700 | 2026-10-31 | 2025-10-31 | 2025-11-04 | 2025-11-17 | ENGG | 2026-03-10 | NG,ESS,LV,TAM | Fresh | 0 | 110 | Spine NG | Go LIVE | Online | "7th "payroll hr set up done, oct tallied,bio int done, logins done, training done, dec done W26jan10986 client FC |  | NA | Mar-26 | Mar-26
SPV110891253010 | 8476 | New | Account Activated | VIVID ELECTROMECH LIMITED | Normal | E | Ritika Dilip Singh | Vinay Kareliya | 2026-03-06 | Mihir Navnath Mungekar | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 250 | 2026-10-31 | 2025-10-30 | 2025-11-18 | 2025-11-19 | ENGG | 2026-03-13 | NG,ESSM,LV,TAM | Fresh | 0 | 96 | Spine NG | FC | Onsite | payroll training and impl done- E25nov7138, E25nov8316 E25nov9114 hrms training and configuration done- E25dec416 geo tagging and integration done E25dec4143 November salary also tallied, dec done- E26jan2964 feb done with attn have few requirements they were not willing to proceed because of that somehow we are convincing them team is in discussion we are following up for salary #28/08 - no resposne | NA | Received | 0 | Jun-26
SPN110876251610 | 8434 | New | Account Activated | NAGRIK CONSULTANCY SERVICES | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2025-12-03 | Aditya Mazire | Direct |  |  | Nandini Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 180 | 2027-04-30 | 2025-10-18 | 2025-10-24 | 2025-10-25 | ENGG | 2026-06-15 | NG,ESSM,LV,TAM,ON/OFF,HD | Fresh | 0 | 100 | Spine NG | FC | Onsite | completed Payroll training .-W25oct5654 completed with HRMS training on 1st Phase with Add on service. processed and tally the salary of Sep 2025 month for all 3 grades for126 employees. processed the salary of Oct 2025 month.- W25nov634 Employee training and logins roll out processed Salary for Nov 2025, for Midas touct MT, NHO, with attendance and tallied the same November salary processed December salary processed Jan salary done. Feb salary done. March salary done. april salary done may salary processed june salary processed As per feedback user Ms. Suvarna said No queries as such we are getting support which we required. June salary is in process. user said no queries and concern if we have we raised the mail as we asked mansi ji has escalated the attendance queries it has been resolved | Suggestion ID: 3709 Requirement: Leave Year Selection in Mobile Application Suggestion ID: 3536 Requirement: Add-On Service Request and Approval Option in Mobile Application | 70% payment to be made in advance to initiate the implementation process. Remaining 30% payment to be made after completion of implementation, i.e., within 30 days. (Received) | Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPH110833253009 | 8409 | New | Account Activated | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | Normal | E | Ankita Bankar | Vinay Kareliya | 2026-04-08 | Mihir Navnath Mungekar | Direct |  |  | Amarprit Kaur | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 135 | 2026-09-30 | 2025-10-08 | 2025-10-16 | 2025-10-17 | ENGG | 2026-05-11 | NX,ESSM,LV,TAM | Fresh | 0 | 110 | Spine HRMS | FC | Onsite | Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on |  | 50% of the product cost +full GST will be receivable after implementation or 45 days whichever is earlier (Received) | 0 | Aug-26
SPC110823252909 | 8381 | New | Account Activated | CENTRE FOR URBANIZATION BUILDINGS | Normal | E | Disha Kiran Kargutkar |  |  |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 95 | 2027-08-31 | 2025-09-29 | 2025-09-30 | 2025-10-02 | OS |  | NG,ESSM,LV,TAM,EXP,ELC,RCT,TS,HD | Fresh | 0 |  | Spine NG | Active | Online | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on |  | Extra amount received need to adjust with future billing | 0 | 0
SPP110783251209 | 8328 | New | Account Activated | PARADISE GROUP | Escalated | E | Ankita Bankar | Amey Telge | 2026-06-26 | Pritesh Barot | Channel |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 624 | 2026-09-30 | 2025-09-12 | 2025-09-16 | 2025-09-23 | ENGG |  | NG,ESSM,LV,TAM,PMS,RCT,ELC | Fresh | 0 | 104 | Spine NG | AC | Online | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August |  | Received | 0 | NA
SPM110771250109 | 8316 | New | Account Activated | MEDIPULSE HOSPITAL | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2026-07-31 | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 731 | 2026-09-30 | 2025-09-06 | 2025-09-09 | 2025-10-09 | ENGG |  | NG,ESSM,LV,TAM,ELC,RCT,EXP | Fresh | 0 | 98 | Spine NG | AC | Online | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. | Using only the HRMS Module, payroll is now initiated | Received | Dec-25,Mar-26,Apr-26,Jun-26,Jul-26 | Jul-26
SPF110735252908 | 8275 | New | Account DeActivated | FUJIYAMA POWER SYSTEMS LIMITED | Premium | E | Divya Bhide | Hiren Bhimani | 2026-01-12 | Komal Kanadiya | Channel |  | PARAMHANS COMPUTERS-SP | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 2400 | 2026-02-28 | 2025-08-29 | 2025-09-08 | 2025-09-23 | PARTNER | 2026-07-29 | NG,ESS,LV,TAM | Fresh | 0 | 110 | Spine NG | Lost | Online | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software | The remaining 50% + Implementation cost will be payable after 90 days.(Lost) | July-25,Aug-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26 | Feb-26
SPS110711252008 | 8245 | New | Account Activated | SETHWALA FOODS LTD | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave | 2026-03-12 | Kunal Joshi | Direct |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 600 | 2027-08-31 | 2025-08-20 | 2025-08-22 | 2025-08-28 | ENGG | 2026-05-14 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | GO FC- Client have completed training session of Payroll & HRMS . Also SMTP setup & locationAPI setting has been done successfully.-E25sep1207 september salary of ho done October salary done The training has been completed in talasari-E25nov8643 client have processed SFLD unit salary for the month of Dec'25 with attendance muster from the software successfully. With Login was provided to employees -E26jan2962 client inform us, for this month, HO salary will be run through Spine, while Talasari salary will be processed via Excel uploading.-E26feb1695 feb salary done march salary processed April salary processed-E26may3191 May salary processed Jun salary processed called for feedback Ms. Vidhya she said no queries and concern it is getting solved. | user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9 | Received | Apr-25,May-25,Aug-25,Sept-25,Oct-25,Nov-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPR110686250108 | 8212 | New | Account DeActivated | RAMYASRI ELECTRICAL AUTOMATION | Normal | E | Divya Bhide | Probian Biswas |  | Ankita Gupta | Channel | SP | BRILLIANT TECHNOLOGIES_Silver - SP | Roopa S | Viral Panchal | Vasu Mohan Dusa | SAAS | 250 | 2026-02-28 | 2025-08-06 | 2025-08-28 | 2025-09-17 | ENGG | 2026-03-31 | NG,TAM | Fresh | 0 | 36 | Spine NG | Lost | Online | 47 emp data recd, tallied, payroll set up done, training pending not responding,esc to PM, partner team, ignoring calls, 5/2 structure recd of 36 recd, uploaded, rest data follow up going on 10/3 meeting done- datafiles will share 12/3 client not showing interest, amc not renewed, no response from client,client deactivated, | No Reponse - No Reason | NA | Sept-25,Oct-25 | Oct-25
SPT110669253107 | 8204 | New | Account DeActivated | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | Normal | E | Mansi Singh | Amey Telge |  | Vijay Bugde | Direct |  |  | Amarprit Kaur | Viral Panchal | Vasu Mohan Dusa | SAAS | 1500 | 2026-07-31 | 2025-08-02 | 2025-08-22 | 2025-09-02 | ENGG | 2026-05-13 | NG | Fresh | 0 | 100 | Spine NG | Lost | Onsite | corp id creation done trng and impl in process Toyota and Hyudai branch employee data uploaded sucessfully also we processed Toyota branch sept month salary Employees work across multiple sites/companies and salary processing happens there. The director is using our software only to verify if the salary tallies with attendance data User is not responding, we are trying to reach user multiple times. vasu is looking into it (planning visit) director is not available, nor he is responding calls vasu went for onsite visit but they are not interested to proceed escalated the concern to amrprit through email client not interested | No Reponse - No Reason | NA | Oct-25 | Oct-25
SPW110622251807 | 8143 | New | Account Activated | MUKTA ARTS LTD | Escalated | E | Ankita Bankar | Amey Telge |  | Nagendra Poojary | Direct |  |  | Mehul Patel | Viral Panchal | Vasu Mohan Dusa | SAAS | 350 | 2027-07-31 | 2025-07-18 | 2025-07-24 | 2025-08-06 | ENGG |  | NG,ESSM,LV,TAM,MOB, PMS,EXP,ELC | Fresh | 0 | 82 | Spine NG | Active | Onsite | Working done on 6th August for training user will let us know the dates attendance integration done as per users request W25aug2358 Payroll Training done & August month processed & tallied September month salary processed January 2026 month salary processed Apr month salary processed June month live with attednace salary processed User is busy interanally in PMS & after July month processing will plan add mod training - 22nd july renewal will be done before 10th august as user convyed at vasu's visit Tech ID - 4192 Currently, the PMS system allows ratings in decimal values. However, as per the client's requirement, there should be a configuration/setting available to disable decimal ratings and allow only whole-number ratings during the performance evaluation process. - This req is yet to delivered user & after that only they are ready to renew - renewal is done | Initially, the user was not using the Spine software, as they felt that performing tasks in the system was time-consuming. To address their concerns, we arranged a meeting with the Project Manager and the client to discuss the issues and provide clarification. Following the meeting, the user agreed to adopt the software and has started using the system. | Received | 0 | Aug-26
SPI110558252806 | 8079 | New | Account DeActivated | ILEAF RITZ BANQUETS | Normal | E | Mansi Singh | Probian Biswas |  | Mayur Pendhari | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 110 | 2026-06-30 | 2025-06-28 | 2025-07-01 | 2025-07-02 | ENGG | 2026-06-18 | NG,ESSM,LV,TAM | Fresh | 0 | 110 | Spine NG | Lost | Onsite | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy | Received | July-25,Aug-25,Oct-25,Nov-25,Dec-25,Jan-26 | Jan-26
SPU110473253105 | 8042 | New | Account Activated | UNITED AIR EXPRESS | Premium | E | Ankita Bankar | Nagesh Tiwari | 2026-02-13 | Shubham Gurav | Channel |  |  | Nirbhay Kumar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 3050 | 2027-05-31 | 2025-06-19 | 2025-06-24 | 2025-07-21 | ENGG | 2026-03-11 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Online | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system | NA | Receeived | 0 | Aug-26
SPM110480253105 | 8009 | New | Account Activated | MESPACK INDIA PVT. LTD | Normal | E | Disha Kiran Kargutkar | Akshay Shinde | 2026-06-19 | Pooja Vikas Shinde | Channel |  |  | Sandeep Ashok Joundal | Viral Panchal | Vasu Mohan Dusa | SAAS | 60 | 2027-05-31 | 2025-06-09 | 2025-06-12 | 2025-07-02 | ENGG | 2026-06-19 | NG,ESSM,LV,TAM | Fresh | 0 | 210 | Spine NG | FC | Onsite | Payroll training done successfully completed the attendance integration activity at the client’s location. W25oct6232 , E25nov1863 october salary has been processed. nov salary done successfully processed the December 2025 salary. - E26jan4924. Expense module training done Jan salary processed February salary done March salary has been processed-E26apr8430 April done may salary done parallelly GO FC- As all activities related to training and implementation have been completed successfully, and the system is now fully ready for use. Due to an internal gap, the attendance has not been regularized so salary processing will be carried out in parallel. August salary has been processed with attendance. Called for feedback to user Ms. Usha not responded the call. | NA | Received | June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jul-26,Aug-26 | Aug-26
SPC110448252805 | 7954 | Add Mod | Account Activated | CIRCLE RESOURCES PRIVATE LIMITED | Escalated | E | Disha Kiran Kargutkar | Amey Telge | 2025-11-13 | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1700 | 2026-08-31 | 2025-05-28 | 2025-06-17 | 2025-06-17 | ENGG | 2026-06-15 | NX,ESSM,LV,TAM,ELC,EXP,HR | Fresh | 0 | 104 | Spine HRMS | FC | Online | WELCOME MAIL DONE WILL PROCEED WITH THIS BY 10TH JUNE - E25jun3240 SPLITTING DONE training and impl done Oct 2025 salary processed - E25nov2426 from spine Disbursement date - 11th of every month. processing salaries parallely additional rule techical given by hemant sir on friday Today meeting regarding recaltions issue of attendance. As per meeting viral sir has given solutions and wayarounds. need to share list of policy and shifts which is not in use compulsory. | Disbursement date by 15th | NA | May-25,June-25,July-25,Aug-25,Sept-25,Oct-25 | Jun-26
SPB110442252705 | 7947 | New | Account Activated | BRIGHT BROTHERS LTD | Normal | E | Ankita Bankar | Akshay Shinde | 2026-02-24 | Yash Pankajkumar | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 330 | 2026-11-30 | 2025-05-27 | 2025-05-27 | 2025-06-07 | ENGG | 2026-08-14 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system | NA | Received | June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25 | Aug-26
SPN110379253004 | 7880 | New | Account Activated | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Premium | E | Ankita Bankar | Amey Telge | 2025-08-18 | Aditya Mazire | Channel | SP | RISHIKESH CONSULTANCY- SP | Tejas Kareliya | Viral Panchal | Vasu Mohan Dusa | On-Premises | 2500 | 2027-04-30 | 2025-05-07 | 2025-05-08 | 2025-05-21 | ENGG | 2025-11-11 | NX,ESSM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live |  | NA | Mar-26 | Mar-26
SPP110398250605 | 7876 | New | Account Activated | PROCON RMC PLANTS PRIVATE LIMITED | Escalated | E | Disha Kiran Kargutkar | Shreyas Karkera | 2025-08-11 | Sushant Thombare | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2025-05-06 | 2025-05-12 | 2025-05-13 | ENGG | 2025-08-15 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | E25jun699 Payroll training confirmation Training confirmation till leave module #E25jun1063 E25jul1122Hrms training and May 25 Salary confirmation july salary done with attn from spine Shambhu ji has shared the previous month data of salary sheet from march to august. | NA | NA | Apr-25,May-25,June-25,July-25 | May-26
SPD110360252904 | 7872 | New | Account Activated | DRS EARTHWORK PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2026-05-15 | Mihir Navnath Mungekar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2026-10-31 | 2025-05-05 | 2025-05-06 | 2025-06-16 | ENGG | 2026-05-15 | NX,ESSM,LV,TAM,EXP | Fresh | 0 | 104 | Spine HRMS | FC | Online | payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we have deleted salary for Apr-25 to Mar-26, and uploaded past salary data for all emps, Now user will process Apr & May this week and will get back to us incase of any query by 27-Jun. client will do june salary by own which will be parallel. As per feedback user said no queries if it is will let you know as I am on leave connected today for july salary As per the discussion done with Shital ji, major emps are in the field, and are not willing to mark attendance through mobile. HRMS is utilitised by approx 100 emps but live disbursement is done through excel and they will process salary in Spine for record keeping purpose only | NA | NA | May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Jul-26 | NA
SPS110245253103 | 7866 | New | Account Activated | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | Normal | E | Ritika Dilip Singh | Amey Telge | 2025-11-12 | Vijay Bugde | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | SAAS | 470 | 2027-05-31 | 2025-05-03 | 2025-05-08 | 2025-05-20 | ENGG | 2026-04-15 | NX,ESSM,LV,TAM,ELC,EXP,PMS,RCT,TS,RD | Fresh | 0 | 98 | Spine HRMS | FC | Onsite | welcome call done payroll done april tallied hrms basic module done geo tagging done logins rolled out integration/smtp done MAY DONE E25jun8292 june salary conf- E25jul5746 LDAP and maker checker. provided processing live salary from system pms and time sheet pending- if session required client will reach out to us.W26apr5969 #10/08 - rcvd a ticket from user regarding issue in approver. #18/08 - feedback was not good at all, she told she would give zero rating, her main issue was about resource allocation charges, which i was explaining her, then she told, she is quite allocated today, we can connect tomorrow. #28/08 - E26aug9070 - user requested for user manual for sharing with their employees. | Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10 | Received | Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Jul-26,Aug-26 | Aug-26
SPA110196252903 | 7773 | New | Account DeActivated | ASHWINI CONTAINER MOVERS LIMITED | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2025-09-08 | Amey Telge | Direct |  |  | Tejas Kareliya | Viral Panchal | Vasu Mohan Dusa | SAAS | 300 | 2025-10-31 | 2025-04-17 | 2025-04-21 | 2025-05-02 | ENGG | 2025-11-25 | NG,ESSM,LV,TAM,PMS | Fresh | 0 | 89 | Spine NG | Lost | Onsite | Client completed the training for Payroll and HRMS.-E25may4794 May salary done for both companies-E25jun3160 June salary Processed july salary has been processed. August salary processed. sept salary processed As per feedback client inform us that the AMC renewal has been kept on hold, as their management has decided not to proceed with the renewal at this time, due to the implementation of a new software solution. | Requirement | NA | Mar-25,Apr-25,May-25,June-25,July-25,Sept-25 | Sept-25
SPE110247253103 | 7706 | New | Account Activated | ELECTROSTEEL CASTINGS LTD | Premium | A | Ankita Bankar | Sahil Gadhave | 2026-05-12 | Kunal Joshi | Channel |  |  | Jayesh Mojidra | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 1000 | 2027-03-31 | 2025-03-31 | 2025-04-25 | 2025-07-09 | ENGG | 2026-05-13 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Online | training and impl conf- E25jul10921 logins rolled out not going to process salary from spine, using hrms. renewal done | SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa | 1.25% of Software Cost payable on Installation of software duly certified by concerned in-charge. 2. 50% of Software Cost + Implementation charges along with GST bills to be submit in accounts duly certified by concerned in-charge. 3. GST amount will be paid against proof of uploading of bills in GSTR1A and GSTR3B. (Received) | 0 | NA
SPC110185252803 | 7668 | New | Account Activated | CONTENDRE GREENERGY LIMITED | Normal | E | Ritika Dilip Singh | Akshay Shinde | 2025-07-17 | Daksh Pawankumar | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 160 | 2027-03-31 | 2025-03-27 | 2025-03-28 | 2025-04-21 | ENGG | 2026-05-14 | NX, ESSM,LV,TAM,MOB-HR, ELC,Travel exp | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | #Trng and impl from 21st April #E25apr9485 - complete upto loan processing module #E25apr10010 - Payroll nx training is completed Location IQ set up has been done #E25apr11264 - have completed HRMS and SMTP training #W26may1493 - update ESIC rules in Payroll #E25jul1135 - june salary conf. #W25aug3365 - PAYROLL HRMS CONF. #W25sep4179 - august salary done. #07/05 - feedback was good, processed april month salary. #18/08 - overall feedback was good, they’ve been facing an issue while transferring employee from one company to another.she require a proper solution for the same. | No open queries as of now, Vasu to connect with the director for review meet 5/9 | NA | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPS110155252403 | 7631 | New | Account Activated | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Normal | E | Mansi Singh | Akshay Shinde | 2025-12-08 | Daksh Pawankumar | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | SAAS | 65 | 2027-03-31 | 2025-03-24 | 2025-03-25 | 2025-04-07 | ENGG | 2025-12-12 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us | Received | Mar-26 | Mar-26
SPV110114251303 | 7577 | New | Account Activated | VABA | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | 2025-06-17 | Karan Rajesh Tiwari | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 430 | 2027-03-31 | 2025-03-13 | 2025-03-17 | 2025-03-26 | ENGG | 2025-10-09 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have successfully completed the PayrollNX training Client have processed the one company Bishan Steel Industries March 2025 month salary and tally with register matches to our salary register. 1. salary attendance days demo done and queries solved Client inform that our executive Mr. Karan Has Done Following works :- 1. smtp work done 2. Leave Workflow & Attendance work flow Done 3. Tally Integration work done as demo basis and it is ok -E25apr4753 As per telecon attendance integration has been done. user is processing the may salary by its own. We have completed our Salary Process for the Month of May 2025-E25jun5684 Client have completed our Salary Process for the Month of June 2025-E25jul5468 July month salary processed August salary processed August salary processed September salary processed Oct salary processed Nov salary processed January Salary processed feb salary is in process as client want to extend the employee count. | Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop | received | Dec-25 | Mar-26
SPR110105251203 | 7568 | New | Account Activated | ROYAL EMBROIDERY THREADS PVT.LTD. | Normal | E | Ritika Dilip Singh | Akshay Shinde | 2026-05-14 | Bhavika Gite | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | SAAS | 350 | 2027-04-30 | 2025-03-12 | 2025-03-13 | 2025-04-03 | ENGG | 2026-05-14 | NG,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | #trng and impl from 3rd april #E25mar4404 - completed training of Payroll & HRMS #W25apr6337 - added all shift schedules, and attendace logics have been added & also training & login rollouts of Mobile HR #W25may504 - Attendace integration has been done #W25may7421 - processed the april salary #W25aug449 - june salary done #W25aug772 - july salary done ##W25sep5963 - conf. of total hours calculation calculation #11/09 - processed wages of 191 employee of pune for Aug_2025, During the verification some discrepancies identified, awaitng for final confirmation. #W25DEC1871 - nov salary done #08/05 - feedback was good no issue as of now, processed april month salary. #18/08 - feedback was neutral as always, right now there is nothing to escalate.. | client conveyed that within this week end will do payment 22/9 | Received | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26
SPB110087250303 | 7567 | New | Account Activated | BIJJARGI MOTORS PVT LTD | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-06-16 | Sahil Gadhave | Channel |  |  | Santosh Bhoja Shetty | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 650 | 2027-03-31 | 2025-03-11 | 2025-03-13 | 2025-03-19 | ENGG | 2025-08-21 | NG,ESSM,LV,TAM,ELC | Fresh | 0 | 100 | Spine NG | Go LIVE | Online | Project Live - Project delivery rcvd Working done 1) Spine NG Training Confirmation Ticket ID : W25mar8629 2) Spine HRMS Training Confirmation Phase I Ticket ID : W25mar9709 (Admin, Self Service, Leave, Time) 3) Spine HRMS Training Confirmation Phase II Ticket ID : W25mar10339 (Mobile HR,ELC Module (Onboarding & Offboarding)) 4) Mar'25 salary processing completed in PayrollNX and tallied for all the employees Ticket ID : #W25apr1467. 5) Login are rollout for all the employees Ticket ID : #W25apr1467. 6) Employee Training Confirmation Ticket ID : #W25apr1467. We have Scheduled the onsite session dated 10th and 11th June onsite. Reference Ticket ID : E25jun1574 Confirmation Ticket ID : W25jun5440 July month live salary with attendance from system is processed |  | Received | Jun-26 | Jun-26
SPB110104251103 | 7566 | New | Account DeActivated | BASANT OVERSEAS | Premium | E | Mansi Singh | Akshay Shinde |  | Yash Pankajkumar | Channel |  |  | Jayesh Mojidra | Viral Panchal | Vasu Mohan Dusa | SAAS | 1454 | 2025-09-30 | 2025-03-11 | 2025-04-23 | 2025-06-19 | ENGG | 2025-11-11 | NX,ESSM,LV,TAM | Fresh | 0 | 13 | Spine NG | Lost | Online | Till date, all the requirements received have been delivered to Team Basant. Mr. Deep has also confirmed that he is satisfied with the updates—reference ticket number W25AUG5167. The delay occurred due to the day-to-day new requirements received from the team, based on which our team made the necessary changes and obtained confirmation accordingly. We are now ready to proceed with the further training and implementation activities. However, the client’s AMC has expired. Requesting your guidance on how we should proceed further. yash is working on the same with hemant sir | Resoure Problem | NA | 0 | 0
SPA104424190108 | 7557 | Add Mod | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Usha Gupta | Viral Panchal | 2025-03-25 | Pritesh Barot | Direct |  |  | Sanket Gosalia |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2025-03-10 | 2025-03-10 | 2025-03-18 | ENGG | 2025-03-25 | PMS | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Files awaiting, training from 18th, training done #W25mar6022 |  | na | 0 | 0
SPM110039252802 | 7556 | New | Account Activated | MADURA INDUSTRIAL TEXTILES LIMITED. | Normal | E | Mansi Singh | Vinay Kareliya | 2025-09-18 | Varun Rajbhar | Channel |  |  | Jayesh Mojidra | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 327 | 2027-03-31 | 2025-03-10 | 2025-03-13 | 2025-04-21 | ENGG | 2025-12-12 | NX,ESSM,LV,TAM,ELC,EXP,TD,VM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | first focus on the HRMS module, as they wil be revising the salary structure after the appraisal so want to proceed with hrms- E25apr8632 we have Completed the HRMS Training for Admin, Self Service, Leave and Time (till Shift) Module.- E25apr8632 they are processing salary live with attn additional module done VM confirmation- E25dec2755 |  | Received | Mar-26 | Mar-26
SPQ109952253101 | 7549 | New | Account Activated | QUALIGENS PHARMA PVT. LTD. | Normal | B | Disha Kiran Kargutkar | Probian Biswas | 2025-08-12 | Ruchit Shailesh Patel | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | On-Premises | 400 | 2027-02-28 | 2025-03-06 | 2025-04-02 | 2025-04-09 | ENGG | 2025-08-12 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have completed Payroll Nx,Spine HRMS & Mobile HR training we processed the salary for March_2025. Client have successfully installed & configured attendance module in Spine HRMS software.-E25apr7956 completed the process of Leave Policy ,we have checked & it is ok. Client was facing issues to process the month of May salary due to new TAX regime,this query has resolved now we are processing the May month salary.-W25jun5512 June salary processed and MLWF Query has resolved -Connected by Ms. Ankita.- W25jul1673 July salary in process.-W25aug2373 |  | Received | Dec-25,Jan-26,Feb-26 | Feb-26
SPA110034252702 | 7521 | New | Account Activated | ANM INDUSTRIES PVT LTD | Normal | E | Ankita Bankar | Vinay Kareliya | 2025-05-13 | Vinay Kareliya | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 135 | 2027-02-28 | 2025-03-03 | 2025-03-04 | 2025-03-15 | ENGG | 2025-06-03 | NG,ESSM,LV,TAM,ELC,EXP | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | Project Live - Training & Implementation of Payroll is completed & February month salary processed - #W25mar6029 completed training for Self Service, Leave & Time modules - W25mar6166 March Month live salary processed & tallied - #W25mar11238 May month live salary processed with attendance & tallied- E25may11820 |  | Received | Mar-26 | Mar-26
SPK110049252802 | 7518 | New | Account DeActivated | KARVY TECHNOLOGIES PVT. LTD. | Normal | E | Mansi Singh | Vinay Kareliya |  | Tejas Rajesh Baragade | Direct |  |  | Vaishali Ramniklal | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 130 | 2026-02-28 | 2025-03-03 | 2025-03-03 | 2025-03-24 | ENGG | 2025-12-24 | NG,ESSM,LV,TAM | Fresh | 0 | 87 | Spine NG | Lost | Onsite | Payroll training confirmation: E25mar9331 HRMS, Mobile HR, and geotagging confirmation: E25mar9330 may processed as ashwini ji left the organisation nikhil from accounts team will take trng post that will proceed with payment but he is not respondng, so vasu is planning to meet phani ji cfo. new user training session done now for salary processing user is not responding positively. geo location, fencing done attendance is coming proper as of now user have few queries, impl team in discussion QUERIES RESOLVED PAYMENT FOLLOW UP ONGOING Few concerns with regards to geo fencing was there, we resolved it too, user not ready to release the pending payment. | Not happy with service | 50% of product cost + Full GST pending | Feb-25,Mar-25,Apr-25,May-25 | May-25
SPM107218233003 | 7491 | Add Mod | Account Activated | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Premium | C | Disha Kiran Kargutkar | Probian Biswas | 2025-09-12 | Ruchit Shailesh Patel | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | On-Premises | 1410 | 2027-03-31 | 2025-02-26 | 2025-02-26 | 2025-03-17 | ENGG | 2025-09-15 | ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Training done #E25mar4260, as per discussion with team leader user is in testing period for this month and will start implementing with salary and attendance from june month. called user Ms. Sushama about update as they said it working properly and we have check the may salary too and attendance queries has been solved. As per our discussion over the call, client will be processing the salary from your end. In case any assistance is required during the process.-W25jul4028. July salary processeed August salary processed- E25sep4242, E25sep4197. | Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9 | Received | May-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26 | NA
SPA109915253101 | 7490 | New | Account Activated | APLAB LIMITED (FOR CONTRACT LICENSE) | Normal | D | Mansi Singh | Vinay Kareliya | 2025-09-04 | Varun Rajbhar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 251 | 2027-03-31 | 2025-02-25 | 2025-04-09 | 2025-05-15 | ENGG | 2025-09-11 | NX,ESSM,TAM | Fresh | 0 |  | Spine HRMS | Go LIVE | Onsite | contractual conv not required user will share fresh data-E25mar2250 TRAINING DONE - They will be using spine for tracking attendance only E25jun5035 - confirmation using only for attendance, will not use for payroll E25jul10109 |  | Received | Dec-25 | NA
SPA109903253001 | 7489 | Conv+New | Account Activated | APLAB LIMITED (FOR STAFF LICENSE) | Normal | C | Mansi Singh | Vinay Kareliya | 2025-09-04 | Varun Rajbhar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 200 | 2027-03-31 | 2025-02-25 | 2025-04-09 | 2025-04-11 | ENGG | 2025-09-11 | NX,ESSM,LV,TAM | Conversion | 0 | 84 | Spine HRMS | Go LIVE | Onsite | conversion done user want separate db- E25mar2449 installation done handholding done today - W25apr4191 confirmation feb & march salay procssed from spine Aplab PayrollNX Training completion Ticket I'd W25apr4191 attendance integration done implementation confirmation- W25jun5948 they will not process payroll live, they process salary for 2 3 months together for statutory reports E25jul10109 - confirmation |  | Received | Dec-25 | NA
SPS110019252102 | 7477 | New | Account Activated | SHREE RAMDEV METALEX LLP | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2025-08-21 | Tejas Rajesh Baragade | Direct |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 325 | 2027-02-28 | 2025-02-21 | 2025-02-25 | 2025-03-12 | ENGG | 2025-11-14 | NX,ESSM,LV,TAM,MOB HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have completed the Spine Payroll Software training on 19/03/2025 -E25mar6215 Spine payroll training for Day-2 has been completed. We covered the HRMS module (Admin, Self-Service, and Leave), as well as the February 2025 salary process and Tally.-E25mar6704 Client have successfully completed the Spine HRMS and Mobile HR training on 21st March 2025.-E25mar7156 March month salary processed The salary of month May-2025 has been successfully processed in spine. -E25jun1773 July has been successfully processed and tallied-W25aug6270 August salary done This is to notify you that currently our employees are not regularizing attendance before payroll, So we are in the process of streaming line our attendance regularization on time. For next few months (3-4) Month we shall process salary in Spine parallel. Currently we have processed salary till Sep-25 and we shall get back to team Spine support in future whenever required-E25oct4126 Oct-25 processed with Spine attendance parallel November salary processing is completed for 179 employees. |  | Received | Dec-25,Jan-26,Feb-26 | Feb-26
SPM110010251902 | 7465 | New | Account DeActivated | MARU CONSULTANCY SERVICES | Normal | E | Usha Gupta | Probian Biswas |  | Ruchit Shailesh Patel | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 150 | 2025-05-31 | 2025-02-19 | 2025-02-19 | 2025-03-24 | ENGG | 2025-06-13 | NG,TAM | Fresh | 0 | 83 | Spine NG | Lost | Onsite | URL & files awaiting, payroll files expected on 22nd, master file will be share on 27th, master file received, kick off meeting on 4th Waiting for revised & Register file #E25mar2864, files received, training date waiting, imple from 24th, training done #E25mar8603, #E25mar9860 Geo fencing #E25mar10496 Geo fencing #E25apr105, session arranged on 3rd #E25apr105 fencing done mobile login given to half employees #E25apr1678, logins given, march salary will be complete in 3rd week April salary expected live March done user will get back to us for April salary, probably complete by 7th S/w not in use, outsourcing, attendance is priority, blue collar employees unable to use attendance, for meeting user will get back to us. Onsite meeting on 29th RECENT UPDATE - MARU CONSULTANCY SERVICES use to process salary for their client, however they have left, if any new cliient onboards then they shall renew it for salary processing. | Funds issue | na | Feb-25,Mar-25 | Mar-25
SPR109998251802 | 7453 | New | Account Activated | RADIX ELECTROSYSTEMS PVT LTD | Premium | E | Ankita Bankar | Probian Biswas | 2025-07-24 | Aditya Pathak | Direct |  |  | Pragnesh Panchal | Viral Panchal | Vasu Mohan Dusa | SAAS | 630 | 2027-02-28 | 2025-02-18 | 2025-02-19 | 2025-03-18 | ENGG | 2026-03-11 | NX,ESSM,LV,TAM,ELC,EXP,PMS,TD | Fresh | 0 | 76 | Spine HRMS | Go LIVE | Onsite | Project Live - PMS mod overviwe is done & for same module training user will get back to us with policies Training & Implementation of Payroll Nx is completed - #E25mar11411 & #E25mar6281 February month salary processed & tallied - #E25mar10450 March month live processing done April month salary processed & tallied June & july month tallied ELC module training & Implementation done PMS & request desk will are doing followup with user but they are not giving us data to do training & Implementation | NA | Recevied | Mar-26 | Mar-26
SPI109902253001 | 7449 | New | Account Activated | INDIANA GRATINGS PVT LTD | Premium | E | Disha Kiran Kargutkar | Akshay Shinde | 2025-07-14 | Akshay Joshi | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | SAAS | 440 | 2026-09-30 | 2025-02-17 | 2025-03-26 | 2025-03-31 | ENGG | 2026-05-13 | NX,ESSM,LV,TAM,REIMB,ELC,EXP,PMS,TRNG,RCT | Fresh | 0 | 79 | Spine HRMS | FC | Onsite | payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response | NA | Received | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Oct-25,Jul-26,Aug-26 | Aug-26
SPI109996251402 | 7445 | New | Account Activated | ISA LOGISTICS PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2025-12-05 | Mihir Navnath Mungekar | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2027-02-28 | 2025-02-14 | 2025-03-03 | 2025-03-24 | ENGG | 2026-03-12 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Completed the training of Payroll, Mobile and HRMS -E25mar9861 payroll process for the month of April 2025 has been processed successfully-E25may7360 May-2025 Salary Processed- E25may12012 June salary processed-W25jul6461 July salary processed August salary processed October month salary done Nov salary processed-E25dec1872 Dec salary processed- Processed the salary for Jan 26 got tallied for all employees-E26feb4932. PMS done- E26feb33. Feb salary processed-E26mar1563. march salary done April salary only 43 employees done new hr manager training completed Client has processed salary from excel. Currently client's priority is to process PMS from Spine, Once done they will process salary for May26 using only hrms module- E26jul2753. New user Mr. Rahul has shared HRMS Scope of Work for Review and Feasibility Confirmation and requirements has mentioned we are still working on it last working in 14th aug has been done by mihir and still we are working and need clarification by client and need to discuss with them. hrms queries are ongoing user has shared attached KRA and KPI document for reference sch to be aligned | Only HRMS | NA | Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26 | NA
SPG109937253101 | 7424 | New | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-07-09 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2025-02-12 | 2025-03-06 | 2025-03-07 | ENGG | 2025-08-14 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training & Implementation of Payroll NX is completed - #E25mar6319 February month salary processed & tallied - #E25mar6319 Training & Implementation of HRMS- Self service, Leave & Admin Module is completed - #E25mar6319 Attendance integration done & HRMS training done - #E25mar9245 logins rolled done to employees March month live salary processed Processing done from system months: FEB (E25MAR6319) JUL (E25aug1663) |  | NA | Dec-25 | Mar-26
SPA109926253101 | 7403 | New | Account Activated | ALLIED INSTRUMENTS PRIVATE LIMITED | Premium | E | Ankita Bankar | Amey Telge | 2026-05-25 | Vijay Bugde | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | On-Premises | 500 | 2027-01-31 | 2025-02-05 | 2025-02-08 | 2025-04-01 | ENGG | 2026-05-25 | NX,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | training and impl confirmation - E25apr6298 training provided on 28th july attendance centralization ongoing daman silvasa khar integration in process. ------------------------------------------ STUCK- july pending new user training provided queries resolving going on Manish ji said from spine we are getting good support, but its my team we are not on track lot many things are going -audits etc & they are hands on tally so getting out of comfort zone for them is the thing. will try to start processing for oct month. E25sep1678- aug processed by importing attendance they use spine for audit purpose only for jan salary we scheduled a session, we have added all the employees they have conveyed that they will start doing live salary within few months client only use our system when they have audit not going to process live salary go live mail sent to client- E26may9307 | NA | Received | Apr-25,May-25,July-25,Aug-25,Sept-25,Oct-25 | NA
SPG109930253101 | 7377 | New | Account Activated | GNG ELECTRONICS LIMITED STAFF | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-06-10 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 370 | 2027-04-30 | 2025-01-31 | 2025-02-12 | 2025-02-17 | ENGG | 2025-06-10 | NX, ESSM, LEAVE, TAM, Mobile HR, ELC | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535 |  | NA | Dec-25 | Mar-26
SPS109898253001 | 7359 | New | Account DeActivated | S K TRADERS NX | Premium | E | Usha Gupta | Viral Panchal | 2025-02-27 | Rahul Ankush Dalvi | Channel |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 25 | 2026-01-31 | 2025-01-30 | 2025-01-31 | 2025-02-12 | ENGG | 2025-04-08 | NX, ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | URL & Files awaiting, files received, imple from 12th, client will not use payroll #E25feb5774 HRMS training #E25feb5780 training done login will be share on 18th #E25feb6379, logins given Client live- #E25feb6379, training & imple done, client will not use payroll, using only HRMS, logins given. |  | received server setup amount pending (Write Off) | 0 | 0
SPK109842251001 | 7288 | New | Account Activated | KHERWADI SOCIAL WELFARE ASSOCIATION | Premium | E | Ankita Bankar | Probian Biswas | 2025-06-05 | Probian Biswas | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 650 | 2026-09-30 | 2025-01-14 | 2025-01-14 | 2025-01-24 | ENGG | 2025-07-08 | NX,ESSM, Leave, Time, Mobile HR, ELC, Claim & Reim | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Payroll Till Tax done/ HRMS & mobile app logins rolled out to employees - E25feb5562 HRMS training done & RCT module training & implementation done - E25feb5562 HRMS training done-E25jan12873 February month salary processed ELC, RCT, RD & PMS Module training & implementation is done April month salary processed May & June month salary processed live from system with attendance | Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary | NA | Mar-26 | Mar-26
SPM109810243112 | 7286 | New | Account DeActivated | MADHUSUMAN ENTERPRISES | Normal | E | Karuna Rajaram Sandim | Vinay Kareliya | 2025-05-07 | Tejas Rajesh Baragade | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 125 | 2025-12-31 | 2025-01-13 | 2025-01-15 | 2025-01-29 | ENGG | 2025-12-08 | NX,TAM | Fresh | 0 | 83 | Spine HRMS | FC Lost | Onsite | Welcome call done URL created #trng and impl from 29 th jan payroll training done - W25jan12818 HRMS on 12th feb We have completed the training on attendance module also december & January month salary process and tally. - W25feb5072 they are going to use mark in mark out, only for few empl if location is proper then logins logins done march salary 26 emp done, pending emp they will complete in this week In Madhusuman as there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | Received | Dec-24,Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25 | Aug-25
SPP109843251301 | 7282 | New | Account DeActivated | PARBHANI MEDICAL COLLEGE (PMC) | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera |  | Sushant Thombare | Channel |  |  | Jayesh Mojidra | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 500 | 2025-12-31 | 2025-01-13 | 2025-01-13 | 2025-02-14 | ENGG | 2026-01-31 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | Lost | Onsite | Welcome call done data file expl done Implementation starts from 14th feb 25 HRMS and Mobile HR Training Completed and All modules Explained and Showed by Engineer -W25feb8024 PayrollNg Training Completed and All modules Explained and Showed by Engineer and Jan 2025 salary Processed -W25feb6982 was following up the user since last week, however call was not received , Today had a call with him , he mentioned he was on leave past 8 to 10 days and now he is working on March salary and will reach out to me i assistance required, and for feb salary he will upload the past salary data. salary processed till march aprl salary mostly till next week, New biometric machine is installed, again we need to integrate data again, and now the user is admitted in hospital and currently there is no other user in his absence. April 25 Salary Process complete - E25may10890 In Parbhani , Half employees do not receive salary yet of april, they shall receive in May or june , told shreyas to take this on mail. May salary he shall process till 10th june. This email is to inform you that we have not been able to process the salaries for our remaining employees through your software. This is due to a temporary issue that we are actively working to resolve. We will resume full salary processing via your platform as soon as possible. We appreciate your understanding in this matter and will keep you updated on our progress. E25jun2237 They have fund issues that is the reason salary is delayed Salary processing is delayed every month as there is funds issue at client end, hence closing as lost | Funds issue | Received | Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Sept-25,Oct-25 | Oct-25
SPB109807243112 | 7268 | New | Account DeActivated | BENGAL ENERGY LTD- CONTRACTUAL | Premium | E | Mansi Singh | Probian Biswas |  | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1100 | 2025-03-31 | 2025-01-08 | 2025-01-15 | 2025-01-18 | ENGG | 2025-06-27 | NX,TAM | Fresh | 0 |  | Spine HRMS | Lost | Online | they clarified that there are no concerns or issues from Spine’s end. The current process is a business decision on their part. For contractual employees, the contractors submit attendance via Excel sheets, which the internal team simply verifies before processing payments. They also mentioned that they are in the process of streamlining their work process system. Once that is properly aligned, they will reconnect with Spine to proceed with the contractual employee license. | Finds excel easy | NA | 0 | 0
SPB109806243112 | 7267 | New | Account Activated | BENGAL ENERGY LTD- STAFF | Premium | E | Mansi Singh | Probian Biswas | 2025-05-26 | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 550 | 2026-10-31 | 2025-01-08 | 2025-01-15 | 2025-01-18 | ENGG | 2025-11-06 | NX,ESSM,LV,TAM,ELC,EXP,PMS | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189 |  | na | Dec-25 | Mar-26
SPT109788243112 | 7263 | New | Account Activated | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-03-05 | Sahil Gadhave | Channel |  |  | Nirbhay Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1400 | 2026-12-31 | 2025-01-07 | 2025-01-10 | 2025-01-23 | ENGG | 2025-07-10 | NX, ESSM, LEAVE, TAM, Mobile HR, ELC | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - 1) Ahemdabad Location PayrollNX Training and Dec'24 Salary Confirmation : W25jan10514 2) Kolkata Location PayrollNX Training and Dec'24 Salary Confirmation : E25jan12587 3) Ahemdabad Location Jan'25 live salary confirmation : W25feb1205 4) Ahemdabad Location Login rollout confirmation : W25feb2040 5) Spine HRMS - (Admin, ESSM. Leave module) training Confirmation : W25feb2040 6) Spine HRMS -Spine HRMS_Phase 1 Training Confirmation : W25feb2365 7) Kolkata Location Jan'25 live salary confirmation : W25feb3068 8) Kolkatta Location Login rollout confirmation : W25feb4649 9) Ahemdabad Attendance Integration Confirmation : E25feb7343 10) ELC module Training Confirmation : W25feb8518 11) Ahemdabad location Feb'25 Live salary confirmation along with Attendance : W25mar1674 12) Kolkatta location Feb'25 live Salary confirmation : W25mar1677 May month live salary processed from system June month live salary from with attendance from system is done |  | Received | Mar-26 | Mar-26
SPT109784243112 | 7262 | New | Account DeActivated | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-07-03 | Sahil Gadhave | Channel |  |  | Nirbhay Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1100 | 2025-05-31 | 2025-01-07 | 2025-01-10 | 2025-02-13 | ENGG | 2025-07-08 | NX, TAM, Mobile HR | Fresh | 0 | 66 | Spine HRMS | Go LIVE | Online | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved |  | Received | Apr-25,May-25 | NA
SPA109790243112 | 7258 | New | Account Activated | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Normal | E | Karuna Rajaram Sandim | Ganesh Jadhav | 2025-03-10 | Hardik Panchal | Direct |  |  | Tejas Kareliya |  | Vasu Mohan Dusa | SAAS | 145 | 2026-12-31 | 2025-01-07 | 2025-01-08 | 2025-01-30 | ENGG | 2025-03-11 | HRIS /Payroll NX,ESSM, Leave, Time Attendance, Mob | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Welcome call done data expl done Training starts from 30th 2025 #completed the Payroll Training and Also Employee rollout has been done and Also december salary has been matched with our records - E25feb974 employees training and all the queries have been resolved.-E25feb7093 salary for the month of February 2025 has been confirmed and tally. - E25mar1995 | Karuna in follow up for balance payment | Received | Dec-24,Jan-25,Feb-25 | Feb-25
SPS109684240612 | 7098 | New | Account DeActivated | SKY PRINTS | Normal | E | Disha Kiran Kargutkar | Viral Panchal | 2025-03-03 | Nagesh Tiwari | Channel |  | AVI DEALER | Manisha Singh |  | Vasu Mohan Dusa | SAAS | 100 | 2025-11-30 | 2024-12-06 | 2024-12-10 | 2024-12-20 | ENGG | 2025-03-11 | HRIS /Payroll NX, Workflow, Time Attendance, Mobil | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Direct Training & Implementation from 20th Dec We have completed and implementation and Training of spine HR and payroll NX We will discussed internally and will update and regarding roll out- W24dec7076 Need session for attendance integration and salary processing query on 28th Jan 2025 December salary done, we will process Jan salary till 03.02.2025 i will let u know if any issue happens, we have not decided to give the logins employees-E25jan8659 February Salary completed with attendance.-E25mar499 February Salary completed |  | NA | Nov-24,Dec-24,Jan-25,Feb-25 | Feb-25
SPN109637243011 | 7053 | New | Account DeActivated | NPSE AUTOMATION PVT. LTD. | Normal | E | Disha Kiran Kargutkar | Prathamesh Mandavkar |  | Nandadeep Mhatre | Channel | SA | Telly Soft Service Private Limited | Amit Arjun Sawant |  | Vasu Mohan Dusa | SAAS | 55 | 2025-02-28 | 2024-11-30 | 2024-11-30 | 2024-12-11 | ENGG | 2025-03-26 | HRIS /Payroll NX, Workflow, Leave, Time Attendance | Fresh | 0 | 56 | Spine HRMS | Lost | Online | Training & Implementation from 16th December 2024 We attend training of payroll nx & we have process salary of nov24 in payroll NX- E24dec3116 we have completed the Training of HRMS and its modules Admin,Leave and Time and MobileHR.-E24dec5532 Attendance integration issue not sorted as we have provided multiple solutions but they are not gave any response and also as cost barer regarding attendance integartions, solutions were provided: We have proposed the following solutions to retrieve attendance data in HRMS: Provide us with the attendance data in a SQL table in the format specified by Spine. Allow us to add the necessary extra fields to the SQL attendance table maintained by the biometric vendor. For daily attendance, use MobileHR, which will be reflected directly in HRMS and does not require a biometric machine. Based on your request, we have also suggested other biometric vendor recommendations. npse partner binu mathew is taking charge of attendance issue we need to wait for 2 days User and Owner not responding call and even mails. | Attendance Integration issue, vendor providing data only through API | SALES RETURN | Nov-24 | Nov-24
SPR109402242809 | 6837 | New | Account DeActivated | LOTUS TEXCOM INDIA LLP | Normal | E | Karuna Rajaram Sandim | Prathamesh Mandavkar |  | Prathamesh Mandavkar | Channel |  | SUN HEIGHTS - SA | Sandeep Ashok Joundal | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 51 | 2025-09-30 | 2024-10-08 | 2024-10-09 | 2024-12-27 | ENGG | 2025-07-28 | NG,TAM | Fresh | 0 |  | Spine NG | Lost | Online | mail done- call done, URL done, data file expln done Impelementation and trng starts from 27th dec 24 biometric data is not proper in atten sql problem from their side suggested vendor As my recent call with user for follow up, Mr. Vaibhav user told that as per their senior, they want unsubscribe the services, told him, whatever your concerns are kindly mail and let me know we can arrange meeting with PM and your senior awaiting mail from his end. user not responding, same is informed to PM and partner, partner team shall do visit at client placed as mentioned by them. Meeting arranged tomorrow for discussion with PM and Lotus Texcom Director. Spoke to Mr. Harshal , he mentioned there are issues going on and on , there were biometric issues, data was not not getting pushed in sql table its not syncing and Mr. Harshal does not want to invest in New Biometric Machine, he mentioned he has informed the same to Sun heights parther Mr. Liayakt too. | Attendance integration issue | WAIVE OFF | 0 | 0
SPG109421243009 | 6799 | New | Account DeActivated | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Normal | E | Ritika Dilip Singh | Shreyas Karkera | 2025-05-12 | Amit Krishnakant Tiwari | Direct |  |  | Ankur Yewalekar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 30 | 2025-09-30 | 2024-09-30 | 2024-10-07 | 2025-01-27 | ENGG | 2025-07-15 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC Lost | Onsite | #Payroll training has been completed, jan salary processing also done and salary tallied, further training and policy setup of hrms will be done next week - W25jan11630 W25mar3684 - HRMS Training is completed #W25apr9497 - march done with attendance #April'2025 Salary processed and Tally with attendance. #W25jul4405 - june salary done & live confirmation #FC LOST : The client was expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | NA | Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25 | Sept-25
SPH109257242608 | 6620 | New | Account Activated | HARDCARB TECHNOLOGIES PRIVATE LIMITED | Normal | E | Ankita Bankar | Prathamesh Mandavkar | 2025-04-09 | Tejas Rajesh Baragade | Direct |  |  | Amarprit Kaur |  | Vasu Mohan Dusa | SAAS | 250 | 2026-09-30 | 2024-08-26 | 2024-08-26 | 2024-09-16 | ENGG | 2025-04-09 | NX, TAM, Mobile HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training of payroll done - #E24oct8342 August month tallied HRMS training done - #E24oct8342 October month salary processed November month salary processed integration done February month salary processed March month live salary processing done with attendance from NX |  | Received | Feb-25 | Mar-25
SPM109213241208 | 6555 | New | Account Activated | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | Normal | E | Karuna Rajaram Sandim | Nagesh Tiwari | 2025-05-19 | Shubham Gurav | Direct |  |  | Giriraj Birendrasingh Tomar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 100 | 2027-07-31 | 2024-08-12 | 2024-08-13 | 2024-08-29 | ENGG | 2025-07-15 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary till Mar 25 and Process from April 25 -E25may5783 May salary done. after june we can do live. We have processed May 25 and June 25 salary with attendance for MUMBAI branch employees. We will get back for Wada branch salary processing -E25jul1557 aug salary shall be done till friday. | NA | Received | Dec-25,Aug-26 | Aug-26
SPC109142243107 | 6511 | New | Account DeActivated | CARTFIRE INDIA | Normal | E | Ankita Bankar | Viral Panchal | 2024-12-19 | Nagendra Poojary | Channel |  |  | Manisha Paradia |  | Vasu Mohan Dusa | SAAS | 26 | 2025-07-31 | 2024-08-03 | 2024-08-28 | 2024-10-09 | ENGG | 2025-02-11 | NX,ESSM, Leave, Time Attendance, Mobile HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Payroll, HRMS and mobile HR training completed - #E24sep6995 Integration is done # processed Oct & Nov. Salary with Attendance from HRMS - E24dec5935 December month salary processed January month salary processed |  | Received |  | Jan-25
SPV109057241607 | 6373 | Conv+New | Account Activated | V ALLIANCE NX | Normal | E | Usha Gupta | Viral Panchal | 2024-11-13 | Rahul Ankush Dalvi | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 1000 | 2027-06-30 | 2024-07-16 | 2024-07-17 | 2024-08-23 | ENGG | 2024-11-13 | Conv nx,TAM | Conversion | 0 | 100 | Spine HRMS | Go LIVE | Onsite | URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513 |  | NA | 0 | Oct-24
SPA108965242906 | 6265 | New | Account DeActivated | AQUAAIR INTERNATIONAL FREIGHT SERVICES | Normal | E | Karuna Rajaram Sandim | Viral Panchal | 2025-02-24 | Nagendra Poojary | Direct |  |  | Jigar Rupani |  | Vasu Mohan Dusa | SAAS | 45 | 2025-06-30 | 2024-06-29 | 2024-07-25 | 2024-09-16 | ENGG | 2025-04-09 | Payroll NX ,ESSM,Leave,Attendance, Mobile HR,,ELC | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Welcome call done data file explanation on 11th july 24 awaiting files training starts from 16 th sep 24 successfully completed the Payroll training and processed and verified the salary for the month of August using the Payroll system they have successfully logged into the app.-402035 HRMS training was successfully completed today.-402035 Salary processed till nov and dec salary they will process with attendance. queries resolved New user training has started. payroll training done , HRMS Training is done.W25mar9197 We have successfully processed salary of March 2025 with attendance from HRMS-W25mar9197 | Karuna in follow up, user waiting for management approval 24/2 | Received | Nov-24,Dec-24,Jan-25,Feb-25,Mar-25 | Mar-25
SPR108865241406 | 6151 | New | Account Activated | RADIX INNOVATIONS PRIVATE LIMITED | Normal | E | Karuna Rajaram Sandim | Arpit Patel | 2024-11-14 | Jay Jatinbhai Kansara | Channel | SA | KGSOFT TECHNOLOGIES | Deepak Choubisia |  | Vasu Mohan Dusa | SAAS | 59 | 2026-09-30 | 2024-06-14 | 2024-06-17 | 2024-06-24 | ENGG | 2024-11-30 | Payroll NX, TVL EXP, LVE, TAM, Mob | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | URL Done / Employee master done / Salar structure done / PayrollNX & HRMS Training done /Waiting for confirmation We have successfully completed the > Installation, Implementation & Training and Team RADIX INNOVATIONS > PRIVATE LIMITED is utilizing SPINE Payroll NX.-E24oct7557 October Salary processed -W24nov4114 | Need to visit onsite for suprise meet Renewal positive update by Arpit | NA |  | Oct-24
SPO108695241605 | 5973 | New | Account DeActivated | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera | 2025-05-13 | Tushar More | Direct |  |  | Nirbhay Kumar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 51 | 2026-05-31 | 2024-05-16 | 2024-06-06 | 2024-07-04 | ENGG | 2026-06-11 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC Lost | Onsite | Welcome Call done URL sent for creation training and Implementation from 4th july 24 We proceed july and august salary.-E24aug7741 ONETEAM LOGISTICS INDIA PRIVATE LIMITED- held up-22nd oct 24 we have completed the training of Payroll NX and HRMS till Self services. -E25feb8341 Add module welcome call done. following up with user for workflow and policies, however still files are not received Leave and TAM module impl and training aligned 4th april 2025 LEave tam training done and Integration done, following up with user he mentioned that still there are lot of queries , told him to mail and we can schedule the same, Schedule aligned for past salary and queries. tomorrow. 09th may. 25 We processed the salary april_2025 with attendance -W25may486 May salary has been processed, No response from user- project is stuck. user was busy in audit, and shall process aug sep in 1st week of oct. oct salary processed Nov will be done till 15th dec 25. user is not responding, we tried reaching out to user many times, no response hence closing as lost | Not responding no reason | NA | Nov-24,Dec-24,Jan-25,Feb-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26 | Mar-26
SPA108616242604 | 5883 | Conv | Account Activated | ANS NG | Normal | E | Ankita Bankar | Viral Panchal | 2024-05-16 | Aditya Mazire | Direct |  |  | Vaishali Ramniklal |  | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2024-04-27 | 2024-04-27 | 2024-05-15 | ENGG | 2024-06-07 | Con NX | Conversion | 0 | 100 | Spine NG | Go LIVE | Onsite | Training of Payroll NX is completed - #371589 March, April & May month salary processed. |  | NA | 0 | May-24
SPP108596242204 | 5850 | New | Account Activated | PVR CONTROLS -STAFF LICENSE | Normal | E | Usha Gupta | Ganesh Jadhav | 2025-02-07 | Shreyas Karkera | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 250 | 2027-04-30 | 2024-04-22 | 2024-04-27 | 2024-06-12 | ENGG | 2025-02-07 | HRIS /Payroll NX, ESSM, Lve, Tam, Mob, Travel exp, | Fresh | 0 | 88 | Spine HRMS | Go LIVE | Onsite | #Training completed #Attn Training integration and mobile training pending, salary processing parallel from dec they will process live, sep will be complete by 10th, session arranged on 10th for salary with attendance. No proper response for salary, sep done, oct done #E24nov2868, New biometric Machin installed, Nov done #E24dec4456, mail follow up for dec salary #E25jan4941, project live #E25feb2274 Client live - #E25feb2274, Trang & imple done, logins given, processing payroll parallelly, For PMS training client will get back |  | NA | 0 | Jan-25
SPM108453242903 | 5694 | Conv+New | Account Activated | MUKTANGAN EDUCATION TRUST. NX | Normal | E | Ankita Bankar | Viral Panchal | 2024-06-26 | Pritesh Barot | Channel |  |  | Sanket Gosalia |  | Vasu Mohan Dusa | SAAS | 608 | 2026-09-30 | 2024-03-29 | 2024-04-10 | 2024-04-26 | ENGG | 2024-06-26 | Conversion to NX, TAM, MOB HR | Conversion | 0 | 80 | Spine HRMS | Go LIVE | Onsite | Training & Implementation done April month salary processed May Month salary processed - #388257 Attendance module training done Ticket #393358: Project Live |  | NA | 0 | May-24
SPI108350242902 | 5579 | New | Account DeActivated | INFEXN LABORATORIES PVT LTD | Normal | E | Shivani Girish Dhonde | Ganesh Jadhav | 2024-05-09 | Shubham Gurav | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 200 | 2026-03-31 | 2024-03-06 | 2024-03-12 | 2024-03-21 | ENGG | 2024-06-07 | NX,ESSM, Lea, Tam, Mob HR, ELC, Rct, Trng, PMS, Re | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed. |  | Testimonial Received |  | May-24
SPM108327242902 | 5551 | Conv+New | Account Activated | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Normal | E | Mansi Singh | Prathamesh Mandavkar | 2024-07-10 | Mayur Pendhari | Direct |  |  | Jatin Thakkar |  | Vasu Mohan Dusa | SAAS | 700 | 2027-02-28 | 2024-02-29 | 2024-03-18 | 2024-03-22 | ENGG | 2024-07-15 | CONVNX, ESSM, Leave, Time Attendance, Mobile HR, | Conversion |  | 78 | Spine HRMS | Go LIVE | Onsite | go live- they want to keep the database separate and conversion will be done for both the companies Micropoint Computers Pvt Ltd. Goanfest Food & Beverages Pvt Ltd-#354379 Database Handholding Both Company Databases Confirmation. # 356675 PAYROLL NX TRAINING COMPLETED #358872 successfully processed month of March 2024 of both company from payroll NX System -363500 April- salary Process #375292 2nd Entity Salary For the month of April- 375286 rct mod they will get back to us when required. few employees are using mobile app for marking attendance disbursing salary live from spine |  | NA | 0 | Jun-24
SPF107062230902 | 5312 | Add Mod | Account Activated | FFSERVICES PRIVATE LIMITED | Normal | E | Ankita Bankar | Ganesh Jadhav | 2024-01-29 | Gaurav Karmokar | Direct |  |  | Bhumika Yogesh Arsania |  | Vasu Mohan Dusa | SAAS | 220 | 2026-09-30 | 2024-01-03 | 2024-01-03 | 2024-01-09 | ENGG | 2024-01-29 | Claim & Reimbursement, Travel Expense | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Training done. Expense Module Training to the Employees and Implementation Confirmation - # 335312 |  | NA | 0 | Dec-23
SPL103086181602 | 5165 | Conv | Account Activated | LATHIA RUBBER MFG CO. PVT. LTD. | Normal | B | Usha Gupta | Viral Panchal | 2024-03-15 | Yash Pankajkumar | Direct |  |  | Pragnesh Panchal |  | Vasu Mohan Dusa | On-Premises | 750 | 2026-10-31 | 2023-11-30 | 2024-01-11 | 2024-01-25 | ENGG | 2024-03-15 | Conv nx | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Pre-requisites & DB awaiting, DB will shared by 2nd, Upasana coordinating with user for amc payment, DB received, installation pending, DB hand holding done #329264, training date awaiting, Training from 25th. Training completed #337791, session arranged on 5th for salary Jan salary #341460, Feb Done #352253 |  |  | Jan-24 | Feb-24
SPP100297152606 | 4978 | Conv | Account Activated | PITAMBARI PRODUCTS PVT. LTD. | Normal | A | Usha Gupta | Prathamesh Mandavkar | 2024-01-10 | Santosh Yadav | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | On-Premises | 1500 | 2027-03-31 | 2023-10-04 | 2023-11-21 | 2023-11-23 | ENGG | 2024-02-13 | Conv nx | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Pre-requisites & DB awaiting, busy in salary will share DB by 20th #303229, DB back up will be shared by 10th Nov #307079, DB backup received, DB Hand Holding done #316236, training from 23rd, Nov Salary #320399, #320827, Dec salary #330763, jan done #344213 |  |  | Nov-23,Dec-23,Jan-24 | Jan-24
SPS107683233108 | 4861 | Conv+New | Account DeActivated | SANKALPAN INFRASTRUCTURE PVT. LTD. | Normal | E | Ankita Bankar | Viral Panchal | 2024-04-25 | Rahul Ankush Dalvi | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 70 | 2025-09-30 | 2023-09-04 | 2023-09-13 | 2023-10-09 | ENGG | 2024-04-25 | ConvNX, ESSM, Leave, TAM, MOB, ELC, PMS | Conversion |  | 78 | Spine HRMS | Go LIVE | Onsite | Training of Payroll NX & HRMS is completed - #305568 August, October & November month salary processed - #321444 December month salary processed - #335184 Logins rolled out - #338967 January month salary processed - #346574 February month salary processed - 358372 March month salary processed - #362620 Project live - 370783 |  | Testimonial Received | March-24 | March-24
SPT107662232808 | 4859 | New | Account Activated | NATIONAL SPORTS CLUB OF INDIA NX | Escalated | B | Disha Kiran Kargutkar | Vinay Kareliya |  | Mihir Navnath Mungekar | Channel |  |  | Sanket Gosalia | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 450 | 2026-07-31 | 2023-09-02 | 2023-10-04 | 2023-12-27 | ENGG |  | NX,LV,TAM | Fresh | 0 | 68 | Spine HRMS | Active | Onsite | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. 4th and 5th September 2026 training and validation activities. | Meeting with the union done, policy changes approval received, need to proceed further & renewal upcoming | Received |  | 0
SPA106322220704 | 4763 | Add Mod | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Prathamesh Mandavkar | 2023-10-09 | Goraksha Pawar | Channel |  | AVI DEALER | Jayesh Mojidra |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2023-08-08 | 2023-08-09 | 2023-08-18 | ENGG | 2023-10-09 | Travel exp, Travel Desk | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite | Files & Policy awaiting, training from 18th. training completed #287080, logins will be shared by 1st week of sep, logins will be shared by 16th sep Training completed, Logins will share as per their convenient. #302271 |  |  | 0 | 0
SPS107604233107 | 4749 | Conv+New | Account Activated | SAI SANKET INDUSTRIES PVT.LTD. NX | Normal | E | Mayuri Thackrey | Viral Panchal | 2023-11-02 | Dakshesh D Nadkar | Channel |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 251 | 2027-07-31 | 2023-08-02 | 2023-08-07 | 2023-08-21 | ENGG | 2023-12-14 | ConvNX,ESSM, LV,TAM,EXP,MOB | Conversion |  | 86 | Spine HRMS | Go LIVE | Onsite | Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth |  |  | 0 | Nov-23
SPP102671182910 | 4620 | Conv | Account Activated | PRASHANT CORNER PRIVATE LIMITED | Normal | A | Nilima Karmokar | Prathamesh Mandavkar | 2023-09-26 | Akshay Joshi | Direct |  |  | Jatin Thakkar |  | Vasu Mohan Dusa | On-Premises | 1500 | 2026-11-30 | 2023-06-28 | 2023-07-21 | 2023-07-31 | ENGG | 2023-09-26 | conv to NX | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Training completed: #283586 Aug Slary done Live from NX: #296319 live mail shred by us : 299979 |  |  | Aug-23 | Aug-23
SPM107218233003 | 4259 | Conv+New | Account Activated | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Premium | C | Usha Gupta | Ganesh Jadhav | 2023-05-12 | Aditya Pathak | Channel |  |  | Jayesh Mojidra |  | Vasu Mohan Dusa | On-Premises | 1410 | 2027-03-31 | 2023-03-30 | 2023-04-13 | 2023-04-25 | ENGG | 2023-06-09 | Conv NX | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Database back up after 15th april, Busy in tds work. installation done, Database in conversion, DB Hand holding done #241335, training from 25th, Training done #247004, april salary will be processed by 10th, april done #253524, may done #263924 |  | Testimonial Received | March-23,April-23,May-23 | May-23
SPM107089232402 | 4244 | Conv+New | Account Activated | MUMBAI CARGO SERVICE CENTER AIRPORT PVT. LTD NX | Normal | E | Aisha Patel | Ganesh Jadhav | 2023-10-09 | Gaurav Karmokar | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 695 | 2027-02-28 | 2023-03-24 | 2023-03-29 | 2023-04-19 | ENGG | 2023-10-09 | Conv to NX, ESSM,LV,TAM,MOB | Conversion |  | 42 | Spine HRMS | Go LIVE | Onsite | Conv conf 243113. Training done on all module. March salary processed and tallied 245031. April Live done 252891. May done 263687. June done. Logins pending. July done. Aug & Sept processed. For Attend module client will get back later. Integration done |  |  | 0 | Sept-23
SPE107169232103 | 4199 | New | Account Activated | ELIXRR INDUSTRIES PVT LTD. | Normal | E | Nilima Karmokar | Ganesh Jadhav | 2023-06-06 | Krishna Yadav | Direct |  |  | Kishan Joshi |  | Vasu Mohan Dusa | SAAS | 1008 | 2027-03-31 | 2023-03-21 | 2023-03-23 | 2023-04-19 | ENGG | 2023-07-14 | HRIS /Payroll NX, WF, ESSM, LV, TAM, ELC, Mobile H | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817 |  |  | April-23,May-23,Jun-23 | Jun-23
SPS101600122310 | 4067 | Conv | Account Activated | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Normal | C | Usha Gupta | Viral Panchal | 2023-03-25 | Pritesh Barot | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | On-Premises | 250 | 2027-03-31 | 2023-02-09 | 2023-02-22 | 2023-02-28 | ENGG | 2023-06-06 | Conv,ELC | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us. |  |  | Feb-23,April-23 | April-23
SPF107062230902 | 4066 | New | Account Activated | FFSERVICES PRIVATE LIMITED | Premium | E | Aisha Patel | Prathamesh Mandavkar | 2023-04-27 | Mayur Pendhari | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | SAAS | 220 | 2026-09-30 | 2023-02-09 | 2023-02-13 | 2023-02-27 | ENGG | 2023-07-11 | NX,ESSM,LV,TAM,MOB,ELC,RCT,PMS,RD | Fresh |  | 63 | Spine HRMS | Go LIVE | Onsite | Payroll NX Training done 221803 HRMS Done. Logins given. Feb done. March & April done. May Live done 263263 For Phase 2 client will get back - 275285 |  | Testimonial Received | 0 | Jun-23
SPA106322220704 | 3920 | Add Mod | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Hemanshu Wadia | 2023-05-08 | Vinay Kareliya | Channel |  | AVI DEALER | Jayesh Mojidra |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2023-01-13 | 2023-01-13 | 2023-05-05 | ENGG | 2023-05-09 | PMS | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Files & policy awaiting, training probably on 20th. client will get back for pms training #215285, no response for standard training & files. Pms Standard training probably by 20th. April., required training on 5th May, Training completed logins will be share in july month #251187 |  |  | 0 | 0
SPA106322220704 | 3053 | New | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Prathamesh Mandavkar | 2022-08-13 | Nayan Choudhary | Channel |  | AVI DEALER | Jigar Rupani |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2022-04-07 | 2022-04-11 | 2022-05-05 | ENGG | 2022-08-13 | NX,ESSM,LV,TAM | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite | July done #168845 |  |  | May-22,Jun-22,Jul-22 | Jul-22
SPA104424190108 | 2980 | Add Mod | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Aisha Patel | Prathamesh Mandavkar | 2022-04-12 | Nayan Choudhary | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2022-01-29 | 2022-01-29 | 2022-02-09 | ENGG | 2022-04-12 | LV | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPV106083220301 | 2919 | Conv+New | Account Activated | VIPUL ORGANICS LTD. - STAFF | Premium | E | Aisha Patel | Hemanshu Wadia | 2022-06-15 | Santosh Yadav | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | SAAS | 145 | 2026-09-30 | 2022-01-06 | 2022-01-06 | 2022-01-17 | ENGG | 2022-06-15 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite | Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745 |  |  | 0 | 0
SPP105402212702 | 2522 | Add Mod | Account Activated | PISCES CONTAINER LINES INDIA PVT. LTD. | Normal | E | Jyoti Mishra | Viral Panchal | 2021-11-11 | Pritesh Barot | Channel |  |  | Kunal Joshi |  | Vasu Mohan Dusa | SAAS | 100 | 2027-02-28 | 2021-08-10 | 2021-08-10 | 2021-08-19 | ENGG | 2021-11-11 | TAM | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPK100839081706 | 2324 | Conv | Account Activated | KAMAL ENTERPRISES | Normal | A | Nilima Karmokar | Hemanshu Wadia | 2021-11-02 | Santosh Yadav | Direct |  |  | Kishan Joshi |  | Vasu Mohan Dusa | Hosting | 2500 | 2026-12-31 | 2021-04-22 | 2021-04-22 | 2021-05-13 | ENGG | 2021-11-02 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPE105433211303 | 2203 | New | Account Activated | ESCON ELEVATORS PVT. LTD. | Normal | A | Riya Jindam | Viral Panchal | 2022-02-07 | Probian Biswas | Channel |  | SOFTCORE SOLUTIONS PVT. LTD. | Jigar Rupani |  | Vasu Mohan Dusa | On-Premises | 805 | 2027-03-31 | 2021-03-11 |  | 2021-04-12 | ENGG | 2022-02-07 |  | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPP105402212702 | 2164 | New | Account Activated | PISCES CONTAINER LINES INDIA PVT. LTD. | Normal | E | Jyoti Mishra | Viral Panchal | 2021-08-14 | Krunal Pandya | Channel |  |  | Kunal Joshi |  | Vasu Mohan Dusa | SAAS | 100 | 2027-02-28 | 2021-03-01 |  | 2021-03-08 | ENGG | 2021-08-14 |  | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPC104730192512 | 1387 | New | Account Activated | CHEMITO INFOTECH PVT.LTD. |  | D | Riya Jindam | Prathamesh Mandavkar |  | Sonali Shejaval | Direct |  |  |  |  | Vasu Mohan Dusa | SAAS | 310 | 2026-09-30 | 2019-12-25 |  | 2019-12-25 | ENGG | 2020-05-09 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPA104424190108 | 1042 | Conv+New | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Riya Jindam | Prathamesh Mandavkar |  | Akshay Halankar | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2019-07-31 |  | 2019-07-31 | ENGG | 2019-10-07 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPP102671182910 | 298 | New | Account Activated | PRASHANT CORNER PRIVATE LIMITED |  | A |  | Hemanshu Wadia |  | Darshit Pithwa | Direct |  |  |  |  | Vasu Mohan Dusa | On-Premises | 1500 | 2026-11-30 | 2018-09-26 |  | 2018-09-26 | ENGG | 2019-05-25 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0
SPL103086181602 | 29 | New | Account Activated | LATHIA RUBBER MFG CO. PVT. LTD. |  | B | Riya Jindam | Prathamesh Mandavkar |  | Prathamesh Mandavkar | Direct |  |  |  |  | Vasu Mohan Dusa | On-Premises | 750 | 2026-10-31 | 2018-10-13 |  | 2018-10-13 | ENGG | 2019-01-19 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0