## Sheet1
Project Code | Project Type | Project Name | Received From | Start date | End Date | Priority | Status | PM Note | Risk Identified | Employee Count | Product | Assigned Engineer | Team Leader | Marketing Executive | Client Type
5001 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Schedule | 2025-01-07 | 2025-10-28 | Low | Completed |  |  | 1270 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost |  |  | 1100 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal
5003 | Escalation | Maharashtra Book Manufacturing | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Shubham Gurav | Nagesh Tiwari | Giriraj Birendrasingh Tomar | Normal |  | 35/79(100)
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 35 | NX | Paras Mahesh Ladva | Viral Panchal | Anuj Kumar Ganga Prasad Tiwari | Normal | 100% | 5/5(35)
5005 | Allocation | Bengal Energy_Staff | Schedule | 2025-01-08 | 2026-03-30 | Low | Completed |  |  | 550 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium |  | 2085/2085(2100)
5006 | Allocation | Bengal Energy_Worker | Schedule | 2025-01-08 | 2025-06-30 | Low | Lost |  |  | 1100 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium
5007 | Allocation | Parbhani Medical College | Schedule | 2025-01-13 | 2026-01-28 | Low | Lost |  |  | 500 | NG | Sushant Thombare | Shreyas Karkera | Jayesh Mojidra | Normal
5008 | Escalation | Aquaair International Frieght Services | Schedule | 2025-01-13 | 2025-04-25 | Low | Completed |  |  | 45 | NX | Nagendra Poojary | Viral Panchal | Jigar Rupani | Normal |  | 45/45(45)
5009 | Escalation | Hardcarb Technologies Private Limited | Maketing | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 250 | NX | Tejas Rajesh Baragade | Prathamesh Mandavkar | Amarprit Kaur | Normal |  | 162/180(180)
5010 | Allocation | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Schedule | 2025-01-14 | 2025-07-17 | Low | Completed |  |  | 125 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Ankur Yewalekar | Normal |  | 111/111(125)
5011 | Allocation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Schedule | 2025-01-14 | 2025-10-28 | Low | Completed |  |  | 350 | NX | Probian Biswas | Probian Biswas | Aparna Santosh | Premium |  | 234/255(300)
5012 | Escalation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Schedule | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Amit Krishnakant Tiwari | Shreyas Karkera | Ankur Yewalekar | Normal
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed |  |  | 270 | NX | Goraksha Pawar | Prathamesh Mandavkar | Amarprit Kaur | Normal | 100% | 178/182(270)
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Santosh Yadav | Prathamesh Mandavkar | Aparna Santosh | Normal | 100% | 29/29(30)
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 55 | NX | Hardik Panchal | Ganesh Jadhav | Pragnesh Panchal | Normal |  | 41/41(50)
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed |  |  | 80 | NX |  | Hiren Bhimani | Manisha Paradia | Normal | 100%
5017 | Escalation | Cartfire India | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 26 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal | 100% | 22/22(26)
5018 | Escalation | Sky Prints | Schedule | 2025-01-25 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Nagesh Tiwari | Viral Panchal | Manisha Singh | Normal |  | 53/60(100)
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed |  |  | 500 | NX | Vikas Yadav | Prathamesh Mandavkar | Pragnesh Panchal | Normal | 100%
5020 | Allocation | S K Traders | Schedule | 2025-01-31 | 2025-06-30 | Low | Completed |  |  | 25 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Premium
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 132 | NX | Darshit Pithwa | Hemanshu Wadia | Nikhil Solanki | Normal | 100% | 93/111(140)
5022 | Escalation | Infexn Laboratories | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 200 | NX | Shubham Gurav | Ganesh Jadhav | Nirbhay Kumar | Normal | 100%
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost |  |  | 70 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Normal
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed |  |  | 42 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Aparna Santosh | Normal
5025 | Allocation | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Schedule | 2025-02-18 | 2026-02-27 | Low | Completed |  |  | 465 | NX | Rahul Ankush Dalvi | Akshay Shinde | Sanket Gosalia | Premium
5026 | Allocation | RADIX ELECTROSYSTEMS PVT LTD | Schedule | 2025-02-18 | 2026-03-30 | Low | Completed |  |  | 630 | NX | Aditya Pathak | Probian Biswas | Pragnesh Panchal | Normal
5027 | Allocation | MARU CONSULTANCY SERVICES | Schedule | 2025-02-19 | 2025-06-04 | Low | Lost |  |  | 150 | NG | Ruchit Shailesh Patel | Probian Biswas | Manisha Singh | Normal
5028 | Allocation | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Schedule | 2025-02-24 | 2026-01-28 | Low | Completed |  |  | 300 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Manisha Singh | Premium
5029 | Allocation | APLAB LIMITED (FOR STAFF LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 165 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal
5030 | Allocation | APLAB LIMITED (FOR CONTRACT LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 251 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal
5031 | Escalation | NPSE AUTOMATION PVT. LTD | Schedule | 2025-02-12 | 2025-04-25 | Low | Lost |  |  | 55 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Amit Arjun Sawant | Normal
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed |  |  | 125 | NG | Vinay Kareliya | Vinay Kareliya | Tejas Kareliya | Normal
5033 | Allocation | KARVY TECHNOLOGIES PVT LTD | Schedule | 2025-03-03 | 2026-03-30 | Low | Lost |  |  | 130 | NG | Tejas Rajesh Baragade | Vinay Kareliya | Vaishali Ramniklal Puj | Normal
5034 | Allocation | QUALIGENS PHARMA PVT. LTD | Schedule | 2025-03-07 | 2025-10-28 | Low | Completed |  |  | 400 | NX | Ruchit Shailesh Patel | Probian Biswas | Giriraj Birendrasingh Tomar | Normal
5035 | Allocation | MADURA INDUSTRIAL TEXTILES LIMITED | Schedule | 2025-03-10 | 2026-04-28 | Low | Completed |  |  | 287 | NX | Varun Rajbhar | Vinay Kareliya | Jayesh Mojidra | Normal
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed |  |  | 700 | NG | Sahil Gadhave | Sahil Gadhave | Santosh Bhoja Shetty | Normal
5037 | Allocation | STEAM PULSE INDIA PVT LTD | Schedule | 2025-03-25 | 2025-10-28 | Low | Completed |  |  | 140 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal
5038 | Allocation | STEAM HARBOUR LOGISTICS PVT LTD | Schedule | 2025-03-25 | 2026-01-28 | Low | Completed |  |  | 60 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed |  |  | 1250 | NX | Sachin Thothawala | Sachin Thothawala | Tejas Kareliya | Normal
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed |  |  | 850 | NX | Kajal Inchanalkar | Saurabh Pednekar | Mehul Patel | Normal
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed |  |  | 60 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active | Monday Meeting scheduled with Payal for further plan of action and date for payment release |  | 450 | NX | Mihir Navnath Mungekar | Vinay Kareliya | Sanket Gosalia | Premium
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed |  |  | 400 | NX | Amol Takkar | Amol Takkar | Tejas Kareliya | Premium
5044 | Allocation | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Schedule | 2025-04-01 | 2026-04-28 | Low | Completed |  |  | 1000 | NX | Kunal Joshi | Sahil Gadhave | Jayesh Mojidra | Premium
5045 | Escalation | SAI SANKET INDUSTRIES PVT.LTD | Schedule | 2025-04-01 | 2025-05-25 | Low | Completed |  |  | 410 | NX | Dakshesh D Nadkar | Viral Panchal | Nirbhay Kumar | Premium
5046 | Escalation | LOTUS TEXCOM INDIA LLP | Schedule | 2025-04-04 | 2025-07-23 | Low | Lost |  |  | 51 | NG | Prathamesh Mandavkar | Prathamesh Mandavkar | Sandeep Ashok Joundal | Normal
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed |  |  | 185 | NX | Probian Biswas | Viral Panchal | Tejas Kareliya | Normal
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed |  |  | 205 | NX | Vikas Yadav | Prathamesh Mandavkar | Nikhil Solanki | Normal
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed |  |  | 60 | NX | Supriya Waghmare | Hemanshu Wadia |  | Normal
5050 | Escalation | BASANT OVERSEAS | Schedule | 2025-04-25 | 2026-03-30 | Low | Lost |  |  | 1454 | NG | Yash Pankajkumar Shah | Akshay Shinde | Jayesh Mojidra | Normal
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost |  |  | 100 | NX | Rahul Ankush Dalvi | Viral Panchal | Aparna Santosh | Normal
5052 | Allocation | SNAPWORK TECHNOLOGIES PVT LTD | Schedule | 2025-05-03 | 2026-02-27 | Low | Completed |  |  | 360 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Normal
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 630 | NX |  | Hiren Bhimani | Rushabh Dinesh Shah | Normal
5054 | Allocation | BRIGHT BROTHERS LTD. / BRITE | Schedule | 2025-05-27 | 2026-02-27 | Low | Completed |  |  | 520 | NG | Rahul Ankush Dalvi | Akshay Shinde | Anuj Kumar Ganga Prasad Tiwari | Normal
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 45 | NX | Mayur Pendhari | Akshay Shinde | Manisha Singh | Normal
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed |  |  | 151 | NX | Shreyas Karkera | Shreyas Karkera | Vaishali Ramniklal Puj | Normal
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost |  |  | 25 | NX |  |  | Sanket Gosalia | Normal
5058 | Escalation | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-08-30 | Low | Completed |  |  | 51 | NX |  |  | Nirbhay Kumar | Normal
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 495 | NX | Amol Takkar | Amol Takkar | Sanket Gosalia | Premium
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 300 | NX | Mukeshkumar Shojiram kumavat | Nagesh Tiwari | Aparna Santosh | Premium
5061 | Allocation | GNG ELECTRONICS LIMITED STAFF | Schedule | 2025-06-01 | 2025-10-28 | Low | Completed |  |  | 250 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost |  |  | 750 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal
5063 | Allocation | ALLIED INSTRUMENTS PRIVATE LIMITED | Schedule | 2025-06-01 | 2026-03-30 | Low | Completed |  |  | 500 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Premium
5064 | Allocation | MESPACK INDIA PVT. LTD | Schedule | 2025-06-09 | 2026-04-28 | Low | Completed |  |  | 50 | NG | Pooja Vikas Shinde | Akshay Shinde | Sandeep Ashok Joundal | Normal
5065 | Allocation | UNITED AIR EXPRESS | Schedule | 2025-06-20 | 2026-04-28 | Low | Completed |  |  | 2550 | NG | Shubham Gurav | Nagesh Tiwari | Nirbhay Kumar | Normal
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost |  |  | 200 | NG | Santosh Yadav | Vinay Kareliya | Giriraj Birendrasingh Tomar | Normal
5067 | Escalation | ISA Logistics Private Limited | Schedule | 2025-06-19 | 2025-07-23 | Low | Completed |  |  | 200 | NG | Mihir Navnath Mungekar | Vinay Kareliya | Ankur Yewalekar | Normal
5068 | Escalation | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Support | 2025-06-27 | 2025-07-23 | Low | Completed |  |  | 250 | NX | Pritesh Barot | Viral Panchal | Nikhil Solanki | Normal
5069 | Escalation | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Schedule | 2025-07-12 | 2025-08-30 | Low | Completed
5070 | Escalation | CONTENDRE GREENERGY LIMITED | Schedule | 2025-07-15 | 2025-08-30 | Low | Completed
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed
5072 | Escalation | ROYAL EMBROIDERY THREADS PVT.LTD. | Schedule | 2025-07-17 | 2025-08-30 | Low | Completed
5073 | Escalation | V ALLIANCE NX | Schedule | 2025-07-18 | 2025-08-30 | Low | Completed
5074 | Escalation | UNITED AIR EXPRESS | Schedule | 2025-07-18 | 2025-08-21 | Low | Completed
5075 | Escalation | ESCON ELEVATORS PVT. LTD. | Schedule | 2025-07-23 | 2025-08-30 | Low | Completed
5076 | Allocation | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Schedule | 2025-08-02 | 2026-04-28 | Low | Lost
5077 | Allocation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Schedule | 2025-08-06 | 2026-04-28 | Low | Lost
5078 | Escalation | FFSERVICES PRIVATE LIMITED | CR | 2025-08-12 | 2025-11-28 | Low | Completed
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost
5080 | Allocation | SETHWALA FOODS LTD | Schedule | 2025-08-21 | 2026-05-26 | Low | Completed
5081 | Allocation | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Schedule | 2025-08-01 | 2026-01-28 | Low | Completed
5082 | Escalation | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Schedule | 2025-08-14 | 2025-09-24 | Low | Completed
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed
5084 | Escalation | VABA | Schedule | 2025-08-04 | 2025-10-28 | Low | Completed
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed
5086 | Escalation | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Schedule | 2025-08-22 | 2025-09-24 | Low | Completed
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 | 2026-09-30 | Low | Completed | Renewal Done, payment confirmation received by Accounts team
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active | Query Resolution onsite Sessions ongoing
5093 | Escalation | DRS EARTHWORK PRIVATE LIMITED | Schedule | 2025-09-24 | 2025-11-28 | Low | Completed
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost
5095 | Escalation | PISCES CONTAINER LINES INDIA PVT. LTD. | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5097 | Allocation | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Schedule | 2025-10-08 | 2026-04-28 | Low | Completed
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed
5099 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active | September Salary Processing scheduled
5101 | Allocation | VIVID ELECTROMECH LTD. / VIVID GROUP | Schedule | 2025-10-30 | 2026-04-28 | Low | Completed
5102 | Allocation | SREE METALIKS LTD | Schedule | 2025-11-11 | 2026-04-28 | Low | Completed
5103 | Escalation | NAGRIK CONSULTANCY SERVICES | Schedule | 2025-11-10 | 2026-02-27 | Low | Completed
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed
5109 | Allocation | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Schedule | 2025-11-26 | 2026-07-31 | Low | Completed | June 2026 Salary Completed with Attendance W26jul873.
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed
5111 | Allocation | NIKIKA ENTERPRISES LLP | Schedule | 2025-11-29 | 2026-05-26 | Low | Completed
5112 | Allocation | PRIJAI HEAT EXCHANGERS PVT. LTD. | Schedule | 2025-12-10 | 2026-04-28 | Low | Completed
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed
5114 | Allocation | PANKAJ FASHION PVT LTD | Schedule | 2026-01-09 | 2026-08-11 | Low | Lost | Client is not interested and said won't be renewing
5115 | Allocation | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Schedule | 2026-01-16 | 2026-04-28 | Low | Lost
5116 | Escalation | GNG ELECTRONICS LIMITED STAFF | Maketing | 2026-01-19 | 2026-01-22 | Low | Completed
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed
5118 | Escalation | Seventy Seven Entertainment Pvt Ltd | Schedule | 2026-01-19 | 2026-03-30 | Low | Completed
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active | Discussion done with Probian, He would be sending a final mail with all the pointers with possible and not possible status remark
5120 | Allocation | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Schedule | 2026-01-31 | 2026-04-28 | Low | Completed
5121 | Allocation | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Schedule | 2026-02-09 | 2026-05-26 | Low | Completed
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed
5126 | Escalation | Elixrr Industries Pvt. Ltd. | Maketing | 2026-02-10 | 2026-04-28 | Low | Completed
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed
5128 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2026-02-25 | 2026-03-30 | Low | Completed
5129 | Allocation | STORM FINANCIAL SERVICES | Schedule | 2026-03-28 | 2026-07-31 | Low | Lost | Client is not responding and is not interested, mail has been shared and an Onsite visit scheduled along with Mukesh
5130 | Escalation | CIRCLE RESOURCES PRIVATE LIMITED | Schedule | 2026-03-12 | 2026-03-30 | Low | Completed
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active | Discussion done with Sheetal Ji, she said everything is aligned and progressing properly, she is coordinating with Atul Ji for further plan of action.
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active | Review Call done with Sadhana, she said sorry and due to internal work processes she does not get time for spine. Tired to understand her processes, salary processing involved Accounts team, so informed her to let us have a common meeting to discuss the roles and accordingly segregate and start the training and implementation. Sadhana to discuss the same internally and arrange for a review meeting.
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | Review Call done with Siddhi, she said everything is streamlined, she highlighted mobile app related login issues informed her basic pratices like clearing the cache and app data etc and if it still doesnt work to raise a ticket, about the payment part she said she has already submitted it to the team for approval, and it will be cleared by the next week.
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active | PMS Training Completed, September Live Planned
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active | #26/09 - new user payroll trng and HRMS trng completed, awaiting for confirmation, will do salary with attendance by 11th.
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed
5137 | Escalation | VIPUL ORGANICS LTD. - STAFF | Schedule | 2026-05-01 | 2026-05-26 | Low | Completed
5138 | Allocation | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Schedule | 2026-05-04 | 2026-08-31 | High | Lost | Live Salary Processing planned
5139 | Allocation | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Schedule | 2026-05-06 | 2026-08-31 | High | Completed | Everything is aligned and leave configuration and live salary processing on going
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed | Live Salary Processing aligned
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active | Payroll training completed-E26apr9978 Hrms training completed-E26apr11242 April salary processed and tallied-E26may4682 May salary done-E26jun6874 contrctual attendance will be by uploading June salary processed. july salary processed The user is now looking for the shortest possible solution for uploading attendance to save time and effort. mail done from outlook that they will upload attendance and do salary . As discussed with client they confirmed us that Till August 2026 we update contractor attendance & salary for report purpose only. We will try to update salary till 7th Oct 2026.-E26sep6547
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active | Review Meeting done along with Partner Team, New HR has joined in, highlighted all the challenges and progress of all the 3 licenses, He said he will discuss and review the same internally and revert on the same.
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active | Discussion done with Pradeep, payment has been sent to their accounts team for processing, he will update tom
5146 | Escalation | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Schedule | 2026-05-19 | 2026-07-31 | High | Completed | Live Salary Processing
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active | C Shift issue done, verification pending
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost | Reminder sent to the user for data and further plan of action
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active | Live Salary Processing planned for September
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active | Live Salary Processing Done
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active | Live Salary Planned for September
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active | Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed | The management has decided not to proceed further and is not willing to continue.
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active | September Salary Processing is being planned
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active | Ongoing Queries session planned
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active | Live Salary processing done, Additional Modules planned for October
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active | #5/10 - as per last sch, salary process was completed, including batch creation, Paytime Basket upload, validation, salary slip generation, and salary register export. The user will check the salary register and confirm the results.
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active | Live Salary Processing Ongoing
5159 | Escalation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Schedule | 2026-06-23 | 2026-07-31 | High | Lost | Discussion done with Amit (Director), explained the current situation, he said Rajesh will coordinate and close the same. Discussion done with Probian, he said coodinated with Rajesh and resolved pending items and processed salary as well and about the payment they would be processing the same in a day or two.
5160 | Escalation | ANS NG | Schedule | 2026-06-24 | 2026-09-30 | High | Completed | Live Salary Processing Done
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 | 2026-09-30 | High | Completed | Salary Processing Session planned
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 | 2026-09-30 | High | Completed | Transfered to Amit Sir
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active | Review Call done with Roshni, everything is now aligned, Pranali is connected for ongoing quries
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active | Review call done with Rahul, he said everything is proper, he was busy in payroll and Archana is connecting properly. He said initial training is done, he will now verify everything and again connect with Archana and plan for login roll out as well.
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active | Training & Implementation of Payroll is compelted along with August month tallied - #E26sep2251 Training & Impelmentation of ESSM, LV & TAM is completed along with Mobile HR - #E26sep2251
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active | September month live target with attendance
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active | processed salary for the month of August 2026 and tallied - W26sep2575
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active | Implementation & Training Planned for Oct
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Active | processed the August 2026 salary and tallied the processed salary data to verify the calculations and ensure the salary processing was completed correctly. |  |  |  | Varun | Vinay
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Active | Backend Working done, Onsite Training Sessions Ongoing |  |  |  | Tejas | Vinay
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start |  |  |  |  | Santosh | Vinay
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Active | #29/09 - today sch aligned for emp. trng #E26sep7598 - Payroll-NG Conf. till Loan Mod. #E26sep8088 - payroll confirmation #E26sep9506 - HRMS & Mob App confirmation
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start | Conversion activity - company realted discuss is going on with user Mr. Mukesh & waiting for thier revert - E26sep5977 |  |  |  | Yash | Akshay Shinde
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active | Meeting done, Vinay will conclude the 2 pending queries of sandwitch leave policy
5176 | Escalation | ARTSON LIMITED | Schedule | 2026-09-01 | 2026-09-30 | High | Completed
5177 | Escalation | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Schedule | 2026-09-28 |  | High | Active | No Response from Even Director
5178 | Allocation | APMOSYS TECHNOLOGIES PVT LTD | Schedule | 2026-09-22 |  | High | Active | Implementation & Training Ongoing |  |  |  | Utkarsh | Nagesh
5179 | Allocation | CONTENDRE GREENERGY PVT. LTD | Schedule | 2026-09-21 |  | High | Active | Conversion Activity done, training ongoing, |  |  |  | Tanwish | Akshay Shinde
5180 | Allocation | PERFECT BELTS PVT. LTD | Schedule | 2026-09-18 |  | High | Active | Payroll- master uploaded, salary set up in process
5181 | Escalation | Saffron Speciality Papers Limited | Schedule | 2026-09-01 |  | High | Active | Implementation & Training Planned for Oct

## Go Live Followup
Project Code | Project Name | Status | Completed Date | Client Interaction Date | Vists / Call | Remark | Feedback | Scope of UpSelling
5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Completed
5003 | Maharashtra Book Manufacturing | Completed
5004 | PLASMA RESEARCH TRUST NX | Completed
5005 | Bengal Energy_Staff | Completed
5008 | Aquaair International Frieght Services | Completed
5009 | Hardcarb Technologies Private Limited | Completed
5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Completed
5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Completed
5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Completed
5013 | Metafab | Completed
5014 | Texple | Completed
5015 | ERMELLI PRIVATE LIMITED | Completed
5016 | Helen Keller Institute for Deaf & Blind | Completed
5017 | Cartfire India | Completed
5018 | Sky Prints | Completed
5019 | Cogencis | Completed
5020 | S K Traders | Completed
5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Completed
5022 | Infexn Laboratories | Completed
5024 | Emmay Entertainment | Completed
5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Completed
5026 | RADIX ELECTROSYSTEMS PVT LTD | Completed
5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Completed
5029 | APLAB LIMITED (FOR STAFF LICENSE) | Completed
5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | Completed
5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Completed
5034 | QUALIGENS PHARMA PVT. LTD | Completed
5035 | MADURA INDUSTRIAL TEXTILES LIMITED | Completed
5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Completed
5037 | STEAM PULSE INDIA PVT LTD | Completed
5038 | STEAM HARBOUR LOGISTICS PVT LTD | Completed
5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Completed
5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Completed
5041 | TATARIA HARDWARE INNOVATION | Completed
5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Completed
5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Completed
5045 | SAI SANKET INDUSTRIES PVT.LTD | Completed
5047 | BRILLIANT POLYMERS PVT. LTD | Completed
5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Completed
5049 | TAO AUTOMATION SERVICES PVT LTD | Completed
5052 | SNAPWORK TECHNOLOGIES PVT LTD | Completed
5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Completed
5054 | BRIGHT BROTHERS LTD. / BRITE | Completed
5055 | ARMITA INDIA SHIPPING PVT. LTD | Completed
5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Completed
5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Completed
5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Completed
5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Completed
5061 | GNG ELECTRONICS LIMITED STAFF | Completed
5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | Completed
5064 | MESPACK INDIA PVT. LTD | Completed
5065 | UNITED AIR EXPRESS | Completed
5067 | ISA Logistics Private Limited | Completed
5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Completed
5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Completed
5070 | CONTENDRE GREENERGY LIMITED | Completed
5071 | ILEAF RITZ BANQUETS | Completed
5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | Completed
5073 | V ALLIANCE NX | Completed
5074 | UNITED AIR EXPRESS | Completed
5075 | ESCON ELEVATORS PVT. LTD. | Completed
5078 | FFSERVICES PRIVATE LIMITED | Completed
5080 | SETHWALA FOODS LTD | Completed
5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Completed
5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Completed
5083 | FUJIYAMA POWER SYSTEM (UTL) | Completed
5084 | VABA | Completed
5085 | KISHAN LAL PAWAN KUMAR JAIN | Completed
5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Completed
5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Completed
5088 | POLMOR STEEL PRIVATE LIMITED | Completed
5089 | ACEY ENGINEERING PVT. LTD | Completed
5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Completed
5091 | MEDIPULSE HOSPITAL | Completed
5093 | DRS EARTHWORK PRIVATE LIMITED | Completed
5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Completed
5096 | AUROUS JEWELS LLP | Completed
5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Completed
5098 | RENMAKCH INDIA PVT. LTD. | Completed
5099 | GNG ELECTRONICS LIMITED FACTORY | Completed
5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | Completed
5102 | SREE METALIKS LTD | Completed
5103 | NAGRIK CONSULTANCY SERVICES | Completed
5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed
5105 | ANUH PHARMA PVT. LTD NX | Completed
5106 | NAIK MOTORS -GOA LOC | Completed
5107 | PPKG AND CO | Completed
5108 | DOSHI MEDICARE PRIVATE LIMITED | Completed
5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Completed
5110 | COSMOS IMPEX INDIA PVT LTD NG | Completed
5111 | NIKIKA ENTERPRISES LLP | Completed
5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | Completed
5113 | parvathyhospital | Completed
5116 | GNG ELECTRONICS LIMITED STAFF | Completed
5117 | Talib and Shamsi Constructions Pvt. Ltd. | Completed
5118 | Seventy Seven Entertainment Pvt Ltd | Completed
5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Completed
5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Completed
5122 | Procon RMC | Completed
5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Completed
5124 | SUNRISE FOODS BANGALORE | Completed
5125 | NOTCH INDIA PROJECTS | Completed
5126 | Elixrr Industries Pvt. Ltd. | Completed
5127 | GUARDIAN CASTING PVT. LTD | Completed
5128 | GNG ELECTRONICS LIMITED FACTORY | Completed
5130 | CIRCLE RESOURCES PRIVATE LIMITED | Completed
5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed
5136 | Navio Shipping | Completed
5137 | VIPUL ORGANICS LTD. - STAFF | Completed
5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Completed
5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed
5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Completed
5153 | Vivan Associate | Completed
5160 | ANS NG | Completed
5161 | STERLING LIFESTYLE LLP | Completed
5162 | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Completed
5165 | Navio Shipping | Completed
5176 | ARTSON LIMITED | Completed