## Dashboard
VASU's Project Tracker - August 2026
Generated: September 18, 2026
KEY METRICS
Total Projects
Completed
Active
Completion Rate
Success Rate
Avg Duration (Days)
Followups Due This Month | 39

## Overall Summary
VASU's Tracker 2026 - Overall Summary
As of: August 2026
OVERALL PROJECT COUNTS
Metric | Count | Formula Reference | Percentage
Total Projects
Total Allocations |  | By Type
Total Escalations |  | By Type
Total Completed |  | By Status
Total Active |  | By Status
Total Yet to Start |  | By Status
Total Held Up |  | By Status
Total Lost |  | By Status
KEY PERFORMANCE INDICATORS
KPI | Value | Description
Completion Rate |  | Projects Completed / Total
Success Rate |  | (Total - Lost) / Total
Active Project % |  | Active / Total Projects
Avg Duration (Days) |  | Avg completion time

## Year on Year Analysis
YEAR ON YEAR ANALYSIS & COMPARISON
Same-period comparison through August 2026
ANNUAL / YTD SUMMARY
Year | Period Covered | Add Alloc | Add Escal | Total Additions | Completed | Lost | Held Up | Closing Balance | Completion Rate | Success Rate
2025 | Jan-Dec | 50 | 63 | 113 | 60 | 11 | 0 | 42 | 53.1% | 90.27%
2026 | Jan-Aug | 32 | 24 | 56 | 53 | 12 | 0 | 33 | 94.64% | 78.57%
SAME-PERIOD YOY COMPARISON
Metric | 2025 Same Period | 2026 Same Period | Change | Change %
Total Additions | 87 | 56 | -31 | -35.63%
Completed | 39 | 53 | 14 | 35.9%
Lost | 9 | 12 | 3 | 33.33%
Held Up | 0 | 0 | 0 | 0%
Completion Rate | 0.44828 | 0.94643 | 0.49815 | 111.1%
Open Pipeline | 4 | 39 | 35 | 875%
MANAGEMENT INSIGHTS
1 | August 2026 portfolio has 175 tracked projects with 113 completed.
2 | Same-period additions are down 35.6% versus last year; pipeline creation needs management focus.
3 | Same-period completions are up 35.9%; delivery performance is improving.
4 | Current completion rate is 64.6%; open pipeline is 39 projects.
5 | 39 completed-client follow-ups are scheduled for this month to validate usage and capture issues.

## Monthly Metrics
Monthly Project Tracking - Opening & Closing Balance
Logic: Closing = Opening + Additions - Completed - Lost - Held
Month | Opening | Add Alloc | Add Escal | Total Add | Completed | Lost | Held | Net Change | Closing
2025-01 | 0 | 8 | 12 | 20 | 0 | 0 | 0 |  | 20
2025-02 | 20 | 6 | 5 | 11 | 0 | 0 | 0 |  | 31
2025-03 | 31 | 7 | 4 | 11 | 0 | 0 | 0 |  | 42
2025-04 | 42 | 2 | 7 | 9 | 15 | 1 | 0 |  | 35
2025-05 | 35 | 2 | 4 | 6 | 2 | 0 | 0 |  | 39
2025-06 | 39 | 7 | 4 | 11 | 6 | 3 | 0 |  | 41
2025-07 | 41 | 0 | 7 | 7 | 9 | 5 | 0 |  | 34
2025-08 | 34 | 5 | 7 | 12 | 7 | 0 | 0 |  | 39
2025-09 | 39 | 4 | 3 | 7 | 3 | 0 | 0 |  | 43
2025-10 | 43 | 3 | 4 | 7 | 16 | 1 | 0 |  | 33
2025-11 | 33 | 5 | 5 | 10 | 2 | 1 | 0 |  | 40
2025-12 | 40 | 1 | 1 | 2 | 0 | 0 | 0 |  | 42
2026-01 | 42 | 4 | 3 | 7 | 9 | 1 | 0 |  | 39
2026-02 | 39 | 2 | 6 | 8 | 5 | 0 | 0 |  | 42
2026-03 | 42 | 1 | 1 | 2 | 12 | 2 | 0 |  | 30
2026-04 | 30 | 5 | 1 | 6 | 13 | 4 | 0 |  | 19
2026-05 | 19 | 7 | 6 | 13 | 5 | 0 | 0 |  | 27
2026-06 | 27 | 6 | 6 | 12 | 0 | 0 | 0 |  | 39
2026-07 | 39 | 3 | 0 | 3 | 7 | 2 | 0 |  | 33
2026-08 | 33 | 4 | 1 | 5 | 2 | 3 | 0 |  | 33
2026-09 | 33 | 5 | 1 | 6 | 0 | 0 | 0 |  | 39
TOTAL

## Latest Month
Latest Month Performance - 2026-08
MONTH SUMMARY
Metric | Value | Details
Month | '2026-08
Opening Balance | 33 | Projects at start of month
New Allocations | 4 | New allocation projects
New Escalations | 1 | New escalation projects
Total Additions | 5 | Total new projects
Completed | 2 | Projects completed this month
Lost | 3 | Projects lost this month
Held Up | 0 | Projects held this month
Net Change | 0 | Add - Comp - Lost - Held
Closing Balance | 33 | Projects at end of month

## Projects
Project Code | Project Type | Project Name | Received From | Start Date | End Date | Priority | Status | Duration
5001 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Schedule | 2025-01-07 | 2025-10-28 | Low | Completed
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost
5003 | Escalation | Maharashtra Book Manufacturing | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed
5005 | Allocation | Bengal Energy_Staff | Schedule | 2025-01-08 | 2026-03-30 | Low | Completed
5006 | Allocation | Bengal Energy_Worker | Schedule | 2025-01-08 | 2025-06-30 | Low | Lost
5007 | Allocation | Parbhani Medical College | Schedule | 2025-01-13 | 2026-01-28 | Low | Lost
5008 | Escalation | Aquaair International Frieght Services | Schedule | 2025-01-13 | 2025-04-25 | Low | Completed
5009 | Escalation | Hardcarb Technologies Private Limited | Maketing | 2025-01-14 | 2025-04-25 | Low | Completed
5010 | Allocation | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Schedule | 2025-01-14 | 2025-07-17 | Low | Completed
5011 | Allocation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Schedule | 2025-01-14 | 2025-10-28 | Low | Completed
5012 | Escalation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Schedule | 2025-01-14 | 2025-04-25 | Low | Completed
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed
5017 | Escalation | Cartfire India | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed
5018 | Escalation | Sky Prints | Schedule | 2025-01-25 | 2025-04-25 | Low | Completed
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed
5020 | Allocation | S K Traders | Schedule | 2025-01-31 | 2025-06-30 | Low | Completed
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed
5022 | Escalation | Infexn Laboratories | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed
5025 | Allocation | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Schedule | 2025-02-18 | 2026-02-27 | Low | Completed
5026 | Allocation | RADIX ELECTROSYSTEMS PVT LTD | Schedule | 2025-02-18 | 2026-03-30 | Low | Completed
5027 | Allocation | MARU CONSULTANCY SERVICES | Schedule | 2025-02-19 | 2025-06-04 | Low | Lost
5028 | Allocation | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Schedule | 2025-02-24 | 2026-01-28 | Low | Completed
5029 | Allocation | APLAB LIMITED (FOR STAFF LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed
5030 | Allocation | APLAB LIMITED (FOR CONTRACT LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed
5031 | Escalation | NPSE AUTOMATION PVT. LTD | Schedule | 2025-02-12 | 2025-04-25 | Low | Lost
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed
5033 | Allocation | KARVY TECHNOLOGIES PVT LTD | Schedule | 2025-03-03 | 2026-03-30 | Low | Lost
5034 | Allocation | QUALIGENS PHARMA PVT. LTD | Schedule | 2025-03-07 | 2025-10-28 | Low | Completed
5035 | Allocation | MADURA INDUSTRIAL TEXTILES LIMITED | Schedule | 2025-03-10 | 2026-04-28 | Low | Completed
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed
5037 | Allocation | STEAM PULSE INDIA PVT LTD | Schedule | 2025-03-25 | 2025-10-28 | Low | Completed
5038 | Allocation | STEAM HARBOUR LOGISTICS PVT LTD | Schedule | 2025-03-25 | 2026-01-28 | Low | Completed
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed
5044 | Allocation | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Schedule | 2025-04-01 | 2026-04-28 | Low | Completed
5045 | Escalation | SAI SANKET INDUSTRIES PVT.LTD | Schedule | 2025-04-01 | 2025-05-25 | Low | Completed
5046 | Escalation | LOTUS TEXCOM INDIA LLP | Schedule | 2025-04-04 | 2025-07-23 | Low | Lost
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed
5050 | Escalation | BASANT OVERSEAS | Schedule | 2025-04-25 | 2026-03-30 | Low | Lost
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost
5052 | Allocation | SNAPWORK TECHNOLOGIES PVT LTD | Schedule | 2025-05-03 | 2026-02-27 | Low | Completed
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed
5054 | Allocation | BRIGHT BROTHERS LTD. / BRITE | Schedule | 2025-05-27 | 2026-02-27 | Low | Completed
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost
5058 | Escalation | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-08-30 | Low | Completed
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed
5061 | Allocation | GNG ELECTRONICS LIMITED STAFF | Schedule | 2025-06-01 | 2025-10-28 | Low | Completed
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost
5063 | Allocation | ALLIED INSTRUMENTS PRIVATE LIMITED | Schedule | 2025-06-01 | 2026-03-30 | Low | Completed
5064 | Allocation | MESPACK INDIA PVT. LTD | Schedule | 2025-06-09 | 2026-04-28 | Low | Completed
5065 | Allocation | UNITED AIR EXPRESS | Schedule | 2025-06-20 | 2026-04-28 | Low | Completed
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost
5067 | Escalation | ISA Logistics Private Limited | Schedule | 2025-06-19 | 2025-07-23 | Low | Completed
5068 | Escalation | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Support | 2025-06-27 | 2025-07-23 | Low | Completed
5069 | Escalation | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Schedule | 2025-07-12 | 2025-08-30 | Low | Completed
5070 | Escalation | CONTENDRE GREENERGY LIMITED | Schedule | 2025-07-15 | 2025-08-30 | Low | Completed
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed
5072 | Escalation | ROYAL EMBROIDERY THREADS PVT.LTD. | Schedule | 2025-07-17 | 2025-08-30 | Low | Completed
5073 | Escalation | V ALLIANCE NX | Schedule | 2025-07-18 | 2025-08-30 | Low | Completed
5074 | Escalation | UNITED AIR EXPRESS | Schedule | 2025-07-18 | 2025-08-21 | Low | Completed
5075 | Escalation | ESCON ELEVATORS PVT. LTD. | Schedule | 2025-07-23 | 2025-08-30 | Low | Completed
5076 | Allocation | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Schedule | 2025-08-02 | 2026-04-28 | Low | Lost
5077 | Allocation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Schedule | 2025-08-06 | 2026-04-28 | Low | Lost
5078 | Escalation | FFSERVICES PRIVATE LIMITED | CR | 2025-08-12 | 2025-11-28 | Low | Completed
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost
5080 | Allocation | SETHWALA FOODS LTD | Schedule | 2025-08-21 | 2026-05-26 | Low | Completed
5081 | Allocation | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Schedule | 2025-08-01 | 2026-01-28 | Low | Completed
5082 | Escalation | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Schedule | 2025-08-14 | 2025-09-24 | Low | Completed
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed
5084 | Escalation | VABA | Schedule | 2025-08-04 | 2025-10-28 | Low | Completed
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed
5086 | Escalation | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Schedule | 2025-08-22 | 2025-09-24 | Low | Completed
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 |  | Low | Active
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active
5093 | Escalation | DRS EARTHWORK PRIVATE LIMITED | Schedule | 2025-09-24 | 2025-11-28 | Low | Completed
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost
5095 | Escalation | PISCES CONTAINER LINES INDIA PVT. LTD. | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5097 | Allocation | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Schedule | 2025-10-08 | 2026-04-28 | Low | Completed
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed
5099 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active
5101 | Allocation | VIVID ELECTROMECH LTD. / VIVID GROUP | Schedule | 2025-10-30 | 2026-04-28 | Low | Completed
5102 | Allocation | SREE METALIKS LTD | Schedule | 2025-11-11 | 2026-04-28 | Low | Completed
5103 | Escalation | NAGRIK CONSULTANCY SERVICES | Schedule | 2025-11-10 | 2026-02-27 | Low | Completed
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed
5109 | Allocation | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Schedule | 2025-11-26 | 2026-07-31 | Low | Completed
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed
5111 | Allocation | NIKIKA ENTERPRISES LLP | Schedule | 2025-11-29 | 2026-05-26 | Low | Completed
5112 | Allocation | PRIJAI HEAT EXCHANGERS PVT. LTD. | Schedule | 2025-12-10 | 2026-04-28 | Low | Completed
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed
5114 | Allocation | PANKAJ FASHION PVT LTD | Schedule | 2026-01-09 | 2026-08-11 | Low | Lost
5115 | Allocation | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Schedule | 2026-01-16 | 2026-04-28 | Low | Lost
5116 | Escalation | GNG ELECTRONICS LIMITED STAFF | Maketing | 2026-01-19 | 2026-01-22 | Low | Completed
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed
5118 | Escalation | Seventy Seven Entertainment Pvt Ltd | Schedule | 2026-01-19 | 2026-03-30 | Low | Completed
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active
5120 | Allocation | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Schedule | 2026-01-31 | 2026-04-28 | Low | Completed
5121 | Allocation | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Schedule | 2026-02-09 | 2026-05-26 | Low | Completed
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed
5126 | Escalation | Elixrr Industries Pvt. Ltd. | Maketing | 2026-02-10 | 2026-04-28 | Low | Completed
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed
5128 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2026-02-25 | 2026-03-30 | Low | Completed
5129 | Allocation | STORM FINANCIAL SERVICES | Schedule | 2026-03-28 | 2026-07-31 | Low | Lost
5130 | Escalation | CIRCLE RESOURCES PRIVATE LIMITED | Schedule | 2026-03-12 | 2026-03-30 | Low | Completed
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed
5137 | Escalation | VIPUL ORGANICS LTD. - STAFF | Schedule | 2026-05-01 | 2026-05-26 | Low | Completed
5138 | Allocation | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Schedule | 2026-05-04 | 2026-08-31 | High | Lost
5139 | Allocation | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Schedule | 2026-05-06 | 2026-08-31 | High | Completed
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active
5146 | Escalation | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Schedule | 2026-05-19 | 2026-07-31 | High | Completed
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active
5159 | Escalation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Schedule | 2026-06-23 | 2026-07-31 | High | Lost
5160 | Escalation | ANS NG | Schedule | 2026-06-24 |  | High | Active
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 |  | High | Active
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 |  | High | Active
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Yet To Start
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Yet To Start
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active

## Quarterly Followup
Followup Due This Month | Followup Quarter | Followup Month | Suggested Followup Date | Project Code | Project Name | Status | Completed Date | Client Interaction Date | Current Usage Status | Challenges / Pain Points | Support Required | Scope of UpSelling | PM Followup Notes | Next Followup Date
No | Q3 2026 | July | 2026-07-15 | 5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5003 | Maharashtra Book Manufacturing | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5004 | PLASMA RESEARCH TRUST NX | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5005 | Bengal Energy_Staff | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5008 | Aquaair International Frieght Services | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5009 | Hardcarb Technologies Private Limited | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Completed | 2025-07-17 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5013 | Metafab | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5014 | Texple | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5015 | ERMELLI PRIVATE LIMITED | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5016 | Helen Keller Institute for Deaf & Blind | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5017 | Cartfire India | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5018 | Sky Prints | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5019 | Cogencis | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5020 | S K Traders | Completed | 2025-06-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5022 | Infexn Laboratories | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5024 | Emmay Entertainment | Completed | 2025-04-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Completed | 2026-02-27 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5026 | RADIX ELECTROSYSTEMS PVT LTD | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5029 | APLAB LIMITED (FOR STAFF LICENSE) | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5034 | QUALIGENS PHARMA PVT. LTD | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5035 | MADURA INDUSTRIAL TEXTILES LIMITED | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5037 | STEAM PULSE INDIA PVT LTD | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5038 | STEAM HARBOUR LOGISTICS PVT LTD | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Completed | 2025-06-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Completed | 2025-06-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5041 | TATARIA HARDWARE INNOVATION | Completed | 2025-06-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Completed | 2025-05-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5045 | SAI SANKET INDUSTRIES PVT.LTD | Completed | 2025-05-25 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5047 | BRILLIANT POLYMERS PVT. LTD | Completed | 2025-06-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Completed | 2025-07-17 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5049 | TAO AUTOMATION SERVICES PVT LTD | Completed | 2025-07-17 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5052 | SNAPWORK TECHNOLOGIES PVT LTD | Completed | 2026-02-27 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Completed | 2025-07-23 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5054 | BRIGHT BROTHERS LTD. / BRITE | Completed | 2026-02-27 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5055 | ARMITA INDIA SHIPPING PVT. LTD | Completed | 2025-07-23 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Completed | 2025-06-01 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Completed | 2025-07-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Completed | 2025-07-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5061 | GNG ELECTRONICS LIMITED STAFF | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5064 | MESPACK INDIA PVT. LTD | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5065 | UNITED AIR EXPRESS | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5067 | ISA Logistics Private Limited | Completed | 2025-07-23 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Completed | 2025-07-23 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5070 | CONTENDRE GREENERGY LIMITED | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5071 | ILEAF RITZ BANQUETS | Completed | 2025-09-24 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5073 | V ALLIANCE NX | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5074 | UNITED AIR EXPRESS | Completed | 2025-08-21 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5075 | ESCON ELEVATORS PVT. LTD. | Completed | 2025-08-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5078 | FFSERVICES PRIVATE LIMITED | Completed | 2025-11-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5080 | SETHWALA FOODS LTD | Completed | 2026-05-26 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Completed | 2025-09-24 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5083 | FUJIYAMA POWER SYSTEM (UTL) | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5084 | VABA | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5085 | KISHAN LAL PAWAN KUMAR JAIN | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Completed | 2025-09-24 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5088 | POLMOR STEEL PRIVATE LIMITED | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5089 | ACEY ENGINEERING PVT. LTD | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5093 | DRS EARTHWORK PRIVATE LIMITED | Completed | 2025-11-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5096 | AUROUS JEWELS LLP | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5098 | RENMAKCH INDIA PVT. LTD. | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5099 | GNG ELECTRONICS LIMITED FACTORY | Completed | 2025-10-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5102 | SREE METALIKS LTD | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5103 | NAGRIK CONSULTANCY SERVICES | Completed | 2026-02-27 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5105 | ANUH PHARMA PVT. LTD NX | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5106 | NAIK MOTORS -GOA LOC | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5107 | PPKG AND CO | Completed | 2026-02-27 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5108 | DOSHI MEDICARE PRIVATE LIMITED | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5110 | COSMOS IMPEX INDIA PVT LTD NG | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5111 | NIKIKA ENTERPRISES LLP | Completed | 2026-05-26 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5113 | parvathyhospital | Completed | 2026-01-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5116 | GNG ELECTRONICS LIMITED STAFF | Completed | 2026-01-22 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5117 | Talib and Shamsi Constructions Pvt. Ltd. | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5118 | Seventy Seven Entertainment Pvt Ltd | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Completed | 2026-05-26 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5122 | Procon RMC | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5124 | SUNRISE FOODS BANGALORE | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5125 | NOTCH INDIA PROJECTS | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5126 | Elixrr Industries Pvt. Ltd. | Completed | 2026-04-28 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5127 | GUARDIAN CASTING PVT. LTD | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5128 | GNG ELECTRONICS LIMITED FACTORY | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5130 | CIRCLE RESOURCES PRIVATE LIMITED | Completed | 2026-03-30 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5136 | Navio Shipping | Completed | 2026-05-26 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5137 | VIPUL ORGANICS LTD. - STAFF | Completed | 2026-05-26 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | July | 2026-07-15 | 5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Completed | 2026-08-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
Yes | Q3 2026 | August | 2026-08-15 | 5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5153 | Vivan Associate | Completed | 2026-07-31 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.
No | Q3 2026 | September | 2026-09-15 | 5165 | Navio Shipping | Completed | 2026-08-11 | [5 empty] | Check if the client is using the system properly, whether any challenge is open, and whether support/optimization is needed.