## Weekly_Mail_Merge
Send Flag | To | CC | Subject | Project Code | Project Name | Tracker Status | SCH Status | Risk Level | Current Milestone | Owner | PM Note Source | Stakeholder PM Update | Next Action | Due Date | Mail Body | Review Notes
Need Recipient |  |  | Project Status Update - THE NATIONAL SPORTS CLUB OF INDIA - Datafile Explanation | 5042 | THE NATIONAL SPORTS CLUB OF INDIA | Active | Active | Critical | Datafile Explanation | Mihir Navnath Mungekar | Manual PM Note | Live Salary Processing Planned. | Live Salary Processing Planned. |  | Dear Team, Please find the latest PM update for the below project. Project: THE NATIONAL SPORTS CLUB OF INDIA Current Milestone: Datafile Explanation Latest PM Update: Live Salary Processing Planned. Next Action: Live Salary Processing Planned. Tracker Status: Active SCH Status: Active Owner: Mihir Navnath Mungekar Regards, Vasu
Need Recipient |  |  | Project Status Update - PARADISE GROUP - Datafile Explanation | 5092 | PARADISE GROUP | Active | AC | Critical | Datafile Explanation | Pritesh Barot | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. |  | Dear Team, Please find the latest PM update for the below project. Project: PARADISE GROUP Current Milestone: Datafile Explanation Latest PM Update: Backend working is ongoing, training & implementation is planned. Next Action: Backend working is ongoing, training & implementation is planned. Tracker Status: Active SCH Status: AC Owner: Pritesh Barot Regards, Vasu
Ready | WHISTLING WOODS INTERNATIONAL <whistlingwoodsinternational@spinetechnologies.in> |  | Project Status Update - WHISTLING WOODS INTERNATIONAL - Datafile Explanation | 5100 | WHISTLING WOODS INTERNATIONAL | Active |  | Critical | Datafile Explanation | Nagendra Poojary | Manual PM Note | PMS Implementation Ongoing. | PMS Implementation Ongoing |  | Dear Team, Please find the latest PM update for the below project. Project: WHISTLING WOODS INTERNATIONAL Current Milestone: Datafile Explanation Latest PM Update: PMS Implementation Ongoing. Next Action: PMS Implementation Ongoing Tracker Status: Active SCH Status: Owner: Nagendra Poojary Regards, Vasu
Ready | SUVARNA DURGA GROUP <suvarnadurgagroup@spinetechnologies.in> |  | Project Status Update - SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED - Datafile Explanation | 5119 | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Active |  | Critical | Datafile Explanation |  | Manual PM Note | Implementation Demo fixed for 8th May. | Implementation Demo fixed for 8th May |  | Dear Team, Please find the latest PM update for the below project. Project: SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED Current Milestone: Datafile Explanation Latest PM Update: Implementation Demo fixed for 8th May. Next Action: Implementation Demo fixed for 8th May Tracker Status: Active SCH Status: Owner: Regards, Vasu
Ready | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) <symbiosiscentrefordistancelearningsdcl@spinetechnologies.in> |  | Project Status Update - SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) - Datafile Explanation | 5131 | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Active | Active | Critical | Datafile Explanation | Riddhi Pramod Sutar | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Confirm milestone progress and next client action. |  | Dear Team, Please find the latest PM update for the below project. Project: SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) Current Milestone: Datafile Explanation Latest PM Update: 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. Next Action: Confirm milestone progress and next client action. Tracker Status: Active SCH Status: Active Owner: Riddhi Pramod Sutar Regards, Vasu
Ready | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES <rashtrasantjanardhanswamigroupofinstitutes@spinetechnologies.in> |  | Project Status Update - SHRI JANARDAN SWAMI HOSPITAL (SJS) - Kick Off Meeting | 5132 | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Active | Held | Critical | Kick Off Meeting | Vikas Yadav | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  | Dear Team, Please find the latest PM update for the below project. Project: SHRI JANARDAN SWAMI HOSPITAL (SJS) Current Milestone: Kick Off Meeting Latest PM Update: Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. Next Action: Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. Tracker Status: Active SCH Status: Held Owner: Vikas Yadav Regards, Vasu
Ready | TRIO JEWELS PVT LTD <triojewelspvtltd@spinetechnologies.in> |  | Project Status Update - TRIO JEWELS PVT LTD - Datafile Explanation | 5134 | TRIO JEWELS PVT LTD | Active | AC | High | Datafile Explanation | Mukeshkumar Shojiram kumavat | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Dear Team, Please find the latest PM update for the below project. Project: TRIO JEWELS PVT LTD Current Milestone: Datafile Explanation Latest PM Update: Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. Next Action: Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. Tracker Status: Active SCH Status: AC Owner: Mukeshkumar Shojiram kumavat Regards, Vasu
Ready | VOGUE N HYDE PVT. LTD <voguenhydepvt.ltd@spinetechnologies.in> |  | Project Status Update - VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED - Kick Off Meeting | 5135 | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Active |  | High | Kick Off Meeting |  | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  | Dear Team, Please find the latest PM update for the below project. Project: VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED Current Milestone: Kick Off Meeting Latest PM Update: Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. Next Action: Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Ready | TRIO JEWELS PVT LTD <triojewelspvtltd@spinetechnologies.in> |  | Project Status Update - TRIO JEWELS PVT LTD Contractual - Kick Off Meeting | 5141 | TRIO JEWELS PVT LTD Contractual | Active | AC | High | Kick Off Meeting | Mukeshkumar Shojiram kumavat | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Dear Team, Please find the latest PM update for the below project. Project: TRIO JEWELS PVT LTD Contractual Current Milestone: Kick Off Meeting Latest PM Update: Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. Next Action: Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. Tracker Status: Active SCH Status: AC Owner: Mukeshkumar Shojiram kumavat Regards, Vasu
Ready | EMPREO PREMIUM PVT LTD <empreopremiumpvtltd@spinetechnologies.in> |  | Project Status Update - EMPREO PREMIUM PVT LTD - Datafile Explanation | 5142 | EMPREO PREMIUM PVT LTD | Active | Active | High | Datafile Explanation | Goraksha Pawar | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Dear Team, Please find the latest PM update for the below project. Project: EMPREO PREMIUM PVT LTD Current Milestone: Datafile Explanation Latest PM Update: April Salary Process and Tally done, Attendance Integration done, May Live processing planned. Next Action: April Salary Process and Tally done, Attendance Integration done, May Live processing planned. Tracker Status: Active SCH Status: Active Owner: Goraksha Pawar Regards, Vasu
Need Recipient |  |  | Project Status Update - EMPREO WHEEL PVT LIMITED (MG) - Datafile Explanation | 5143 | EMPREO WHEEL PVT LIMITED (MG) | Active | Active | High | Datafile Explanation | Goraksha Pawar | Manual PM Note | Same. | Same |  | Dear Team, Please find the latest PM update for the below project. Project: EMPREO WHEEL PVT LIMITED (MG) Current Milestone: Datafile Explanation Latest PM Update: Same. Next Action: Same Tracker Status: Active SCH Status: Active Owner: Goraksha Pawar Regards, Vasu
Need Recipient |  |  | Project Status Update - SHREEKHETRA AUTOMOTIVE (TATA) - Kick Off Meeting | 5144 | SHREEKHETRA AUTOMOTIVE (TATA) | Active | Lost | High | Kick Off Meeting | Goraksha Pawar | Manual PM Note | Same. | Same |  | Dear Team, Please find the latest PM update for the below project. Project: SHREEKHETRA AUTOMOTIVE (TATA) Current Milestone: Kick Off Meeting Latest PM Update: Same. Next Action: Same Tracker Status: Active SCH Status: Lost Owner: Goraksha Pawar Regards, Vasu
Ready | AMAL EMBROIDERIES PRIVATE LIMITED <amalembroideriesprivatelimited@spinetechnologies.in> |  | Project Status Update - AMAL EMBROIDERIES PVT. LTD - Datafile Explanation | 5145 | AMAL EMBROIDERIES PVT. LTD | Active | AC | High | Datafile Explanation | Vijay Bugde | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | Dear Team, Please find the latest PM update for the below project. Project: AMAL EMBROIDERIES PVT. LTD Current Milestone: Datafile Explanation Latest PM Update: Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. Next Action: Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. Tracker Status: Active SCH Status: AC Owner: Vijay Bugde Regards, Vasu
Ready | MULTI ORGANICS PVT LTD <multiorganicspvtltd@spinetechnologies.in> |  | Project Status Update - MULTI ORGANICS PVT LTD - Kick Off Meeting | 5147 | MULTI ORGANICS PVT LTD | Active | Active | High | Kick Off Meeting | Rajesh Ravindra Panchal | Manual PM Note | KickOff & Datafile Explaination done. | KickOff & Datafile Explaination done |  | Dear Team, Please find the latest PM update for the below project. Project: MULTI ORGANICS PVT LTD Current Milestone: Kick Off Meeting Latest PM Update: KickOff & Datafile Explaination done. Next Action: KickOff & Datafile Explaination done Tracker Status: Active SCH Status: Active Owner: Rajesh Ravindra Panchal Regards, Vasu
Ready | MANJUSHREE INNOVATIONS PRIVATE LIMITED <manjushreeinnovationsprivatelimited@spinetechnologies.in> |  | Project Status Update - MANJUSHREE INNOVATIONS PVT. LTD - Kick Off Meeting | 5149 | MANJUSHREE INNOVATIONS PVT. LTD | Active | Active | High | Kick Off Meeting | Mayur Pendhari | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | Dear Team, Please find the latest PM update for the below project. Project: MANJUSHREE INNOVATIONS PVT. LTD Current Milestone: Kick Off Meeting Latest PM Update: KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. Next Action: KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. Tracker Status: Active SCH Status: Active Owner: Mayur Pendhari Regards, Vasu
Ready | CRYOGAS EQUIPMENT PRIVATE LIMITED NG <cryogasequipmentprivatelimitedng@spinetechnologies.in> |  | Project Status Update - CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA - Kick Off Meeting | 5150 | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Active | Active | High | Kick Off Meeting | Varun Rajbhar | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA Current Milestone: Kick Off Meeting Latest PM Update: KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Active Owner: Varun Rajbhar Regards, Vasu
Ready | MANSHA AGENCIES PVT LTD <manshaagenciespvtltd@spinetechnologies.in> |  | Project Status Update - Mansha Agencies - Kick Off Meeting | 5151 | Mansha Agencies | Active | Active | High | Kick Off Meeting | Aditya Mazire | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: Mansha Agencies Current Milestone: Kick Off Meeting Latest PM Update: Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Active Owner: Aditya Mazire Regards, Vasu
Ready | MUKTANGAN EDUCATION TRUST NX <muktanganeducationtrustnx@spinetechnologies.in> |  | Project Status Update - Muktangan Education Trust - Datafile Explanation | 5152 | Muktangan Education Trust | Active | Active | High | Datafile Explanation | Aditya Mazire | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: Muktangan Education Trust Current Milestone: Datafile Explanation Latest PM Update: Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Active Owner: Aditya Mazire Regards, Vasu
Need Recipient |  |  | Project Status Update - BSA CORPORATION LIMITED / BSA GROUP - Kick Off Meeting | 5154 | BSA CORPORATION LIMITED / BSA GROUP | Active |  | High | Kick Off Meeting |  | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: BSA CORPORATION LIMITED / BSA GROUP Current Milestone: Kick Off Meeting Latest PM Update: KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) - Kick Off Meeting | 5155 | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Active | Active | High | Kick Off Meeting | Ankita Gupta | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) Current Milestone: Kick Off Meeting Latest PM Update: Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Active Owner: Ankita Gupta Regards, Vasu
Need Recipient |  |  | Project Status Update - SACRED HEART HOSPITAL JAL - Kick Off Meeting | 5156 | SACRED HEART HOSPITAL JAL | Active | AC | High | Kick Off Meeting | Mayur Pendhari | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: SACRED HEART HOSPITAL JAL Current Milestone: Kick Off Meeting Latest PM Update: KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: AC Owner: Mayur Pendhari Regards, Vasu
Need Recipient |  |  | Project Status Update - VED INDUSTRIES/ ROHIDA GROUP - Kick Off Meeting | 5157 | VED INDUSTRIES/ ROHIDA GROUP | Active |  | High | Kick Off Meeting |  | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: VED INDUSTRIES/ ROHIDA GROUP Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI - Kick Off Meeting | 5158 | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Active |  | High | Kick Off Meeting |  | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - HELL ENERGY PVT LTD - Datafile Explanation | 5163 | HELL ENERGY PVT LTD | Active | AC | High | Datafile Explanation |  | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: HELL ENERGY PVT LTD Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: AC Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - VISHWAKARMA FOUNDERS (I) PVT. LTD - Kick Off Meeting | 5164 | VISHWAKARMA FOUNDERS (I) PVT. LTD | Active |  | Watch | Kick Off Meeting |  | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: VISHWAKARMA FOUNDERS (I) PVT. LTD Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - AKRITI PHARMACEUTICALS PVT LTD - Datafile Explanation | 5167 | AKRITI PHARMACEUTICALS PVT LTD | Active | Active | Watch | Datafile Explanation | Ankush Rampyare Rajbhar | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: AKRITI PHARMACEUTICALS PVT LTD Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Active Owner: Ankush Rampyare Rajbhar Regards, Vasu
Need Recipient |  |  | Project Status Update - CREATIONS BY SHANAGAR - Datafile Explanation | 5166 | CREATIONS BY SHANAGAR | Active |  | Watch | Datafile Explanation |  | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: CREATIONS BY SHANAGAR Current Milestone: Datafile Explanation Latest PM Update: No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) - Datafile Explanation | 5168 | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Active |  | Watch | Datafile Explanation |  | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) Current Milestone: Datafile Explanation Latest PM Update: No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - JIET MEDICAL COLLEGE HOSPITAL - Datafile Explanation | 5169 | JIET MEDICAL COLLEGE HOSPITAL | Active | Active | Watch | Datafile Explanation | Varun Rajbhar | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: JIET MEDICAL COLLEGE HOSPITAL Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Active Owner: Varun Rajbhar Regards, Vasu
Need Recipient |  |  | Project Status Update - MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE - Kick Off Meeting | 5171 | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Active |  | Watch | Kick Off Meeting | Tejas | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Tejas Regards, Vasu
Need Recipient |  |  | Project Status Update - SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | 5170 | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Active |  | Watch | Kick Off Meeting | Varun | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Varun Regards, Vasu
Need Recipient |  |  | Project Status Update - SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | 5172 | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Yet To Start |  | Watch | Kick Off Meeting | Santosh | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: SURANA GROUP OF HOSPITAL / SURANA HOSPITAL Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Yet To Start SCH Status: Owner: Santosh Regards, Vasu
Need Recipient |  |  | Project Status Update - ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST - Kick Off Meeting | 5173 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Active |  | Watch | Kick Off Meeting |  | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - NAVKAR CORPORATION LIMITED - Kick Off Meeting | 5174 | NAVKAR CORPORATION LIMITED | Yet To Start |  | Watch | Kick Off Meeting | Yash | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | Confirm kickoff date, data readiness, and owner. |  | Dear Team, Please find the latest PM update for the below project. Project: NAVKAR CORPORATION LIMITED Current Milestone: Kick Off Meeting Latest PM Update: No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. Next Action: Confirm kickoff date, data readiness, and owner. Tracker Status: Yet To Start SCH Status: Owner: Yash Regards, Vasu
Need Recipient |  |  | Project Status Update - THE KANDIVALI EDUCATION SOCIETY - Datafile Explanation | 5175 | THE KANDIVALI EDUCATION SOCIETY | Active |  | Watch | Datafile Explanation |  | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: THE KANDIVALI EDUCATION SOCIETY Current Milestone: Datafile Explanation Latest PM Update: No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - CONTENDRE GREENERGY PVT. LTD - Datafile Explanation | 5179 | CONTENDRE GREENERGY PVT. LTD | Active |  | Watch | Datafile Explanation | Tanwish | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: CONTENDRE GREENERGY PVT. LTD Current Milestone: Datafile Explanation Latest PM Update: No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Owner: Tanwish Regards, Vasu
Need Recipient |  |  | Project Status Update - DIPESH ENGINEERING WORKS -STAFF LICENSE NG - Datafile Explanation | 5177 | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Active |  | Watch | Datafile Explanation |  | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: DIPESH ENGINEERING WORKS -STAFF LICENSE NG Current Milestone: Datafile Explanation Latest PM Update: No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - Saffron Speciality Papers Limited - Datafile Explanation | 5181 | Saffron Speciality Papers Limited | Active | Active | Healthy | Datafile Explanation | Yash Pankajkumar | SCH Project Update | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: Saffron Speciality Papers Limited Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Active Owner: Yash Pankajkumar Regards, Vasu
Need Recipient |  |  | Project Status Update - PERFECT BELTS PVT. LTD - Datafile Explanation | 5180 | PERFECT BELTS PVT. LTD | Active | Active | Healthy | Datafile Explanation |  | SCH Project Remark | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: PERFECT BELTS PVT. LTD Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Active Owner: Regards, Vasu
Need Recipient |  |  | Project Status Update - APMOSYS TECHNOLOGIES PVT LTD - Datafile Explanation | 5178 | APMOSYS TECHNOLOGIES PVT LTD | Active | Active | Healthy | Datafile Explanation | Utkarsh | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. | Confirm progress for milestone: Datafile Explanation. |  | Dear Team, Please find the latest PM update for the below project. Project: APMOSYS TECHNOLOGIES PVT LTD Current Milestone: Datafile Explanation Latest PM Update: As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. Next Action: Confirm progress for milestone: Datafile Explanation. Tracker Status: Active SCH Status: Active Owner: Utkarsh Regards, Vasu