## Dashboard
PM Cockpit Dashboard
Spine Technologies India Private Limited ¦ Generated 06-Oct-2026 12:25
Total Projects |  | Open Pipeline |  | Critical Risks | High Risks |  | Unmatched | Project Summaries
181 |  | 40 |  | 8 | 29 |  | 66 | 40
Recommended Focus
Critical risk items: 8 |  |  | Risk Mix |  |  | Status Mix
High risk items: 29 |  |  | Risk Level | Count |  | Tracker Status | Count
Open pipeline: 40 |  |  | Critical | 8 |  | Completed | 118
Unmatched tracker rows: 66 |  |  | High | 29 |  | Active | 38
Review Action_List first, then update PM Notes / Next Action / Owner. |  |  | Watch | 62 |  | Yet To Start | 2
|  |  | Healthy | 3 |  | Lost | 23
|  |  | Closed | 79
Run Health
Metric | Value
Run Timestamp | 06-Oct-2026 12:25:27
Tracker Rows Used | 181
SCH Rows Used | 156
Merged Cockpit Rows | 181
Unmatched Tracker Rows | 66
Rows Needing Match Review | 80
Preserved Note Keys | 169
Critical Risks | 8
High Risks | 29
Open Pipeline | 40

## Execution_Master
Project Code | Project Name | Project Type | Tracker Status | SCH Client Name | SCH Status | SCH Status Meaning | Current Milestone | Owner | Risk Level | Risk Reason | Next Action | PM Notes | Stakeholder PM Update | PM Note Source | Match Method | Match Review Needed | Start Date | End Date | Age Days | Effective Employee Count | Effective Product | Effective Client Type | SCH Implementation Engg | SCH Project Remark | SCH Project Update
5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Allocation | Completed | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | Go LIVE | Project is handed over from implementation team to support team. | Completed | Sahil Gadhave | Closed | Closed/lost item, monitor only | plan for further activities scheduled for 10th. | plan for further activities scheduled for 10th. | plan for further activities scheduled for 10th. | Manual PM Note | Approved Alias | FALSE | 2025-01-07 | 2025-10-28 | 631 | 1270 | NX | Normal | Sahil Gadhave | Project Live - 1) Ahemdabad Location PayrollNX Training and Dec'24 Salary Confirmation : W25jan10514 2) Kolkata Location PayrollNX Training and Dec'24 Salary Confirmation : E25jan12587 3) Ahemdabad Location Jan'25 live salary confirmation : W25feb1205 4) Ahemdabad Location Login rollout confirmation : W25feb2040 5) Spine HRMS - (Admin, ESSM. Leave module) training Confirmation : W25feb2040 6) Spine HRMS -Spine HRMS_Phase 1 Training Confirmation : W25feb2365 7) Kolkata Location Jan'25 live salary confirmation : W25feb3068 8) Kolkatta Location Login rollout confirmation : W25feb4649 9) Ahemdabad Attendance Integration Confirmation : E25feb7343 10) ELC module Training Confirmation : W25feb8518 11) Ahemdabad location Feb'25 Live salary confirmation along with Attendance : W25mar1674 12) Kolkatta location Feb'25 live Salary confirmation : W25mar1677 May month live salary processed from system June month live salary from with attendance from system is done
5002 | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Allocation | Lost | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | Go LIVE | Project is handed over from implementation team to support team. | Completed | Sahil Gadhave | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project remark: Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved. Tracker status is Lost; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Go LIVE'. | SCH Project Remark | Approved Alias | FALSE | 2025-01-07 | 2025-07-17 | 631 | 1100 | NX | Normal | Sahil Gadhave | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved
5003 | Maharashtra Book Manufacturing | Escalation | Completed | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | FC | Live salary processing is complete and client is on watch list. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary... Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Shubham Gurav. | SCH Project Remark | Approved Alias | FALSE | 2025-01-07 | 2025-04-25 | 631 | 100 | NX | Normal | Shubham Gurav | Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary till Mar 25 and Process from April 25 -E25may5783 May salary done. after june we can do live. We have processed May 25 and June 25 salary with attendance for MUMBAI branch employees. We will get back for Wada branch salary processing -E25jul1557 aug salary shall be done till friday.
5004 | PLASMA RESEARCH TRUST NX | Escalation | Completed |  |  |  | Completed | Paras Mahesh Ladva | Watch | No approved SCH match |  |  | No manual PM note is available for PLASMA RESEARCH TRUST NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Paras Mahesh Ladva. | Tracker/SCH Status | No Match | TRUE | 2025-01-07 | 2025-04-25 | 631 | 35 | NX | Normal
5005 | Bengal Energy_Staff | Allocation | Completed | BENGAL ENERGY LTD- STAFF | Go LIVE | Project is handed over from implementation team to support team. | Completed | Mayur Pendhari | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. | SCH Project Remark | Approved Alias | FALSE | 2025-01-08 | 2026-03-30 | 630 | 550 | NX | Premium | Mayur Pendhari | welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189
5006 | Bengal Energy_Worker | Allocation | Lost | BENGAL ENERGY LTD- CONTRACTUAL | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Mayur Pendhari | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: Finds excel easy. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. | SCH Project Update | Approved Alias | FALSE | 2025-01-08 | 2025-06-30 | 630 | 1100 | NX | Premium | Mayur Pendhari | they clarified that there are no concerns or issues from Spine’s end. The current process is a business decision on their part. For contractual employees, the contractors submit attendance via Excel sheets, which the internal team simply verifies before processing payments. They also mentioned that they are in the process of streamlining their work process system. Once that is properly aligned, they will reconnect with Spine to proceed with the contractual employee license. | Finds excel easy
5007 | Parbhani Medical College | Allocation | Lost | PARBHANI MEDICAL COLLEGE (PMC) | Lost | Client/project lost and license is deactivated. | Completed | Sushant Thombare | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Funds issue. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Sushant Thombare. | SCH Project Update | Approved Alias | FALSE | 2025-01-13 | 2026-01-28 | 625 | 500 | NG | Normal | Sushant Thombare | Welcome call done data file expl done Implementation starts from 14th feb 25 HRMS and Mobile HR Training Completed and All modules Explained and Showed by Engineer -W25feb8024 PayrollNg Training Completed and All modules Explained and Showed by Engineer and Jan 2025 salary Processed -W25feb6982 was following up the user since last week, however call was not received , Today had a call with him , he mentioned he was on leave past 8 to 10 days and now he is working on March salary and will reach out to me i assistance required, and for feb salary he will upload the past salary data. salary processed till march aprl salary mostly till next week, New biometric machine is installed, again we need to integrate data again, and now the user is admitted in hospital and currently there is no other user in his absence. April 25 Salary Process complete - E25may10890 In Parbhani , Half employees do not receive salary yet of april, they shall receive in May or june , told shreyas to take this on mail. May salary he shall process till 10th june. This email is to inform you that we have not been able to process the salaries for our remaining employees through your software. This is due to a temporary issue that we are actively working to resolve. We will resume full salary processing via your platform as soon as possible. We appreciate your understanding in this matter and will keep you updated on our progress. E25jun2237 They have fund issues that is the reason salary is delayed Salary processing is delayed every month as there is funds issue at client end, hence closing as lost | Funds issue
5008 | Aquaair International Frieght Services | Escalation | Completed | AQUAAIR INTERNATIONAL FREIGHT SERVICES | Go LIVE | Project is handed over from implementation team to support team. | Completed | Nagendra Poojary | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Karuna in follow up, user waiting for management approval 24/2. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Nagendra Poojary. | SCH Project Update | Approved Alias | FALSE | 2025-01-13 | 2025-04-25 | 625 | 45 | NX | Normal | Nagendra Poojary | Welcome call done data file explanation on 11th july 24 awaiting files training starts from 16 th sep 24 successfully completed the Payroll training and processed and verified the salary for the month of August using the Payroll system they have successfully logged into the app.-402035 HRMS training was successfully completed today.-402035 Salary processed till nov and dec salary they will process with attendance. queries resolved New user training has started. payroll training done , HRMS Training is done.W25mar9197 We have successfully processed salary of March 2025 with attendance from HRMS-W25mar9197 | Karuna in follow up, user waiting for management approval 24/2
5009 | Hardcarb Technologies Private Limited | Escalation | Completed | HARDCARB TECHNOLOGIES PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Tejas Rajesh Baragade | Closed | Closed/lost item, monitor only | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Manual PM Note | Approved Alias | FALSE | 2025-01-14 | 2025-04-25 | 624 | 250 | NX | Normal | Tejas Rajesh Baragade | Project Live - Training of payroll done - #E24oct8342 August month tallied HRMS training done - #E24oct8342 October month salary processed November month salary processed integration done February month salary processed March month live salary processing done with attendance from NX
5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Allocation | Completed | MADHUSUMAN ENTERPRISES | FC Lost | Project was fully completed but later lost. | Completed | Tejas Rajesh Baragade | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. Tracker status is Completed; SCH status is FC Lost (Project was fully completed but later lost.). Current milestone: Completed. Current owner/implementation contact: Tejas Rajesh Baragade. | SCH Project Update | Approved Alias | FALSE | 2025-01-14 | 2025-07-17 | 624 | 125 | NX | Normal | Tejas Rajesh Baragade | Welcome call done URL created #trng and impl from 29 th jan payroll training done - W25jan12818 HRMS on 12th feb We have completed the training on attendance module also december & January month salary process and tally. - W25feb5072 they are going to use mark in mark out, only for few empl if location is proper then logins logins done march salary 26 emp done, pending emp they will complete in this week In Madhusuman as there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine.
5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Allocation | Completed | KHERWADI SOCIAL WELFARE ASSOCIATION | Go LIVE | Project is handed over from implementation team to support team. | Completed | Probian Biswas | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | SCH Project Update | Approved Alias | FALSE | 2025-01-14 | 2025-10-28 | 624 | 350 | NX | Premium | Probian Biswas | Project Live - Payroll Till Tax done/ HRMS & mobile app logins rolled out to employees - E25feb5562 HRMS training done & RCT module training & implementation done - E25feb5562 HRMS training done-E25jan12873 February month salary processed ELC, RCT, RD & PMS Module training & implementation is done April month salary processed May & June month salary processed live from system with attendance | Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary
5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Escalation | Completed | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | FC Lost | Project was fully completed but later lost. | Completed | Amit Krishnakant Tiwari | Closed | Closed/lost item, monitor only | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Manual PM Note | Approved Alias | FALSE | 2025-01-14 | 2025-04-25 | 624 | 30 | NX | Normal | Amit Krishnakant Tiwari | #Payroll training has been completed, jan salary processing also done and salary tallied, further training and policy setup of hrms will be done next week - W25jan11630 W25mar3684 - HRMS Training is completed #W25apr9497 - march done with attendance #April'2025 Salary processed and Tally with attendance. #W25jul4405 - june salary done & live confirmation #FC LOST : The client was expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software.
5013 | Metafab | Escalation | Completed |  |  |  | Completed | Goraksha Pawar | Watch | No approved SCH match |  |  | No manual PM note is available for Metafab; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Goraksha Pawar. | Tracker/SCH Status | No Match | TRUE | 2025-01-21 | 2025-04-25 | 617 | 270 | NX | Normal
5014 | Texple | Escalation | Completed |  |  |  | Completed | Santosh Yadav | Watch | No approved SCH match |  |  | No manual PM note is available for Texple; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Santosh Yadav. | Tracker/SCH Status | No Match | TRUE | 2025-01-23 | 2025-04-25 | 615 | 30 | NX | Normal
5015 | ERMELLI PRIVATE LIMITED | Escalation | Completed |  |  |  | Completed | Hardik Panchal | Watch | No approved SCH match |  |  | No manual PM note is available for ERMELLI PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Hardik Panchal. | Tracker/SCH Status | No Match | TRUE | 2025-01-24 | 2025-04-25 | 614 | 55 | NX | Normal
5016 | Helen Keller Institute for Deaf & Blind | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for Helen Keller Institute for Deaf & Blind; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-01-15 | 2025-04-25 | 623 | 80 | NX | Normal
5017 | Cartfire India | Escalation | Completed | CARTFIRE INDIA | Go LIVE | Project is handed over from implementation team to support team. | Completed | Nagendra Poojary | Closed | Closed/lost item, monitor only | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Manual PM Note | Approved Alias | FALSE | 2025-01-24 | 2025-04-25 | 614 | 26 | NX | Normal | Nagendra Poojary | Payroll, HRMS and mobile HR training completed - #E24sep6995 Integration is done # processed Oct & Nov. Salary with Attendance from HRMS - E24dec5935 December month salary processed January month salary processed
5018 | Sky Prints | Escalation | Completed | SKY PRINTS | Go LIVE | Project is handed over from implementation team to support team. | Completed | Nagesh Tiwari | Closed | Closed/lost item, monitor only | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Manual PM Note | Approved Alias | FALSE | 2025-01-25 | 2025-04-25 | 613 | 100 | NX | Normal | Nagesh Tiwari | Direct Training & Implementation from 20th Dec We have completed and implementation and Training of spine HR and payroll NX We will discussed internally and will update and regarding roll out- W24dec7076 Need session for attendance integration and salary processing query on 28th Jan 2025 December salary done, we will process Jan salary till 03.02.2025 i will let u know if any issue happens, we have not decided to give the logins employees-E25jan8659 February Salary completed with attendance.-E25mar499 February Salary completed
5019 | Cogencis | Escalation | Completed |  |  |  | Completed | Vikas Yadav | Watch | No approved SCH match |  |  | No manual PM note is available for Cogencis; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Tracker/SCH Status | No Match | TRUE | 2025-01-31 | 2025-04-25 | 607 | 500 | NX | Normal
5020 | S K Traders | Allocation | Completed | S K TRADERS NX | Go LIVE | Project is handed over from implementation team to support team. | Completed | Rahul Ankush Dalvi | Closed | Closed/lost item, monitor only | Progress & Review Call | Progress & Review Call | Progress & Review Call. | Manual PM Note | Approved Alias | FALSE | 2025-01-31 | 2025-06-30 | 607 | 25 | NX | Premium | Rahul Ankush Dalvi | URL & Files awaiting, files received, imple from 12th, client will not use payroll #E25feb5774 HRMS training #E25feb5780 training done login will be share on 18th #E25feb6379, logins given Client live- #E25feb6379, training & imple done, client will not use payroll, using only HRMS, logins given.
5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Escalation | Completed |  |  |  | Completed | Darshit Pithwa | Watch | No approved SCH match |  |  | No manual PM note is available for SEEBA INDUSTRIES PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Darshit Pithwa. | Tracker/SCH Status | No Match | TRUE | 2025-02-05 | 2025-04-25 | 602 | 132 | NX | Normal
5022 | Infexn Laboratories | Escalation | Completed | INFEXN LABORATORIES PVT LTD | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Shubham Gurav. | SCH Project Remark | Approved Alias | FALSE | 2025-02-05 | 2025-04-25 | 602 | 200 | NX | Normal | Shubham Gurav | #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed.
5023 | Sankalpan | Escalation | Lost |  |  |  |  | Rahul Ankush Dalvi | Watch | No approved SCH match |  |  | No manual PM note is available for Sankalpan; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Tracker/SCH Status | No Match | TRUE | 2025-02-12 | 2025-10-28 | 595 | 70 | NX | Normal
5024 | Emmay Entertainment | Escalation | Completed |  |  |  | Completed | Nandadeep Mhatre | Watch | No approved SCH match |  |  | No manual PM note is available for Emmay Entertainment; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nandadeep Mhatre. | Tracker/SCH Status | No Match | TRUE | 2025-02-18 | 2025-04-25 | 589 | 42 | NX | Normal
5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Allocation | Completed | INDIANA GRATINGS PVT LTD | FC | Live salary processing is complete and client is on watch list. | Completed | Rahul Ankush Dalvi | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response sept sal will be live processing. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. | SCH Project Remark | Approved Alias | FALSE | 2025-02-18 | 2026-02-27 | 589 | 465 | NX | Premium | Akshay Joshi | payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response sept sal will be live processing
5026 | RADIX ELECTROSYSTEMS PVT LTD | Allocation | Completed | RADIX ELECTROSYSTEMS PVT LTD | Go LIVE | Project is handed over from implementation team to support team. | Completed | Aditya Pathak | Closed | Closed/lost item, monitor only | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | Manual PM Note | Approved Alias | FALSE | 2025-02-18 | 2026-03-30 | 589 | 630 | NX | Normal | Aditya Pathak | Project Live - PMS mod overviwe is done & for same module training user will get back to us with policies Training & Implementation of Payroll Nx is completed - #E25mar11411 & #E25mar6281 February month salary processed & tallied - #E25mar10450 March month live processing done April month salary processed & tallied June & july month tallied ELC module training & Implementation done PMS & request desk will are doing followup with user but they are not giving us data to do training & Implementation
5027 | MARU CONSULTANCY SERVICES | Allocation | Lost | MARU CONSULTANCY SERVICES | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Ruchit Shailesh Patel | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manual PM Note | Approved Alias | FALSE | 2025-02-19 | 2025-06-04 | 588 | 150 | NG | Normal | Ruchit Shailesh Patel | URL & files awaiting, payroll files expected on 22nd, master file will be share on 27th, master file received, kick off meeting on 4th Waiting for revised & Register file #E25mar2864, files received, training date waiting, imple from 24th, training done #E25mar8603, #E25mar9860 Geo fencing #E25mar10496 Geo fencing #E25apr105, session arranged on 3rd #E25apr105 fencing done mobile login given to half employees #E25apr1678, logins given, march salary will be complete in 3rd week April salary expected live March done user will get back to us for April salary, probably complete by 7th S/w not in use, outsourcing, attendance is priority, blue collar employees unable to use attendance, for meeting user will get back to us. Onsite meeting on 29th RECENT UPDATE - MARU CONSULTANCY SERVICES use to process salary for their client, however they have left, if any new cliient onboards then they shall renew it for salary processing. | Funds issue
5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Allocation | Completed | SHREE RAMDEV METALEX LLP | Go LIVE | Project is handed over from implementation team to support team. | Completed | Tejas Rajesh Baragade | Closed | Closed/lost item, monitor only | Progress & Review Call | Progress & Review Call | Progress & Review Call. | Manual PM Note | Approved Alias | FALSE | 2025-02-24 | 2026-01-28 | 583 | 300 | NX | Premium | Tejas Rajesh Baragade | Client have completed the Spine Payroll Software training on 19/03/2025 -E25mar6215 Spine payroll training for Day-2 has been completed. We covered the HRMS module (Admin, Self-Service, and Leave), as well as the February 2025 salary process and Tally.-E25mar6704 Client have successfully completed the Spine HRMS and Mobile HR training on 21st March 2025.-E25mar7156 March month salary processed The salary of month May-2025 has been successfully processed in spine. -E25jun1773 July has been successfully processed and tallied-W25aug6270 August salary done This is to notify you that currently our employees are not regularizing attendance before payroll, So we are in the process of streaming line our attendance regularization on time. For next few months (3-4) Month we shall process salary in Spine parallel. Currently we have processed salary till Sep-25 and we shall get back to team Spine support in future whenever required-E25oct4126 Oct-25 processed with Spine attendance parallel November salary processing is completed for 179 employees.
5029 | APLAB LIMITED (FOR STAFF LICENSE) | Allocation | Completed | APLAB LIMITED (FOR STAFF LICENSE) | Go LIVE | Project is handed over from implementation team to support team. | Completed | Varun Rajbhar | Closed | Closed/lost item, monitor only | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Manual PM Note | Approved Alias | FALSE | 2025-02-26 | 2025-10-28 | 581 | 165 | NX | Normal | Varun Rajbhar | conversion done user want separate db- E25mar2449 installation done handholding done today - W25apr4191 confirmation feb & march salay procssed from spine Aplab PayrollNX Training completion Ticket I'd W25apr4191 attendance integration done implementation confirmation- W25jun5948 they will not process payroll live, they process salary for 2 3 months together for statutory reports E25jul10109 - confirmation
5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | Allocation | Completed | APLAB LIMITED (FOR CONTRACT LICENSE) | Go LIVE | Project is handed over from implementation team to support team. | Completed | Varun Rajbhar | Closed | Closed/lost item, monitor only | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Manual PM Note | Approved Alias | FALSE | 2025-02-26 | 2025-10-28 | 581 | 251 | NX | Normal | Varun Rajbhar | contractual conv not required user will share fresh data-E25mar2250 TRAINING DONE - They will be using spine for tracking attendance only E25jun5035 - confirmation using only for attendance, will not use for payroll E25jul10109
5031 | NPSE AUTOMATION PVT. LTD | Escalation | Lost | NPSE AUTOMATION PVT. LTD. | Lost | Client/project lost and license is deactivated. | Completed | Nandadeep Mhatre | Closed | Closed/lost item, monitor only | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Manual PM Note | Approved Alias | FALSE | 2025-02-12 | 2025-04-25 | 595 | 55 | NX | Normal | Nandadeep Mhatre | Training & Implementation from 16th December 2024 We attend training of payroll nx & we have process salary of nov24 in payroll NX- E24dec3116 we have completed the Training of HRMS and its modules Admin,Leave and Time and MobileHR.-E24dec5532 Attendance integration issue not sorted as we have provided multiple solutions but they are not gave any response and also as cost barer regarding attendance integartions, solutions were provided: We have proposed the following solutions to retrieve attendance data in HRMS: Provide us with the attendance data in a SQL table in the format specified by Spine. Allow us to add the necessary extra fields to the SQL attendance table maintained by the biometric vendor. For daily attendance, use MobileHR, which will be reflected directly in HRMS and does not require a biometric machine. Based on your request, we have also suggested other biometric vendor recommendations. npse partner binu mathew is taking charge of attendance issue we need to wait for 2 days User and Owner not responding call and even mails. | Attendance Integration issue, vendor providing data only through API
5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Allocation | Completed |  |  |  | Completed | Vinay Kareliya | Watch | No approved SCH match |  |  | No manual PM note is available for ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vinay Kareliya. | Tracker/SCH Status | No Match | TRUE | 2025-03-03 | 2025-10-28 | 576 | 125 | NG | Normal
5033 | KARVY TECHNOLOGIES PVT LTD | Allocation | Lost | KARVY TECHNOLOGIES PVT. LTD. | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Tejas Rajesh Baragade | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month. | Manual PM Note | Approved Alias | FALSE | 2025-03-03 | 2026-03-30 | 576 | 130 | NG | Normal | Tejas Rajesh Baragade | Payroll training confirmation: E25mar9331 HRMS, Mobile HR, and geotagging confirmation: E25mar9330 may processed as ashwini ji left the organisation nikhil from accounts team will take trng post that will proceed with payment but he is not respondng, so vasu is planning to meet phani ji cfo. new user training session done now for salary processing user is not responding positively. geo location, fencing done attendance is coming proper as of now user have few queries, impl team in discussion QUERIES RESOLVED PAYMENT FOLLOW UP ONGOING Few concerns with regards to geo fencing was there, we resolved it too, user not ready to release the pending payment. | Not happy with service
5034 | QUALIGENS PHARMA PVT. LTD | Allocation | Completed | QUALIGENS PHARMA PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Ruchit Shailesh Patel | Closed | Closed/lost item, monitor only | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Manual PM Note | Approved Alias | FALSE | 2025-03-07 | 2025-10-28 | 572 | 400 | NX | Normal | Ruchit Shailesh Patel | Client have completed Payroll Nx,Spine HRMS & Mobile HR training we processed the salary for March_2025. Client have successfully installed & configured attendance module in Spine HRMS software.-E25apr7956 completed the process of Leave Policy ,we have checked & it is ok. Client was facing issues to process the month of May salary due to new TAX regime,this query has resolved now we are processing the May month salary.-W25jun5512 June salary processed and MLWF Query has resolved -Connected by Ms. Ankita.- W25jul1673 July salary in process.-W25aug2373
5035 | MADURA INDUSTRIAL TEXTILES LIMITED | Allocation | Completed | MADURA INDUSTRIAL TEXTILES LIMITED. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Varun Rajbhar | Closed | Closed/lost item, monitor only | Closed | Closed | Closed. | Manual PM Note | Approved Alias | FALSE | 2025-03-10 | 2026-04-28 | 569 | 287 | NX | Normal | Varun Rajbhar | first focus on the HRMS module, as they wil be revising the salary structure after the appraisal so want to proceed with hrms- E25apr8632 we have Completed the HRMS Training for Admin, Self Service, Leave and Time (till Shift) Module.- E25apr8632 they are processing salary live with attn additional module done VM confirmation- E25dec2755
5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Allocation | Completed |  |  |  | Completed | Sahil Gadhave | Watch | No approved SCH match |  |  | No manual PM note is available for BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. | Tracker/SCH Status | No Match | TRUE | 2025-03-18 | 2025-10-28 | 561 | 700 | NG | Normal
5037 | STEAM PULSE INDIA PVT LTD | Allocation | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Daksh Pawankumar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Daksh Pawankumar. | SCH Project Update | Approved Alias | FALSE | 2025-03-25 | 2025-10-28 | 554 | 140 | NG | Normal | Daksh Pawankumar | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us
5038 | STEAM HARBOUR LOGISTICS PVT LTD | Allocation | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Daksh Pawankumar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Daksh Pawankumar. | SCH Project Update | Approved Alias | FALSE | 2025-03-25 | 2026-01-28 | 554 | 60 | NG | Normal | Daksh Pawankumar | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us
5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Escalation | Completed |  |  |  | Completed | Sachin Thothawala | Watch | No approved SCH match |  |  | No manual PM note is available for GUJARAT TEA PROCESSOR & PACKERS LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sachin Thothawala. | Tracker/SCH Status | No Match | TRUE | 2025-03-25 | 2025-06-01 | 554 | 1250 | NX | Normal
5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Escalation | Completed |  |  |  | Completed | Kajal Inchanalkar | Watch | No approved SCH match |  |  | No manual PM note is available for INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Kajal Inchanalkar. | Tracker/SCH Status | No Match | TRUE | 2025-03-17 | 2025-06-01 | 562 | 850 | NX | Normal
5041 | TATARIA HARDWARE INNOVATION | Escalation | Completed |  |  |  | Completed | Nagendra Poojary | Watch | No approved SCH match |  |  | No manual PM note is available for TATARIA HARDWARE INNOVATION; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nagendra Poojary. | Tracker/SCH Status | No Match | TRUE | 2025-03-18 | 2025-06-01 | 561 | 60 | NX | Normal
5042 | THE NATIONAL SPORTS CLUB OF INDIA | Escalation | Active | NATIONAL SPORTS CLUB OF INDIA NX | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Mihir Navnath Mungekar | Critical | Ageing 560 days from start date | Live Salary Processing Planned. | Live Salary Processing Planned. | Live Salary Processing Planned. | Manual PM Note | Approved Alias | FALSE | 2025-03-19 |  | 560 | 450 | NX | Premium | Mihir Navnath Mungekar | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. Due to biometric machine was not working due to which there were many employees who had not punched in the system. Because of which they have to do the salary as per the previous process. Were we told Mdm. Megha that as they have processed the September salary. So we will not regularize the September attendance. Will update the attendance from 25th September to 28th September. Sept salary processed by uploading atten. October sal is live target Need to discuss with client on monday with vasu for payment related.
5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Allocation | Completed |  |  |  | Completed | Amol Takkar | Watch | No approved SCH match |  |  | No manual PM note is available for EROS ELEVATORS & ESCALATORS PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Tracker/SCH Status | No Match | TRUE | 2025-04-01 | 2025-05-01 | 547 | 400 | NX | Premium
5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Allocation | Completed | ELECTROSTEEL CASTINGS LTD | FC | Live salary processing is complete and client is on watch list. | Completed | Kunal Joshi | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Kunal Joshi. | SCH Project Update | Approved Alias | FALSE | 2025-04-01 | 2026-04-28 | 547 | 1000 | NX | Premium | Kunal Joshi | training and impl conf- E25jul10921 logins rolled out not going to process salary from spine, using hrms. renewal done | SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa
5045 | SAI SANKET INDUSTRIES PVT.LTD | Escalation | Completed | SAI SANKET INDUSTRIES PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Dakshesh D Nadkar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Dakshesh D Nadkar. | SCH Project Remark | Exact Name | TRUE | 2025-04-01 | 2025-05-25 | 547 | 410 | NX | Premium | Dakshesh D Nadkar | Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth
5046 | LOTUS TEXCOM INDIA LLP | Escalation | Lost | LOTUS TEXCOM INDIA LLP | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Prathamesh Mandavkar | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority. | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority. | Manual PM Note | Approved Alias | FALSE | 2025-04-04 | 2025-07-23 | 544 | 51 | NG | Normal | Prathamesh Mandavkar | mail done- call done, URL done, data file expln done Impelementation and trng starts from 27th dec 24 biometric data is not proper in atten sql problem from their side suggested vendor As my recent call with user for follow up, Mr. Vaibhav user told that as per their senior, they want unsubscribe the services, told him, whatever your concerns are kindly mail and let me know we can arrange meeting with PM and your senior awaiting mail from his end. user not responding, same is informed to PM and partner, partner team shall do visit at client placed as mentioned by them. Meeting arranged tomorrow for discussion with PM and Lotus Texcom Director. Spoke to Mr. Harshal , he mentioned there are issues going on and on , there were biometric issues, data was not not getting pushed in sql table its not syncing and Mr. Harshal does not want to invest in New Biometric Machine, he mentioned he has informed the same to Sun heights parther Mr. Liayakt too. | Attendance integration issue
5047 | BRILLIANT POLYMERS PVT. LTD | Escalation | Completed |  |  |  | Completed | Probian Biswas | Watch | No approved SCH match |  |  | No manual PM note is available for BRILLIANT POLYMERS PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Tracker/SCH Status | No Match | TRUE | 2025-04-14 | 2025-06-01 | 534 | 185 | NX | Normal
5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Escalation | Completed |  |  |  | Completed | Vikas Yadav | Watch | No approved SCH match |  |  | No manual PM note is available for AUTOTECH-SIRMAX INDIA PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Tracker/SCH Status | No Match | TRUE | 2025-04-21 | 2025-07-17 | 527 | 205 | NX | Normal
5049 | TAO AUTOMATION SERVICES PVT LTD | Escalation | Completed |  |  |  | Completed | Supriya Waghmare | Watch | No approved SCH match |  |  | No manual PM note is available for TAO AUTOMATION SERVICES PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Supriya Waghmare. | Tracker/SCH Status | No Match | TRUE | 2025-04-22 | 2025-07-17 | 526 | 60 | NX | Normal
5050 | BASANT OVERSEAS | Escalation | Lost | BASANT OVERSEAS | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Yash Pankajkumar Shah | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Live Salary Processing Planned. | Live Salary Processing Planned. | Manual PM Note | Approved Alias | FALSE | 2025-04-25 | 2026-03-30 | 523 | 1454 | NG | Normal | Yash Pankajkumar | Till date, all the requirements received have been delivered to Team Basant. Mr. Deep has also confirmed that he is satisfied with the updates—reference ticket number W25AUG5167. The delay occurred due to the day-to-day new requirements received from the team, based on which our team made the necessary changes and obtained confirmation accordingly. We are now ready to proceed with the further training and implementation activities. However, the client’s AMC has expired. Requesting your guidance on how we should proceed further. yash is working on the same with hemant sir | Resoure Problem
5051 | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | Escalation | Lost |  |  |  |  | Rahul Ankush Dalvi | Watch | No approved SCH match |  |  | No manual PM note is available for POONAM ROLLER FLOUR MILLS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Tracker/SCH Status | No Match | TRUE | 2025-04-28 | 2025-06-04 | 520 | 100 | NX | Normal
5052 | SNAPWORK TECHNOLOGIES PVT LTD | Allocation | Completed | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Vijay Bugde | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Vijay Bugde. | SCH Project Update | Approved Alias | FALSE | 2025-05-03 | 2026-02-27 | 515 | 360 | NX | Normal | Vijay Bugde | welcome call done payroll done april tallied hrms basic module done geo tagging done logins rolled out integration/smtp done MAY DONE E25jun8292 june salary conf- E25jul5746 LDAP and maker checker. provided processing live salary from system pms and time sheet pending- if session required client will reach out to us.W26apr5969 #10/08 - rcvd a ticket from user regarding issue in approver. #18/08 - feedback was not good at all, she told she would give zero rating, her main issue was about resource allocation charges, which i was explaining her, then she told, she is quite allocated today, we can connect tomorrow. #28/08 - E26aug9070 - user requested for user manual for sharing with their employees. | Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10
5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-05-24 | 2025-07-23 | 494 | 630 | NX | Normal
5054 | BRIGHT BROTHERS LTD. / BRITE | Allocation | Completed | BRIGHT BROTHERS LTD | FC | Live salary processing is complete and client is on watch list. | Completed | Rahul Ankush Dalvi | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project remark: Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. Next action: Review blocker, confirm owner, and update next closure plan. | SCH Project Remark | Approved Alias | FALSE | 2025-05-27 | 2026-02-27 | 491 | 520 | NG | Normal | Yash Pankajkumar | Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system
5055 | ARMITA INDIA SHIPPING PVT. LTD | Escalation | Completed |  |  |  | Completed | Mayur Pendhari | Watch | No approved SCH match |  |  | No manual PM note is available for ARMITA INDIA SHIPPING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. | Tracker/SCH Status | No Match | TRUE | 2025-05-24 | 2025-07-23 | 494 | 45 | NX | Normal
5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Escalation | Completed |  |  |  | Completed | Shreyas Karkera | Watch | No approved SCH match |  |  | No manual PM note is available for PRECIOUS ALLOYS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Shreyas Karkera. | Tracker/SCH Status | No Match | TRUE | 2025-05-24 | 2025-06-01 | 494 | 151 | NX | Normal
5057 | SUKHKARTA MULTISPECIALITY HOSPITAL | Escalation | Lost | [5 empty] | Watch | No approved SCH match |  |  | No manual PM note is available for SUKHKARTA MULTISPECIALITY HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Lost. | Tracker/SCH Status | No Match | TRUE | 2025-05-24 | 2025-07-23 | 494 | 25 | NX | Normal
5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Escalation | Completed | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | FC Lost | Project was fully completed but later lost. | Completed | Tushar More | Closed | Closed/lost item, monitor only | Review Meeting | Review Meeting | Review Meeting. | Manual PM Note | Approved Alias | FALSE | 2025-06-01 | 2025-08-30 | 486 | 51 | NX | Normal | Tushar More | Welcome Call done URL sent for creation training and Implementation from 4th july 24 We proceed july and august salary.-E24aug7741 ONETEAM LOGISTICS INDIA PRIVATE LIMITED- held up-22nd oct 24 we have completed the training of Payroll NX and HRMS till Self services. -E25feb8341 Add module welcome call done. following up with user for workflow and policies, however still files are not received Leave and TAM module impl and training aligned 4th april 2025 LEave tam training done and Integration done, following up with user he mentioned that still there are lot of queries , told him to mail and we can schedule the same, Schedule aligned for past salary and queries. tomorrow. 09th may. 25 We processed the salary april_2025 with attendance -W25may486 May salary has been processed, No response from user- project is stuck. user was busy in audit, and shall process aug sep in 1st week of oct. oct salary processed Nov will be done till 15th dec 25. user is not responding, we tried reaching out to user many times, no response hence closing as lost | Not responding no reason
5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Allocation | Completed |  |  |  | Completed | Amol Takkar | Watch | No approved SCH match |  |  | No manual PM note is available for GOLDSTAR ELITE JEWELS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Tracker/SCH Status | No Match | TRUE | 2025-06-01 | 2025-07-30 | 486 | 495 | NX | Premium
5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Allocation | Completed |  |  |  | Completed | Mukeshkumar Shojiram kumavat | Watch | No approved SCH match |  |  | No manual PM note is available for SAINI ELECTRICAL & ENGINEERING WORKS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mukeshkumar Shojiram kumavat. | Tracker/SCH Status | No Match | TRUE | 2025-06-01 | 2025-07-30 | 486 | 300 | NX | Premium
5061 | GNG ELECTRONICS LIMITED STAFF | Allocation | Completed | GNG ELECTRONICS LIMITED STAFF | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | plan activities in 2days. | plan activities in 2days. | plan activities in 2days. | Manual PM Note | Approved Alias | TRUE | 2025-06-01 | 2025-10-28 | 486 | 250 | NX | Normal | Shubham Gurav | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535
5062 | GNG ELECTRONICS LIMITED FACTORY | Allocation | Lost | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | Review Meeting | Review Meeting | Review Meeting. | Manual PM Note | Approved Alias | TRUE | 2025-06-01 | 2025-07-23 | 486 | 750 | NX | Normal | Shubham Gurav | Project Live - Training & Implementation of RCT Module is done - E26jan11064
5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | Allocation | Completed | ALLIED INSTRUMENTS PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Vijay Bugde | Closed | Closed/lost item, monitor only | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Manual PM Note | Approved Alias | FALSE | 2025-06-01 | 2026-03-30 | 486 | 500 | NX | Premium | Vijay Bugde | training and impl confirmation - E25apr6298 training provided on 28th july attendance centralization ongoing daman silvasa khar integration in process. ------------------------------------------ STUCK- july pending new user training provided queries resolving going on Manish ji said from spine we are getting good support, but its my team we are not on track lot many things are going -audits etc & they are hands on tally so getting out of comfort zone for them is the thing. will try to start processing for oct month. E25sep1678- aug processed by importing attendance they use spine for audit purpose only for jan salary we scheduled a session, we have added all the employees they have conveyed that they will start doing live salary within few months client only use our system when they have audit not going to process live salary go live mail sent to client- E26may9307
5064 | MESPACK INDIA PVT. LTD | Allocation | Completed | MESPACK INDIA PVT. LTD | FC | Live salary processing is complete and client is on watch list. | Completed | Pooja Vikas Shinde | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Pranit to coordinate internally and align the implementation, team to coordinate for further activities | Pranit to coordinate internally and align the implementation, team to coordinate for further activities. | Manual PM Note | Approved Alias | FALSE | 2025-06-09 | 2026-04-28 | 478 | 50 | NG | Normal | Pooja Vikas Shinde | Payroll training done successfully completed the attendance integration activity at the client’s location. W25oct6232 , E25nov1863 october salary has been processed. nov salary done successfully processed the December 2025 salary. - E26jan4924. Expense module training done Jan salary processed February salary done March salary has been processed-E26apr8430 April done may salary done parallelly GO FC- As all activities related to training and implementation have been completed successfully, and the system is now fully ready for use. Due to an internal gap, the attendance has not been regularized so salary processing will be carried out in parallel. August salary has been processed with attendance. Called for feedback to user Ms. Usha not responded the call. sept live sal target As per akshay sept sal followup is going on
5065 | UNITED AIR EXPRESS | Allocation | Completed | UNITED AIR EXPRESS | FC | Live salary processing is complete and client is on watch list. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Manual PM Note | Approved Alias | FALSE | 2025-06-20 | 2026-04-28 | 467 | 2550 | NG | Normal | Shubham Gurav | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system
5066 | Kuboz Arc Pvt Ltd | Escalation | Lost |  |  |  |  | Santosh Yadav | Watch | No approved SCH match |  |  | No manual PM note is available for Kuboz Arc Pvt Ltd; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Santosh Yadav. | Tracker/SCH Status | No Match | TRUE | 2025-06-24 | 2025-07-23 | 463 | 200 | NG | Normal
5067 | ISA Logistics Private Limited | Escalation | Completed | ISA LOGISTICS PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Mihir Navnath Mungekar | Closed | Closed/lost item, monitor only | April Salary Processed, Review Meeting | April Salary Processed, Review Meeting | April Salary Processed, Review Meeting. | Manual PM Note | Approved Alias | FALSE | 2025-06-19 | 2025-07-23 | 468 | 200 | NG | Normal | Mihir Navnath Mungekar | Completed the training of Payroll, Mobile and HRMS -E25mar9861 payroll process for the month of April 2025 has been processed successfully-E25may7360 May-2025 Salary Processed- E25may12012 June salary processed-W25jul6461 July salary processed August salary processed October month salary done Nov salary processed-E25dec1872 Dec salary processed- Processed the salary for Jan 26 got tallied for all employees-E26feb4932. PMS done- E26feb33. Feb salary processed-E26mar1563. march salary done April salary only 43 employees done new hr manager training completed Client has processed salary from excel. Currently client's priority is to process PMS from Spine, Once done they will process salary for May26 using only hrms module- E26jul2753. New user Mr. Rahul has shared HRMS Scope of Work for Review and Feasibility Confirmation and requirements has mentioned we are still working on it last working in 14th aug has been done by mihir and still we are working and need clarification by client and need to discuss with them. hrms queries are ongoing user has shared attached KRA and KPI document for reference sch to be aligned | Only HRMS
5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Escalation | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Pritesh Barot | Closed | Closed/lost item, monitor only | Datafiles Received, Implementation planned, Team to followup | Datafiles Received, Implementation planned, Team to followup | Datafiles Received, Implementation planned, Team to followup. | Manual PM Note | Approved Alias | FALSE | 2025-06-27 | 2025-07-23 | 460 | 250 | NX | Normal | Pritesh Barot | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us.
5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Escalation | Completed | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Go LIVE | Project is handed over from implementation team to support team. | Completed | Hardik Panchal | Closed | Closed/lost item, monitor only | Need to plan Review Meeting | Need to plan Review Meeting | Need to plan Review Meeting. | Manual PM Note | Approved Alias | FALSE | 2025-07-12 | 2025-08-30 | 445 | 145 | Spine HRMS | SAAS | Hardik Panchal | Welcome call done data expl done Training starts from 30th 2025 #completed the Payroll Training and Also Employee rollout has been done and Also december salary has been matched with our records - E25feb974 employees training and all the queries have been resolved.-E25feb7093 salary for the month of February 2025 has been confirmed and tally. - E25mar1995 | Karuna in follow up for balance payment
5070 | CONTENDRE GREENERGY LIMITED | Escalation | Completed | CONTENDRE GREENERGY LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Daksh Pawankumar | Closed | Closed/lost item, monitor only | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Manual PM Note | Approved Alias | TRUE | 2025-07-15 | 2025-08-30 | 442 | 160 | Spine NG | SAAS | Daksh Pawankumar | #Trng and impl from 21st April #E25apr9485 - complete upto loan processing module #E25apr10010 - Payroll nx training is completed Location IQ set up has been done #E25apr11264 - have completed HRMS and SMTP training #W26may1493 - update ESIC rules in Payroll #E25jul1135 - june salary conf. #W25aug3365 - PAYROLL HRMS CONF. #W25sep4179 - august salary done. #07/05 - feedback was good, processed april month salary. #18/08 - overall feedback was good, they’ve been facing an issue while transferring employee from one company to another.she require a proper solution for the same. | No open queries as of now, Vasu to connect with the director for review meet 5/9
5071 | ILEAF RITZ BANQUETS | Escalation | Completed | ILEAF RITZ BANQUETS | Lost | Client/project lost and license is deactivated. | Completed | Mayur Pendhari | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | SCH Project Update | Approved Alias | FALSE | 2025-07-17 | 2025-09-24 | 440 | 110 | Spine NG | SAAS | Mayur Pendhari | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy
5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | Escalation | Completed | ROYAL EMBROIDERY THREADS PVT.LTD. | FC | Live salary processing is complete and client is on watch list. | Completed | Bhavika Gite | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: client conveyed that within this week end will do payment 22/9. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Bhavika Gite. | SCH Project Update | Approved Alias | FALSE | 2025-07-17 | 2025-08-30 | 440 | 370 | Spine NG | SAAS | Bhavika Gite | #trng and impl from 3rd april #E25mar4404 - completed training of Payroll & HRMS #W25apr6337 - added all shift schedules, and attendace logics have been added & also training & login rollouts of Mobile HR #W25may504 - Attendace integration has been done #W25may7421 - processed the april salary #W25aug449 - june salary done #W25aug772 - july salary done ##W25sep5963 - conf. of total hours calculation calculation #11/09 - processed wages of 191 employee of pune for Aug_2025, During the verification some discrepancies identified, awaitng for final confirmation. #W25DEC1871 - nov salary done #08/05 - feedback was good no issue as of now, processed april month salary. #18/08 - feedback was neutral as always, right now there is nothing to escalate.. | client conveyed that within this week end will do payment 22/9
5073 | V ALLIANCE NX | Escalation | Completed | V ALLIANCE NX | Go LIVE | Project is handed over from implementation team to support team. | Completed | Rahul Ankush Dalvi | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. | SCH Project Remark | Approved Alias | FALSE | 2025-07-18 | 2025-08-30 | 439 | 1000 | Spine HRMS | SAAS | Rahul Ankush Dalvi | URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513
5074 | UNITED AIR EXPRESS | Escalation | Completed | UNITED AIR EXPRESS | FC | Live salary processing is complete and client is on watch list. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Manual PM Note | Approved Alias | FALSE | 2025-07-18 | 2025-08-21 | 439 | 3050 | Spine NG | SAAS | Shubham Gurav | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system
5075 | ESCON ELEVATORS PVT. LTD. | Escalation | Completed | ESCON ELEVATORS PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Probian Biswas | Closed | Closed/lost item, monitor only |  |  | No manual PM note is available for ESCON ELEVATORS PVT. LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Tracker/SCH Status | Approved Alias | FALSE | 2025-07-23 | 2025-08-30 | 434 | 805 | Spine HRMS | On-Premises | Probian Biswas
5076 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Allocation | Lost | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | Lost | Client/project lost and license is deactivated. | Completed | Vijay Bugde | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: No Reponse - No Reason. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Vijay Bugde. Next action: Review blocker, confirm owner, and update next closure plan. | SCH Project Update | Approved Alias | FALSE | 2025-08-02 | 2026-04-28 | 424 | 1500 | Spine NG | SAAS | Vijay Bugde | corp id creation done trng and impl in process Toyota and Hyudai branch employee data uploaded sucessfully also we processed Toyota branch sept month salary Employees work across multiple sites/companies and salary processing happens there. The director is using our software only to verify if the salary tallies with attendance data User is not responding, we are trying to reach user multiple times. vasu is looking into it (planning visit) director is not available, nor he is responding calls vasu went for onsite visit but they are not interested to proceed escalated the concern to amrprit through email client not interested | No Reponse - No Reason
5077 | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Allocation | Lost | RAMYASRI ELECTRICAL AUTOMATION | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Ankita Gupta | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: No Reponse - No Reason. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankita Gupta. Next action: Review blocker, confirm owner, and update next closure plan. | SCH Project Update | Approved Alias | FALSE | 2025-08-06 | 2026-04-28 | 420 | 250 | Spine NG | SAAS | Ankita Gupta | 47 emp data recd, tallied, payroll set up done, training pending not responding,esc to PM, partner team, ignoring calls, 5/2 structure recd of 36 recd, uploaded, rest data follow up going on 10/3 meeting done- datafiles will share 12/3 client not showing interest, amc not renewed, no response from client,client deactivated, | No Reponse - No Reason
5078 | FFSERVICES PRIVATE LIMITED | Escalation | Completed | FFSERVICES PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Harsh Dilip Ashar | Closed | Closed/lost item, monitor only | April Salary Processed, Review Meeting & Closure Note | April Salary Processed, Review Meeting & Closure Note | April Salary Processed, Review Meeting & Closure Note. | Manual PM Note | Approved Alias | TRUE | 2025-08-12 | 2025-11-28 | 414 | 220 | Spine HRMS | SAAS | Harsh Dilip Ashar | Project Live - PMS CONF (E26feb3272) Training & Implementation is done of PMS module
5079 | PRASAD JEWELLERS | Escalation | Lost | [5 empty] | Watch | No approved SCH match |  |  | No manual PM note is available for PRASAD JEWELLERS; this update is generated from Tracker and SCH status. Tracker status is Lost. | Tracker/SCH Status | No Match | TRUE | 2025-08-18 | 2025-11-28 | 408
5080 | SETHWALA FOODS LTD | Allocation | Completed | SETHWALA FOODS LTD | FC | Live salary processing is complete and client is on watch list. | Completed | Kunal Joshi | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Kunal Joshi. | SCH Project Update | Approved Alias | FALSE | 2025-08-21 | 2026-05-26 | 405 | 600 | Spine NG | SAAS | Kunal Joshi | GO FC- Client have completed training session of Payroll & HRMS . Also SMTP setup & locationAPI setting has been done successfully.-E25sep1207 september salary of ho done October salary done The training has been completed in talasari-E25nov8643 client have processed SFLD unit salary for the month of Dec'25 with attendance muster from the software successfully. With Login was provided to employees -E26jan2962 client inform us, for this month, HO salary will be run through Spine, while Talasari salary will be processed via Excel uploading.-E26feb1695 feb salary done march salary processed April salary processed-E26may3191 May salary processed Jun salary processed july salary done August salary processed. Called for feedback user vidhya user said queries are coming but it is getting resolved first only mumbai loc we were doing live but now talasari loc we are doing for aug but lie with attendance. sept will be fully live for both loc. will do sept live by 10th | user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9
5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Allocation | Completed | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Aditya Mazire | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Aditya Mazire. | SCH Project Remark | Approved Alias | FALSE | 2025-08-01 | 2026-01-28 | 425 | 2500 | Spine HRMS | On-Premises | Aditya Mazire | Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live
5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Escalation | Completed | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Go LIVE | Project is handed over from implementation team to support team. | Completed | Ruchit Shailesh Patel | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Ruchit Shailesh Patel. | SCH Project Update | Approved Alias | TRUE | 2025-08-14 | 2025-09-24 | 412 | 1410 | Spine HRMS | On-Premises | Ruchit Shailesh Patel | Training done #E25mar4260, as per discussion with team leader user is in testing period for this month and will start implementing with salary and attendance from june month. called user Ms. Sushama about update as they said it working properly and we have check the may salary too and attendance queries has been solved. As per our discussion over the call, client will be processing the salary from your end. In case any assistance is required during the process.-W25jul4028. July salary processeed August salary processed- E25sep4242, E25sep4197. | Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9
5083 | FUJIYAMA POWER SYSTEM (UTL) | Allocation | Completed | FUJIYAMA POWER SYSTEMS LIMITED | Lost | Client/project lost and license is deactivated. | Completed | Komal Kanadiya | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: Another Software. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | SCH Project Update | Approved Alias | FALSE | 2025-08-28 | 2026-03-30 | 398 | 2400 | Spine NG | SAAS | Komal Kanadiya | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software
5084 | VABA | Escalation | Completed | VABA | Go LIVE | Project is handed over from implementation team to support team. | Completed | Karan Rajesh Tiwari | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Karan Rajesh Tiwari. | SCH Project Update | Approved Alias | FALSE | 2025-08-04 | 2025-10-28 | 422 | 430 | Spine HRMS | SAAS | Karan Rajesh Tiwari | Client have successfully completed the PayrollNX training Client have processed the one company Bishan Steel Industries March 2025 month salary and tally with register matches to our salary register. 1. salary attendance days demo done and queries solved Client inform that our executive Mr. Karan Has Done Following works :- 1. smtp work done 2. Leave Workflow & Attendance work flow Done 3. Tally Integration work done as demo basis and it is ok -E25apr4753 As per telecon attendance integration has been done. user is processing the may salary by its own. We have completed our Salary Process for the Month of May 2025-E25jun5684 Client have completed our Salary Process for the Month of June 2025-E25jul5468 July month salary processed August salary processed August salary processed September salary processed Oct salary processed Nov salary processed January Salary processed feb salary is in process as client want to extend the employee count. | Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop
5085 | KISHAN LAL PAWAN KUMAR JAIN | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for KISHAN LAL PAWAN KUMAR JAIN; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-08-22 | 2025-10-28 | 404
5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Escalation | Completed | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Go LIVE | Project is handed over from implementation team to support team. | Completed | Mayur Pendhari | Closed | Closed/lost item, monitor only | Progress & Review Call | Progress & Review Call | Progress & Review Call. | Manual PM Note | Approved Alias | FALSE | 2025-08-22 | 2025-09-24 | 404 | 700 | Spine HRMS | SAAS | Mayur Pendhari | go live- they want to keep the database separate and conversion will be done for both the companies Micropoint Computers Pvt Ltd. Goanfest Food & Beverages Pvt Ltd-#354379 Database Handholding Both Company Databases Confirmation. # 356675 PAYROLL NX TRAINING COMPLETED #358872 successfully processed month of March 2024 of both company from payroll NX System -363500 April- salary Process #375292 2nd Entity Salary For the month of April- 375286 rct mod they will get back to us when required. few employees are using mobile app for marking attendance disbursing salary live from spine
5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for TORQUE INSURANCE BROKING PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-08-23 | 2025-10-28 | 403
5088 | POLMOR STEEL PRIVATE LIMITED | Allocation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for POLMOR STEEL PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-09-04 | 2026-01-28 | 391
5089 | ACEY ENGINEERING PVT. LTD | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for ACEY ENGINEERING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-09-04 | 2026-03-30 | 391
5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for ATHARVA FACILITY MANAGEMENT AND SECURITY; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-09-17 | 2025-10-28 | 378
5091 | MEDIPULSE HOSPITAL | Allocation | Completed | MEDIPULSE HOSPITAL | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Varun Rajbhar | High | Tracker status 'Completed' conflicts with SCH status 'AC' | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month. | Manual PM Note | Approved Alias | FALSE | 2025-09-09 | 2026-09-30 | 386 | 731 | Spine NG | SAAS | Varun Rajbhar | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. August salary on monday | Using only the HRMS Module, payroll is now initiated
5092 | PARADISE GROUP | Allocation | Active | PARADISE GROUP | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Pritesh Barot | Critical | Ageing 383 days from start date | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Manual PM Note | Approved Alias | FALSE | 2025-09-12 |  | 383 | 624 | Spine NG | SAAS | Pritesh Barot | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August
5093 | DRS EARTHWORK PRIVATE LIMITED | Escalation | Completed | DRS EARTHWORK PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Mihir Navnath Mungekar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we hav... Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | SCH Project Remark | Approved Alias | FALSE | 2025-09-24 | 2025-11-28 | 371 | 200 | Spine HRMS | SAAS | Mihir Navnath Mungekar | payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we have deleted salary for Apr-25 to Mar-26, and uploaded past salary data for all emps, Now user will process Apr & May this week and will get back to us incase of any query by 27-Jun. client will do june salary by own which will be parallel. As per feedback user said no queries if it is will let you know as I am on leave connected today for july salary As per the discussion done with Shital ji, major emps are in the field, and are not willing to mark attendance through mobile. HRMS is utilitised by approx 100 emps but live disbursement is done through excel and they will process salary in Spine for record keeping purpose only As per the feedback received from user Ms. Shital, the client is currently using the HRMS, but the process is partially manual and partially system-based. For employees who work outside the office, proper in/out punches are not recorded, so their attendance is managed manually. For employees working in the office, attendance is recorded through the system. The client uses the system for attendance summary reports and collect leave data; however, salary processing is still done manually based on these reports. Currently she has a few minor query. We told her to share the queries on the support ticket ID for further assistance.
5094 | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Allocation | Lost | CENTRE FOR URBANIZATION BUILDINGS | Active | Project has started and is moving through implementation milestones. | Datafile Explanation |  | High | Tracker status 'Lost' conflicts with SCH status 'Active' | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project remark: training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on. Tracker status is Lost; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Active'. | SCH Project Remark | Approved Alias | FALSE | 2025-09-29 | 2026-04-28 | 366 | 95 | Spine NG | SAAS |  | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on
5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Escalation | Completed | PISCES CONTAINER LINES INDIA PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Pritesh Barot | Closed | Closed/lost item, monitor only | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated. | Manual PM Note | Approved Alias | TRUE | 2025-10-13 | 2025-10-28 | 352 | 100 | Spine HRMS | SAAS | Pritesh Barot
5096 | AUROUS JEWELS LLP | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for AUROUS JEWELS LLP; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-10-13 | 2025-10-28 | 352
5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Allocation | Completed | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | FC | Live salary processing is complete and client is on watch list. | Completed | Mihir Navnath Mungekar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | SCH Project Remark | Approved Alias | FALSE | 2025-10-08 | 2026-04-28 | 357 | 135 | Spine HRMS | SAAS | Mihir Navnath Mungekar | Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on
5098 | RENMAKCH INDIA PVT. LTD. | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for RENMAKCH INDIA PVT. LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-10-28 | 2026-01-28 | 337
5099 | GNG ELECTRONICS LIMITED FACTORY | Escalation | Completed | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | Review Meeting | Review Meeting | Review Meeting. | Manual PM Note | Approved Alias | TRUE | 2025-10-13 | 2025-10-28 | 352 | 1600 | Spine HRMS | SAAS | Shubham Gurav | Project Live - Training & Implementation of RCT Module is done - E26jan11064
5100 | WHISTLING WOODS INTERNATIONAL | Allocation | Active |  |  |  | Datafile Explanation | Nagendra Poojary | Critical | No approved SCH match; Ageing 364 days from start date | PMS Implementation Ongoing | PMS Implementation Ongoing | PMS Implementation Ongoing. | Manual PM Note | No Match | TRUE | 2025-10-01 |  | 364
5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | Allocation | Completed | VIVID ELECTROMECH LIMITED | FC Lost | Project was fully completed but later lost. | Completed | Mihir Navnath Mungekar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Requirement. Tracker status is Completed; SCH status is FC Lost (Project was fully completed but later lost.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | SCH Project Update | Approved Alias | FALSE | 2025-10-30 | 2026-04-28 | 335 | 250 | Spine NG | SAAS | Mihir Navnath Mungekar | #payroll training and impl done- E25nov7138, E25nov8316 E25nov9114 #hrms training and configuration done- E25dec416 #geo tagging and integration done #E25dec4143 November salary also tallied, #dec done- E26jan2964 #feb done with attn have few requirements they were not willing to proceed because of that somehow we are convincing them team is in discussion we are following up for salary #28/09 - no response #FC LOST - As discussed with User Akash, Vivid Electro has decided not to continue using our software. They require certain modifications to the dashboard, along with changes to the hierarchy structure. These requirements are currently not feasible within our software. | Requirement
5102 | SREE METALIKS LTD | Allocation | Completed | SREE METALIKS LTD | Go LIVE | Project is handed over from implementation team to support team. | Completed | Nandadeep Mhatre | Closed | Closed/lost item, monitor only | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month. | Manual PM Note | Approved Alias | FALSE | 2025-11-11 | 2026-04-28 | 323 | 700 | Spine NG | SAAS | Nandadeep Mhatre | "7th "payroll hr set up done, oct tallied,bio int done, logins done, training done, dec done W26jan10986 client FC
5103 | NAGRIK CONSULTANCY SERVICES | Escalation | Completed | NAGRIK CONSULTANCY SERVICES | FC | Live salary processing is complete and client is on watch list. | Completed | Aditya Mazire | Closed | Closed/lost item, monitor only | Progress & Review Call | Progress & Review Call | Progress & Review Call. | Manual PM Note | Approved Alias | FALSE | 2025-11-10 | 2026-02-27 | 324 | 205 | Spine NG | SAAS | Aditya Mazire | completed Payroll training .-W25oct5654 completed with HRMS training on 1st Phase with Add on service. processed and tally the salary of Sep 2025 month for all 3 grades for126 employees. processed the salary of Oct 2025 month.- W25nov634 Employee training and logins roll out processed Salary for Nov 2025, for Midas touct MT, NHO, with attendance and tallied the same November salary processed December salary processed Jan salary done. Feb salary done. March salary done. april salary done may salary processed june salary processed As per feedback user Ms. Suvarna said No queries as such we are getting support which we required. June salary is in process. user said no queries and concern if we have we raised the mail as we asked mansi ji has escalated the attendance queries it has been resolved | Suggestion ID: 3709 Requirement: Leave Year Selection in Mobile Application Suggestion ID: 3536 Requirement: Add-On Service Request and Approval Option in Mobile Application
5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Allocation | Completed | NAIK MOTORS - RATNAGIRI LOC | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Aditya Mazire | High | Tracker status 'Completed' conflicts with SCH status 'AC' | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month. | Manual PM Note | Approved Alias | FALSE | 2025-11-13 | 2026-07-31 | 321 | 180 | Spine NG | SAAS | Aditya Mazire | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also."
5105 | ANUH PHARMA PVT. LTD NX | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for ANUH PHARMA PVT. LTD NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-11-18 | 2026-01-28 | 316
5106 | NAIK MOTORS -GOA LOC | Allocation | Completed | NAIK MOTORS -GOA LOC | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Aditya Mazire | High | Tracker status 'Completed' conflicts with SCH status 'AC' | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month. | Manual PM Note | Approved Alias | FALSE | 2025-11-13 | 2026-07-31 | 321 | 410 | Spine NG | SAAS | Aditya Mazire | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn july done Aug sal done add module after 10th oct we will ask client. sept live sal will do.
5107 | PPKG AND CO | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for PPKG AND CO; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-11-26 | 2026-02-27 | 308
5108 | DOSHI MEDICARE PRIVATE LIMITED | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for DOSHI MEDICARE PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-11-03 | 2026-01-28 | 331
5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Allocation | Completed | FEATHERTOUCH LEARNING PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Datafile Explanation | Sunita Yadav | Closed | Closed/lost item, monitor only | Need to discuss internally for live processing | Need to discuss internally for live processing | Need to discuss internally for live processing. | Manual PM Note | Approved Alias | FALSE | 2025-11-26 | 2026-07-31 | 308 | 500 | Spine NG | SAAS | Sunita Yadav | welcome mail done #3/12 - eng - Corp ID done, datafiles awaiting #22/12 - no response Non Payroll Master Data received and uploaded. Salary Calculation received and configured. #19/01 - eng - salary processed, shared register to client for verification, waiting for reply Payroll Training and Implementation Completed W26jan4046. Mobile HR Training Completed W26jan5841. 19/01 - User is on leave and will connect on 21/01 for salary processing. SMTP Configuration Completed #W26jan7987. Location Configuration Completed #W26jan7983. HRMS Training Completed #W26jan8122. December 2025 Salary Completed #E26jan11453. January 2026 Salary Completed #W26feb6498. 08/04 - February processed and tallied, awaiting confirmation. User is too busy in internal work. Attendance Policy changes done. User will process salary by 15/04. #10/4 - busy February 2026 Salary Completed E26apr9176. Roll Out Completed E26apr9176. 24/04 - As per discussion, user not able to process March salary due to license count exhausted. In April as well count is exceeded. User is in discussion with management to increase the license count. User will discuss internally and will update. March salary will be processed post license update. #14/05 - eng - Non payroll employees april processed. Payroll employees configuration is completed and client will process salary in few days #1/06 - eng - in last schedule, they processed may salary with attendance. #W26may11974 - may salary conf. #25/06 - eng -All configuration done and training completed. Till May salary done but May confirmation not received as the Payroll user left the organization so coordinating with another user for all the processes. Now user have shared some changes in the calculation for Payroll category employees so we are finding a way to configure this. From June month user will process the salary with attendance data as they have some internal issues with the attendance. June 2026 Salary Completed with Attendance W26jul873. #10/08 - feedback good and positive #24/09 - regarding renewal as discussed with our accounts team, partner has rcvd the payment from user end, however, payment from partner is still pending. #5/10 - as discussed with our accounts team, partner has released the payment to spine.
5110 | COSMOS IMPEX INDIA PVT LTD NG | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for COSMOS IMPEX INDIA PVT LTD NG; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-11-29 | 2026-03-30 | 305
5111 | NIKIKA ENTERPRISES LLP | Allocation | Completed | NIKIKA ENTERPRISES LLP | Go LIVE | Project is handed over from implementation team to support team. | Completed |  | Closed | Closed/lost item, monitor only | Arpit informed that Partner team was not available, informed him to push and | Arpit informed that Partner team was not available, informed him to push and | Arpit informed that Partner team was not available, informed him to push and. | Manual PM Note | Approved Alias | FALSE | 2025-11-29 | 2026-05-26 | 305 | 175 | Spine NG | SAAS |  | go live - training and impl done april processed
5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | Allocation | Completed | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | FC | Live salary processing is complete and client is on watch list. | Completed | Goraksha Pawar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Goraksha Pawar. | SCH Project Remark | Approved Alias | FALSE | 2025-12-10 | 2026-04-28 | 294 | 400 | Spine NG | SAAS | Goraksha Pawar | Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system
5113 | parvathyhospital | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for parvathyhospital; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2025-12-23 | 2026-01-28 | 281
5114 | PANKAJ FASHION PVT LTD | Allocation | Lost | PANKAJ FASHION PVT LTD | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Arpit Patel | Closed | Closed/lost item, monitor only | Review blocker, confirm owner, and update next closure plan. | Onsite Visit planned for 15th June | Onsite Visit planned for 15th June. | Manual PM Note | Approved Alias | FALSE | 2026-01-09 | 2026-08-11 | 264 | 1001 | Spine NG | SAAS | Aditya Mazire | "10th, 15th, 25th" 110 emp- E26jan8973, payroll hr set up done, training done, int done, logins done, meeting done- workers not stable hence unable to share accurate data, meeting done may target, later will share data ot policy pending W26jun7203, contractual basic- change- card assign Director has not confidence on his user, Client LOST- Director dont have confidence on his user, meeting done onsite but not productive. Director has stopped receiving calls, client deactivated | Resource Problem
5115 | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Allocation | Lost | RAJESHWARI INFOTEL PVT. LTD | Lost | Client/project lost and license is deactivated. | Completed | Riddhi Pramod Sutar | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project update: Another Software. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Riddhi Pramod Sutar. | SCH Project Update | Approved Alias | FALSE | 2026-01-16 | 2026-04-28 | 257 | 1200 | Spine NG | SAAS | Riddhi Pramod Sutar | payroll hr set up done, jan tallied, payroll hr training done, onboard impl going on- client lost report as per their req not possible, had taken on trail basis, they will continue with TCS | Another Software
5116 | GNG ELECTRONICS LIMITED STAFF | Escalation | Completed | GNG ELECTRONICS LIMITED STAFF | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | plan activities in 2days. | plan activities in 2days. | plan activities in 2days. | Manual PM Note | Approved Alias | TRUE | 2026-01-19 | 2026-01-22 | 254 | 400 | Spine NG | SAAS | Shubham Gurav | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535
5117 | Talib and Shamsi Constructions Pvt. Ltd. | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for Talib and Shamsi Constructions Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2026-01-13 | 2026-03-30 | 260
5118 | Seventy Seven Entertainment Pvt Ltd | Escalation | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Pritesh Barot | Closed | Closed/lost item, monitor only | Datafiles Received, Implementation planned, Team to followup | Datafiles Received, Implementation planned, Team to followup | Datafiles Received, Implementation planned, Team to followup. | Manual PM Note | Approved Alias | FALSE | 2026-01-19 | 2026-03-30 | 254 | 250 | Spine HRMS | On-Premises | Pritesh Barot | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us.
5119 | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Allocation | Active |  |  |  | Datafile Explanation |  | Critical | No approved SCH match; Ageing 268 days from start date | Implementation Demo fixed for 8th May | Implementation Demo fixed for 8th May | Implementation Demo fixed for 8th May. | Manual PM Note | No Match | TRUE | 2026-01-05 |  | 268
5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Allocation | Completed | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Go LIVE | Project is handed over from implementation team to support team. | Completed |  | Closed | Closed/lost item, monitor only | Informed Vinay to Send a status mail | Informed Vinay to Send a status mail | Informed Vinay to Send a status mail. | Manual PM Note | Approved Alias | TRUE | 2026-01-31 | 2026-04-28 | 242 | 710 | Spine NG | SAAS |  | Training done Client is live processing. Time sheet module also live.
5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Allocation | Completed | VED INDUSTRIES POC | Go LIVE | Project is handed over from implementation team to support team. | Completed | Dhanashree Dalvi | Closed | Closed/lost item, monitor only | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Manual PM Note | Approved Alias | FALSE | 2026-02-09 | 2026-05-26 | 233 | 300 | Spine HRMS | SAAS | Dhanashree Dalvi | employee master uploaded attn was there priority attn integration done currently their main focus in only on attendance mail lic follow up ongoing ankur and vasu will co-ordinate with client opted on premises lic
5122 | Procon RMC | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for Procon RMC; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2026-02-23 | 2026-04-28 | 219
5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Allocation | Completed | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | Active | Project has started and is moving through implementation milestones. | Completed | Komal Kanadiya | High | Tracker status 'Completed' conflicts with SCH status 'Active' | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project remark: set up & training done, jan done, feb done later client is not responding to calls n mails. Tracker status is Completed; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Active'. | SCH Project Remark | Approved Alias | FALSE | 2026-02-27 | 2026-04-28 | 215 | 1400 | Spine NG | Hosting | Komal Kanadiya | set up & training done, jan done, feb done later client is not responding to calls n mails
5124 | SUNRISE FOODS BANGALORE | Escalation | Completed | SUNRISE FOODS BANGALORE | Held | Project/license is running but implementation is on hold. | Completed | Tushar More | Critical | Held-up status needs management intervention | Review blocker, confirm owner, and update next closure plan. |  | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention. | SCH Project Update | Approved Alias | FALSE | 2026-02-25 | 2026-04-28 | 217 | 50 | Spine NG | SAAS | Tushar More | Payroll Training completed July month salary processed and tallied. HRMS Training done. client were using hrms attendance for 2 months but after that they were not using are not taking interest for payroll module. after a multiple followup for aug salary aug sal done followup is going on for sept sal but no response. Not responding calledMr. Jeson he said will let us know in 2 days. afte 2-3 days we are calling and doing mail but no response. Held up- Payroll training has been completed. July salary was processed and successfully tallied. HRMS training has also been completed. The client was using HRMS attendance for around two months; however, they have not been actively using the system thereafter and are currently not showing much interest in the Payroll module. Follow-ups are currently ongoing for the September salary processing, but there has been no response from the client. We contacted Mr. Jeson, who informed us that he would provide an update within two days. However, even after 2–3 days, despite repeated calls and email follow-ups, we have not received any further response from the client. The client is currently not responding to our calls or follow-ups. | No Response - No Reason
5125 | NOTCH INDIA PROJECTS | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for NOTCH INDIA PROJECTS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2026-02-24 | 2026-03-30 | 218
5126 | Elixrr Industries Pvt. Ltd. | Escalation | Completed | ELIXRR INDUSTRIES PVT LTD. | Go LIVE | Project is handed over from implementation team to support team. | Completed | Krishna Yadav | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Krishna Yadav. | SCH Project Remark | Approved Alias | FALSE | 2026-02-10 | 2026-04-28 | 232 | 1078 | Spine HRMS | SAAS | Krishna Yadav | Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817
5127 | GUARDIAN CASTING PVT. LTD | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for GUARDIAN CASTING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2026-02-13 | 2026-03-30 | 229
5128 | GNG ELECTRONICS LIMITED FACTORY | Escalation | Completed | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Project is handed over from implementation team to support team. | Completed | Shubham Gurav | Closed | Closed/lost item, monitor only | Review Meeting | Review Meeting | Review Meeting. | Manual PM Note | Approved Alias | TRUE | 2026-02-25 | 2026-03-30 | 217 | 1600 | Spine HRMS | SAAS | Shubham Gurav | Project Live - Training & Implementation of RCT Module is done - E26jan11064
5129 | STORM FINANCIAL SERVICES | Allocation | Lost | STORM FINANCIAL SERVICES | Lost | Client/project lost and license is deactivated. | Completed | Mukeshkumar Shojiram kumavat | Closed | Closed/lost item, monitor only | April Salary Process and Tally done, Attendance Integration is planned. | April Salary Process and Tally done, Attendance Integration is planned. | April Salary Process and Tally done, Attendance Integration is planned. | Manual PM Note | Approved Alias | FALSE | 2026-03-28 | 2026-07-31 | 186 | 410 | Spine NG | SAAS | Mukeshkumar Shojiram kumavat | Completed Payroll training and also processed February 26 payroll and matched.-E26apr3050 completed all the training, also provided login access to employee-E26apr3347. completed with March Salary process for 391 employees.-E26apr4776. April month payroll has been processed, and payslip has been published for the employees. -E26may5873. Held up-As per the discussion with the client during the onsite visit by engineer mukesh the client is not ready to continue with the Spine. They have decided to develop and implement their own in-house software. | Another Software
5130 | CIRCLE RESOURCES PRIVATE LIMITED | Escalation | Completed | CIRCLE RESOURCES PRIVATE LIMITED | FC | Live salary processing is complete and client is on watch list. | Completed | Mayur Pendhari | Closed | Closed/lost item, monitor only | Progress & Review Call | Progress & Review Call | Progress & Review Call. | Manual PM Note | Approved Alias | FALSE | 2026-03-12 | 2026-03-30 | 202 | 1700 | Spine HRMS | SAAS | Mayur Pendhari | WELCOME MAIL DONE WILL PROCEED WITH THIS BY 10TH JUNE - E25jun3240 SPLITTING DONE training and impl done Oct 2025 salary processed - E25nov2426 from spine Disbursement date - 11th of every month. processing salaries parallely additional rule techical given by hemant sir on friday Engineer mayur has restored the database after that we will check and update the client as viral sir said till thursday we will connect client as mayur is onsite. One month extension is given by accounts team. As discussed with Mayur, some policies and shifts were removed as per the client’s requirements. A solution was provided for attendance recalculation, regularisation, and lock/unlock of attendance for 7 days at a time. The client will check and monitor the solution for one month. The salary disbursement date is the 7th of every month. After September salary processing and one month of observation, the client will decide on renewal. | Disbursement date by 15th
5131 | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Allocation | Active | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Riddhi Pramod Sutar | Critical | Ageing 181 days from start date | Confirm milestone progress and next client action. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Manual PM Note | Approved Alias | FALSE | 2026-04-02 |  | 181 | 650 | Spine NG | SAAS | Riddhi Pramod Sutar | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) target live sep live salary
5132 | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Allocation | Active | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | Held | Project/license is running but implementation is on hold. | Kick Off Meeting | Vikas Yadav | Critical | Held-up status needs management intervention | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Manual PM Note | Approved Alias | FALSE | 2026-04-06 |  | 177 | 300 | Spine NG | SAAS | Vikas Yadav | Basic payroll training has been completed. W26jul9046 Client is occupied in a full-day meeting today. T As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. not responding whatsapp group msg as their bal payment pending called Mr. Ganesh yesterday for issues and concern and recommend outsourcing options. they said will check and inform you. Held up-Basic Payroll training has been completed. Ticket reference: W26jul9046. The client was occupied in a full-day meeting today. The client is currently not responding to messages in the WhatsApp group, and the balance payment is also pending. We called Mr. Ganesh yesterday to understand the current issues and concerns and also discussed the option of outsourcing payroll processing. Mr. Ganesh informed us that they would check internally and get back to us. However, we have not received any further response from the client yet. The client currently does not have a dedicated resource for the software, and due to limited availability of the client/resource, they are unable to spend sufficient time on software utilisation and payroll activities. | Resource Problem
5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Allocation | Completed | RUPA SOLUTIONS PRIVATE LIMITED | Active | Project has started and is moving through implementation milestones. | Completed | Ankush Rampyare Rajbhar | High | Tracker status 'Completed' conflicts with SCH status 'Active' | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | Approved Alias | FALSE | 2026-04-07 | 2026-07-31 | 176 | 300 | Spine NG | SAAS | Ankush Rampyare Rajbhar | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744
5134 | TRIO JEWELS PVT LTD | Allocation | Active | TRIO JEWELS PVT LTD | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Mukeshkumar Shojiram kumavat | High | Ageing 174 days from start date | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Approved Alias | FALSE | 2026-04-09 |  | 174 | 301 | Spine NG | SAAS | Mukeshkumar Shojiram kumavat | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak
5135 | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Allocation | Active |  |  |  | Kick Off Meeting |  | High | No approved SCH match; Ageing 161 days from start date | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Manual PM Note | No Match | TRUE | 2026-04-22 |  | 161
5136 | Navio Shipping | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Manual PM Note | No Match | TRUE | 2026-04-23 | 2026-05-26 | 160
5137 | VIPUL ORGANICS LTD. - STAFF | Escalation | Completed | VIPUL ORGANICS LTD. - STAFF | Go LIVE | Project is handed over from implementation team to support team. | Completed | Santosh Yadav | Closed | Closed/lost item, monitor only |  |  | As per the latest SCH project remark: Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Santosh Yadav. | SCH Project Remark | Approved Alias | FALSE | 2026-05-01 | 2026-05-26 | 152 | 145 | Spine HRMS | SAAS | Santosh Yadav | Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745
5138 | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Allocation | Lost | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | Lost | Client/project lost and license is deactivated. | Kick Off Meeting | Mihir Navnath Mungekar | Closed | Closed/lost item, monitor only | Implementation & Training has been completed. Vinay is aligning a review meeting. | Implementation & Training has been completed. Vinay is aligning a review meeting. | Implementation & Training has been completed. Vinay is aligning a review meeting. | Manual PM Note | Approved Alias | FALSE | 2026-05-04 | 2026-08-31 | 149 | 400 | Spine NG | SAAS | Mihir Navnath Mungekar | Project Lost -Mr. Ravi informed us that they will not be renewing the software due to low utilization by their staff & a lack of acceptance of automation within the organization. He appreciated our software and support; however, management has decided not to continue with the renewal. Welcome maild on 4th May Project delivery rcvd Training & Implementation of Payorll is completed along with April month tallied - HRMS modules Training & Implementation is done Attendance integration is done Logins rolled out to employees - E26may6183 Live salary with attednace proceed of June month for some employees | July wth attendance
5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Allocation | Completed | CAM TOOLS INDUSTRIES PVT LTD | FC | Live salary processing is complete and client is on watch list. | Kick Off Meeting | Harsh Dilip Ashar | Closed | Closed/lost item, monitor only | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Manual PM Note | Approved Alias | FALSE | 2026-05-06 | 2026-08-31 | 147 | 315 | Spine NG | SAAS | Harsh Dilip Ashar | Project Live- Training & Implementation is done along with April month tallied - W26may10013 Attendance inetgration is done Logins rolled out June month with attednace done & July month processed with attedance Leave policy is pending from client's end, they will share as per their convience- E26sep4961 processed Live salary for the month of August- E26sep3629
5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Allocation | Completed |  |  |  | Kick Off Meeting |  | Watch | No approved SCH match | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | Manual PM Note | No Match | TRUE | 2026-05-01 | 2026-07-31 | 152
5141 | TRIO JEWELS PVT LTD Contractual | Allocation | Active | TRIO JEWELS PVT LTD | AC | Everything is successfully completed and client is on watch list. | Kick Off Meeting | Mukeshkumar Shojiram kumavat | High | Ageing 152 days from start date | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Approved Alias | FALSE | 2026-05-01 |  | 152 | 301 | Spine NG | SAAS | Mukeshkumar Shojiram kumavat | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak
5142 | EMPREO PREMIUM PVT LTD | Escalation | Active | EMPREO PREMIUM PVT LTD | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Goraksha Pawar | High | Ageing 135 days from start date | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | Approved Alias | FALSE | 2026-05-18 |  | 135 | 105 | Spine NG | SAAS | Goraksha Pawar | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process
5143 | EMPREO WHEEL PVT LIMITED (MG) | Escalation | Active | EMPREO WHEEL PVT LIMITED (MG) | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Goraksha Pawar | High | Ageing 135 days from start date | Same | Same | Same. | Manual PM Note | Approved Alias | FALSE | 2026-05-18 |  | 135 | 150 | Spine NG | SAAS | Goraksha Pawar | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process
5144 | SHREEKHETRA AUTOMOTIVE (TATA) | Escalation | Active | SHREEKHETRA AUTOMOTIVE (TATA) | Lost | Client/project lost and license is deactivated. | Kick Off Meeting | Goraksha Pawar | High | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date | Same | Same | Same. | Manual PM Note | Approved Alias | FALSE | 2026-05-18 |  | 135 | 200 | Spine NG | SAAS | Goraksha Pawar | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up
5145 | AMAL EMBROIDERIES PVT. LTD | Allocation | Active | AMAL EMBROIDERIES PRIVATE LIMITED | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Vijay Bugde | High | Ageing 134 days from start date | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Manual PM Note | Approved Alias | FALSE | 2026-05-19 |  | 134 | 1200 | Spine NG | SAAS | Vijay Bugde | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. As per call accounts team is connected for payment with user Aparna. Only add mod pms left which will be done in the month of november directly.
5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Escalation | Completed | AEGIS PRECISION PVT LTD | Go LIVE | Project is handed over from implementation team to support team. | Completed | Goraksha Pawar | Closed | Closed/lost item, monitor only | Review Meeting pending. | Review Meeting pending. | Review Meeting pending. | Manual PM Note | Approved Alias | TRUE | 2026-05-19 | 2026-07-31 | 134 | 172 | Spine HRMS | SAAS | Goraksha Pawar | Files & Policy awaiting, training from 18th. training completed #287080, logins will be shared by 1st week of sep, logins will be shared by 16th sep Training completed, Logins will share as per their convenient. #302271
5147 | MULTI ORGANICS PVT LTD | Allocation | Active | MULTI ORGANICS PVT LTD | Active | Project has started and is moving through implementation milestones. | Kick Off Meeting | Rajesh Ravindra Panchal | High | Ageing 128 days from start date | KickOff & Datafile Explaination done | KickOff & Datafile Explaination done | KickOff & Datafile Explaination done. | Manual PM Note | Approved Alias | FALSE | 2026-05-25 |  | 128 | 350 | Spine NG | SAAS | Mihir Navnath Mungekar | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out
5148 | BFMS FACILITY MANAGEMENT PVT LTD | Escalation | Lost | BFMS FACILITY MANAGEMENT PVT LTD | Held | Project/license is running but implementation is on hold. | Datafile Explanation | Amit Krishnakant Tiwari | Critical | Held-up status needs management intervention | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manual PM Note | Approved Alias | FALSE | 2026-05-26 | 2026-08-31 | 127 | 500 | Spine NG | SAAS | Amit Krishnakant Tiwari | (E26aug6724) Project Held Up - Despite our continuous efforts to support and resolve queries and concerns, we have not received the required response from client Implementation and Training session aligned from 13th Jan E26jan1479 W26jan5503 Bfms Payroll Training and December Salary confirmation BFMS will not process with Attendance - W26mar1378 the salary of compliance section is not yet decided (in discussion) post that they will process march on monday team will update the company is shifting to pvt ltd hence they are bsy client not responding properly The client mentioned that they have employees such as delivery personnel working with platforms like Zomato, Swiggy, and Urban Company. These employees typically work for only 4–5 days and then leave the job after comparing their earnings with other platforms, stating that they are being paid less. Due to this high attrition and short working duration, salary processing becomes challenging. We also asked why they opted for the software despite this situation. The user responded that it was a management decision. as per vasu's meting client will be providing data post salary processing of june had a call with user to make her undertsand that all isue can be handled through spine which she is having but she seems not interested | FInds excel easy
5149 | MANJUSHREE INNOVATIONS PVT. LTD | Allocation | Active | MANJUSHREE INNOVATIONS PRIVATE LIMITED | Active | Project has started and is moving through implementation milestones. | Kick Off Meeting | Mayur Pendhari | High | Ageing 126 days from start date | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Manual PM Note | Approved Alias | FALSE | 2026-05-27 |  | 126 | 370 | Spine NG | SAAS | Mayur Pendhari | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. August sal processed by their own but not live- W26sep2587 sept will be target for live sal Attrition &amp; Absenteeism Report Query is going on client want automatic shifts. The September salary will be processed live through Spine for the staff with attendance, while the workers’ attendance will be uploaded manually for salary processing.
5150 | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Allocation | Active | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | Active | Project has started and is moving through implementation milestones. | Kick Off Meeting | Varun Rajbhar | High | Ageing 121 days from start date | Confirm kickoff date, data readiness, and owner. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Manual PM Note | Approved Alias | FALSE | 2026-06-01 |  | 121 | 550 | Spine NG | SAAS | Santosh Yadav | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NG & live target month for processing is August month August month live salary processed - W26aug7425
5151 | Mansha Agencies | Escalation | Active | MANSHA AGENCIES PVT LTD | Active | Project has started and is moving through implementation milestones. | Kick Off Meeting | Aditya Mazire | High | Ageing 117 days from start date | Confirm kickoff date, data readiness, and owner. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Manual PM Note | Approved Alias | FALSE | 2026-06-05 |  | 117 | 260 | Spine NG | SAAS | Aditya Mazire | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied june salary upload Aug salary processed integration done Logins roll out by next week. sept will be live sal | User is hospitalized so that’s why data files are received late & implementation is delayed
5152 | Muktangan Education Trust | Escalation | Active | MUKTANGAN EDUCATION TRUST. NX | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Aditya Mazire | High | Ageing 117 days from start date | Confirm kickoff date, data readiness, and owner. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Manual PM Note | Approved Alias | TRUE | 2026-06-05 |  | 117 | 608 | Spine HRMS | SAAS | Aditya Mazire | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly."
5153 | Vivan Associate | Escalation | Completed |  |  |  | Datafile Explanation |  | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Manual PM Note | No Match | TRUE | 2026-06-04 | 2026-07-31 | 118
5154 | BSA CORPORATION LIMITED / BSA GROUP | Allocation | Active |  |  |  | Kick Off Meeting |  | High | No approved SCH match; Ageing 114 days from start date | Confirm kickoff date, data readiness, and owner. | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | Manual PM Note | No Match | TRUE | 2026-06-08 |  | 114
5155 | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Allocation | Active | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | Active | Project has started and is moving through implementation milestones. | Kick Off Meeting | Ankita Gupta | High | Ageing 113 days from start date | Confirm kickoff date, data readiness, and owner. | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Manual PM Note | Approved Alias | FALSE | 2026-06-09 |  | 113 | 500 | Spine NG | SAAS | Ankita Gupta | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion
5156 | SACRED HEART HOSPITAL JAL | Allocation | Active | SACRED HEART HOSPITAL JAL | AC | Everything is successfully completed and client is on watch list. | Kick Off Meeting | Mayur Pendhari | High | Ageing 112 days from start date | Confirm kickoff date, data readiness, and owner. | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Manual PM Note | Approved Alias | FALSE | 2026-06-10 |  | 112 | 801 | Spine HRMS | On-Premises | Mayur Pendhari | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul
5157 | VED INDUSTRIES/ ROHIDA GROUP | Allocation | Active |  |  |  | Kick Off Meeting |  | High | No approved SCH match; Ageing 105 days from start date | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | Tracker/SCH Status | No Match | TRUE | 2026-06-17 |  | 105
5158 | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Allocation | Active |  |  |  | Kick Off Meeting |  | High | No approved SCH match; Ageing 104 days from start date | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | Tracker/SCH Status | No Match | TRUE | 2026-06-18 |  | 104
5159 | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Escalation | Lost | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Lost | Client/project lost and license is deactivated. | Datafile Explanation | Bhavika Gite | Closed | Closed/lost item, monitor only | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project update: Attendance Integration issue. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Bhavika Gite. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Update | Approved Alias | FALSE | 2026-06-23 | 2026-07-31 | 99 | 251 | Spine NG | SAAS | Bhavika Gite | Payroll training done hrms training done april tallied may salary process june salary process integration is pending As per the user's update, due to heavy rainfall, our Director is not present for renewal discussion and therefore the vendor has also not visited. We will update you on mail. Lost- Payroll & HRMS training completed, and June salary was processed. Only biometric integration remained pending. Earlier as informed by Director Amit to Swati Ji that already their existing biometric device did not support integration and a new device was required. Despite multiple follow-ups and discussions, the client did not respond and later informed us they would coordinate with another vendor. Due to delays from client side the integration remained pending and the client ultimately decided to discontinue the software. | Attendance Integration issue
5160 | ANS NG | Escalation | Completed | ANS NG | Go LIVE | Project is handed over from implementation team to support team. | Datafile Explanation | Aditya Mazire | Closed | Closed/lost item, monitor only | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: Training of Payroll NX is completed - #371589 March, April & May month salary processed. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aditya Mazire. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Remark | Approved Alias | TRUE | 2026-06-24 | 2026-09-30 | 98 | 200 | Spine NG | SAAS | Aditya Mazire | Training of Payroll NX is completed - #371589 March, April & May month salary processed.
5161 | STERLING LIFESTYLE LLP | Escalation | Completed | STERLING LIFESTYLE LLP | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation | Aarati Subhashchandra Yadav | High | Tracker status 'Completed' conflicts with SCH status 'AC' | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'. | SCH Project Remark | Approved Alias | FALSE | 2026-06-30 | 2026-09-30 | 92 | 75 | Spine NG | SAAS | Aarati Subhashchandra Yadav | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response
5162 | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Allocation | Completed |  |  |  | Datafile Explanation |  | Watch | No approved SCH match | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-07-01 | 2026-09-30 | 91
5163 | HELL ENERGY PVT LTD | Allocation | Active | HELL ENERGY PVT LTD | AC | Everything is successfully completed and client is on watch list. | Datafile Explanation |  | High | SCH milestone 'AC' has not progressed for 86 days | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | SCH Project Remark | Approved Alias | FALSE | 2026-07-06 |  | 86 | 550 | Spine NG | SAAS |  | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp )
5164 | VISHWAKARMA FOUNDERS (I) PVT. LTD | Allocation | Active |  |  |  | Kick Off Meeting |  | Watch | No approved SCH match; PM note missing for ageing open item | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-07-07 |  | 85
5165 | Navio Shipping | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Manual PM Note | No Match | TRUE | 2026-08-03 | 2026-08-11 | 58
5166 | CREATIONS BY SHANAGAR | Allocation | Active |  |  |  | Datafile Explanation |  | Watch | No approved SCH match; PM note missing for ageing open item | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-08-03 |  | 58
5167 | AKRITI PHARMACEUTICALS PVT LTD | Allocation | Active | AKRITI PHARMACEUTICALS PVT LTD | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Ankush Rampyare Rajbhar | Watch | PM note missing for ageing open item | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Remark | Approved Alias | FALSE | 2026-08-03 |  | 58 | 310 | Spine NG | SAAS | Ankush Rampyare Rajbhar | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance
5168 | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Allocation | Active |  |  |  | Datafile Explanation |  | Watch | No approved SCH match; PM note missing for ageing open item | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-08-13 |  | 48
5169 | JIET MEDICAL COLLEGE HOSPITAL | Allocation | Active | JIET MEDICAL COLLEGE HOSPITAL | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Varun Rajbhar | Watch | PM note missing for ageing open item | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Remark | Approved Alias | FALSE | 2026-08-13 |  | 48 | 800 | Spine NG | SAAS | Varun Rajbhar | we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935
5170 | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Allocation | Active |  |  |  | Kick Off Meeting | Varun | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-09-05 |  | 25
5171 | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Allocation | Active |  |  |  | Kick Off Meeting | Tejas | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-09-05 |  | 25
5172 | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Allocation | Yet To Start |  |  |  | Kick Off Meeting | Santosh | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-09-05 |  | 25
5173 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Allocation | Active |  |  |  | Kick Off Meeting |  | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-09-16 |  | 14
5174 | NAVKAR CORPORATION LIMITED | Allocation | Yet To Start |  |  |  | Kick Off Meeting | Yash | Watch | No approved SCH match | Confirm kickoff date, data readiness, and owner. |  | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | Tracker/SCH Status | No Match | TRUE | 2026-09-17 |  | 13
5175 | THE KANDIVALI EDUCATION SOCIETY | Escalation | Active |  |  |  | Datafile Explanation |  | Watch | No approved SCH match | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-09-17 |  | 13
5176 | ARTSON LIMITED | Escalation | Completed |  |  |  | Completed |  | Watch | No approved SCH match |  |  | No manual PM note is available for ARTSON LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Tracker/SCH Status | No Match | TRUE | 2026-09-01 | 2026-09-30 | 29
5177 | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Escalation | Active |  |  |  | Datafile Explanation |  | Watch | No approved SCH match | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-09-28 |  | 2
5178 | APMOSYS TECHNOLOGIES PVT LTD | Allocation | Active | APMOSYS TECHNOLOGIES PVT LTD | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Utkarsh | Healthy | No immediate exception detected | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Remark | Exact Name | FALSE | 2026-09-22 |  | 8 | 1500 | Spine NG | SAAS | Utkarsh Sanjay Chavan | Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data
5179 | CONTENDRE GREENERGY PVT. LTD | Allocation | Active |  |  |  | Datafile Explanation | Tanwish | Watch | No approved SCH match | Confirm progress for milestone: Datafile Explanation. |  | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | Tracker/SCH Status | No Match | TRUE | 2026-09-21 |  | 9
5180 | PERFECT BELTS PVT. LTD | Allocation | Active | PERFECT BELTS PVT. LTD | Active | Project has started and is moving through implementation milestones. | Datafile Explanation |  | Healthy | No immediate exception detected | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Remark | Exact Name | FALSE | 2026-09-18 |  | 12 | 850 | Spine NG | SAAS |  | Payroll- master uploaded, salary set up in process
5181 | Saffron Speciality Papers Limited | Escalation | Active | SAFFRON SPECIALITY PAPERS LIMITED | Active | Project has started and is moving through implementation milestones. | Datafile Explanation | Yash Pankajkumar | Healthy | No immediate exception detected | Confirm progress for milestone: Datafile Explanation. |  | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. | SCH Project Update | Exact Name | FALSE | 2026-09-01 |  | 29 | 440 | Spine NG | SAAS | Yash Pankajkumar | HRMS Training yet to start, for Dec 25 salary the attendance data yet to come YASH is in discussion salary processing session aligned post that user will release payment planning to proceed with one unit only user has conveyed that she will process march with attn from system in process The client is processing salary for her unit now. They process salary on a 45-day basis. Attendance integration is done. Logins won't be rolled out. The user has uploaded the roster; post manager's approval, she'll process salary with attendance from Spine. march processed for 114 employees logins rolled out they will be processing june live with attn- in process #30/07 - meeting planned for tomorrow. #5/08 - salary is delayed due to different salary cycle of 45 days, it is usually delayed because they receive data late from their site. #2/09 - eng - following up going on for attendance for august salary #8/09 - eng - As discussed, the current HR, Rupali, is serving her notice period, and this is her last working month. Since she is in the process of leaving, she is not showing much interest in the ongoing activities. For further communication, we are coordinating directly with Director Siddharth. However, he is currently occupied with a medical emergency involving a family member, so we will not be able to connect with him this week. We will follow up with him by 11th September based on his availability. Additionally, we are planning a surprise visit on Monday along with the PM and Engineer. We have also heard that the office may be relocating to Thane, so it would be important to discuss this with them at the earliest and understand the impact on the ongoing activities. #9/09 - As discussed with MD Siddharth, I asked him about the reason for the delay in salary processing and the pending salaries for July and August. He asked me to connect with Ms. Rupali regarding the same. He added her to the call and then left. During my discussion with Ms. Rupali, she explained that they have two units, and the employees there do not properly punch in and out for attendance. Due to this, attendance mismatches occur, which she has to regularize manually. This process takes a lot of time and is the main reason for the delay. I understood the issue and asked for her availability so that we could proceed with clearing the backlog and processing the July and August salaries. She requested us to give her a few minutes and said that she would try to clear the pending attendance backlogs herself. She also informed us that if she faces any issue, she will call us back. #26/09 - new user trng completed, awaiting for confirmation, user sunita is on leave, she will connect us for confirmation monday. #28/09 - Planned a onsite meeting for tomorrow. | All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay

## PM_Cockpit
Project Code | Project Type | Project Name | Received From | Start Date | End Date | Tracker Priority | Tracker Status | Age Days | Cycle Days | Risk Level | Risk Reason | Status Mismatch | SCH Status | SCH Status Meaning | SCH Stage Group | SCH Milestone | Current Milestone | SCH Client Name | SCH Project Code | SCH Client Status | SCH Project Remark | SCH Project Update | SCH Achieved Percent | SCH Last Processed Year Month | Owner | Effective Employee Count | Effective Product | Effective Client Type | PM Note Source | Stakeholder PM Update | Stakeholder Update Subject | Next Action | Due Date | Action Date | PM Notes | Manual Risk Reason | Mail Include | Match Method | Match Score | SCH Match Count | Match Review Needed | Assigned Engineer | Team Leader | Marketing Executive | Product | Employee Count | SCH Implementation Engg | SCH Project Manager | SCH Project MKT | SCH No. Emp | Tracker Name Key | SCH Name Key | Notes Source | Tracker Client Type | SCH Client Code | SCH Priority | SCH Class | SCH Co-ordinator | SCH Team Leader | SCH Project Team Manager | SCH Client Type | SCH Project Start Date | SCH Project Implementation Date | SCH Project Close Date | SCH Product Type | SCH Project Product | SCH Project Mode | SCH Row Number | SCH Suggested Milestone
5001 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Schedule | 2025-01-07 | 2025-10-28 | Low | Completed | 631 | 294 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | 7263 | Account Activated | Project Live - 1) Ahemdabad Location PayrollNX Training and Dec'24 Salary Confirmation : W25jan10514 2) Kolkata Location PayrollNX Training and Dec'24 Salary Confirmation : E25jan12587 3) Ahemdabad Location Jan'25 live salary confirmation : W25feb1205 4) Ahemdabad Location Login rollout confirmation : W25feb2040 5) Spine HRMS - (Admin, ESSM. Leave module) training Confirmation : W25feb2040 6) Spine HRMS -Spine HRMS_Phase 1 Training Confirmation : W25feb2365 7) Kolkata Location Jan'25 live salary confirmation : W25feb3068 8) Kolkatta Location Login rollout confirmation : W25feb4649 9) Ahemdabad Attendance Integration Confirmation : E25feb7343 10) ELC module Training Confirmation : W25feb8518 11) Ahemdabad location Feb'25 Live salary confirmation along with Attendance : W25mar1674 12) Kolkatta location Feb'25 live Salary confirmation : W25mar1677 May month live salary processed from system June month live salary from with attendance from system is done |  | 100 | Mar-26 | Sahil Gadhave | 1270 | NX | Normal | Manual PM Note | plan for further activities scheduled for 10th. | Project Status Update - TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF - Completed | plan for further activities scheduled for 10th. |  |  | plan for further activities scheduled for 10th. |  | No | Approved Alias | 1 | 1 | FALSE | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | NX | 1270 | Sahil Gadhave | Vasu Mohan Dusa | Nirbhay Kumar | 1400 | tarasafeintlpvtlimitedstaff | tarasafeintlpvtltdstafflicense | Previous PM Cockpit | Normal | SPT109788243112 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-01-07 | 2025-01-23 | 2025-07-10 | Fresh | Spine HRMS | Online | 114 | Completed
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost | 631 | 191 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | 7262 | Account DeActivated | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved |  | 66 |  | Sahil Gadhave | 1100 | NX | Normal | SCH Project Remark | As per the latest SCH project remark: Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved. Tracker status is Lost; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Go LIVE'. | Project Status Update - TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | NX | 1100 | Sahil Gadhave | Vasu Mohan Dusa | Nirbhay Kumar | 1100 | tarasafeintlpvtlimitedworker | tarasafeintlpvtltdworkerlicense | Previous PM Cockpit | Normal | SPT109784243112 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-01-07 | 2025-02-13 | 2025-07-08 | Fresh | Spine HRMS | Online | 115 | Completed
5003 | Escalation | Maharashtra Book Manufacturing | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed | 631 | 108 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | 6555 | Account Activated | Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary till Mar 25 and Process from April 25 -E25may5783 May salary done. after june we can do live. We have processed May 25 and June 25 salary with attendance for MUMBAI branch employees. We will get back for Wada branch salary processing -E25jul1557 aug salary shall be done till friday. |  | 100 | Aug-26 | Shubham Gurav | 100 | NX | Normal | SCH Project Remark | As per the latest SCH project remark: Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary... Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Shubham Gurav. | Project Status Update - Maharashtra Book Manufacturing - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Shubham Gurav | Nagesh Tiwari | Giriraj Birendrasingh Tomar | NX | 100 | Shubham Gurav | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 100 | maharashtrabookmanufacturing | maharashtrabookmanufacturingconx | Previous PM Cockpit | Normal | SPM109213241208 | Normal | E | Karuna Rajaram Sandim | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2024-08-12 | 2024-08-29 | 2025-07-15 | Fresh | Spine HRMS | Onsite | 122 | Live Salary Processing
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed | 631 | 108 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Paras Mahesh Ladva | 35 | NX | Normal | Tracker/SCH Status | No manual PM note is available for PLASMA RESEARCH TRUST NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Paras Mahesh Ladva. | Project Status Update - PLASMA RESEARCH TRUST NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Paras Mahesh Ladva | Viral Panchal | Anuj Kumar Ganga Prasad Tiwari | NX | 35 |  |  |  |  | plasmaresearchtrustnx |  | Previous PM Cockpit | Normal
5005 | Allocation | Bengal Energy_Staff | Schedule | 2025-01-08 | 2026-03-30 | Low | Completed | 630 | 446 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | BENGAL ENERGY LTD- STAFF | 7267 | Account Activated | welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189 |  | 100 | Mar-26 | Mayur Pendhari | 550 | NX | Premium | SCH Project Remark | As per the latest SCH project remark: welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. | Project Status Update - Bengal Energy_Staff - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | NX | 550 | Mayur Pendhari | Vasu Mohan Dusa | Nirbhay Kumar | 550 | bengalenergystaff | bengalenergyltdstaff | Previous PM Cockpit | Premium | SPB109806243112 | Premium | E | Mansi Singh | Probian Biswas | Viral Panchal | SAAS | 2025-01-08 | 2025-01-18 | 2025-11-06 | Fresh | Spine HRMS | Online | 113 | Completed
5006 | Allocation | Bengal Energy_Worker | Schedule | 2025-01-08 | 2025-06-30 | Low | Lost | 630 | 173 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | BENGAL ENERGY LTD- CONTRACTUAL | 7268 | Account DeActivated | they clarified that there are no concerns or issues from Spine’s end. The current process is a business decision on their part. For contractual employees, the contractors submit attendance via Excel sheets, which the internal team simply verifies before processing payments. They also mentioned that they are in the process of streamlining their work process system. Once that is properly aligned, they will reconnect with Spine to proceed with the contractual employee license. | Finds excel easy |  | 0 | Mayur Pendhari | 1100 | NX | Premium | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. | Project Status Update - Bengal Energy_Worker - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | NX | 1100 | Mayur Pendhari | Vasu Mohan Dusa | Nirbhay Kumar | 1100 | bengalenergyworker | bengalenergyltdcontractual | Previous PM Cockpit | Premium | SPB109807243112 | Premium | E | Mansi Singh | Probian Biswas | Viral Panchal | SAAS | 2025-01-08 | 2025-01-18 | 2025-06-27 | Fresh | Spine HRMS | Online | 112 | Completed
5007 | Allocation | Parbhani Medical College | Schedule | 2025-01-13 | 2026-01-28 | Low | Lost | 625 | 380 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | PARBHANI MEDICAL COLLEGE (PMC) | 7282 | Account DeActivated | Welcome call done data file expl done Implementation starts from 14th feb 25 HRMS and Mobile HR Training Completed and All modules Explained and Showed by Engineer -W25feb8024 PayrollNg Training Completed and All modules Explained and Showed by Engineer and Jan 2025 salary Processed -W25feb6982 was following up the user since last week, however call was not received , Today had a call with him , he mentioned he was on leave past 8 to 10 days and now he is working on March salary and will reach out to me i assistance required, and for feb salary he will upload the past salary data. salary processed till march aprl salary mostly till next week, New biometric machine is installed, again we need to integrate data again, and now the user is admitted in hospital and currently there is no other user in his absence. April 25 Salary Process complete - E25may10890 In Parbhani , Half employees do not receive salary yet of april, they shall receive in May or june , told shreyas to take this on mail. May salary he shall process till 10th june. This email is to inform you that we have not been able to process the salaries for our remaining employees through your software. This is due to a temporary issue that we are actively working to resolve. We will resume full salary processing via your platform as soon as possible. We appreciate your understanding in this matter and will keep you updated on our progress. E25jun2237 They have fund issues that is the reason salary is delayed Salary processing is delayed every month as there is funds issue at client end, hence closing as lost | Funds issue | 100 | Oct-25 | Sushant Thombare | 500 | NG | Normal | SCH Project Update | As per the latest SCH project update: Funds issue. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Sushant Thombare. | Project Status Update - Parbhani Medical College - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Sushant Thombare | Shreyas Karkera | Jayesh Mojidra | NG | 500 | Sushant Thombare | Vasu Mohan Dusa | Jayesh Mojidra | 500 | parbhanimedicalcollege | parbhanimedicalcollegepmc | Previous PM Cockpit | Normal | SPP109843251301 | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-01-13 | 2025-02-14 | 2026-01-31 | Fresh | Spine NG | Onsite | 111 | Completed
5008 | Escalation | Aquaair International Frieght Services | Schedule | 2025-01-13 | 2025-04-25 | Low | Completed | 625 | 102 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | AQUAAIR INTERNATIONAL FREIGHT SERVICES | 6265 | Account DeActivated | Welcome call done data file explanation on 11th july 24 awaiting files training starts from 16 th sep 24 successfully completed the Payroll training and processed and verified the salary for the month of August using the Payroll system they have successfully logged into the app.-402035 HRMS training was successfully completed today.-402035 Salary processed till nov and dec salary they will process with attendance. queries resolved New user training has started. payroll training done , HRMS Training is done.W25mar9197 We have successfully processed salary of March 2025 with attendance from HRMS-W25mar9197 | Karuna in follow up, user waiting for management approval 24/2 | 100 | Mar-25 | Nagendra Poojary | 45 | NX | Normal | SCH Project Update | As per the latest SCH project update: Karuna in follow up, user waiting for management approval 24/2. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Nagendra Poojary. | Project Status Update - Aquaair International Frieght Services - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Nagendra Poojary | Viral Panchal | Jigar Rupani | NX | 45 | Nagendra Poojary | Vasu Mohan Dusa | Jigar Rupani | 45 | aquaairintlfrieghtservices | aquaairintlfreightservices | Previous PM Cockpit | Normal | SPA108965242906 | Normal | E | Karuna Rajaram Sandim | Viral Panchal |  | SAAS | 2024-06-29 | 2024-09-16 | 2025-04-09 | Fresh | Spine HRMS | Onsite | 125 | Completed
5009 | Escalation | Hardcarb Technologies Private Limited | Maketing | 2025-01-14 | 2025-04-25 | Low | Completed | 624 | 101 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | HARDCARB TECHNOLOGIES PRIVATE LIMITED | 6620 | Account Activated | Project Live - Training of payroll done - #E24oct8342 August month tallied HRMS training done - #E24oct8342 October month salary processed November month salary processed integration done February month salary processed March month live salary processing done with attendance from NX |  | 100 | Mar-25 | Tejas Rajesh Baragade | 250 | NX | Normal | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Project Status Update - Hardcarb Technologies Private Limited - Completed | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. |  |  | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. |  | No | Approved Alias | 1 | 1 | FALSE | Tejas Rajesh Baragade | Prathamesh Mandavkar | Amarprit Kaur | NX | 250 | Tejas Rajesh Baragade | Vasu Mohan Dusa | Amarprit Kaur | 250 | hardcarbtechpvtltd | hardcarbtechpvtltd | Previous PM Cockpit | Normal | SPH109257242608 | Normal | E | Ankita Bankar | Prathamesh Mandavkar |  | SAAS | 2024-08-26 | 2024-09-16 | 2025-04-09 | Fresh | Spine HRMS | Onsite | 121 | Completed
5010 | Allocation | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Schedule | 2025-01-14 | 2025-07-17 | Low | Completed | 624 | 184 | Closed | Closed/lost item, monitor only | FALSE | FC Lost | Project was fully completed but later lost. | FC Lost | Completed | Completed | MADHUSUMAN ENTERPRISES | 7286 | Account DeActivated | Welcome call done URL created #trng and impl from 29 th jan payroll training done - W25jan12818 HRMS on 12th feb We have completed the training on attendance module also december & January month salary process and tally. - W25feb5072 they are going to use mark in mark out, only for few empl if location is proper then logins logins done march salary 26 emp done, pending emp they will complete in this week In Madhusuman as there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | 83 | Aug-25 | Tejas Rajesh Baragade | 125 | NX | Normal | SCH Project Update | As per the latest SCH project update: there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. Tracker status is Completed; SCH status is FC Lost (Project was fully completed but later lost.). Current milestone: Completed. Current owner/implementation contact: Tejas Rajesh Baragade. | Project Status Update - MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Tejas Rajesh Baragade | Vinay Kareliya | Ankur Yewalekar | NX | 125 | Tejas Rajesh Baragade | Vasu Mohan Dusa | Ankur Yewalekar | 125 | madhusumanenterprisesmsehvacservicesindia | madhusumanenterprises | Previous PM Cockpit | Normal | SPM109810243112 | Normal | E | Karuna Rajaram Sandim | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-01-13 | 2025-01-29 | 2025-12-08 | Fresh | Spine HRMS | Onsite | 110 | Completed
5011 | Allocation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Schedule | 2025-01-14 | 2025-10-28 | Low | Completed | 624 | 287 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | KHERWADI SOCIAL WELFARE ASSOCIATION | 7288 | Account Activated | Project Live - Payroll Till Tax done/ HRMS & mobile app logins rolled out to employees - E25feb5562 HRMS training done & RCT module training & implementation done - E25feb5562 HRMS training done-E25jan12873 February month salary processed ELC, RCT, RD & PMS Module training & implementation is done April month salary processed May & June month salary processed live from system with attendance | Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary | 100 | Mar-26 | Probian Biswas | 350 | NX | Premium | SCH Project Update | As per the latest SCH project update: Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Project Status Update - YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Probian Biswas | Probian Biswas | Aparna Santosh | NX | 350 | Probian Biswas | Vasu Mohan Dusa | Aparna Santosh | 650 | yuvaparivartankherwadisocialwelfareassociation | kherwadisocialwelfareassociation | Previous PM Cockpit | Premium | SPK109842251001 | Premium | E | Ankita Bankar | Probian Biswas | Viral Panchal | SAAS | 2025-01-14 | 2025-01-24 | 2025-07-08 | Fresh | Spine HRMS | Onsite | 109 | Completed
5012 | Escalation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Schedule | 2025-01-14 | 2025-04-25 | Low | Completed | 624 | 101 | Closed | Closed/lost item, monitor only | FALSE | FC Lost | Project was fully completed but later lost. | FC Lost | Completed | Completed | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | 6799 | Account DeActivated | #Payroll training has been completed, jan salary processing also done and salary tallied, further training and policy setup of hrms will be done next week - W25jan11630 W25mar3684 - HRMS Training is completed #W25apr9497 - march done with attendance #April'2025 Salary processed and Tally with attendance. #W25jul4405 - june salary done & live confirmation #FC LOST : The client was expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | 100 | Sept-25 | Amit Krishnakant Tiwari | 30 | NX | Normal | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Project Status Update - GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) - Completed | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. |  |  | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. |  | No | Approved Alias | 1 | 1 | FALSE | Amit Krishnakant Tiwari | Shreyas Karkera | Ankur Yewalekar | NX | 30 | Amit Krishnakant Tiwari | Vasu Mohan Dusa | Ankur Yewalekar | 30 | gcomsystemsandsolutionsourladyofsalvation | gcomsystemsandsolutionsourladyofsalvation | Previous PM Cockpit | Normal | SPG109421243009 | Normal | E | Ritika Dilip Singh | Shreyas Karkera | Ganesh Jadhav | SAAS | 2024-09-30 | 2025-01-27 | 2025-07-15 | Fresh | Spine HRMS | Onsite | 120 | Completed
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed | 617 | 94 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Goraksha Pawar | 270 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Metafab; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Goraksha Pawar. | Project Status Update - Metafab - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Goraksha Pawar | Prathamesh Mandavkar | Amarprit Kaur | NX | 270 |  |  |  |  | metafab |  | Previous PM Cockpit | Normal
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed | 615 | 92 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Santosh Yadav | 30 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Texple; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Santosh Yadav. | Project Status Update - Texple - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Santosh Yadav | Prathamesh Mandavkar | Aparna Santosh | NX | 30 |  |  |  |  | texple |  | Previous PM Cockpit | Normal
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed | 614 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Hardik Panchal | 55 | NX | Normal | Tracker/SCH Status | No manual PM note is available for ERMELLI PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Hardik Panchal. | Project Status Update - ERMELLI PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Hardik Panchal | Ganesh Jadhav | Pragnesh Panchal | NX | 55 |  |  |  |  | ermellipvtltd |  | Previous PM Cockpit | Normal
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed | 623 | 100 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [8 empty] | 80 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Helen Keller Institute for Deaf & Blind; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Helen Keller Institute for Deaf & Blind - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE |  | Hiren Bhimani | Manisha Paradia | NX | 80 |  |  |  |  | helenkellerinstitutefordeafblind |  | Previous PM Cockpit | Normal
5017 | Escalation | Cartfire India | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed | 614 | 91 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | CARTFIRE INDIA | 6511 | Account DeActivated | Payroll, HRMS and mobile HR training completed - #E24sep6995 Integration is done # processed Oct & Nov. Salary with Attendance from HRMS - E24dec5935 December month salary processed January month salary processed |  | 100 | Jan-25 | Nagendra Poojary | 26 | NX | Normal | Manual PM Note | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Project Status Update - Cartfire India - Completed | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. |  |  | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. |  | No | Approved Alias | 1 | 1 | FALSE | Nagendra Poojary | Viral Panchal | Manisha Paradia | NX | 26 | Nagendra Poojary | Vasu Mohan Dusa | Manisha Paradia | 26 | cartfireindia | cartfireindia | Previous PM Cockpit | Normal | SPC109142243107 | Normal | E | Ankita Bankar | Viral Panchal |  | SAAS | 2024-08-03 | 2024-10-09 | 2025-02-11 | Fresh | Spine HRMS | Onsite | 123 | Completed
5018 | Escalation | Sky Prints | Schedule | 2025-01-25 | 2025-04-25 | Low | Completed | 613 | 90 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SKY PRINTS | 7098 | Account DeActivated | Direct Training & Implementation from 20th Dec We have completed and implementation and Training of spine HR and payroll NX We will discussed internally and will update and regarding roll out- W24dec7076 Need session for attendance integration and salary processing query on 28th Jan 2025 December salary done, we will process Jan salary till 03.02.2025 i will let u know if any issue happens, we have not decided to give the logins employees-E25jan8659 February Salary completed with attendance.-E25mar499 February Salary completed |  | 100 | Feb-25 | Nagesh Tiwari | 100 | NX | Normal | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Project Status Update - Sky Prints - Completed | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. |  |  | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. |  | No | Approved Alias | 1 | 1 | FALSE | Nagesh Tiwari | Viral Panchal | Manisha Singh | NX | 100 | Nagesh Tiwari | Vasu Mohan Dusa | Manisha Singh | 100 | skyprints | skyprints | Previous PM Cockpit | Normal | SPS109684240612 | Normal | E | Disha Kiran Kargutkar | Viral Panchal |  | SAAS | 2024-12-06 | 2024-12-20 | 2025-03-11 | Fresh | Spine HRMS | Onsite | 117 | Completed
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed | 607 | 84 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vikas Yadav | 500 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Cogencis; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Project Status Update - Cogencis - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vikas Yadav | Prathamesh Mandavkar | Pragnesh Panchal | NX | 500 |  |  |  |  | cogencis |  | Previous PM Cockpit | Normal
5020 | Allocation | S K Traders | Schedule | 2025-01-31 | 2025-06-30 | Low | Completed | 607 | 150 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | S K TRADERS NX | 7359 | Account DeActivated | URL & Files awaiting, files received, imple from 12th, client will not use payroll #E25feb5774 HRMS training #E25feb5780 training done login will be share on 18th #E25feb6379, logins given Client live- #E25feb6379, training & imple done, client will not use payroll, using only HRMS, logins given. |  | 100 | 0 | Rahul Ankush Dalvi | 25 | NX | Premium | Manual PM Note | Progress & Review Call. | Project Status Update - S K Traders - Completed | Progress & Review Call |  |  | Progress & Review Call |  | No | Approved Alias | 1 | 1 | FALSE | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | NX | 25 | Rahul Ankush Dalvi | Vasu Mohan Dusa | Nirbhay Kumar | 25 | sktraders | sktradersnx | Previous PM Cockpit | Premium | SPS109898253001 | Premium | E | Usha Gupta | Viral Panchal |  | SAAS | 2025-01-30 | 2025-02-12 | 2025-04-08 | Fresh | Spine HRMS | Online | 108 | Completed
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed | 602 | 79 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Darshit Pithwa | 132 | NX | Normal | Tracker/SCH Status | No manual PM note is available for SEEBA INDUSTRIES PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Darshit Pithwa. | Project Status Update - SEEBA INDUSTRIES PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Darshit Pithwa | Hemanshu Wadia | Nikhil Solanki | NX | 132 |  |  |  |  | seebaindustriespvtltd |  | Previous PM Cockpit | Normal
5022 | Escalation | Infexn Laboratories | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed | 602 | 79 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | INFEXN LABORATORIES PVT LTD | 5579 | Account DeActivated | #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed. |  | 100 | May-24 | Shubham Gurav | 200 | NX | Normal | SCH Project Remark | As per the latest SCH project remark: #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Shubham Gurav. | Project Status Update - Infexn Laboratories - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Shubham Gurav | Ganesh Jadhav | Nirbhay Kumar | NX | 200 | Shubham Gurav | Vasu Mohan Dusa | Nirbhay Kumar | 200 | infexnlaboratories | infexnlaboratoriespvtltd | Previous PM Cockpit | Normal | SPI108350242902 | Normal | E | Shivani Girish Dhonde | Ganesh Jadhav |  | SAAS | 2024-03-06 | 2024-03-21 | 2024-06-07 | Fresh | Spine HRMS | Onsite | 131 | Completed
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost | 595 | 258 | Watch | No approved SCH match | FALSE | [12 empty] | Rahul Ankush Dalvi | 70 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Sankalpan; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - Sankalpan | [5 empty] | No | No Match | 0 | 0 | TRUE | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | NX | 70 |  |  |  |  | sankalpan |  | Previous PM Cockpit | Normal
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed | 589 | 66 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Nandadeep Mhatre | 42 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Emmay Entertainment; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nandadeep Mhatre. | Project Status Update - Emmay Entertainment - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Nandadeep Mhatre | Prathamesh Mandavkar | Aparna Santosh | NX | 42 |  |  |  |  | emmayentertainment |  | Previous PM Cockpit | Normal
5025 | Allocation | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Schedule | 2025-02-18 | 2026-02-27 | Low | Completed | 589 | 374 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | INDIANA GRATINGS PVT LTD | 7449 | Account Activated | payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response sept sal will be live processing |  | 79 | Aug-26 | Rahul Ankush Dalvi | 465 | NX | Premium | SCH Project Remark | As per the latest SCH project remark: payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response sept sal will be live processing. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Rahul Ankush Dalvi | Akshay Shinde | Sanket Gosalia | NX | 465 | Akshay Joshi | Vasu Mohan Dusa | Sanket Gosalia | 440 | indianagroupindianagratingspvtltd | indianagratingspvtltd | Previous PM Cockpit | Premium | SPI109902253001 | Premium | E | Disha Kiran Kargutkar | Akshay Shinde | Viral Panchal | SAAS | 2025-02-17 | 2025-03-31 | 2026-05-13 | Fresh | Spine HRMS | Onsite | 103 | Live Salary Processing
5026 | Allocation | RADIX ELECTROSYSTEMS PVT LTD | Schedule | 2025-02-18 | 2026-03-30 | Low | Completed | 589 | 405 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | RADIX ELECTROSYSTEMS PVT LTD | 7453 | Account Activated | Project Live - PMS mod overviwe is done & for same module training user will get back to us with policies Training & Implementation of Payroll Nx is completed - #E25mar11411 & #E25mar6281 February month salary processed & tallied - #E25mar10450 March month live processing done April month salary processed & tallied June & july month tallied ELC module training & Implementation done PMS & request desk will are doing followup with user but they are not giving us data to do training & Implementation |  | 76 | Mar-26 | Aditya Pathak | 630 | NX | Normal | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | Project Status Update - RADIX ELECTROSYSTEMS PVT LTD - Completed | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. |  |  | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. |  | No | Approved Alias | 1 | 1 | FALSE | Aditya Pathak | Probian Biswas | Pragnesh Panchal | NX | 630 | Aditya Pathak | Vasu Mohan Dusa | Pragnesh Panchal | 630 | radixelectrosystemspvtltd | radixelectrosystemspvtltd | Previous PM Cockpit | Normal | SPR109998251802 | Premium | E | Ankita Bankar | Probian Biswas | Viral Panchal | SAAS | 2025-02-18 | 2025-03-18 | 2026-03-11 | Fresh | Spine HRMS | Onsite | 102 | Completed
5027 | Allocation | MARU CONSULTANCY SERVICES | Schedule | 2025-02-19 | 2025-06-04 | Low | Lost | 588 | 105 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | MARU CONSULTANCY SERVICES | 7465 | Account DeActivated | URL & files awaiting, payroll files expected on 22nd, master file will be share on 27th, master file received, kick off meeting on 4th Waiting for revised & Register file #E25mar2864, files received, training date waiting, imple from 24th, training done #E25mar8603, #E25mar9860 Geo fencing #E25mar10496 Geo fencing #E25apr105, session arranged on 3rd #E25apr105 fencing done mobile login given to half employees #E25apr1678, logins given, march salary will be complete in 3rd week April salary expected live March done user will get back to us for April salary, probably complete by 7th S/w not in use, outsourcing, attendance is priority, blue collar employees unable to use attendance, for meeting user will get back to us. Onsite meeting on 29th RECENT UPDATE - MARU CONSULTANCY SERVICES use to process salary for their client, however they have left, if any new cliient onboards then they shall renew it for salary processing. | Funds issue | 83 | Mar-25 | Ruchit Shailesh Patel | 150 | NG | Normal | Manual PM Note | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Project Status Update - MARU CONSULTANCY SERVICES - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | No | Approved Alias | 1 | 1 | FALSE | Ruchit Shailesh Patel | Probian Biswas | Manisha Singh | NG | 150 | Ruchit Shailesh Patel | Vasu Mohan Dusa | Manisha Singh | 150 | maruconsultancyservices | maruconsultancyservices | Previous PM Cockpit | Normal | SPM110010251902 | Normal | E | Usha Gupta | Probian Biswas | Viral Panchal | SAAS | 2025-02-19 | 2025-03-24 | 2025-06-13 | Fresh | Spine NG | Onsite | 101 | Completed
5028 | Allocation | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Schedule | 2025-02-24 | 2026-01-28 | Low | Completed | 583 | 338 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SHREE RAMDEV METALEX LLP | 7477 | Account Activated | Client have completed the Spine Payroll Software training on 19/03/2025 -E25mar6215 Spine payroll training for Day-2 has been completed. We covered the HRMS module (Admin, Self-Service, and Leave), as well as the February 2025 salary process and Tally.-E25mar6704 Client have successfully completed the Spine HRMS and Mobile HR training on 21st March 2025.-E25mar7156 March month salary processed The salary of month May-2025 has been successfully processed in spine. -E25jun1773 July has been successfully processed and tallied-W25aug6270 August salary done This is to notify you that currently our employees are not regularizing attendance before payroll, So we are in the process of streaming line our attendance regularization on time. For next few months (3-4) Month we shall process salary in Spine parallel. Currently we have processed salary till Sep-25 and we shall get back to team Spine support in future whenever required-E25oct4126 Oct-25 processed with Spine attendance parallel November salary processing is completed for 179 employees. |  | 100 | Feb-26 | Tejas Rajesh Baragade | 300 | NX | Premium | Manual PM Note | Progress & Review Call. | Project Status Update - SHREE RAMDEV METALEX LLP / RAMDEV GROUP - Completed | Progress & Review Call |  |  | Progress & Review Call |  | No | Approved Alias | 1 | 1 | FALSE | Tejas Rajesh Baragade | Vinay Kareliya | Manisha Singh | NX | 300 | Tejas Rajesh Baragade | Vasu Mohan Dusa | Manisha Singh | 325 | shreeramdevmetalexllpramdevgroup | shreeramdevmetalexllp | Previous PM Cockpit | Premium | SPS110019252102 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-02-21 | 2025-03-12 | 2025-11-14 | Fresh | Spine HRMS | Onsite | 100 | Completed
5029 | Allocation | APLAB LIMITED (FOR STAFF LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed | 581 | 244 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | APLAB LIMITED (FOR STAFF LICENSE) | 7489 | Account Activated | conversion done user want separate db- E25mar2449 installation done handholding done today - W25apr4191 confirmation feb & march salay procssed from spine Aplab PayrollNX Training completion Ticket I'd W25apr4191 attendance integration done implementation confirmation- W25jun5948 they will not process payroll live, they process salary for 2 3 months together for statutory reports E25jul10109 - confirmation |  | 84 |  | Varun Rajbhar | 165 | NX | Normal | Manual PM Note | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Project Status Update - APLAB LIMITED (FOR STAFF LICENSE) - Completed | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. |  |  | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. |  | No | Approved Alias | 1 | 1 | FALSE | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | NX | 165 | Varun Rajbhar | Vasu Mohan Dusa | Tejas Kareliya | 200 | aplabltdforstafflicense | aplabltdforstafflicense | Previous PM Cockpit | Normal | SPA109903253001 | Normal | C | Mansi Singh | Vinay Kareliya | Prathamesh Mandavkar | On-Premises | 2025-02-25 | 2025-04-11 | 2025-09-11 | Conversion | Spine HRMS | Onsite | 99 | Completed
5030 | Allocation | APLAB LIMITED (FOR CONTRACT LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed | 581 | 244 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | APLAB LIMITED (FOR CONTRACT LICENSE) | 7490 | Account Activated | contractual conv not required user will share fresh data-E25mar2250 TRAINING DONE - They will be using spine for tracking attendance only E25jun5035 - confirmation using only for attendance, will not use for payroll E25jul10109 |  |  |  | Varun Rajbhar | 251 | NX | Normal | Manual PM Note | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Project Status Update - APLAB LIMITED (FOR CONTRACT LICENSE) - Completed | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. |  |  | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. |  | No | Approved Alias | 1 | 1 | FALSE | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | NX | 251 | Varun Rajbhar | Vasu Mohan Dusa | Tejas Kareliya | 251 | aplabltdforcontractlicense | aplabltdforcontractlicense | Previous PM Cockpit | Normal | SPA109915253101 | Normal | D | Mansi Singh | Vinay Kareliya | Prathamesh Mandavkar | On-Premises | 2025-02-25 | 2025-05-15 | 2025-09-11 | Fresh | Spine HRMS | Onsite | 98 | Completed
5031 | Escalation | NPSE AUTOMATION PVT. LTD | Schedule | 2025-02-12 | 2025-04-25 | Low | Lost | 595 | 72 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | NPSE AUTOMATION PVT. LTD. | 7053 | Account DeActivated | Training & Implementation from 16th December 2024 We attend training of payroll nx & we have process salary of nov24 in payroll NX- E24dec3116 we have completed the Training of HRMS and its modules Admin,Leave and Time and MobileHR.-E24dec5532 Attendance integration issue not sorted as we have provided multiple solutions but they are not gave any response and also as cost barer regarding attendance integartions, solutions were provided: We have proposed the following solutions to retrieve attendance data in HRMS: Provide us with the attendance data in a SQL table in the format specified by Spine. Allow us to add the necessary extra fields to the SQL attendance table maintained by the biometric vendor. For daily attendance, use MobileHR, which will be reflected directly in HRMS and does not require a biometric machine. Based on your request, we have also suggested other biometric vendor recommendations. npse partner binu mathew is taking charge of attendance issue we need to wait for 2 days User and Owner not responding call and even mails. | Attendance Integration issue, vendor providing data only through API | 56 | Nov-24 | Nandadeep Mhatre | 55 | NX | Normal | Manual PM Note | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Project Status Update - NPSE AUTOMATION PVT. LTD - Completed | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. |  |  | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. |  | No | Approved Alias | 1 | 1 | FALSE | Nandadeep Mhatre | Prathamesh Mandavkar | Amit Arjun Sawant | NX | 55 | Nandadeep Mhatre | Vasu Mohan Dusa | Amit Arjun Sawant | 55 | npseautomationpvtltd | npseautomationpvtltd | Previous PM Cockpit | Normal | SPN109637243011 | Normal | E | Disha Kiran Kargutkar | Prathamesh Mandavkar |  | SAAS | 2024-11-30 | 2024-12-11 | 2025-03-26 | Fresh | Spine HRMS | Online | 118 | Completed
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed | 576 | 239 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vinay Kareliya | 125 | NG | Normal | Tracker/SCH Status | No manual PM note is available for ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vinay Kareliya. | Project Status Update - ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vinay Kareliya | Vinay Kareliya | Tejas Kareliya | NG | 125 |  |  |  |  | anmindustriespvtltdanmallianceanmgroupamketteanalyticsltd |  | Previous PM Cockpit | Normal
5033 | Allocation | KARVY TECHNOLOGIES PVT LTD | Schedule | 2025-03-03 | 2026-03-30 | Low | Lost | 576 | 392 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | KARVY TECHNOLOGIES PVT. LTD. | 7518 | Account DeActivated | Payroll training confirmation: E25mar9331 HRMS, Mobile HR, and geotagging confirmation: E25mar9330 may processed as ashwini ji left the organisation nikhil from accounts team will take trng post that will proceed with payment but he is not respondng, so vasu is planning to meet phani ji cfo. new user training session done now for salary processing user is not responding positively. geo location, fencing done attendance is coming proper as of now user have few queries, impl team in discussion QUERIES RESOLVED PAYMENT FOLLOW UP ONGOING Few concerns with regards to geo fencing was there, we resolved it too, user not ready to release the pending payment. | Not happy with service | 87 | May-25 | Tejas Rajesh Baragade | 130 | NG | Normal | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - KARVY TECHNOLOGIES PVT LTD - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  | Live Salary Processing Planned for this Month |  | No | Approved Alias | 1 | 1 | FALSE | Tejas Rajesh Baragade | Vinay Kareliya | Vaishali Ramniklal Puj | NG | 130 | Tejas Rajesh Baragade | Vasu Mohan Dusa | Vaishali Ramniklal | 130 | karvytechpvtltd | karvytechpvtltd | Previous PM Cockpit | Normal | SPK110049252802 | Normal | E | Mansi Singh | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-03-03 | 2025-03-24 | 2025-12-24 | Fresh | Spine NG | Onsite | 96 | Completed
5034 | Allocation | QUALIGENS PHARMA PVT. LTD | Schedule | 2025-03-07 | 2025-10-28 | Low | Completed | 572 | 235 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | QUALIGENS PHARMA PVT. LTD. | 7549 | Account Activated | Client have completed Payroll Nx,Spine HRMS & Mobile HR training we processed the salary for March_2025. Client have successfully installed & configured attendance module in Spine HRMS software.-E25apr7956 completed the process of Leave Policy ,we have checked & it is ok. Client was facing issues to process the month of May salary due to new TAX regime,this query has resolved now we are processing the May month salary.-W25jun5512 June salary processed and MLWF Query has resolved -Connected by Ms. Ankita.- W25jul1673 July salary in process.-W25aug2373 |  | 100 | Feb-26 | Ruchit Shailesh Patel | 400 | NX | Normal | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Project Status Update - QUALIGENS PHARMA PVT. LTD - Completed | Backend working is ongoing, training & implementation is planned. |  |  | Backend working is ongoing, training & implementation is planned. |  | No | Approved Alias | 1 | 1 | FALSE | Ruchit Shailesh Patel | Probian Biswas | Giriraj Birendrasingh Tomar | NX | 400 | Ruchit Shailesh Patel | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 400 | qualigenspharmapvtltd | qualigenspharmapvtltd | Previous PM Cockpit | Normal | SPQ109952253101 | Normal | B | Disha Kiran Kargutkar | Probian Biswas | Viral Panchal | On-Premises | 2025-03-06 | 2025-04-09 | 2025-08-12 | Fresh | Spine HRMS | Onsite | 94 | Completed
5035 | Allocation | MADURA INDUSTRIAL TEXTILES LIMITED | Schedule | 2025-03-10 | 2026-04-28 | Low | Completed | 569 | 414 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | MADURA INDUSTRIAL TEXTILES LIMITED. | 7556 | Account Activated | first focus on the HRMS module, as they wil be revising the salary structure after the appraisal so want to proceed with hrms- E25apr8632 we have Completed the HRMS Training for Admin, Self Service, Leave and Time (till Shift) Module.- E25apr8632 they are processing salary live with attn additional module done VM confirmation- E25dec2755 |  | 100 | Mar-26 | Varun Rajbhar | 287 | NX | Normal | Manual PM Note | Closed. | Project Status Update - MADURA INDUSTRIAL TEXTILES LIMITED - Completed | Closed |  |  | Closed |  | No | Approved Alias | 1 | 1 | FALSE | Varun Rajbhar | Vinay Kareliya | Jayesh Mojidra | NX | 287 | Varun Rajbhar | Vasu Mohan Dusa | Jayesh Mojidra | 327 | maduraindustrialtextilesltd | maduraindustrialtextilesltd | Previous PM Cockpit | Normal | SPM110039252802 | Normal | E | Mansi Singh | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-03-10 | 2025-04-21 | 2025-12-12 | Fresh | Spine HRMS | Onsite | 93 | Completed
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed | 561 | 224 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Sahil Gadhave | 700 | NG | Normal | Tracker/SCH Status | No manual PM note is available for BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. | Project Status Update - BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Sahil Gadhave | Sahil Gadhave | Santosh Bhoja Shetty | NG | 700 |  |  |  |  | bijjargimotorspvtltdbijjargimotorsbijjargiexcavationsolutions |  | Previous PM Cockpit | Normal
5037 | Allocation | STEAM PULSE INDIA PVT LTD | Schedule | 2025-03-25 | 2025-10-28 | Low | Completed | 554 | 217 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 7631 | Account Activated | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us | 100 | Mar-26 | Daksh Pawankumar | 140 | NG | Normal | SCH Project Update | As per the latest SCH project update: HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Daksh Pawankumar. | Project Status Update - STEAM PULSE INDIA PVT LTD - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | NG | 140 | Daksh Pawankumar | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 65 | steampulseindiapvtltd | steamharbourlogisticspvtltd | Previous PM Cockpit | Normal | SPS110155252403 | Normal | E | Mansi Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-03-24 | 2025-04-07 | 2025-12-12 | Fresh | Spine NG | Onsite | 87 | Completed
5038 | Allocation | STEAM HARBOUR LOGISTICS PVT LTD | Schedule | 2025-03-25 | 2026-01-28 | Low | Completed | 554 | 309 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 7631 | Account Activated | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us | 100 | Mar-26 | Daksh Pawankumar | 60 | NG | Normal | SCH Project Update | As per the latest SCH project update: HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Daksh Pawankumar. | Project Status Update - STEAM HARBOUR LOGISTICS PVT LTD - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | NG | 60 | Daksh Pawankumar | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 65 | steamharbourlogisticspvtltd | steamharbourlogisticspvtltd | Previous PM Cockpit | Normal | SPS110155252403 | Normal | E | Mansi Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-03-24 | 2025-04-07 | 2025-12-12 | Fresh | Spine NG | Onsite | 87 | Completed
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed | 554 | 68 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Sachin Thothawala | 1250 | NX | Normal | Tracker/SCH Status | No manual PM note is available for GUJARAT TEA PROCESSOR & PACKERS LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sachin Thothawala. | Project Status Update - GUJARAT TEA PROCESSOR & PACKERS LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Sachin Thothawala | Sachin Thothawala | Tejas Kareliya | NX | 1250 |  |  |  |  | gujaratteaprocessorpackersltd |  | Previous PM Cockpit | Normal
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed | 562 | 76 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Kajal Inchanalkar | 850 | NX | Normal | Tracker/SCH Status | No manual PM note is available for INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Kajal Inchanalkar. | Project Status Update - INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Kajal Inchanalkar | Saurabh Pednekar | Mehul Patel | NX | 850 |  |  |  |  | industrialxrayalliedradiographersnx |  | Previous PM Cockpit | Normal
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed | 561 | 75 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Nagendra Poojary | 60 | NX | Normal | Tracker/SCH Status | No manual PM note is available for TATARIA HARDWARE INNOVATION; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nagendra Poojary. | Project Status Update - TATARIA HARDWARE INNOVATION - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Nagendra Poojary | Viral Panchal | Manisha Paradia | NX | 60 |  |  |  |  | tatariahardwareinnovation |  | Previous PM Cockpit | Normal
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active | 560 |  | Critical | Ageing 560 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | NATIONAL SPORTS CLUB OF INDIA NX | 4859 | Account Activated | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. Due to biometric machine was not working due to which there were many employees who had not punched in the system. Because of which they have to do the salary as per the previous process. Were we told Mdm. Megha that as they have processed the September salary. So we will not regularize the September attendance. Will update the attendance from 25th September to 28th September. Sept salary processed by uploading atten. October sal is live target Need to discuss with client on monday with vasu for payment related. |  | 68 | Aug-26 | Mihir Navnath Mungekar | 450 | NX | Premium | Manual PM Note | Live Salary Processing Planned. | Project Status Update - THE NATIONAL SPORTS CLUB OF INDIA - Datafile Explanation | Live Salary Processing Planned. |  |  | Live Salary Processing Planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | Mihir Navnath Mungekar | Vinay Kareliya | Sanket Gosalia | NX | 450 | Mihir Navnath Mungekar | Vasu Mohan Dusa | Sanket Gosalia | 450 | thenationalsportsclubofindia | nationalsportsclubofindianx | Previous PM Cockpit | Premium | SPT107662232808 | Premium | B | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | On-Premises | 2023-09-02 | 2023-12-27 |  | Fresh | Spine HRMS | Onsite | 137 | Datafile Explanation
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed | 547 | 30 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Amol Takkar | 400 | NX | Premium | Tracker/SCH Status | No manual PM note is available for EROS ELEVATORS & ESCALATORS PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Project Status Update - EROS ELEVATORS & ESCALATORS PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Amol Takkar | Amol Takkar | Tejas Kareliya | NX | 400 |  |  |  |  | eroselevatorsescalatorspvtltd |  | Previous PM Cockpit | Premium
5044 | Allocation | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Schedule | 2025-04-01 | 2026-04-28 | Low | Completed | 547 | 392 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | ELECTROSTEEL CASTINGS LTD | 7706 | Account Activated | training and impl conf- E25jul10921 logins rolled out not going to process salary from spine, using hrms. renewal done | SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa | 100 |  | Kunal Joshi | 1000 | NX | Premium | SCH Project Update | As per the latest SCH project update: SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Kunal Joshi. | Project Status Update - ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Kunal Joshi | Sahil Gadhave | Jayesh Mojidra | NX | 1000 | Kunal Joshi | Vasu Mohan Dusa | Jayesh Mojidra | 1000 | electrosteelcastingsltdelectrosteelgroup | electrosteelcastingsltd | Previous PM Cockpit | Premium | SPE110247253103 | Premium | A | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | On-Premises | 2025-03-31 | 2025-07-09 | 2026-05-13 | Fresh | Spine HRMS | Online | 85 | Live Salary Processing
5045 | Escalation | SAI SANKET INDUSTRIES PVT.LTD | Schedule | 2025-04-01 | 2025-05-25 | Low | Completed | 547 | 54 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SAI SANKET INDUSTRIES PVT. LTD. | 4749 | Account Activated | Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth |  | 86 | Nov-23 | Dakshesh D Nadkar | 410 | NX | Premium | SCH Project Remark | As per the latest SCH project remark: Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Dakshesh D Nadkar. | Project Status Update - SAI SANKET INDUSTRIES PVT.LTD - Completed | [5 empty] | No | Exact Name | 1 | 2 | TRUE | Dakshesh D Nadkar | Viral Panchal | Nirbhay Kumar | NX | 410 | Dakshesh D Nadkar | Vasu Mohan Dusa | Nirbhay Kumar | 251 | saisanketindustriespvtltd | saisanketindustriespvtltd | Previous PM Cockpit | Premium | SPS107604233107 | Normal | E | Mayuri Thackrey | Viral Panchal |  | SAAS | 2023-08-02 | 2023-08-21 | 2023-12-14 | Conversion | Spine NG | Onsite | 139 | Completed
5046 | Escalation | LOTUS TEXCOM INDIA LLP | Schedule | 2025-04-04 | 2025-07-23 | Low | Lost | 544 | 110 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | LOTUS TEXCOM INDIA LLP | 6837 | Account DeActivated | mail done- call done, URL done, data file expln done Impelementation and trng starts from 27th dec 24 biometric data is not proper in atten sql problem from their side suggested vendor As my recent call with user for follow up, Mr. Vaibhav user told that as per their senior, they want unsubscribe the services, told him, whatever your concerns are kindly mail and let me know we can arrange meeting with PM and your senior awaiting mail from his end. user not responding, same is informed to PM and partner, partner team shall do visit at client placed as mentioned by them. Meeting arranged tomorrow for discussion with PM and Lotus Texcom Director. Spoke to Mr. Harshal , he mentioned there are issues going on and on , there were biometric issues, data was not not getting pushed in sql table its not syncing and Mr. Harshal does not want to invest in New Biometric Machine, he mentioned he has informed the same to Sun heights parther Mr. Liayakt too. | Attendance integration issue |  | 0 | Prathamesh Mandavkar | 51 | NG | Normal | Manual PM Note | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority. | Project Status Update - LOTUS TEXCOM INDIA LLP - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority. |  | No | Approved Alias | 1 | 1 | FALSE | Prathamesh Mandavkar | Prathamesh Mandavkar | Sandeep Ashok Joundal | NG | 51 | Prathamesh Mandavkar | Vasu Mohan Dusa | Sandeep Ashok Joundal | 51 | lotustexcomindiallp | lotustexcomindiallp | Previous PM Cockpit | Normal | SPR109402242809 | Normal | E | Karuna Rajaram Sandim | Prathamesh Mandavkar | Prathamesh Mandavkar | SAAS | 2024-10-08 | 2024-12-27 | 2025-07-28 | Fresh | Spine NG | Online | 119 | Completed
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed | 534 | 48 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Probian Biswas | 185 | NX | Normal | Tracker/SCH Status | No manual PM note is available for BRILLIANT POLYMERS PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Project Status Update - BRILLIANT POLYMERS PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Probian Biswas | Viral Panchal | Tejas Kareliya | NX | 185 |  |  |  |  | brilliantpolymerspvtltd |  | Previous PM Cockpit | Normal
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed | 527 | 87 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vikas Yadav | 205 | NX | Normal | Tracker/SCH Status | No manual PM note is available for AUTOTECH-SIRMAX INDIA PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Project Status Update - AUTOTECH-SIRMAX INDIA PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vikas Yadav | Prathamesh Mandavkar | Nikhil Solanki | NX | 205 |  |  |  |  | autotechsirmaxindiapvtltd |  | Previous PM Cockpit | Normal
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed | 526 | 86 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Supriya Waghmare | 60 | NX | Normal | Tracker/SCH Status | No manual PM note is available for TAO AUTOMATION SERVICES PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Supriya Waghmare. | Project Status Update - TAO AUTOMATION SERVICES PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Supriya Waghmare | Hemanshu Wadia |  | NX | 60 |  |  |  |  | taoautomationservicespvtltd |  | Previous PM Cockpit | Normal
5050 | Escalation | BASANT OVERSEAS | Schedule | 2025-04-25 | 2026-03-30 | Low | Lost | 523 | 339 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | BASANT OVERSEAS | 7566 | Account DeActivated | Till date, all the requirements received have been delivered to Team Basant. Mr. Deep has also confirmed that he is satisfied with the updates—reference ticket number W25AUG5167. The delay occurred due to the day-to-day new requirements received from the team, based on which our team made the necessary changes and obtained confirmation accordingly. We are now ready to proceed with the further training and implementation activities. However, the client’s AMC has expired. Requesting your guidance on how we should proceed further. yash is working on the same with hemant sir | Resoure Problem | 13 | 0 | Yash Pankajkumar Shah | 1454 | NG | Normal | Manual PM Note | Live Salary Processing Planned. | Project Status Update - BASANT OVERSEAS - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  | Live Salary Processing Planned. |  | No | Approved Alias | 1 | 1 | FALSE | Yash Pankajkumar Shah | Akshay Shinde | Jayesh Mojidra | NG | 1454 | Yash Pankajkumar | Vasu Mohan Dusa | Jayesh Mojidra | 1454 | basantoverseas | basantoverseas | Previous PM Cockpit | Normal | SPB110104251103 | Premium | E | Mansi Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-03-11 | 2025-06-19 | 2025-11-11 | Fresh | Spine NG | Online | 91 | Completed
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost | 520 | 37 | Watch | No approved SCH match | FALSE | [12 empty] | Rahul Ankush Dalvi | 100 | NX | Normal | Tracker/SCH Status | No manual PM note is available for POONAM ROLLER FLOUR MILLS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | [5 empty] | No | No Match | 0 | 0 | TRUE | Rahul Ankush Dalvi | Viral Panchal | Aparna Santosh | NX | 100 |  |  |  |  | poonamrollerflourmillspvtltd |  | Previous PM Cockpit | Normal
5052 | Allocation | SNAPWORK TECHNOLOGIES PVT LTD | Schedule | 2025-05-03 | 2026-02-27 | Low | Completed | 515 | 300 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 7866 | Account Activated | welcome call done payroll done april tallied hrms basic module done geo tagging done logins rolled out integration/smtp done MAY DONE E25jun8292 june salary conf- E25jul5746 LDAP and maker checker. provided processing live salary from system pms and time sheet pending- if session required client will reach out to us.W26apr5969 #10/08 - rcvd a ticket from user regarding issue in approver. #18/08 - feedback was not good at all, she told she would give zero rating, her main issue was about resource allocation charges, which i was explaining her, then she told, she is quite allocated today, we can connect tomorrow. #28/08 - E26aug9070 - user requested for user manual for sharing with their employees. | Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10 | 98 | Sep-26 | Vijay Bugde | 360 | NX | Normal | SCH Project Update | As per the latest SCH project update: Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Vijay Bugde. | Project Status Update - SNAPWORK TECHNOLOGIES PVT LTD - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | Vijay Bugde | Amey Telge | Sanket Gosalia | NX | 360 | Vijay Bugde | Vasu Mohan Dusa | Sanket Gosalia | 470 | snapworktechpvtltd | snapworktechpvtltd | Previous PM Cockpit | Normal | SPS110245253103 | Normal | E | Ritika Dilip Singh | Amey Telge | Viral Panchal | SAAS | 2025-05-03 | 2025-05-20 | 2026-04-15 | Fresh | Spine HRMS | Onsite | 83 | Live Salary Processing
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed | 494 | 60 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [8 empty] | 630 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE |  | Hiren Bhimani | Rushabh Dinesh Shah | NX | 630 |  |  |  |  | royalchainspvtltdandroyalitalianjewelrypvtltd |  | Previous PM Cockpit | Normal
5054 | Allocation | BRIGHT BROTHERS LTD. / BRITE | Schedule | 2025-05-27 | 2026-02-27 | Low | Completed | 491 | 276 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | BRIGHT BROTHERS LTD | 7947 | Account Activated | Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system |  | 100 | Sep-26 | Rahul Ankush Dalvi | 520 | NG | Normal | SCH Project Remark | As per the latest SCH project remark: Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. Next action: Review blocker, confirm owner, and update next closure plan. | Project Status Update - BRIGHT BROTHERS LTD. / BRITE - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | Rahul Ankush Dalvi | Akshay Shinde | Anuj Kumar Ganga Prasad Tiwari | NG | 520 | Yash Pankajkumar | Vasu Mohan Dusa | Anuj Kumar Ganga Prasad Tiwari | 330 | brightbrothersltdbrite | brightbrothersltd | Previous PM Cockpit | Normal | SPB110442252705 | Normal | E | Ankita Bankar | Akshay Shinde | Viral Panchal | SAAS | 2025-05-27 | 2025-06-07 | 2026-08-14 | Fresh | Spine NG | Onsite | 79 | Live Salary Processing
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed | 494 | 60 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Mayur Pendhari | 45 | NX | Normal | Tracker/SCH Status | No manual PM note is available for ARMITA INDIA SHIPPING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. | Project Status Update - ARMITA INDIA SHIPPING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Mayur Pendhari | Akshay Shinde | Manisha Singh | NX | 45 |  |  |  |  | armitaindiashippingpvtltd |  | Previous PM Cockpit | Normal
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed | 494 | 8 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Shreyas Karkera | 151 | NX | Normal | Tracker/SCH Status | No manual PM note is available for PRECIOUS ALLOYS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Shreyas Karkera. | Project Status Update - PRECIOUS ALLOYS PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Shreyas Karkera | Shreyas Karkera | Vaishali Ramniklal Puj | NX | 151 |  |  |  |  | preciousalloyspvtltd |  | Previous PM Cockpit | Normal
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost | 494 | 60 | Watch | No approved SCH match | FALSE | [13 empty] | 25 | NX | Normal | Tracker/SCH Status | No manual PM note is available for SUKHKARTA MULTISPECIALITY HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Lost. | Project Status Update - SUKHKARTA MULTISPECIALITY HOSPITAL | [5 empty] | No | No Match | 0 | 0 | TRUE |  |  | Sanket Gosalia | NX | 25 |  |  |  |  | sukhkartamultispecialityhospital |  | Previous PM Cockpit | Normal
5058 | Escalation | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-08-30 | Low | Completed | 486 | 90 | Closed | Closed/lost item, monitor only | FALSE | FC Lost | Project was fully completed but later lost. | FC Lost | Completed | Completed | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 5973 | Account DeActivated | Welcome Call done URL sent for creation training and Implementation from 4th july 24 We proceed july and august salary.-E24aug7741 ONETEAM LOGISTICS INDIA PRIVATE LIMITED- held up-22nd oct 24 we have completed the training of Payroll NX and HRMS till Self services. -E25feb8341 Add module welcome call done. following up with user for workflow and policies, however still files are not received Leave and TAM module impl and training aligned 4th april 2025 LEave tam training done and Integration done, following up with user he mentioned that still there are lot of queries , told him to mail and we can schedule the same, Schedule aligned for past salary and queries. tomorrow. 09th may. 25 We processed the salary april_2025 with attendance -W25may486 May salary has been processed, No response from user- project is stuck. user was busy in audit, and shall process aug sep in 1st week of oct. oct salary processed Nov will be done till 15th dec 25. user is not responding, we tried reaching out to user many times, no response hence closing as lost | Not responding no reason | 100 | Mar-26 | Tushar More | 51 | NX | Normal | Manual PM Note | Review Meeting. | Project Status Update - ONETEAM LOGISTICS INDIA PRIVATE LIMITED - Completed | Review Meeting |  |  | Review Meeting |  | No | Approved Alias | 1 | 1 | FALSE |  |  | Nirbhay Kumar | NX | 51 | Tushar More | Vasu Mohan Dusa | Nirbhay Kumar | 51 | oneteamlogisticsindiapvtltd | oneteamlogisticsindiapvtltd | Previous PM Cockpit | Normal | SPO108695241605 | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera | Ganesh Jadhav | SAAS | 2024-05-16 | 2024-07-04 | 2026-06-11 | Fresh | Spine HRMS | Onsite | 127 | Completed
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed | 486 | 59 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Amol Takkar | 495 | NX | Premium | Tracker/SCH Status | No manual PM note is available for GOLDSTAR ELITE JEWELS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Project Status Update - GOLDSTAR ELITE JEWELS PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Amol Takkar | Amol Takkar | Sanket Gosalia | NX | 495 |  |  |  |  | goldstarelitejewelspvtltd |  | Previous PM Cockpit | Premium
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed | 486 | 59 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Mukeshkumar Shojiram kumavat | 300 | NX | Premium | Tracker/SCH Status | No manual PM note is available for SAINI ELECTRICAL & ENGINEERING WORKS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mukeshkumar Shojiram kumavat. | Project Status Update - SAINI ELECTRICAL & ENGINEERING WORKS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Mukeshkumar Shojiram kumavat | Nagesh Tiwari | Aparna Santosh | NX | 300 |  |  |  |  | sainielectricalengineeringworks |  | Previous PM Cockpit | Premium
5061 | Allocation | GNG ELECTRONICS LIMITED STAFF | Schedule | 2025-06-01 | 2025-10-28 | Low | Completed | 486 | 149 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED STAFF | 7377 | Account Activated | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535 |  | 100 | Mar-26 | Shubham Gurav | 250 | NX | Normal | Manual PM Note | plan activities in 2days. | Project Status Update - GNG ELECTRONICS LIMITED STAFF - Completed | plan activities in 2days. |  |  | plan activities in 2days. |  | No | Approved Alias | 1 | 2 | TRUE | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | NX | 250 | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 400 | gngelectronicsltdstaff | gngelectronicsltdstaff | Previous PM Cockpit | Normal | SPG109930253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2025-01-31 | 2025-02-17 | 2025-06-10 | Fresh | Spine NG | Onsite | 107 | Completed
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost | 486 | 52 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED FACTORY | 8831 | Account Activated | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | 100 |  | Shubham Gurav | 750 | NX | Normal | Manual PM Note | Review Meeting. | Project Status Update - GNG ELECTRONICS LIMITED FACTORY - Completed | Review Meeting |  |  | Review Meeting |  | Yes | Approved Alias | 1 | 3 | TRUE | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | NX | 750 | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 1600 | gngelectronicsltdfactory | gngelectronicsltdfactory | Previous PM Cockpit | Normal | SPG109937253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-01-29 | 2026-01-30 | 2026-02-10 | Fresh | Spine HRMS | Online | 47 | Completed
5063 | Allocation | ALLIED INSTRUMENTS PRIVATE LIMITED | Schedule | 2025-06-01 | 2026-03-30 | Low | Completed | 486 | 302 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | ALLIED INSTRUMENTS PRIVATE LIMITED | 7403 | Account Activated | training and impl confirmation - E25apr6298 training provided on 28th july attendance centralization ongoing daman silvasa khar integration in process. ------------------------------------------ STUCK- july pending new user training provided queries resolving going on Manish ji said from spine we are getting good support, but its my team we are not on track lot many things are going -audits etc & they are hands on tally so getting out of comfort zone for them is the thing. will try to start processing for oct month. E25sep1678- aug processed by importing attendance they use spine for audit purpose only for jan salary we scheduled a session, we have added all the employees they have conveyed that they will start doing live salary within few months client only use our system when they have audit not going to process live salary go live mail sent to client- E26may9307 |  | 100 |  | Vijay Bugde | 500 | NX | Premium | Manual PM Note | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Project Status Update - ALLIED INSTRUMENTS PRIVATE LIMITED - Completed | Feedback is positive, User to resolve internal issues and plan for live processing from June. |  |  | Feedback is positive, User to resolve internal issues and plan for live processing from June. |  | No | Approved Alias | 1 | 1 | FALSE | Vijay Bugde | Amey Telge | Sanket Gosalia | NX | 500 | Vijay Bugde | Vasu Mohan Dusa | Sanket Gosalia | 500 | alliedinstrumentspvtltd | alliedinstrumentspvtltd | Previous PM Cockpit | Premium | SPA109926253101 | Premium | E | Ankita Bankar | Amey Telge | Viral Panchal | On-Premises | 2025-02-05 | 2025-04-01 | 2026-05-25 | Fresh | Spine HRMS | Onsite | 106 | Live Salary Processing
5064 | Allocation | MESPACK INDIA PVT. LTD | Schedule | 2025-06-09 | 2026-04-28 | Low | Completed | 478 | 323 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | MESPACK INDIA PVT. LTD | 8009 | Account Activated | Payroll training done successfully completed the attendance integration activity at the client’s location. W25oct6232 , E25nov1863 october salary has been processed. nov salary done successfully processed the December 2025 salary. - E26jan4924. Expense module training done Jan salary processed February salary done March salary has been processed-E26apr8430 April done may salary done parallelly GO FC- As all activities related to training and implementation have been completed successfully, and the system is now fully ready for use. Due to an internal gap, the attendance has not been regularized so salary processing will be carried out in parallel. August salary has been processed with attendance. Called for feedback to user Ms. Usha not responded the call. sept live sal target As per akshay sept sal followup is going on |  | 100 | Aug-26 | Pooja Vikas Shinde | 50 | NG | Normal | Manual PM Note | Pranit to coordinate internally and align the implementation, team to coordinate for further activities. | Project Status Update - MESPACK INDIA PVT. LTD - Completed | Review blocker, confirm owner, and update next closure plan. |  |  | Pranit to coordinate internally and align the implementation, team to coordinate for further activities |  | No | Approved Alias | 1 | 1 | FALSE | Pooja Vikas Shinde | Akshay Shinde | Sandeep Ashok Joundal | NG | 50 | Pooja Vikas Shinde | Vasu Mohan Dusa | Sandeep Ashok Joundal | 60 | mespackindiapvtltd | mespackindiapvtltd | Previous PM Cockpit | Normal | SPM110480253105 | Normal | E | Disha Kiran Kargutkar | Akshay Shinde | Viral Panchal | SAAS | 2025-06-09 | 2025-07-02 | 2026-06-19 | Fresh | Spine NG | Onsite | 77 | Live Salary Processing
5065 | Allocation | UNITED AIR EXPRESS | Schedule | 2025-06-20 | 2026-04-28 | Low | Completed | 467 | 312 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | UNITED AIR EXPRESS | 8042 | Account Activated | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system |  | 100 | Aug-26 | Shubham Gurav | 2550 | NG | Normal | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Project Status Update - UNITED AIR EXPRESS - Completed | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  | No | Approved Alias | 1 | 1 | FALSE | Shubham Gurav | Nagesh Tiwari | Nirbhay Kumar | NG | 2550 | Shubham Gurav | Vasu Mohan Dusa | Nirbhay Kumar | 3050 | unitedairexpress | unitedairexpress | Previous PM Cockpit | Normal | SPU110473253105 | Premium | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2025-06-19 | 2025-07-21 | 2026-03-11 | Fresh | Spine NG | Online | 76 | Live Salary Processing
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost | 463 | 29 | Watch | No approved SCH match | FALSE | [12 empty] | Santosh Yadav | 200 | NG | Normal | Tracker/SCH Status | No manual PM note is available for Kuboz Arc Pvt Ltd; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Santosh Yadav. | Project Status Update - Kuboz Arc Pvt Ltd | [5 empty] | No | No Match | 0 | 0 | TRUE | Santosh Yadav | Vinay Kareliya | Giriraj Birendrasingh Tomar | NG | 200 |  |  |  |  | kubozarcpvtltd |  | Previous PM Cockpit | Normal
5067 | Escalation | ISA Logistics Private Limited | Schedule | 2025-06-19 | 2025-07-23 | Low | Completed | 468 | 34 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | ISA LOGISTICS PRIVATE LIMITED | 7445 | Account Activated | Completed the training of Payroll, Mobile and HRMS -E25mar9861 payroll process for the month of April 2025 has been processed successfully-E25may7360 May-2025 Salary Processed- E25may12012 June salary processed-W25jul6461 July salary processed August salary processed October month salary done Nov salary processed-E25dec1872 Dec salary processed- Processed the salary for Jan 26 got tallied for all employees-E26feb4932. PMS done- E26feb33. Feb salary processed-E26mar1563. march salary done April salary only 43 employees done new hr manager training completed Client has processed salary from excel. Currently client's priority is to process PMS from Spine, Once done they will process salary for May26 using only hrms module- E26jul2753. New user Mr. Rahul has shared HRMS Scope of Work for Review and Feasibility Confirmation and requirements has mentioned we are still working on it last working in 14th aug has been done by mihir and still we are working and need clarification by client and need to discuss with them. hrms queries are ongoing user has shared attached KRA and KPI document for reference sch to be aligned | Only HRMS | 100 |  | Mihir Navnath Mungekar | 200 | NG | Normal | Manual PM Note | April Salary Processed, Review Meeting. | Project Status Update - ISA Logistics Private Limited - Completed | April Salary Processed, Review Meeting |  |  | April Salary Processed, Review Meeting |  | No | Approved Alias | 1 | 1 | FALSE | Mihir Navnath Mungekar | Vinay Kareliya | Ankur Yewalekar | NG | 200 | Mihir Navnath Mungekar | Vasu Mohan Dusa | Ankur Yewalekar | 200 | isalogisticspvtltd | isalogisticspvtltd | Previous PM Cockpit | Normal | SPI109996251402 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-02-14 | 2025-03-24 | 2026-03-12 | Fresh | Spine NG | Onsite | 104 | Live Salary Processing
5068 | Escalation | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Support | 2025-06-27 | 2025-07-23 | Low | Completed | 460 | 26 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 4067 | Account Activated | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us. |  | 100 | April-23 | Pritesh Barot | 250 | NX | Normal | Manual PM Note | Datafiles Received, Implementation planned, Team to followup. | Project Status Update - SEVENTY SEVEN ENTERTAINMENT PVT. LTD - Completed | Datafiles Received, Implementation planned, Team to followup |  |  | Datafiles Received, Implementation planned, Team to followup |  | No | Approved Alias | 1 | 1 | FALSE | Pritesh Barot | Viral Panchal | Nikhil Solanki | NX | 250 | Pritesh Barot | Vasu Mohan Dusa | Nikhil Solanki | 250 | seventysevenentertainmentpvtltd | seventysevenentertainmentpvtltd | Previous PM Cockpit | Normal | SPS101600122310 | Normal | C | Usha Gupta | Viral Panchal |  | On-Premises | 2023-02-09 | 2023-02-28 | 2023-06-06 | Conversion | Spine HRMS | Onsite | 144 | Completed
5069 | Escalation | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Schedule | 2025-07-12 | 2025-08-30 | Low | Completed | 445 | 49 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 7258 | Account Activated | Welcome call done data expl done Training starts from 30th 2025 #completed the Payroll Training and Also Employee rollout has been done and Also december salary has been matched with our records - E25feb974 employees training and all the queries have been resolved.-E25feb7093 salary for the month of February 2025 has been confirmed and tally. - E25mar1995 | Karuna in follow up for balance payment | 100 | Feb-25 | Hardik Panchal | 145 | Spine HRMS | SAAS | Manual PM Note | Need to plan Review Meeting. | Project Status Update - ANSHUTECH AIR CONDITIONING PVT. LTD. NX - Completed | Need to plan Review Meeting |  |  | Need to plan Review Meeting |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Hardik Panchal | Vasu Mohan Dusa | Tejas Kareliya | 145 | anshutechairconditioningpvtltdnx | anshutechairconditioningpvtltdnx | Previous PM Cockpit |  | SPA109790243112 | Normal | E | Karuna Rajaram Sandim | Ganesh Jadhav |  | SAAS | 2025-01-07 | 2025-01-30 | 2025-03-11 | Fresh | Spine HRMS | Onsite | 116 | Completed
5070 | Escalation | CONTENDRE GREENERGY LIMITED | Schedule | 2025-07-15 | 2025-08-30 | Low | Completed | 442 | 46 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | CONTENDRE GREENERGY LIMITED | 7668 | Account Activated | #Trng and impl from 21st April #E25apr9485 - complete upto loan processing module #E25apr10010 - Payroll nx training is completed Location IQ set up has been done #E25apr11264 - have completed HRMS and SMTP training #W26may1493 - update ESIC rules in Payroll #E25jul1135 - june salary conf. #W25aug3365 - PAYROLL HRMS CONF. #W25sep4179 - august salary done. #07/05 - feedback was good, processed april month salary. #18/08 - overall feedback was good, they’ve been facing an issue while transferring employee from one company to another.she require a proper solution for the same. | No open queries as of now, Vasu to connect with the director for review meet 5/9 | 100 | Sep-26 | Daksh Pawankumar | 160 | Spine NG | SAAS | Manual PM Note | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Project Status Update - CONTENDRE GREENERGY LIMITED - Completed | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. |  |  | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. |  | No | Approved Alias | 1 | 2 | TRUE | [5 empty] | Daksh Pawankumar | Vasu Mohan Dusa | Aparna Santosh | 160 | contendregreenergyltd | contendregreenergyltd | Previous PM Cockpit |  | SPC110185252803 | Normal | E | Ritika Dilip Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-03-27 | 2025-04-21 | 2026-05-14 | Fresh | Spine NG | Onsite | 86 | Live Salary Processing
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed | 440 | 69 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | ILEAF RITZ BANQUETS | 8079 | Account DeActivated | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy | 110 | Jan-26 | Mayur Pendhari | 110 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - ILEAF RITZ BANQUETS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Anuj Kumar Ganga Prasad Tiwari | 110 | ileafritzbanquets | ileafritzbanquets | Previous PM Cockpit |  | SPI110558252806 | Normal | E | Mansi Singh | Probian Biswas | Viral Panchal | SAAS | 2025-06-28 | 2025-07-02 | 2026-06-18 | Fresh | Spine NG | Onsite | 75 | Completed
5072 | Escalation | ROYAL EMBROIDERY THREADS PVT.LTD. | Schedule | 2025-07-17 | 2025-08-30 | Low | Completed | 440 | 44 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | ROYAL EMBROIDERY THREADS PVT.LTD. | 7568 | Account Activated | #trng and impl from 3rd april #E25mar4404 - completed training of Payroll & HRMS #W25apr6337 - added all shift schedules, and attendace logics have been added & also training & login rollouts of Mobile HR #W25may504 - Attendace integration has been done #W25may7421 - processed the april salary #W25aug449 - june salary done #W25aug772 - july salary done ##W25sep5963 - conf. of total hours calculation calculation #11/09 - processed wages of 191 employee of pune for Aug_2025, During the verification some discrepancies identified, awaitng for final confirmation. #W25DEC1871 - nov salary done #08/05 - feedback was good no issue as of now, processed april month salary. #18/08 - feedback was neutral as always, right now there is nothing to escalate.. | client conveyed that within this week end will do payment 22/9 | 100 | Sep-26 | Bhavika Gite | 370 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: client conveyed that within this week end will do payment 22/9. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Bhavika Gite. | Project Status Update - ROYAL EMBROIDERY THREADS PVT.LTD. - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Bhavika Gite | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 370 | royalembroiderythreadspvtltd | royalembroiderythreadspvtltd | Previous PM Cockpit |  | SPR110105251203 | Normal | E | Ritika Dilip Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-03-12 | 2025-04-03 | 2026-05-14 | Fresh | Spine NG | Onsite | 89 | Live Salary Processing
5073 | Escalation | V ALLIANCE NX | Schedule | 2025-07-18 | 2025-08-30 | Low | Completed | 439 | 43 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | V ALLIANCE NX | 6373 | Account Activated | URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513 |  | 100 | Oct-24 | Rahul Ankush Dalvi | 1000 | Spine HRMS | SAAS | SCH Project Remark | As per the latest SCH project remark: URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - V ALLIANCE NX - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Rahul Ankush Dalvi | Vasu Mohan Dusa | Mehul Patel | 1000 | valliancenx | valliancenx | Previous PM Cockpit |  | SPV109057241607 | Normal | E | Usha Gupta | Viral Panchal |  | SAAS | 2024-07-16 | 2024-08-23 | 2024-11-13 | Conversion | Spine HRMS | Onsite | 124 | Completed
5074 | Escalation | UNITED AIR EXPRESS | Schedule | 2025-07-18 | 2025-08-21 | Low | Completed | 439 | 34 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | UNITED AIR EXPRESS | 8042 | Account Activated | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system |  | 100 | Aug-26 | Shubham Gurav | 3050 | Spine NG | SAAS | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Project Status Update - UNITED AIR EXPRESS - Completed | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Shubham Gurav | Vasu Mohan Dusa | Nirbhay Kumar | 3050 | unitedairexpress | unitedairexpress | Previous PM Cockpit |  | SPU110473253105 | Premium | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2025-06-19 | 2025-07-21 | 2026-03-11 | Fresh | Spine NG | Online | 76 | Live Salary Processing
5075 | Escalation | ESCON ELEVATORS PVT. LTD. | Schedule | 2025-07-23 | 2025-08-30 | Low | Completed | 434 | 38 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | ESCON ELEVATORS PVT. LTD. | 2203 | Account Activated |  |  | 0 | 0 | Probian Biswas | 805 | Spine HRMS | On-Premises | Tracker/SCH Status | No manual PM note is available for ESCON ELEVATORS PVT. LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Project Status Update - ESCON ELEVATORS PVT. LTD. - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Probian Biswas | Vasu Mohan Dusa | Jigar Rupani | 805 | esconelevatorspvtltd | esconelevatorspvtltd | Previous PM Cockpit |  | SPE105433211303 | Normal | A | Riya Jindam | Viral Panchal |  | On-Premises | 2021-03-11 | 2021-04-12 | 2022-02-07 | Fresh | Spine HRMS | Onsite | 152 | Completed
5076 | Allocation | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Schedule | 2025-08-02 | 2026-04-28 | Low | Lost | 424 | 269 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | 8204 | Account DeActivated | corp id creation done trng and impl in process Toyota and Hyudai branch employee data uploaded sucessfully also we processed Toyota branch sept month salary Employees work across multiple sites/companies and salary processing happens there. The director is using our software only to verify if the salary tallies with attendance data User is not responding, we are trying to reach user multiple times. vasu is looking into it (planning visit) director is not available, nor he is responding calls vasu went for onsite visit but they are not interested to proceed escalated the concern to amrprit through email client not interested | No Reponse - No Reason | 100 | Oct-25 | Vijay Bugde | 1500 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: No Reponse - No Reason. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Vijay Bugde. Next action: Review blocker, confirm owner, and update next closure plan. | Project Status Update - TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Vijay Bugde | Vasu Mohan Dusa | Amarprit Kaur | 1500 | trishulelectromechengineeringindiapvtltdtrishulgroup | trishulelectromechengineeringindiapvtltd | Previous PM Cockpit |  | SPT110669253107 | Normal | E | Mansi Singh | Amey Telge | Viral Panchal | SAAS | 2025-08-02 | 2025-09-02 | 2026-05-13 | Fresh | Spine NG | Onsite | 73 | Completed
5077 | Allocation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Schedule | 2025-08-06 | 2026-04-28 | Low | Lost | 420 | 265 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | RAMYASRI ELECTRICAL AUTOMATION | 8212 | Account DeActivated | 47 emp data recd, tallied, payroll set up done, training pending not responding,esc to PM, partner team, ignoring calls, 5/2 structure recd of 36 recd, uploaded, rest data follow up going on 10/3 meeting done- datafiles will share 12/3 client not showing interest, amc not renewed, no response from client,client deactivated, | No Reponse - No Reason | 36 | Oct-25 | Ankita Gupta | 250 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: No Reponse - No Reason. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankita Gupta. Next action: Review blocker, confirm owner, and update next closure plan. | Project Status Update - SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankita Gupta | Vasu Mohan Dusa | Roopa S | 250 | svsengineeringramyasrielectricalautomation | ramyasrielectricalautomation | Previous PM Cockpit |  | SPR110686250108 | Normal | E | Divya Bhide | Probian Biswas | Viral Panchal | SAAS | 2025-08-06 | 2025-09-17 | 2026-03-31 | Fresh | Spine NG | Online | 72 | Completed
5078 | Escalation | FFSERVICES PRIVATE LIMITED | CR | 2025-08-12 | 2025-11-28 | Low | Completed | 414 | 108 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | FFSERVICES PRIVATE LIMITED | 8880 | Account Activated | Project Live - PMS CONF (E26feb3272) Training & Implementation is done of PMS module |  | 100 |  | Harsh Dilip Ashar | 220 | Spine HRMS | SAAS | Manual PM Note | April Salary Processed, Review Meeting & Closure Note. | Project Status Update - FFSERVICES PRIVATE LIMITED - Completed | April Salary Processed, Review Meeting & Closure Note |  |  | April Salary Processed, Review Meeting & Closure Note |  | No | Approved Alias | 1 | 3 | TRUE | [5 empty] | Harsh Dilip Ashar | Vasu Mohan Dusa | Amarprit Kaur | 220 | ffservicespvtltd | ffservicespvtltd | Previous PM Cockpit |  | SPF107062230902 | Normal | E | Ankita Bankar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2026-02-05 | 2026-02-10 | 2026-02-14 | Fresh | Spine HRMS | Online | 45 | Completed
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost | 408 | 102 | Watch | No approved SCH match | FALSE | [16 empty] | Tracker/SCH Status | No manual PM note is available for PRASAD JEWELLERS; this update is generated from Tracker and SCH status. Tracker status is Lost. | Project Status Update - PRASAD JEWELLERS | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | prasadjewellers |  | Previous PM Cockpit
5080 | Allocation | SETHWALA FOODS LTD | Schedule | 2025-08-21 | 2026-05-26 | Low | Completed | 405 | 278 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | SETHWALA FOODS LTD | 8245 | Account Activated | GO FC- Client have completed training session of Payroll & HRMS . Also SMTP setup & locationAPI setting has been done successfully.-E25sep1207 september salary of ho done October salary done The training has been completed in talasari-E25nov8643 client have processed SFLD unit salary for the month of Dec'25 with attendance muster from the software successfully. With Login was provided to employees -E26jan2962 client inform us, for this month, HO salary will be run through Spine, while Talasari salary will be processed via Excel uploading.-E26feb1695 feb salary done march salary processed April salary processed-E26may3191 May salary processed Jun salary processed july salary done August salary processed. Called for feedback user vidhya user said queries are coming but it is getting resolved first only mumbai loc we were doing live but now talasari loc we are doing for aug but lie with attendance. sept will be fully live for both loc. will do sept live by 10th | user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9 | 100 | Aug-26 | Kunal Joshi | 600 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Kunal Joshi. | Project Status Update - SETHWALA FOODS LTD - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Kunal Joshi | Vasu Mohan Dusa | Nandini Tiwari | 600 | sethwalafoodsltd | sethwalafoodsltd | Previous PM Cockpit |  | SPS110711252008 | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-08-20 | 2025-08-28 | 2026-05-14 | Fresh | Spine NG | Onsite | 71 | Live Salary Processing
5081 | Allocation | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Schedule | 2025-08-01 | 2026-01-28 | Low | Completed | 425 | 180 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 7880 | Account Activated | Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live |  | 100 | Mar-26 | Aditya Mazire | 2500 | Spine HRMS | On-Premises | SCH Project Remark | As per the latest SCH project remark: Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Aditya Mazire. | Project Status Update - NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Tejas Kareliya | 2500 | nationalbulkhandlingcorporationpvtltd | nationalbulkhandlingcorporationpvtltd | Previous PM Cockpit |  | SPN110379253004 | Premium | E | Ankita Bankar | Amey Telge | Viral Panchal | On-Premises | 2025-05-07 | 2025-05-21 | 2025-11-11 | Fresh | Spine HRMS | Onsite | 80 | Completed
5082 | Escalation | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Schedule | 2025-08-14 | 2025-09-24 | Low | Completed | 412 | 41 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 7491 | Account Activated | Training done #E25mar4260, as per discussion with team leader user is in testing period for this month and will start implementing with salary and attendance from june month. called user Ms. Sushama about update as they said it working properly and we have check the may salary too and attendance queries has been solved. As per our discussion over the call, client will be processing the salary from your end. In case any assistance is required during the process.-W25jul4028. July salary processeed August salary processed- E25sep4242, E25sep4197. | Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9 | 100 |  | Ruchit Shailesh Patel | 1410 | Spine HRMS | On-Premises | SCH Project Update | As per the latest SCH project update: Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Ruchit Shailesh Patel. | Project Status Update - MAHWS OILFIELD SERVICES PRIVATE LIMITED - Completed | [5 empty] | No | Approved Alias | 1 | 2 | TRUE | [5 empty] | Ruchit Shailesh Patel | Vasu Mohan Dusa | Giriraj Birendrasingh Tomar | 1410 | mahwsoilfieldservicespvtltd | mahwsoilfieldservicespvtltd | Previous PM Cockpit |  | SPM107218233003 | Premium | C | Disha Kiran Kargutkar | Probian Biswas | Viral Panchal | On-Premises | 2025-02-26 | 2025-03-17 | 2025-09-15 | Fresh | Spine HRMS | Onsite | 97 | Completed
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed | 398 | 214 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | FUJIYAMA POWER SYSTEMS LIMITED | 8275 | Account DeActivated | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software | 110 | Feb-26 | Komal Kanadiya | 2400 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Another Software. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - FUJIYAMA POWER SYSTEM (UTL) - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 2400 | fujiyamapowersystemutl | fujiyamapowersystemsltd | Previous PM Cockpit |  | SPF110735252908 | Premium | E | Divya Bhide | Hiren Bhimani | Hiren Bhimani | SAAS | 2025-08-29 | 2025-09-23 | 2026-07-29 | Fresh | Spine NG | Online | 70 | Completed
5084 | Escalation | VABA | Schedule | 2025-08-04 | 2025-10-28 | Low | Completed | 422 | 85 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | VABA | 7577 | Account Activated | Client have successfully completed the PayrollNX training Client have processed the one company Bishan Steel Industries March 2025 month salary and tally with register matches to our salary register. 1. salary attendance days demo done and queries solved Client inform that our executive Mr. Karan Has Done Following works :- 1. smtp work done 2. Leave Workflow & Attendance work flow Done 3. Tally Integration work done as demo basis and it is ok -E25apr4753 As per telecon attendance integration has been done. user is processing the may salary by its own. We have completed our Salary Process for the Month of May 2025-E25jun5684 Client have completed our Salary Process for the Month of June 2025-E25jul5468 July month salary processed August salary processed August salary processed September salary processed Oct salary processed Nov salary processed January Salary processed feb salary is in process as client want to extend the employee count. | Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop | 100 | Mar-26 | Karan Rajesh Tiwari | 430 | Spine HRMS | SAAS | SCH Project Update | As per the latest SCH project update: Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Karan Rajesh Tiwari. | Project Status Update - VABA - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Karan Rajesh Tiwari | Vasu Mohan Dusa | Anuj Kumar Ganga Prasad Tiwari | 430 | vaba | vaba | Previous PM Cockpit |  | SPV110114251303 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-03-13 | 2025-03-26 | 2025-10-09 | Fresh | Spine HRMS | Onsite | 88 | Completed
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed | 404 | 67 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for KISHAN LAL PAWAN KUMAR JAIN; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - KISHAN LAL PAWAN KUMAR JAIN - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | kishanlalpawankumarjain |  | Previous PM Cockpit
5086 | Escalation | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Schedule | 2025-08-22 | 2025-09-24 | Low | Completed | 404 | 33 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | MICROPOINT COMPUTERS PRIVATE LIMITED NX | 5551 | Account Activated | go live- they want to keep the database separate and conversion will be done for both the companies Micropoint Computers Pvt Ltd. Goanfest Food & Beverages Pvt Ltd-#354379 Database Handholding Both Company Databases Confirmation. # 356675 PAYROLL NX TRAINING COMPLETED #358872 successfully processed month of March 2024 of both company from payroll NX System -363500 April- salary Process #375292 2nd Entity Salary For the month of April- 375286 rct mod they will get back to us when required. few employees are using mobile app for marking attendance disbursing salary live from spine |  | 78 | Jun-24 | Mayur Pendhari | 700 | Spine HRMS | SAAS | Manual PM Note | Progress & Review Call. | Project Status Update - MICROPOINT COMPUTERS PRIVATE LIMITED NX - Completed | Progress & Review Call |  |  | Progress & Review Call |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Jatin Thakkar | 700 | micropointcomputerspvtltdnx | micropointcomputerspvtltdnx | Previous PM Cockpit |  | SPM108327242902 | Normal | E | Mansi Singh | Prathamesh Mandavkar |  | SAAS | 2024-02-29 | 2024-03-22 | 2024-07-15 | Conversion | Spine HRMS | Onsite | 132 | Completed
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed | 403 | 66 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for TORQUE INSURANCE BROKING PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - TORQUE INSURANCE BROKING PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | torqueinsurancebrokingpvtltd |  | Previous PM Cockpit
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed | 391 | 146 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for POLMOR STEEL PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - POLMOR STEEL PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | polmorsteelpvtltd |  | Previous PM Cockpit
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed | 391 | 207 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ACEY ENGINEERING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ACEY ENGINEERING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | aceyengineeringpvtltd |  | Previous PM Cockpit
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed | 378 | 41 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ATHARVA FACILITY MANAGEMENT AND SECURITY; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ATHARVA FACILITY MANAGEMENT AND SECURITY - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | atharvafacilitymanagementandsecurity |  | Previous PM Cockpit
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 | 2026-09-30 | Low | Completed | 386 | 386 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | MEDIPULSE HOSPITAL | 8316 | Account Activated | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. August salary on monday | Using only the HRMS Module, payroll is now initiated | 98 | Aug-26 | Varun Rajbhar | 731 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - MEDIPULSE HOSPITAL - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Varun Rajbhar | Vasu Mohan Dusa | Manisha Singh | 731 | medipulsehospital | medipulsehospital | Previous PM Cockpit, Book1 |  | SPM110771250109 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-09-06 | 2025-10-09 |  | Fresh | Spine NG | Online | 69 | Completed
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active | 383 |  | Critical | Ageing 383 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | PARADISE GROUP | 8328 | Account Activated | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August |  | 97 |  | Pritesh Barot | 624 | Spine NG | SAAS | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Project Status Update - PARADISE GROUP - Datafile Explanation | Backend working is ongoing, training & implementation is planned. |  |  | Backend working is ongoing, training & implementation is planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Pritesh Barot | Vasu Mohan Dusa | Ankur Yewalekar | 624 | paradisegroup | paradisegroup | Previous PM Cockpit |  | SPP110783251209 | Premium | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2025-09-12 | 2025-09-23 |  | Fresh | Spine NG | Online | 68 | Completed
5093 | Escalation | DRS EARTHWORK PRIVATE LIMITED | Schedule | 2025-09-24 | 2025-11-28 | Low | Completed | 371 | 65 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | DRS EARTHWORK PRIVATE LIMITED | 7872 | Account Activated | payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we have deleted salary for Apr-25 to Mar-26, and uploaded past salary data for all emps, Now user will process Apr & May this week and will get back to us incase of any query by 27-Jun. client will do june salary by own which will be parallel. As per feedback user said no queries if it is will let you know as I am on leave connected today for july salary As per the discussion done with Shital ji, major emps are in the field, and are not willing to mark attendance through mobile. HRMS is utilitised by approx 100 emps but live disbursement is done through excel and they will process salary in Spine for record keeping purpose only As per the feedback received from user Ms. Shital, the client is currently using the HRMS, but the process is partially manual and partially system-based. For employees who work outside the office, proper in/out punches are not recorded, so their attendance is managed manually. For employees working in the office, attendance is recorded through the system. The client uses the system for attendance summary reports and collect leave data; however, salary processing is still done manually based on these reports. Currently she has a few minor query. We told her to share the queries on the support ticket ID for further assistance. |  | 97 |  | Mihir Navnath Mungekar | 200 | Spine HRMS | SAAS | SCH Project Remark | As per the latest SCH project remark: payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we hav... Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | Project Status Update - DRS EARTHWORK PRIVATE LIMITED - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Tejas Kareliya | 200 | drsearthworkpvtltd | drsearthworkpvtltd | Previous PM Cockpit |  | SPD110360252904 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-05-05 | 2025-06-16 | 2026-05-15 | Fresh | Spine HRMS | Online | 82 | Live Salary Processing
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost | 366 | 211 | High | Tracker status 'Lost' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | CENTRE FOR URBANIZATION BUILDINGS | 8381 | Account Activated | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on |  |  | 0 |  | 95 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on. Tracker status is Lost; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Active'. | Project Status Update - CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Roopa S | 95 | centreforurbanizationbuildingsandenvironmentcubeiitm | centreforurbanizationbuildings | Previous PM Cockpit |  | SPC110823252909 | Normal | E | Disha Kiran Kargutkar |  | Saurabh Thakur | SAAS | 2025-09-29 | 2025-10-02 |  | Fresh | Spine NG | Online | 67 | Datafile Explanation
5095 | Escalation | PISCES CONTAINER LINES INDIA PVT. LTD. | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | 352 | 15 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | PISCES CONTAINER LINES INDIA PVT. LTD. | 2522 | Account Activated |  |  | 0 | 0 | Pritesh Barot | 100 | Spine HRMS | SAAS | Manual PM Note | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated. | Project Status Update - PISCES CONTAINER LINES INDIA PVT. LTD. - Completed | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated |  |  | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated |  | No | Approved Alias | 1 | 2 | TRUE | [5 empty] | Pritesh Barot | Vasu Mohan Dusa | Kunal Joshi | 100 | piscescontainerlinesindiapvtltd | piscescontainerlinesindiapvtltd | Previous PM Cockpit |  | SPP105402212702 | Normal | E | Jyoti Mishra | Viral Panchal |  | SAAS | 2021-08-10 | 2021-08-19 | 2021-11-11 | Fresh | Spine HRMS | Onsite | 150 | Completed
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | 352 | 15 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for AUROUS JEWELS LLP; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - AUROUS JEWELS LLP - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | aurousjewelsllp |  | Previous PM Cockpit
5097 | Allocation | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Schedule | 2025-10-08 | 2026-04-28 | Low | Completed | 357 | 202 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | 8409 | Account Activated | Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on |  | 100 | Sep-26 | Mihir Navnath Mungekar | 135 | Spine HRMS | SAAS | SCH Project Remark | As per the latest SCH project remark: Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | Project Status Update - HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Amarprit Kaur | 135 | hardcarbtechpvtltdvautidshahhardfacepvtltdstafflicense | hardcarbtechpvtltdstaff | Previous PM Cockpit |  | SPH110833253009 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-10-08 | 2025-10-17 | 2026-05-11 | Fresh | Spine HRMS | Onsite | 66 | Live Salary Processing
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed | 337 | 92 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for RENMAKCH INDIA PVT. LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - RENMAKCH INDIA PVT. LTD. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | renmakchindiapvtltd |  | Previous PM Cockpit
5099 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | 352 | 15 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED FACTORY | 8831 | Account Activated | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | 100 |  | Shubham Gurav | 1600 | Spine HRMS | SAAS | Manual PM Note | Review Meeting. | Project Status Update - GNG ELECTRONICS LIMITED FACTORY - Completed | Review Meeting |  |  | Review Meeting |  | No | Approved Alias | 1 | 3 | TRUE | [5 empty] | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 1600 | gngelectronicsltdfactory | gngelectronicsltdfactory | Previous PM Cockpit |  | SPG109937253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-01-29 | 2026-01-30 | 2026-02-10 | Fresh | Spine HRMS | Online | 47 | Completed
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active | 364 |  | Critical | No approved SCH match; Ageing 364 days from start date | FALSE |  |  |  |  | Datafile Explanation | [7 empty] | Nagendra Poojary |  |  |  | Manual PM Note | PMS Implementation Ongoing. | Project Status Update - WHISTLING WOODS INTERNATIONAL - Datafile Explanation | PMS Implementation Ongoing |  |  | PMS Implementation Ongoing |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | whistlingwoodsintl |  | Previous PM Cockpit, Book1
5101 | Allocation | VIVID ELECTROMECH LTD. / VIVID GROUP | Schedule | 2025-10-30 | 2026-04-28 | Low | Completed | 335 | 180 | Closed | Closed/lost item, monitor only | FALSE | FC Lost | Project was fully completed but later lost. | FC Lost | Completed | Completed | VIVID ELECTROMECH LIMITED | 8476 | Account Activated | #payroll training and impl done- E25nov7138, E25nov8316 E25nov9114 #hrms training and configuration done- E25dec416 #geo tagging and integration done #E25dec4143 November salary also tallied, #dec done- E26jan2964 #feb done with attn have few requirements they were not willing to proceed because of that somehow we are convincing them team is in discussion we are following up for salary #28/09 - no response #FC LOST - As discussed with User Akash, Vivid Electro has decided not to continue using our software. They require certain modifications to the dashboard, along with changes to the hierarchy structure. These requirements are currently not feasible within our software. | Requirement | 96 | Jun-26 | Mihir Navnath Mungekar | 250 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Requirement. Tracker status is Completed; SCH status is FC Lost (Project was fully completed but later lost.). Current milestone: Completed. Current owner/implementation contact: Mihir Navnath Mungekar. | Project Status Update - VIVID ELECTROMECH LTD. / VIVID GROUP - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Ankur Yewalekar | 250 | vividelectromechltdvividgroup | vividelectromechltd | Previous PM Cockpit |  | SPV110891253010 | Normal | E | Ritika Dilip Singh | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-10-30 | 2025-11-19 | 2026-09-30 | Fresh | Spine NG | Onsite | 63 | Completed
5102 | Allocation | SREE METALIKS LTD | Schedule | 2025-11-11 | 2026-04-28 | Low | Completed | 323 | 168 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SREE METALIKS LTD | 8487 | Account Activated | "7th "payroll hr set up done, oct tallied,bio int done, logins done, training done, dec done W26jan10986 client FC |  | 110 | Mar-26 | Nandadeep Mhatre | 700 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - SREE METALIKS LTD - Completed | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Nandadeep Mhatre | Vasu Mohan Dusa | Sumit Kumar | 700 | sreemetaliksltd | sreemetaliksltd | Previous PM Cockpit |  | SPS110901253110 | Premium | E | Divya Bhide | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-10-31 | 2025-11-17 | 2026-03-10 | Fresh | Spine NG | Online | 62 | Completed
5103 | Escalation | NAGRIK CONSULTANCY SERVICES | Schedule | 2025-11-10 | 2026-02-27 | Low | Completed | 324 | 109 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | NAGRIK CONSULTANCY SERVICES | 8434 | Account Activated | completed Payroll training .-W25oct5654 completed with HRMS training on 1st Phase with Add on service. processed and tally the salary of Sep 2025 month for all 3 grades for126 employees. processed the salary of Oct 2025 month.- W25nov634 Employee training and logins roll out processed Salary for Nov 2025, for Midas touct MT, NHO, with attendance and tallied the same November salary processed December salary processed Jan salary done. Feb salary done. March salary done. april salary done may salary processed june salary processed As per feedback user Ms. Suvarna said No queries as such we are getting support which we required. June salary is in process. user said no queries and concern if we have we raised the mail as we asked mansi ji has escalated the attendance queries it has been resolved | Suggestion ID: 3709 Requirement: Leave Year Selection in Mobile Application Suggestion ID: 3536 Requirement: Add-On Service Request and Approval Option in Mobile Application | 100 | Aug-26 | Aditya Mazire | 205 | Spine NG | SAAS | Manual PM Note | Progress & Review Call. | Project Status Update - NAGRIK CONSULTANCY SERVICES - Completed | Progress & Review Call |  |  | Progress & Review Call |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Nandini Tiwari | 205 | nagrikconsultancyservices | nagrikconsultancyservices | Previous PM Cockpit |  | SPN110876251610 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-10-18 | 2025-10-25 | 2026-06-15 | Fresh | Spine NG | Onsite | 64 | Live Salary Processing
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS - RATNAGIRI LOC | 8547 | Account Activated | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also." | 98 | Aug-26 | Aditya Mazire | 180 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Aparna Santosh | 180 | naikmotorsnaikmahindraratnagiriloc | naikmotorsratnagiriloc | Previous PM Cockpit, Book1 |  | SPN110948251311 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-13 | 2025-12-22 |  | Fresh | Spine NG | Online | 60 | Completed
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed | 316 | 71 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ANUH PHARMA PVT. LTD NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ANUH PHARMA PVT. LTD NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | anuhpharmapvtltdnx |  | Previous PM Cockpit
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS -GOA LOC | 8531 | Account Activated | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn july done Aug sal done add module after 10th oct we will ask client. sept live sal will do. |  | 88 | Aug-26 | Aditya Mazire | 410 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS -GOA LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Sandeep Ashok Joundal | 410 | naikmotorsgoaloc | naikmotorsgoaloc | Previous PM Cockpit, Book1 |  | SPN110937250811 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-08 | 2025-12-17 |  | Fresh | Spine NG | Online | 61 | Completed
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed | 308 | 93 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for PPKG AND CO; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - PPKG AND CO - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | ppkgandco |  | Previous PM Cockpit
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed | 331 | 86 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for DOSHI MEDICARE PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - DOSHI MEDICARE PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | doshimedicarepvtltd |  | Previous PM Cockpit
5109 | Allocation | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Schedule | 2025-11-26 | 2026-07-31 | Low | Completed | 308 | 247 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Datafile Explanation | FEATHERTOUCH LEARNING PRIVATE LIMITED | 8600 | Account Activated | welcome mail done #3/12 - eng - Corp ID done, datafiles awaiting #22/12 - no response Non Payroll Master Data received and uploaded. Salary Calculation received and configured. #19/01 - eng - salary processed, shared register to client for verification, waiting for reply Payroll Training and Implementation Completed W26jan4046. Mobile HR Training Completed W26jan5841. 19/01 - User is on leave and will connect on 21/01 for salary processing. SMTP Configuration Completed #W26jan7987. Location Configuration Completed #W26jan7983. HRMS Training Completed #W26jan8122. December 2025 Salary Completed #E26jan11453. January 2026 Salary Completed #W26feb6498. 08/04 - February processed and tallied, awaiting confirmation. User is too busy in internal work. Attendance Policy changes done. User will process salary by 15/04. #10/4 - busy February 2026 Salary Completed E26apr9176. Roll Out Completed E26apr9176. 24/04 - As per discussion, user not able to process March salary due to license count exhausted. In April as well count is exceeded. User is in discussion with management to increase the license count. User will discuss internally and will update. March salary will be processed post license update. #14/05 - eng - Non payroll employees april processed. Payroll employees configuration is completed and client will process salary in few days #1/06 - eng - in last schedule, they processed may salary with attendance. #W26may11974 - may salary conf. #25/06 - eng -All configuration done and training completed. Till May salary done but May confirmation not received as the Payroll user left the organization so coordinating with another user for all the processes. Now user have shared some changes in the calculation for Payroll category employees so we are finding a way to configure this. From June month user will process the salary with attendance data as they have some internal issues with the attendance. June 2026 Salary Completed with Attendance W26jul873. #10/08 - feedback good and positive #24/09 - regarding renewal as discussed with our accounts team, partner has rcvd the payment from user end, however, payment from partner is still pending. #5/10 - as discussed with our accounts team, partner has released the payment to spine. |  | 100 | Sep-26 | Sunita Yadav | 500 | Spine NG | SAAS | Manual PM Note | Need to discuss internally for live processing. | Project Status Update - FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE - Datafile Explanation | Need to discuss internally for live processing |  |  | Need to discuss internally for live processing |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Sunita Yadav | Vasu Mohan Dusa | Roopa S | 500 | feathertouchlearningpvtltdfeathertouhdaycare | feathertouchlearningpvtltd | Previous PM Cockpit, Book1 |  | SPF110994252511 | Normal | E | Ritika Dilip Singh | Saurabh Pednekar | Hiren Bhimani | SAAS | 2025-11-25 | 2025-12-30 | 2026-07-15 | Fresh | Spine NG | Online | 58 | Live Salary Processing
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed | 305 | 121 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for COSMOS IMPEX INDIA PVT LTD NG; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - COSMOS IMPEX INDIA PVT LTD NG - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | cosmosimpexindiapvtltdng |  | Previous PM Cockpit
5111 | Allocation | NIKIKA ENTERPRISES LLP | Schedule | 2025-11-29 | 2026-05-26 | Low | Completed | 305 | 178 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | NIKIKA ENTERPRISES LLP | 8623 | Account Activated | go live - training and impl done april processed |  |  | Apr-26 |  | 175 | Spine NG | SAAS | Manual PM Note | Arpit informed that Partner team was not available, informed him to push and. | Project Status Update - NIKIKA ENTERPRISES LLP - Completed | Arpit informed that Partner team was not available, informed him to push and |  |  | Arpit informed that Partner team was not available, informed him to push and |  | No | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Roopa S | 175 | nikikaenterprisesllp | nikikaenterprisesllp | Previous PM Cockpit |  | SPN111014252911 | Normal | E | Mansi Singh |  | Saurabh Thakur | SAAS | 2025-11-29 | 2025-12-03 | 2026-05-19 | Fresh | Spine NG | Onsite | 56 | Completed
5112 | Allocation | PRIJAI HEAT EXCHANGERS PVT. LTD. | Schedule | 2025-12-10 | 2026-04-28 | Low | Completed | 294 | 139 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | 8619 | Account Activated | Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system |  | 100 | Aug-26 | Goraksha Pawar | 400 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system. Tracker status is Completed; SCH status is FC (Live salary processing is complete and client is on watch list.). Current milestone: Completed. Current owner/implementation contact: Goraksha Pawar. | Project Status Update - PRIJAI HEAT EXCHANGERS PVT. LTD. - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Amarprit Kaur | 400 | prijaiheatexchangerspvtltd | prijaiheatexchangerspvtltdng | Previous PM Cockpit |  | SPP111012252911 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-12-10 | 2026-01-02 | 2026-03-11 | Fresh | Spine NG | Onsite | 57 | Live Salary Processing
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed | 281 | 36 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for parvathyhospital; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - parvathyhospital - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | parvathyhospital |  | Previous PM Cockpit
5114 | Allocation | PANKAJ FASHION PVT LTD | Schedule | 2026-01-09 | 2026-08-11 | Low | Lost | 264 | 214 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | PANKAJ FASHION PVT LTD | 8782 | Account DeActivated | "10th, 15th, 25th" 110 emp- E26jan8973, payroll hr set up done, training done, int done, logins done, meeting done- workers not stable hence unable to share accurate data, meeting done may target, later will share data ot policy pending W26jun7203, contractual basic- change- card assign Director has not confidence on his user, Client LOST- Director dont have confidence on his user, meeting done onsite but not productive. Director has stopped receiving calls, client deactivated | Resource Problem | 88 | May-26 | Arpit Patel | 1001 | Spine NG | SAAS | Manual PM Note | Onsite Visit planned for 15th June. | Project Status Update - PANKAJ FASHION PVT LTD - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  | Onsite Visit planned for 15th June |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Deepak Choubisia | 1001 | pankajfashionpvtltd | pankajfashionpvtltd | Previous PM Cockpit, Book1 |  | SPP111159260801 | Premium | E | Divya Bhide | Amey Telge | Viral Panchal | SAAS | 2026-01-08 | 2026-01-28 | 2026-08-20 | Fresh | Spine NG | Online | 49 | Completed
5115 | Allocation | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Schedule | 2026-01-16 | 2026-04-28 | Low | Lost | 257 | 102 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | RAJESHWARI INFOTEL PVT. LTD | 8709 | Account DeActivated | payroll hr set up done, jan tallied, payroll hr training done, onboard impl going on- client lost report as per their req not possible, had taken on trail basis, they will continue with TCS | Another Software | 56 | Feb-26 | Riddhi Pramod Sutar | 1200 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Another Software. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Riddhi Pramod Sutar. | Project Status Update - RAJESHWARI INFOTEL PVT. LTD. (RIPL) - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Riddhi Pramod Sutar | Vasu Mohan Dusa | Sumit Kumar | 1200 | rajeshwariinfotelpvtltdripl | rajeshwariinfotelpvtltd | Previous PM Cockpit |  | SPR111093252212 | Normal | E | Karuna Rajaram Sandim |  | Hiren Bhimani | SAAS | 2025-12-22 | 2026-01-08 | 2026-05-12 | Fresh | Spine NG | Online | 55 | Completed
5116 | Escalation | GNG ELECTRONICS LIMITED STAFF | Maketing | 2026-01-19 | 2026-01-22 | Low | Completed | 254 | 3 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED STAFF | 7377 | Account Activated | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535 |  | 100 | Mar-26 | Shubham Gurav | 400 | Spine NG | SAAS | Manual PM Note | plan activities in 2days. | Project Status Update - GNG ELECTRONICS LIMITED STAFF - Completed | plan activities in 2days. |  |  | plan activities in 2days. |  | No | Approved Alias | 1 | 2 | TRUE | [5 empty] | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 400 | gngelectronicsltdstaff | gngelectronicsltdstaff | Previous PM Cockpit |  | SPG109930253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2025-01-31 | 2025-02-17 | 2025-06-10 | Fresh | Spine NG | Onsite | 107 | Completed
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed | 260 | 76 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for Talib and Shamsi Constructions Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Talib and Shamsi Constructions Pvt. Ltd. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | talibandshamsiconstructionspvtltd |  | Previous PM Cockpit
5118 | Escalation | Seventy Seven Entertainment Pvt Ltd | Schedule | 2026-01-19 | 2026-03-30 | Low | Completed | 254 | 70 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 4067 | Account Activated | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us. |  | 100 | April-23 | Pritesh Barot | 250 | Spine HRMS | On-Premises | Manual PM Note | Datafiles Received, Implementation planned, Team to followup. | Project Status Update - Seventy Seven Entertainment Pvt Ltd - Completed | Datafiles Received, Implementation planned, Team to followup |  |  | Datafiles Received, Implementation planned, Team to followup |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Pritesh Barot | Vasu Mohan Dusa | Nikhil Solanki | 250 | seventysevenentertainmentpvtltd | seventysevenentertainmentpvtltd | Previous PM Cockpit |  | SPS101600122310 | Normal | C | Usha Gupta | Viral Panchal |  | On-Premises | 2023-02-09 | 2023-02-28 | 2023-06-06 | Conversion | Spine HRMS | Onsite | 144 | Completed
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active | 268 |  | Critical | No approved SCH match; Ageing 268 days from start date | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Manual PM Note | Implementation Demo fixed for 8th May. | Project Status Update - SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED - Datafile Explanation | Implementation Demo fixed for 8th May |  |  | Implementation Demo fixed for 8th May |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | suvarnadurgagroupsdgsuvarnadurgapaperboardspvtltd |  | Previous PM Cockpit, Book1
5120 | Allocation | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Schedule | 2026-01-31 | 2026-04-28 | Low | Completed | 242 | 87 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | 9521 | Account Activated | Training done Client is live processing. Time sheet module also live. |  | 0 | 0 |  | 710 | Spine NG | SAAS | Manual PM Note | Informed Vinay to Send a status mail. | Project Status Update - ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP - Completed | Informed Vinay to Send a status mail |  |  | Informed Vinay to Send a status mail |  | No | Approved Alias | 1 | 3 | TRUE | [6 empty] | Vasu Mohan Dusa | Roopa S | 710 | arssteelsalloyintlpvtltdarsgroup | arssteelsalloyintlpvtltd | Previous PM Cockpit |  | SPA111227263101 | Normal | E | Disha Kiran Kargutkar |  | Saurabh Thakur | SAAS | 2026-07-07 | 2026-07-07 | 2026-08-07 | Fresh | Spine NG | Online | 15 | Completed
5121 | Allocation | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Schedule | 2026-02-09 | 2026-05-26 | Low | Completed | 233 | 106 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | VED INDUSTRIES POC | 8886 | Account DeActivated | employee master uploaded attn was there priority attn integration done currently their main focus in only on attendance mail lic follow up ongoing ankur and vasu will co-ordinate with client opted on premises lic |  | 58 |  | Dhanashree Dalvi | 300 | Spine HRMS | SAAS | Manual PM Note | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Project Status Update - VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE - Completed | Feedback is positive, User to resolve internal issues and plan for live processing from June. |  |  | Feedback is positive, User to resolve internal issues and plan for live processing from June. |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Dhanashree Dalvi | Vasu Mohan Dusa | Ankur Yewalekar | 300 | vedindustriesrohidagrouppoclicense | vedindustriespoc | Previous PM Cockpit |  | SPV111249260602 | Premium | E | Mansi Singh | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-02-06 | 2026-03-06 | 2026-06-24 | Fresh | Spine HRMS | Onsite | 44 | Completed
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed | 219 | 64 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for Procon RMC; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Procon RMC - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | proconrmc |  | Previous PM Cockpit
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed | 215 | 60 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | 8713 | Account Activated | set up & training done, jan done, feb done later client is not responding to calls n mails |  | 100 | Feb-26 | Komal Kanadiya | 1400 | Spine NG | Hosting | SCH Project Remark | As per the latest SCH project remark: set up & training done, jan done, feb done later client is not responding to calls n mails. Tracker status is Completed; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Active'. | Project Status Update - EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 1400 | evergreenhousekeepingservicespvtevergreenfacilitysolutions | evergreenhousekeepingservicespvt | Previous PM Cockpit |  | SPE111097252312 | Escalated | C | Divya Bhide | Hiren Bhimani | Hiren Bhimani | Hosting | 2025-12-23 | 2026-01-07 |  | Fresh | Spine NG | Online | 54 | Datafile Explanation
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed | 217 | 62 | Critical | Held-up status needs management intervention | TRUE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Completed | SUNRISE FOODS BANGALORE | 8720 | Account Activated | Payroll Training completed July month salary processed and tallied. HRMS Training done. client were using hrms attendance for 2 months but after that they were not using are not taking interest for payroll module. after a multiple followup for aug salary aug sal done followup is going on for sept sal but no response. Not responding calledMr. Jeson he said will let us know in 2 days. afte 2-3 days we are calling and doing mail but no response. Held up- Payroll training has been completed. July salary was processed and successfully tallied. HRMS training has also been completed. The client was using HRMS attendance for around two months; however, they have not been actively using the system thereafter and are currently not showing much interest in the Payroll module. Follow-ups are currently ongoing for the September salary processing, but there has been no response from the client. We contacted Mr. Jeson, who informed us that he would provide an update within two days. However, even after 2–3 days, despite repeated calls and email follow-ups, we have not received any further response from the client. The client is currently not responding to our calls or follow-ups. | No Response - No Reason | 88 | Jul-26 | Tushar More | 50 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention. | Project Status Update - SUNRISE FOODS BANGALORE - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Tushar More | Vasu Mohan Dusa | Roopa S | 50 | sunrisefoodsbangalore | sunrisefoodsbangalore | Previous PM Cockpit |  | SPS111104252912 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-12-29 | 2026-01-17 | 2026-09-30 | Fresh | Spine NG | Online | 53 | Datafile Explanation
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed | 218 | 34 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for NOTCH INDIA PROJECTS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - NOTCH INDIA PROJECTS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | notchindiaprojects |  | Previous PM Cockpit
5126 | Escalation | Elixrr Industries Pvt. Ltd. | Maketing | 2026-02-10 | 2026-04-28 | Low | Completed | 232 | 77 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | ELIXRR INDUSTRIES PVT LTD. | 4199 | Account Activated | Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817 |  | 100 | Jun-23 | Krishna Yadav | 1078 | Spine HRMS | SAAS | SCH Project Remark | As per the latest SCH project remark: Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Krishna Yadav. | Project Status Update - Elixrr Industries Pvt. Ltd. - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Krishna Yadav | Vasu Mohan Dusa | Kishan Joshi | 1078 | elixrrindustriespvtltd | elixrrindustriespvtltd | Previous PM Cockpit |  | SPE107169232103 | Normal | E | Nilima Karmokar | Ganesh Jadhav |  | SAAS | 2023-03-21 | 2023-04-19 | 2023-07-14 | Fresh | Spine HRMS | Onsite | 143 | Completed
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed | 229 | 45 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for GUARDIAN CASTING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - GUARDIAN CASTING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | guardiancastingpvtltd |  | Previous PM Cockpit
5128 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2026-02-25 | 2026-03-30 | Low | Completed | 217 | 33 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED FACTORY | 8831 | Account Activated | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | 100 |  | Shubham Gurav | 1600 | Spine HRMS | SAAS | Manual PM Note | Review Meeting. | Project Status Update - GNG ELECTRONICS LIMITED FACTORY - Completed | Review Meeting |  |  | Review Meeting |  | No | Approved Alias | 1 | 3 | TRUE | [5 empty] | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 1600 | gngelectronicsltdfactory | gngelectronicsltdfactory | Previous PM Cockpit |  | SPG109937253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-01-29 | 2026-01-30 | 2026-02-10 | Fresh | Spine HRMS | Online | 47 | Completed
5129 | Allocation | STORM FINANCIAL SERVICES | Schedule | 2026-03-28 | 2026-07-31 | Low | Lost | 186 | 125 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | STORM FINANCIAL SERVICES | 9081 | Account DeActivated | Completed Payroll training and also processed February 26 payroll and matched.-E26apr3050 completed all the training, also provided login access to employee-E26apr3347. completed with March Salary process for 391 employees.-E26apr4776. April month payroll has been processed, and payslip has been published for the employees. -E26may5873. Held up-As per the discussion with the client during the onsite visit by engineer mukesh the client is not ready to continue with the Spine. They have decided to develop and implement their own in-house software. | Another Software | 100 | Apr-26 | Mukeshkumar Shojiram kumavat | 410 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration is planned. | Project Status Update - STORM FINANCIAL SERVICES - Completed | April Salary Process and Tally done, Attendance Integration is planned. |  |  | April Salary Process and Tally done, Attendance Integration is planned. |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mukeshkumar Shojiram kumavat | Vasu Mohan Dusa | Utsavi Setu | 410 | stormfinancialservices | stormfinancialservices | Previous PM Cockpit, Book1 |  | SPS111411262803 | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-03-28 | 2026-04-01 | 2026-07-10 | Fresh | Spine NG | Onsite | 39 | Completed
5130 | Escalation | CIRCLE RESOURCES PRIVATE LIMITED | Schedule | 2026-03-12 | 2026-03-30 | Low | Completed | 202 | 18 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Completed | CIRCLE RESOURCES PRIVATE LIMITED | 7954 | Account Activated | WELCOME MAIL DONE WILL PROCEED WITH THIS BY 10TH JUNE - E25jun3240 SPLITTING DONE training and impl done Oct 2025 salary processed - E25nov2426 from spine Disbursement date - 11th of every month. processing salaries parallely additional rule techical given by hemant sir on friday Engineer mayur has restored the database after that we will check and update the client as viral sir said till thursday we will connect client as mayur is onsite. One month extension is given by accounts team. As discussed with Mayur, some policies and shifts were removed as per the client’s requirements. A solution was provided for attendance recalculation, regularisation, and lock/unlock of attendance for 7 days at a time. The client will check and monitor the solution for one month. The salary disbursement date is the 7th of every month. After September salary processing and one month of observation, the client will decide on renewal. | Disbursement date by 15th | 91 | Jun-26 | Mayur Pendhari | 1700 | Spine HRMS | SAAS | Manual PM Note | Progress & Review Call. | Project Status Update - CIRCLE RESOURCES PRIVATE LIMITED - Completed | Progress & Review Call |  |  | Progress & Review Call |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Nirbhay Kumar | 1700 | circleresourcespvtltd | circleresourcespvtltd | Previous PM Cockpit |  | SPC110448252805 | Premium | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-05-28 | 2025-06-17 | 2026-06-15 | Fresh | Spine HRMS | Online | 78 | Live Salary Processing
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active | 181 |  | Critical | Ageing 181 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | 9142 | Account Activated | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) target live sep live salary |  | 0 | Jun-26 | Riddhi Pramod Sutar | 650 | Spine NG | SAAS | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Project Status Update - SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) - Datafile Explanation | Confirm milestone progress and next client action. |  |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Riddhi Pramod Sutar | Vasu Mohan Dusa | Utsavi Setu | 650 | symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl | symbiosiscentrefordistancelearningsdcl | Previous PM Cockpit, Book1 |  | SPS111464263103 | Premium | E | Karuna Rajaram Sandim |  | Hiren Bhimani | SAAS | 2026-04-02 | 2026-05-20 |  | Fresh | Spine NG | Online | 37 | Datafile Explanation
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active | 177 |  | Critical | Held-up status needs management intervention | FALSE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Kick Off Meeting | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | 9121 | Account Activated | Basic payroll training has been completed. W26jul9046 Client is occupied in a full-day meeting today. T As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. not responding whatsapp group msg as their bal payment pending called Mr. Ganesh yesterday for issues and concern and recommend outsourcing options. they said will check and inform you. Held up-Basic Payroll training has been completed. Ticket reference: W26jul9046. The client was occupied in a full-day meeting today. The client is currently not responding to messages in the WhatsApp group, and the balance payment is also pending. We called Mr. Ganesh yesterday to understand the current issues and concerns and also discussed the option of outsourcing payroll processing. Mr. Ganesh informed us that they would check internally and get back to us. However, we have not received any further response from the client yet. The client currently does not have a dedicated resource for the software, and due to limited availability of the client/resource, they are unable to spend sufficient time on software utilisation and payroll activities. | Resource Problem | 10 | Mar-26 | Vikas Yadav | 300 | Spine NG | SAAS | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Project Status Update - SHRI JANARDAN SWAMI HOSPITAL (SJS) - Kick Off Meeting | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  |  | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Vikas Yadav | Vasu Mohan Dusa | Nandini Tiwari | 300 | shrijanardanswamihospitalsjs | rashtrasantjanardhanswamigroupofinstitutes | Previous PM Cockpit, Book1 |  | SPR111446263103 | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-04 | 2026-06-30 | 2026-09-30 | Fresh | Spine NG | Online | 38 | Datafile Explanation
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | 176 | 115 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | RUPA SOLUTIONS PRIVATE LIMITED | 9146 | Account Activated | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744 |  | 100 | Aug-26 | Ankush Rampyare Rajbhar | 300 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES - Completed | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  |  | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankush Rampyare Rajbhar | Vasu Mohan Dusa | Ankur Yewalekar | 300 | rupasolutionspvtltdrupagrouprupaproperties | rupasolutionspvtltd | Previous PM Cockpit, Book1 |  | SPR111468263103 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-07 | 2026-04-16 |  | Fresh | Spine NG | Onsite | 36 | Datafile Explanation
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active | 174 |  | High | Ageing 174 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | TRIO JEWELS PVT LTD | 9191 | Account Activated | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Aug-26 | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD - Datafile Explanation | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  |  | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mukeshkumar Shojiram kumavat | Vasu Mohan Dusa | Vaishali Ramniklal | 301 | triojewelspvtltd | triojewelspvtltd | Previous PM Cockpit, Book1 |  | SPT111502260904 | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-04-09 | 2026-04-24 |  | Fresh | Spine NG | Onsite | 34 | Completed
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active | 161 |  | High | No approved SCH match; Ageing 161 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Project Status Update - VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED - Kick Off Meeting | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | voguenhydepvtltdmodapellebagsaccessoriespvtltd |  | Previous PM Cockpit, Book1
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed | 160 | 33 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Manual PM Note | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Project Status Update - Navio Shipping - Completed | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  |  | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  | No | No Match | 0 | 0 | TRUE | [9 empty] | navioshipping |  | Previous PM Cockpit
5137 | Escalation | VIPUL ORGANICS LTD. - STAFF | Schedule | 2026-05-01 | 2026-05-26 | Low | Completed | 152 | 25 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | VIPUL ORGANICS LTD. - STAFF | 2919 | Account Activated | Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745 |  | 0 | 0 | Santosh Yadav | 145 | Spine HRMS | SAAS | SCH Project Remark | As per the latest SCH project remark: Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Santosh Yadav. | Project Status Update - VIPUL ORGANICS LTD. - STAFF - Completed | [5 empty] | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Santosh Yadav | Vasu Mohan Dusa | Nikhil Solanki | 145 | vipulorganicsltdstaff | vipulorganicsltdstaff | Previous PM Cockpit |  | SPV106083220301 | Premium | E | Aisha Patel | Hemanshu Wadia |  | SAAS | 2022-01-06 | 2022-01-17 | 2022-06-15 | Conversion | Spine HRMS | Onsite | 149 | Completed
5138 | Allocation | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Schedule | 2026-05-04 | 2026-08-31 | High | Lost | 149 | 119 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | 9280 | Account DeActivated | Project Lost -Mr. Ravi informed us that they will not be renewing the software due to low utilization by their staff & a lack of acceptance of automation within the organization. He appreciated our software and support; however, management has decided not to continue with the renewal. Welcome maild on 4th May Project delivery rcvd Training & Implementation of Payorll is completed along with April month tallied - HRMS modules Training & Implementation is done Attendance integration is done Logins rolled out to employees - E26may6183 Live salary with attednace proceed of June month for some employees | July wth attendance | 85 | Jun-26 | Mihir Navnath Mungekar | 400 | Spine NG | SAAS | Manual PM Note | Implementation & Training has been completed. Vinay is aligning a review meeting. | Project Status Update - NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM - Kick Off Meeting | Implementation & Training has been completed. Vinay is aligning a review meeting. |  | 8th May | Implementation & Training has been completed. Vinay is aligning a review meeting. |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Nandini Tiwari | 400 | nivanbalajiautomoverspvtltdbalajikiacarshowroom | nivanbalajiautomoverspvtltd | Previous PM Cockpit, Book1 |  | SPN111575260205 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-05-04 | 2026-05-26 | 2026-08-05 | Fresh | Spine NG | Online | 27 | Completed
5139 | Allocation | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Schedule | 2026-05-06 | 2026-08-31 | High | Completed | 147 | 117 | Closed | Closed/lost item, monitor only | FALSE | FC | Live salary processing is complete and client is on watch list. | Fully Complete | Live Salary Processing | Kick Off Meeting | CAM TOOLS INDUSTRIES PVT LTD | 9261 | Account Activated | Project Live- Training & Implementation is done along with April month tallied - W26may10013 Attendance inetgration is done Logins rolled out June month with attednace done & July month processed with attedance Leave policy is pending from client's end, they will share as per their convience- E26sep4961 processed Live salary for the month of August- E26sep3629 |  | 100 | Aug-26 | Harsh Dilip Ashar | 315 | Spine NG | SAAS | Manual PM Note | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Project Status Update - CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM - Kick Off Meeting | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. |  | 8th May | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Harsh Dilip Ashar | Vasu Mohan Dusa | Tejas Kareliya | 315 | camtoolsindustriespvtltddigitaltoolroom | camtoolsindustriespvtltd | Previous PM Cockpit, Book1 |  | SPC111560263004 | Normal | E | Ankita Bankar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2026-05-05 | 2026-05-20 | 2026-09-11 | Fresh | Spine NG | Onsite | 29 | Live Salary Processing
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed | 152 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | Project Status Update - GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG - Kick Off Meeting | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  | 4th May | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | gngelectronicsltdelectronicsbazaarforstafflicenseconversiontong |  | Previous PM Cockpit, Book1
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active | 152 |  | High | Ageing 152 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | TRIO JEWELS PVT LTD | 9191 | Account Activated | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Aug-26 | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD Contractual - Kick Off Meeting | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | 8th May | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mukeshkumar Shojiram kumavat | Vasu Mohan Dusa | Vaishali Ramniklal | 301 | triojewelspvtltdcontractual | triojewelspvtltd | Previous PM Cockpit, Book1 |  | SPT111502260904 | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-04-09 | 2026-04-24 |  | Fresh | Spine NG | Onsite | 34 | Completed
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Ageing 135 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | EMPREO PREMIUM PVT LTD | 8919 | Account Activated | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 80 | Mar-26 | Goraksha Pawar | 105 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - EMPREO PREMIUM PVT LTD - Datafile Explanation | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | 8th May | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Tejas Kareliya | 105 | empreopremiumpvtltd | empreopremiumpvtltd | Previous PM Cockpit, Book1 |  | SPE111274261802 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-02-18 | 2026-03-25 |  | Fresh | Spine NG | Online | 43 | Datafile Explanation
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Ageing 135 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | EMPREO WHEEL PVT LIMITED (MG) | 8958 | Account Activated | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 65 | Apr-26 | Goraksha Pawar | 150 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - EMPREO WHEEL PVT LIMITED (MG) - Datafile Explanation | Same |  | 8th May | Same |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Swati Sangani | 150 | empreowheelpvtltdmg | empreowheelpvtltdmg | Previous PM Cockpit, Book1 |  | SPE111306262702 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-16 | 2026-05-28 |  | Fresh | Spine NG | Online | 41 | Datafile Explanation
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | SHREEKHETRA AUTOMOTIVE (TATA) | 8957 | Account DeActivated | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 4 | 0 | Goraksha Pawar | 200 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - SHREEKHETRA AUTOMOTIVE (TATA) - Kick Off Meeting | Same |  | 8th May | Same |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Tejas Kareliya | 200 | shreekhetraautomotivetata | shreekhetraautomotivetata | Previous PM Cockpit, Book1 |  | SPS111305262702 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-15 |  | 2026-10-02 | Fresh | Spine NG | Online | 42 | Completed
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active | 134 |  | High | Ageing 134 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | AMAL EMBROIDERIES PRIVATE LIMITED | 9304 | Account Activated | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. As per call accounts team is connected for payment with user Aparna. Only add mod pms left which will be done in the month of november directly. |  | 91 | Aug-26 | Vijay Bugde | 1200 | Spine NG | SAAS | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Project Status Update - AMAL EMBROIDERIES PVT. LTD - Datafile Explanation | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | 4th May | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Vijay Bugde | Vasu Mohan Dusa | Ankur Yewalekar | 1200 | amalembroideriespvtltd | amalembroideriespvtltd | Previous PM Cockpit, Book1 |  | SPA111591261305 | Premium | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-05-19 | 2026-06-04 |  | Fresh | Spine NG | Onsite | 25 | Completed
5146 | Escalation | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Schedule | 2026-05-19 | 2026-07-31 | High | Completed | 134 | 73 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | AEGIS PRECISION PVT LTD | 4763 | Account Activated | Files & Policy awaiting, training from 18th. training completed #287080, logins will be shared by 1st week of sep, logins will be shared by 16th sep Training completed, Logins will share as per their convenient. #302271 |  | 0 | 0 | Goraksha Pawar | 172 | Spine HRMS | SAAS | Manual PM Note | Review Meeting pending. | Project Status Update - AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD - Completed | Review Meeting pending. |  | 4th May | Review Meeting pending. |  | No | Approved Alias | 1 | 3 | TRUE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Jayesh Mojidra | 172 | aegisprecisionpvtltdshimnitindiapvtltd | aegisprecisionpvtltd | Previous PM Cockpit, Book1 |  | SPA106322220704 | Normal | E | Usha Gupta | Prathamesh Mandavkar |  | SAAS | 2023-08-08 | 2023-08-18 | 2023-10-09 | Fresh | Spine HRMS | Onsite | 138 | Completed
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active | 128 |  | High | Ageing 128 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MULTI ORGANICS PVT LTD | 9257 | Account Activated | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out |  | 95 | Jul-26 | Rajesh Ravindra Panchal | 350 | Spine NG | SAAS | Manual PM Note | KickOff & Datafile Explaination done. | Project Status Update - MULTI ORGANICS PVT LTD - Kick Off Meeting | KickOff & Datafile Explaination done |  | 5th May | KickOff & Datafile Explaination done |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Tejas Kareliya | 350 | multiorganicspvtltd | multiorganicspvtltd | Previous PM Cockpit, Book1 |  | SPM111555263004 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-05-23 | 2026-07-25 |  | Fresh | Spine NG | Onsite | 30 | Datafile Explanation
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost | 127 | 97 | Critical | Held-up status needs management intervention | FALSE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Datafile Explanation | BFMS FACILITY MANAGEMENT PVT LTD | 8728 | Account Activated | (E26aug6724) Project Held Up - Despite our continuous efforts to support and resolve queries and concerns, we have not received the required response from client Implementation and Training session aligned from 13th Jan E26jan1479 W26jan5503 Bfms Payroll Training and December Salary confirmation BFMS will not process with Attendance - W26mar1378 the salary of compliance section is not yet decided (in discussion) post that they will process march on monday team will update the company is shifting to pvt ltd hence they are bsy client not responding properly The client mentioned that they have employees such as delivery personnel working with platforms like Zomato, Swiggy, and Urban Company. These employees typically work for only 4–5 days and then leave the job after comparing their earnings with other platforms, stating that they are being paid less. Due to this high attrition and short working duration, salary processing becomes challenging. We also asked why they opted for the software despite this situation. The user responded that it was a management decision. as per vasu's meting client will be providing data post salary processing of june had a call with user to make her undertsand that all isue can be handled through spine which she is having but she seems not interested | FInds excel easy | 100 | Feb-26 | Amit Krishnakant Tiwari | 500 | Spine NG | SAAS | Manual PM Note | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Project Status Update - BFMS FACILITY MANAGEMENT PVT LTD - Datafile Explanation | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | 5th May | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Amit Krishnakant Tiwari | Vasu Mohan Dusa | Amarprit Kaur | 500 | bfmsfacilitymanagementpvtltd | bfmsfacilitymanagementpvtltd | Previous PM Cockpit, Book1 |  | SPB111113253112 | Normal | E | Ankita Bankar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-12-31 | 2026-01-13 | 2026-09-21 | Fresh | Spine NG | Onsite | 52 | Datafile Explanation
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active | 126 |  | High | Ageing 126 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MANJUSHREE INNOVATIONS PRIVATE LIMITED | 9354 | Account Activated | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. August sal processed by their own but not live- W26sep2587 sept will be target for live sal Attrition &amp; Absenteeism Report Query is going on client want automatic shifts. The September salary will be processed live through Spine for the staff with attendance, while the workers’ attendance will be uploaded manually for salary processing. |  | 76 | Aug-26 | Mayur Pendhari | 370 | Spine NG | SAAS | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Project Status Update - MANJUSHREE INNOVATIONS PVT. LTD - Kick Off Meeting | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | 5th May | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Manisha Singh | 370 | manjushreeinnovationspvtltd | manjushreeinnovationspvtltd | Previous PM Cockpit, Book1 |  | SPM111635262705 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-05-27 | 2026-06-15 |  | Fresh | Spine NG | Online | 24 | Datafile Explanation
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active | 121 |  | High | Ageing 121 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | 9374 | Account Activated | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NG & live target month for processing is August month August month live salary processed - W26aug7425 |  | 79 | Aug-26 | Varun Rajbhar | 550 | Spine NG | SAAS | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Project Status Update - CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Santosh Yadav | Vasu Mohan Dusa | Tejas Kareliya | 550 | cryogasequipmentpvtltdcryogasindia | cryogasequipmentpvtltdng | Previous PM Cockpit, Book1 |  | SPC111653263005 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-06-02 | 2026-06-24 |  | Fresh | Spine NG | Online | 23 | Datafile Explanation
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active | 117 |  | High | Ageing 117 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MANSHA AGENCIES PVT LTD | 9075 | Account Activated | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied june salary upload Aug salary processed integration done Logins roll out by next week. sept will be live sal | User is hospitalized so that’s why data files are received late & implementation is delayed | 80 | Aug-26 | Aditya Mazire | 260 | Spine NG | SAAS | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Project Status Update - Mansha Agencies - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Manisha Singh | 260 | manshaagencies | manshaagenciespvtltd | Previous PM Cockpit, Book1 |  | SPM111405262703 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-03-27 | 2026-06-22 |  | Fresh | Spine NG | Onsite | 40 | Datafile Explanation
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active | 117 |  | High | Ageing 117 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | MUKTANGAN EDUCATION TRUST. NX | 8778 | Account Activated | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly." | 93 |  | Aditya Mazire | 608 | Spine HRMS | SAAS | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Project Status Update - Muktangan Education Trust - Datafile Explanation | Confirm kickoff date, data readiness, and owner. |  |  | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. |  | Yes | Approved Alias | 1 | 2 | TRUE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Manisha Singh | 608 | muktanganeducationtrust | muktanganeducationtrustnx | Previous PM Cockpit, Book1 |  | SPM108453242903 | Normal | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2026-01-06 | 2026-04-18 |  | Fresh | Spine HRMS | Online | 50 | Datafile Explanation
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed | 118 | 57 | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Manual PM Note | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Project Status Update - Vivan Associate - Datafile Explanation | Confirm kickoff date, data readiness, and owner. |  |  | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vivanassociate |  | Previous PM Cockpit, Book1
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active | 114 |  | High | No approved SCH match; Ageing 114 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | Project Status Update - BSA CORPORATION LIMITED / BSA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | bsacorporationltdbsagroup |  | Previous PM Cockpit
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active | 113 |  | High | Ageing 113 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | 9398 | Account Activated | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion |  | 48 | Aug-26 | Ankita Gupta | 500 | Spine NG | SAAS | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Project Status Update - INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankita Gupta | Vasu Mohan Dusa | Ankur Yewalekar | 500 | integratedpestmanagementsolutionsindiapvtltdipmsindia | integratedpestmanagementsolutionsindia | Previous PM Cockpit |  | SPI111677260206 | Normal | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2026-06-09 | 2026-06-17 |  | Fresh | Spine NG | Online | 21 | Datafile Explanation
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active | 112 |  | High | Ageing 112 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | SACRED HEART HOSPITAL JAL | 9392 | Account Activated | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul | 88 |  | Mayur Pendhari | 801 | Spine HRMS | On-Premises | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Project Status Update - SACRED HEART HOSPITAL JAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Jayesh Mojidra | 801 | sacredhearthospitaljal | sacredhearthospitaljal | Previous PM Cockpit |  | SPS111671263005 | Premium | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | On-Premises | 2026-06-10 | 2026-07-27 |  | Fresh | Spine HRMS | Online | 22 | Completed
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active | 105 |  | High | No approved SCH match; Ageing 105 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | Project Status Update - VED INDUSTRIES/ ROHIDA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vedindustriesrohidagroup |  | Previous PM Cockpit
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active | 104 |  | High | No approved SCH match; Ageing 104 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | Project Status Update - ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | itcfortunehotelsiligurickimpromotersllpfortuneselectsiliguri |  | Previous PM Cockpit
5159 | Escalation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Schedule | 2026-06-23 | 2026-07-31 | High | Lost | 99 | 38 | Closed | Closed/lost item, monitor only | FALSE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Datafile Explanation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | 9164 | Account DeActivated | Payroll training done hrms training done april tallied may salary process june salary process integration is pending As per the user's update, due to heavy rainfall, our Director is not present for renewal discussion and therefore the vendor has also not visited. We will update you on mail. Lost- Payroll & HRMS training completed, and June salary was processed. Only biometric integration remained pending. Earlier as informed by Director Amit to Swati Ji that already their existing biometric device did not support integration and a new device was required. Despite multiple follow-ups and discussions, the client did not respond and later informed us they would coordinate with another vendor. Due to delays from client side the integration remained pending and the client ultimately decided to discontinue the software. | Attendance Integration issue | 50 | Jun-26 | Bhavika Gite | 251 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Attendance Integration issue. Tracker status is Lost; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Datafile Explanation. Current owner/implementation contact: Bhavika Gite. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - SHREE DHOLI SATI TEXTILES PRIVATE LIMITED - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Bhavika Gite | Vasu Mohan Dusa | Manisha Singh | 251 | shreedholisatitextilespvtltd | shreedholisatitextilespvtltd | Previous PM Cockpit |  | SPS111486260104 | Premium | E | Disha Kiran Kargutkar | Probian Biswas | Viral Panchal | SAAS | 2026-04-04 | 2026-04-29 | 2026-08-06 | Fresh | Spine NG | Online | 35 | Completed
5160 | Escalation | ANS NG | Schedule | 2026-06-24 | 2026-09-30 | High | Completed | 98 | 98 | Closed | Closed/lost item, monitor only | FALSE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Datafile Explanation | ANS NG | 5883 | Account Activated | Training of Payroll NX is completed - #371589 March, April & May month salary processed. |  | 100 | May-24 | Aditya Mazire | 200 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Training of Payroll NX is completed - #371589 March, April & May month salary processed. Tracker status is Completed; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aditya Mazire. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - ANS NG - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | No | Approved Alias | 1 | 2 | TRUE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Vaishali Ramniklal | 200 | ansng | ansng | Previous PM Cockpit |  | SPA108616242604 | Normal | E | Ankita Bankar | Viral Panchal |  | SAAS | 2024-04-27 | 2024-05-15 | 2024-06-07 | Conversion | Spine NG | Onsite | 128 | Completed
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 | 2026-09-30 | High | Completed | 92 | 92 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | STERLING LIFESTYLE LLP | 8821 | Account Activated | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response |  | 100 | Aug-26 | Aarati Subhashchandra Yadav | 75 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'. | Project Status Update - STERLING LIFESTYLE LLP - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aarati Subhashchandra Yadav | Vasu Mohan Dusa | Amarprit Kaur | 75 | sterlinglifestylellp | sterlinglifestylellp | Previous PM Cockpit |  | SPS111195262301 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2026-01-23 | 2026-02-12 |  | Fresh | Spine NG | Onsite | 48 | Completed
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 | 2026-09-30 | High | Completed | 91 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | acnhealthcarercmservicespvtltdacninfotech |  | Previous PM Cockpit
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active | 86 |  | High | SCH milestone 'AC' has not progressed for 86 days | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | HELL ENERGY PVT LTD | 9514 | Account Activated | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ) |  | 85 | Aug-26 |  | 550 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | Project Status Update - HELL ENERGY PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Sanket Gosalia | 550 | hellenergypvtltd | hellenergypvtltd | Previous PM Cockpit |  | SPH111773260307 | Normal | E | Karuna Rajaram Sandim |  | Hiren Bhimani | SAAS | 2026-07-03 | 2026-07-28 |  | Fresh | Spine NG | Onsite | 16 | Completed
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active | 85 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - VISHWAKARMA FOUNDERS (I) PVT. LTD - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vishwakarmafoundersipvtltd |  | Previous PM Cockpit
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed | 58 | 8 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Manual PM Note | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Project Status Update - Navio Shipping - Completed | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  |  | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  | No | No Match | 0 | 0 | TRUE | [9 empty] | navioshipping |  | Previous PM Cockpit
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active | 58 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CREATIONS BY SHANAGAR - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | creationsbyshanagar |  | Previous PM Cockpit
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active | 58 |  | Watch | PM note missing for ageing open item | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | AKRITI PHARMACEUTICALS PVT LTD | 9512 | Account Activated | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance |  | 96 | Aug-26 | Ankush Rampyare Rajbhar | 310 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - AKRITI PHARMACEUTICALS PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankush Rampyare Rajbhar | Vasu Mohan Dusa | Bhavin Nitin Naik | 310 | akritipharmaceuticalspvtltd | akritipharmaceuticalspvtltd | Previous PM Cockpit |  | SPA111771260207 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-08-03 | 2026-08-20 |  | Fresh | Spine NG | Online | 17 | Datafile Explanation
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active | 48 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | fabtechmultistatecooperativecreditsocietyfmsccs |  | Previous PM Cockpit
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active | 48 |  | Watch | PM note missing for ageing open item | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | JIET MEDICAL COLLEGE HOSPITAL | 9644 | Account Activated | we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935 |  | 0 |  | Varun Rajbhar | 800 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - JIET MEDICAL COLLEGE HOSPITAL - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Varun Rajbhar | Vasu Mohan Dusa | Manisha Singh | 800 | jietmedicalcollegehospital | jietmedicalcollegehospital | Previous PM Cockpit |  | SPJ111881261908 | Premium | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-08-19 | 2026-09-15 |  | Fresh | Spine NG | Online | 10 | Datafile Explanation
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Active | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Varun |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Varun | Vinay | [7 empty] | suranacharitabletrustsuranahospitalandresearchcentrempcthospitalsuranagroupofhospitalsuranahospital |  | Previous PM Cockpit
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Active | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Tejas |  |  |  | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Tejas | Vinay | [7 empty] | mahatmaphulecharitabletrustmpcthospitalsuranagroupofhospitalsuranahospitalsuranahospitalandresearchcentre |  | Previous PM Cockpit
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Santosh |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Santosh | Vinay | [7 empty] | suranagroupofhospitalsuranahospital |  | Previous PM Cockpit
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Active | 14 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | alshifamultispecialtyhospitalhumanwelfaretrust |  | Previous PM Cockpit
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start | 13 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Yash |  |  |  | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - NAVKAR CORPORATION LIMITED - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Yash | Akshay Shinde | [7 empty] | navkarcorporationltd |  | Previous PM Cockpit
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active | 13 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - THE KANDIVALI EDUCATION SOCIETY - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | thekandivalieducationsociety |  | Previous PM Cockpit
5176 | Escalation | ARTSON LIMITED | Schedule | 2026-09-01 | 2026-09-30 | High | Completed | 29 | 29 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ARTSON LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ARTSON LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | artsonltd
5177 | Escalation | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Schedule | 2026-09-28 |  | High | Active | 2 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - DIPESH ENGINEERING WORKS -STAFF LICENSE NG - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | dipeshengineeringworksstafflicenseng
5178 | Allocation | APMOSYS TECHNOLOGIES PVT LTD | Schedule | 2026-09-22 |  | High | Active | 8 |  | Healthy | No immediate exception detected | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | APMOSYS TECHNOLOGIES PVT LTD | 9756 | Account Activated | Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data |  | 24 | 0 | Utkarsh | 1500 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - APMOSYS TECHNOLOGIES PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Exact Name | 1 | 1 | FALSE | Utkarsh | Nagesh |  |  |  | Utkarsh Sanjay Chavan | Vasu Mohan Dusa | Jayesh Mojidra | 1500 | apmosystechpvtltd | apmosystechpvtltd |  |  | SPA111975262209 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-09-22 | 2026-09-29 |  | Fresh | Spine NG | Online | 2 | Datafile Explanation
5179 | Allocation | CONTENDRE GREENERGY PVT. LTD | Schedule | 2026-09-21 |  | High | Active | 9 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [7 empty] | Tanwish |  |  |  | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CONTENDRE GREENERGY PVT. LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Tanwish | Akshay Shinde | [7 empty] | contendregreenergypvtltd
5180 | Allocation | PERFECT BELTS PVT. LTD | Schedule | 2026-09-18 |  | High | Active | 12 |  | Healthy | No immediate exception detected | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | PERFECT BELTS PVT. LTD | 9739 | Account Activated | Payroll- master uploaded, salary set up in process |  | 4 | 0 |  | 850 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - PERFECT BELTS PVT. LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Exact Name | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Manish Sikarwar | 850 | perfectbeltspvtltd | perfectbeltspvtltd |  |  | SPP111961261709 | Normal | E | Divya Bhide |  | Hiren Bhimani | SAAS | 2026-09-17 | 2026-09-19 |  | Fresh | Spine NG | Online | 4 | Datafile Explanation
5181 | Escalation | Saffron Speciality Papers Limited | Schedule | 2026-09-01 |  | High | Active | 29 |  | Healthy | No immediate exception detected | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | SAFFRON SPECIALITY PAPERS LIMITED | 8410 | Account Activated | HRMS Training yet to start, for Dec 25 salary the attendance data yet to come YASH is in discussion salary processing session aligned post that user will release payment planning to proceed with one unit only user has conveyed that she will process march with attn from system in process The client is processing salary for her unit now. They process salary on a 45-day basis. Attendance integration is done. Logins won't be rolled out. The user has uploaded the roster; post manager's approval, she'll process salary with attendance from Spine. march processed for 114 employees logins rolled out they will be processing june live with attn- in process #30/07 - meeting planned for tomorrow. #5/08 - salary is delayed due to different salary cycle of 45 days, it is usually delayed because they receive data late from their site. #2/09 - eng - following up going on for attendance for august salary #8/09 - eng - As discussed, the current HR, Rupali, is serving her notice period, and this is her last working month. Since she is in the process of leaving, she is not showing much interest in the ongoing activities. For further communication, we are coordinating directly with Director Siddharth. However, he is currently occupied with a medical emergency involving a family member, so we will not be able to connect with him this week. We will follow up with him by 11th September based on his availability. Additionally, we are planning a surprise visit on Monday along with the PM and Engineer. We have also heard that the office may be relocating to Thane, so it would be important to discuss this with them at the earliest and understand the impact on the ongoing activities. #9/09 - As discussed with MD Siddharth, I asked him about the reason for the delay in salary processing and the pending salaries for July and August. He asked me to connect with Ms. Rupali regarding the same. He added her to the call and then left. During my discussion with Ms. Rupali, she explained that they have two units, and the employees there do not properly punch in and out for attendance. Due to this, attendance mismatches occur, which she has to regularize manually. This process takes a lot of time and is the main reason for the delay. I understood the issue and asked for her availability so that we could proceed with clearing the backlog and processing the July and August salaries. She requested us to give her a few minutes and said that she would try to clear the pending attendance backlogs herself. She also informed us that if she faces any issue, she will call us back. #26/09 - new user trng completed, awaiting for confirmation, user sunita is on leave, she will connect us for confirmation monday. #28/09 - Planned a onsite meeting for tomorrow. | All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay | 95 | Jun-26 | Yash Pankajkumar | 440 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - Saffron Speciality Papers Limited - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Exact Name | 1 | 1 | FALSE | [5 empty] | Yash Pankajkumar | Vasu Mohan Dusa | Amarprit Kaur | 440 | saffronspecialitypapersltd | saffronspecialitypapersltd |  |  | SPS110851253009 | Normal | E | Ritika Dilip Singh | Akshay Shinde | Viral Panchal | SAAS | 2025-10-08 | 2025-10-28 |  | Fresh | Spine NG | Onsite | 65 | Datafile Explanation

## Action_List
Risk Level | Project Name | Tracker Status | SCH Status | SCH Status Meaning | SCH Stage Group | SCH Milestone | Current Milestone | Age Days | Owner | Next Action | Due Date | PM Notes | PM Note Source | Stakeholder PM Update | Risk Reason
Critical | THE NATIONAL SPORTS CLUB OF INDIA | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 560 | Mihir Navnath Mungekar | Live Salary Processing Planned. |  | Live Salary Processing Planned. | Manual PM Note | Live Salary Processing Planned. | Ageing 560 days from start date
Critical | PARADISE GROUP | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 383 | Pritesh Barot | Backend working is ongoing, training & implementation is planned. |  | Backend working is ongoing, training & implementation is planned. | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Ageing 383 days from start date
Critical | WHISTLING WOODS INTERNATIONAL | Active |  |  |  |  | Datafile Explanation | 364 | Nagendra Poojary | PMS Implementation Ongoing |  | PMS Implementation Ongoing | Manual PM Note | PMS Implementation Ongoing. | No approved SCH match; Ageing 364 days from start date
Critical | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Active |  |  |  |  | Datafile Explanation | 268 |  | Implementation Demo fixed for 8th May |  | Implementation Demo fixed for 8th May | Manual PM Note | Implementation Demo fixed for 8th May. | No approved SCH match; Ageing 268 days from start date
Critical | SUNRISE FOODS BANGALORE | Completed | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Completed | 217 | Tushar More | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Update | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention. | Held-up status needs management intervention
Critical | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 181 | Riddhi Pramod Sutar | Confirm milestone progress and next client action. |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Ageing 181 days from start date
Critical | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Active | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Kick Off Meeting | 177 | Vikas Yadav | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Held-up status needs management intervention
Critical | BFMS FACILITY MANAGEMENT PVT LTD | Lost | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Datafile Explanation | 127 | Amit Krishnakant Tiwari | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manual PM Note | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Held-up status needs management intervention
High | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Lost | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | 631 | Sahil Gadhave | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Remark | As per the latest SCH project remark: Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved. Tracker status is Lost; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Go LIVE'. | Tracker status 'Lost' conflicts with SCH status 'Go LIVE'
High | GNG ELECTRONICS LIMITED FACTORY | Lost | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | 486 | Shubham Gurav | Review Meeting |  | Review Meeting | Manual PM Note | Review Meeting. | Tracker status 'Lost' conflicts with SCH status 'Go LIVE'
High | ILEAF RITZ BANQUETS | Completed | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | 440 | Mayur Pendhari | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Tracker status 'Completed' conflicts with SCH status 'Lost'
High | FUJIYAMA POWER SYSTEM (UTL) | Completed | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | 398 | Komal Kanadiya | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Update | As per the latest SCH project update: Another Software. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Tracker status 'Completed' conflicts with SCH status 'Lost'
High | MEDIPULSE HOSPITAL | Completed | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 386 | Varun Rajbhar | Live Salary Processing Planned for this Month |  | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month. | Tracker status 'Completed' conflicts with SCH status 'AC'
High | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Lost | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 366 |  | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Remark | As per the latest SCH project remark: training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on. Tracker status is Lost; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Active'. | Tracker status 'Lost' conflicts with SCH status 'Active'
High | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 321 | Aditya Mazire | Live Salary Processing Planned for this Month |  | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month. | Tracker status 'Completed' conflicts with SCH status 'AC'
High | NAIK MOTORS -GOA LOC | Completed | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 321 | Aditya Mazire | Live Salary Processing Planned for this Month |  | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month. | Tracker status 'Completed' conflicts with SCH status 'AC'
High | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Completed | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | 215 | Komal Kanadiya | Review blocker, confirm owner, and update next closure plan. |  |  | SCH Project Remark | As per the latest SCH project remark: set up & training done, jan done, feb done later client is not responding to calls n mails. Tracker status is Completed; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Active'. | Tracker status 'Completed' conflicts with SCH status 'Active'
High | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | 176 | Ankush Rampyare Rajbhar | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Tracker status 'Completed' conflicts with SCH status 'Active'
High | TRIO JEWELS PVT LTD | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 174 | Mukeshkumar Shojiram kumavat | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Ageing 174 days from start date
High | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Active |  |  |  |  | Kick Off Meeting | 161 |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | No approved SCH match; Ageing 161 days from start date
High | TRIO JEWELS PVT LTD Contractual | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | 152 | Mukeshkumar Shojiram kumavat | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Ageing 152 days from start date
High | EMPREO PREMIUM PVT LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 135 | Goraksha Pawar | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Ageing 135 days from start date
High | EMPREO WHEEL PVT LIMITED (MG) | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 135 | Goraksha Pawar | Same |  | Same | Manual PM Note | Same. | Ageing 135 days from start date
High | SHREEKHETRA AUTOMOTIVE (TATA) | Active | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | 135 | Goraksha Pawar | Same |  | Same | Manual PM Note | Same. | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date
High | AMAL EMBROIDERIES PVT. LTD | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 134 | Vijay Bugde | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Ageing 134 days from start date
High | MULTI ORGANICS PVT LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | 128 | Rajesh Ravindra Panchal | KickOff & Datafile Explaination done |  | KickOff & Datafile Explaination done | Manual PM Note | KickOff & Datafile Explaination done. | Ageing 128 days from start date
High | MANJUSHREE INNOVATIONS PVT. LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | 126 | Mayur Pendhari | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Ageing 126 days from start date
High | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | 121 | Varun Rajbhar | Confirm kickoff date, data readiness, and owner. |  | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Ageing 121 days from start date
High | Mansha Agencies | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | 117 | Aditya Mazire | Confirm kickoff date, data readiness, and owner. |  | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Ageing 117 days from start date
High | Muktangan Education Trust | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 117 | Aditya Mazire | Confirm kickoff date, data readiness, and owner. |  | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Ageing 117 days from start date
High | BSA CORPORATION LIMITED / BSA GROUP | Active |  |  |  |  | Kick Off Meeting | 114 |  | Confirm kickoff date, data readiness, and owner. |  | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | No approved SCH match; Ageing 114 days from start date
High | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | 113 | Ankita Gupta | Confirm kickoff date, data readiness, and owner. |  | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Ageing 113 days from start date
High | SACRED HEART HOSPITAL JAL | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | 112 | Mayur Pendhari | Confirm kickoff date, data readiness, and owner. |  | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Ageing 112 days from start date
High | VED INDUSTRIES/ ROHIDA GROUP | Active |  |  |  |  | Kick Off Meeting | 105 |  | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | No approved SCH match; Ageing 105 days from start date
High | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Active |  |  |  |  | Kick Off Meeting | 104 |  | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | No approved SCH match; Ageing 104 days from start date
High | STERLING LIFESTYLE LLP | Completed | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 92 | Aarati Subhashchandra Yadav | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'. | Tracker status 'Completed' conflicts with SCH status 'AC'
High | HELL ENERGY PVT LTD | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | 86 |  | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | SCH milestone 'AC' has not progressed for 86 days
Watch | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed |  |  |  |  | Kick Off Meeting | 152 |  | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | Manual PM Note | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | No approved SCH match
Watch | Vivan Associate | Completed |  |  |  |  | Datafile Explanation | 118 |  | Confirm kickoff date, data readiness, and owner. |  | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Manual PM Note | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | No approved SCH match
Watch | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Completed |  |  |  |  | Datafile Explanation | 91 |  | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match
Watch | VISHWAKARMA FOUNDERS (I) PVT. LTD | Active |  |  |  |  | Kick Off Meeting | 85 |  | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match; PM note missing for ageing open item
Watch | CREATIONS BY SHANAGAR | Active |  |  |  |  | Datafile Explanation | 58 |  | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match; PM note missing for ageing open item
Watch | AKRITI PHARMACEUTICALS PVT LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 58 | Ankush Rampyare Rajbhar | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | PM note missing for ageing open item
Watch | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Active |  |  |  |  | Datafile Explanation | 48 |  | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match; PM note missing for ageing open item
Watch | JIET MEDICAL COLLEGE HOSPITAL | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 48 | Varun Rajbhar | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | PM note missing for ageing open item
Watch | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Active |  |  |  |  | Kick Off Meeting | 25 | Varun | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match
Watch | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Active |  |  |  |  | Kick Off Meeting | 25 | Tejas | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match
Watch | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Yet To Start |  |  |  |  | Kick Off Meeting | 25 | Santosh | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match
Watch | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Active |  |  |  |  | Kick Off Meeting | 14 |  | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match
Watch | NAVKAR CORPORATION LIMITED | Yet To Start |  |  |  |  | Kick Off Meeting | 13 | Yash | Confirm kickoff date, data readiness, and owner. |  |  | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | No approved SCH match
Watch | THE KANDIVALI EDUCATION SOCIETY | Active |  |  |  |  | Datafile Explanation | 13 |  | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match
Watch | CONTENDRE GREENERGY PVT. LTD | Active |  |  |  |  | Datafile Explanation | 9 | Tanwish | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match
Watch | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Active |  |  |  |  | Datafile Explanation | 2 |  | Confirm progress for milestone: Datafile Explanation. |  |  | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No approved SCH match
Healthy | Saffron Speciality Papers Limited | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 29 | Yash Pankajkumar | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Update | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. | No immediate exception detected
Healthy | PERFECT BELTS PVT. LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 12 |  | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | No immediate exception detected
Healthy | APMOSYS TECHNOLOGIES PVT LTD | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | 8 | Utkarsh | Confirm progress for milestone: Datafile Explanation. |  |  | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. | No immediate exception detected

## Completed_Followup_Plan
Followup Due This Month | Followup Quarter | Followup Month | Suggested Followup Date | Project Code | Project Name | Completed Date | SCH Status | Owner | Last Processed Year Month | Client Usage Status | Challenges / Pain Points | Support Required | Upsell Scope | PM Followup Notes | Next Followup Date
No | Q3 2026 | July | 2026-07-15 | 5160 | ANS NG | 2026-09-30 | Go LIVE | Aditya Mazire | May-24 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5055 | ARMITA INDIA SHIPPING PVT. LTD | 2025-07-23 |  | Mayur Pendhari | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | 2026-08-31 | FC | Harsh Dilip Ashar | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5130 | CIRCLE RESOURCES PRIVATE LIMITED | 2026-03-30 | FC | Mayur Pendhari | Jun-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5070 | CONTENDRE GREENERGY LIMITED | 2025-08-30 | FC | Daksh Pawankumar | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5019 | Cogencis | 2025-04-25 |  | Vikas Yadav | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5043 | EROS ELEVATORS & ESCALATORS PVT LTD | 2025-05-01 |  | Amol Takkar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | 2026-07-31 | FC | Sunita Yadav | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5061 | GNG ELECTRONICS LIMITED STAFF | 2025-10-28 | Go LIVE | Shubham Gurav | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5127 | GUARDIAN CASTING PVT. LTD | 2026-03-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | 2026-04-28 | FC | Mihir Navnath Mungekar | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5016 | Helen Keller Institute for Deaf & Blind | 2025-04-25 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | 2026-02-27 | FC | Rahul Ankush Dalvi | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | 2025-06-01 |  | Kajal Inchanalkar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5067 | ISA Logistics Private Limited | 2025-07-23 | FC | Mihir Navnath Mungekar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5022 | Infexn Laboratories | 2025-04-25 | Go LIVE | Shubham Gurav | May-24 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5085 | KISHAN LAL PAWAN KUMAR JAIN | 2025-10-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | 2025-07-17 | FC Lost | Tejas Rajesh Baragade | Aug-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 2025-09-24 | Go LIVE | Ruchit Shailesh Patel | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5091 | MEDIPULSE HOSPITAL | 2026-09-30 | AC | Varun Rajbhar | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5064 | MESPACK INDIA PVT. LTD | 2026-04-28 | FC | Pooja Vikas Shinde | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5013 | Metafab | 2025-04-25 |  | Goraksha Pawar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5103 | NAGRIK CONSULTANCY SERVICES | 2026-02-27 | FC | Aditya Mazire | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5106 | NAIK MOTORS -GOA LOC | 2026-07-31 | AC | Aditya Mazire | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5136 | Navio Shipping | 2026-05-26 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 2025-08-30 | FC Lost | Tushar More | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5004 | PLASMA RESEARCH TRUST NX | 2025-04-25 |  | Paras Mahesh Ladva | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5088 | POLMOR STEEL PRIVATE LIMITED | 2026-01-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | 2026-04-28 | FC | Goraksha Pawar | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5034 | QUALIGENS PHARMA PVT. LTD | 2025-10-28 | Go LIVE | Ruchit Shailesh Patel | Feb-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | 2026-07-31 | Active | Ankush Rampyare Rajbhar | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | 2026-01-28 | Go LIVE | Tejas Rajesh Baragade | Feb-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5052 | SNAPWORK TECHNOLOGIES PVT LTD | 2026-02-27 | FC | Vijay Bugde | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5037 | STEAM PULSE INDIA PVT LTD | 2025-10-28 | Go LIVE | Daksh Pawankumar | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5124 | SUNRISE FOODS BANGALORE | 2026-04-28 | Held | Tushar More | Jul-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5118 | Seventy Seven Entertainment Pvt Ltd | 2026-03-30 | Go LIVE | Pritesh Barot | April-23 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5049 | TAO AUTOMATION SERVICES PVT LTD | 2025-07-17 |  | Supriya Waghmare | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | 2025-10-28 | Go LIVE | Sahil Gadhave | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5073 | V ALLIANCE NX | 2025-08-30 | Go LIVE | Rahul Ankush Dalvi | Oct-24 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | July | 2026-07-15 | 5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | 2026-05-26 | Go LIVE | Dhanashree Dalvi | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5089 | ACEY ENGINEERING PVT. LTD | 2026-03-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 2026-07-31 | Go LIVE | Goraksha Pawar | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | 2025-10-28 |  | Vinay Kareliya | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5029 | APLAB LIMITED (FOR STAFF LICENSE) | 2025-10-28 | Go LIVE | Varun Rajbhar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5176 | ARTSON LIMITED | 2026-09-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5008 | Aquaair International Frieght Services | 2025-04-25 | Go LIVE | Nagendra Poojary | Mar-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5047 | BRILLIANT POLYMERS PVT. LTD | 2025-06-01 |  | Probian Biswas | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5005 | Bengal Energy_Staff | 2026-03-30 | Go LIVE | Mayur Pendhari | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5110 | COSMOS IMPEX INDIA PVT LTD NG | 2026-03-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5017 | Cartfire India | 2025-04-25 | Go LIVE | Nagendra Poojary | Jan-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | 2026-04-28 | FC | Kunal Joshi | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5083 | FUJIYAMA POWER SYSTEM (UTL) | 2026-03-30 | Lost | Komal Kanadiya | Feb-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | 2026-07-31 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5128 | GNG ELECTRONICS LIMITED FACTORY | 2026-03-30 | Go LIVE | Shubham Gurav | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5116 | GNG ELECTRONICS LIMITED STAFF | 2026-01-22 | Go LIVE | Shubham Gurav | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | 2025-07-30 |  | Amol Takkar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5071 | ILEAF RITZ BANQUETS | 2025-09-24 | Lost | Mayur Pendhari | Jan-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5035 | MADURA INDUSTRIAL TEXTILES LIMITED | 2026-04-28 | Go LIVE | Varun Rajbhar | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | 2025-09-24 | Go LIVE | Mayur Pendhari | Jun-24 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | 2026-07-31 | AC | Aditya Mazire | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5125 | NOTCH INDIA PROJECTS | 2026-03-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | 2025-10-28 | Go LIVE | Pritesh Barot | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5107 | PPKG AND CO | 2026-02-27 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5056 | PRECIOUS ALLOYS PRIVATE LIMITED | 2025-06-01 |  | Shreyas Karkera | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5122 | Procon RMC | 2026-04-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5026 | RADIX ELECTROSYSTEMS PVT LTD | 2026-03-30 | Go LIVE | Aditya Pathak | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5098 | RENMAKCH INDIA PVT. LTD. | 2026-01-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | 2025-07-23 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5020 | S K Traders | 2025-06-30 | Go LIVE | Rahul Ankush Dalvi | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5080 | SETHWALA FOODS LTD | 2026-05-26 | FC | Kunal Joshi | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | 2025-07-23 | Go LIVE | Pritesh Barot | April-23 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5038 | STEAM HARBOUR LOGISTICS PVT LTD | 2026-01-28 | Go LIVE | Daksh Pawankumar | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5161 | STERLING LIFESTYLE LLP | 2026-09-30 | AC | Aarati Subhashchandra Yadav | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5041 | TATARIA HARDWARE INNOVATION | 2025-06-01 |  | Nagendra Poojary | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5014 | Texple | 2025-04-25 |  | Santosh Yadav | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5065 | UNITED AIR EXPRESS | 2026-04-28 | FC | Shubham Gurav | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5074 | UNITED AIR EXPRESS | 2025-08-21 | FC | Shubham Gurav | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5137 | VIPUL ORGANICS LTD. - STAFF | 2026-05-26 | Go LIVE | Santosh Yadav | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | 2026-04-28 | FC Lost | Mihir Navnath Mungekar | Jun-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | 2025-10-28 | Go LIVE | Probian Biswas | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
No | Q3 2026 | August | 2026-08-15 | 5113 | parvathyhospital | 2026-01-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5162 | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | 2026-09-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | 2026-03-30 | FC | Vijay Bugde | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 2025-08-30 | Go LIVE | Hardik Panchal | Feb-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5105 | ANUH PHARMA PVT. LTD NX | 2026-01-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | 2025-10-28 | Go LIVE | Varun Rajbhar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | 2026-04-28 | Go LIVE |  | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | 2025-10-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5096 | AUROUS JEWELS LLP | 2025-10-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5048 | AUTOTECH-SIRMAX INDIA PVT LTD | 2025-07-17 |  | Vikas Yadav | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | 2025-10-28 |  | Sahil Gadhave | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5054 | BRIGHT BROTHERS LTD. / BRITE | 2026-02-27 | FC | Rahul Ankush Dalvi | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5108 | DOSHI MEDICARE PRIVATE LIMITED | 2026-01-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5093 | DRS EARTHWORK PRIVATE LIMITED | 2025-11-28 | FC | Mihir Navnath Mungekar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5015 | ERMELLI PRIVATE LIMITED | 2025-04-25 |  | Hardik Panchal | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5075 | ESCON ELEVATORS PVT. LTD. | 2025-08-30 | Go LIVE | Probian Biswas | 0 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | 2026-04-28 | Active | Komal Kanadiya | Feb-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5126 | Elixrr Industries Pvt. Ltd. | 2026-04-28 | Go LIVE | Krishna Yadav | Jun-23 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5024 | Emmay Entertainment | 2025-04-25 |  | Nandadeep Mhatre | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5078 | FFSERVICES PRIVATE LIMITED | 2025-11-28 | Go LIVE | Harsh Dilip Ashar | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | 2025-04-25 | FC Lost | Amit Krishnakant Tiwari | Sept-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5099 | GNG ELECTRONICS LIMITED FACTORY | 2025-10-28 | Go LIVE | Shubham Gurav | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | 2025-06-01 |  | Sachin Thothawala | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5009 | Hardcarb Technologies Private Limited | 2025-04-25 | Go LIVE | Tejas Rajesh Baragade | Mar-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5003 | Maharashtra Book Manufacturing | 2025-04-25 | FC | Shubham Gurav | Aug-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 2026-01-28 | Go LIVE | Aditya Mazire | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5111 | NIKIKA ENTERPRISES LLP | 2026-05-26 | Go LIVE |  | Apr-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5165 | Navio Shipping | 2026-08-11 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | 2025-08-30 | FC | Bhavika Gite | Sep-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5045 | SAI SANKET INDUSTRIES PVT.LTD | 2025-05-25 | Go LIVE | Dakshesh D Nadkar | Nov-23 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5060 | SAINI ELECTRICAL & ENGINEERING WORKS | 2025-07-30 |  | Mukeshkumar Shojiram kumavat | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5021 | SEEBA INDUSTRIES PRIVATE LIMITED | 2025-04-25 |  | Darshit Pithwa | [5 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5102 | SREE METALIKS LTD | 2026-04-28 | Go LIVE | Nandadeep Mhatre | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5018 | Sky Prints | 2025-04-25 | Go LIVE | Nagesh Tiwari | Feb-25 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | 2025-10-28 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5117 | Talib and Shamsi Constructions Pvt. Ltd. | 2026-03-30 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5084 | VABA | 2025-10-28 | Go LIVE | Karan Rajesh Tiwari | Mar-26 |  |  |  |  | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.
Yes | Q3 2026 | September | 2026-09-15 | 5153 | Vivan Associate | 2026-07-31 | [7 empty] | Check if client is using the system properly, whether any challenges are open, and if optimization/support is needed.

## Stale_Items
Project Code | Project Type | Project Name | Received From | Start Date | End Date | Tracker Priority | Tracker Status | Age Days | Cycle Days | Risk Level | Risk Reason | Status Mismatch | SCH Status | SCH Status Meaning | SCH Stage Group | SCH Milestone | Current Milestone | SCH Client Name | SCH Project Code | SCH Client Status | SCH Project Remark | SCH Project Update | SCH Achieved Percent | SCH Last Processed Year Month | Owner | Effective Employee Count | Effective Product | Effective Client Type | PM Note Source | Stakeholder PM Update | Stakeholder Update Subject | Next Action | Due Date | Action Date | PM Notes | Manual Risk Reason | Mail Include | Match Method | Match Score | SCH Match Count | Match Review Needed | Assigned Engineer | Team Leader | Marketing Executive | Product | Employee Count | SCH Implementation Engg | SCH Project Manager | SCH Project MKT | SCH No. Emp | Tracker Name Key | SCH Name Key | Notes Source | Tracker Client Type | SCH Client Code | SCH Priority | SCH Class | SCH Co-ordinator | SCH Team Leader | SCH Project Team Manager | SCH Client Type | SCH Project Start Date | SCH Project Implementation Date | SCH Project Close Date | SCH Product Type | SCH Project Product | SCH Project Mode | SCH Row Number | SCH Suggested Milestone
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost | 631 | 191 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | 7262 | Account DeActivated | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved |  | 66 |  | Sahil Gadhave | 1100 | NX | Normal | SCH Project Remark | As per the latest SCH project remark: Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved. Tracker status is Lost; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Go LIVE'. | Project Status Update - TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | NX | 1100 | Sahil Gadhave | Vasu Mohan Dusa | Nirbhay Kumar | 1100 | tarasafeintlpvtlimitedworker | tarasafeintlpvtltdworkerlicense | Previous PM Cockpit | Normal | SPT109784243112 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-01-07 | 2025-02-13 | 2025-07-08 | Fresh | Spine HRMS | Online | 115 | Completed
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed | 631 | 108 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Paras Mahesh Ladva | 35 | NX | Normal | Tracker/SCH Status | No manual PM note is available for PLASMA RESEARCH TRUST NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Paras Mahesh Ladva. | Project Status Update - PLASMA RESEARCH TRUST NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Paras Mahesh Ladva | Viral Panchal | Anuj Kumar Ganga Prasad Tiwari | NX | 35 |  |  |  |  | plasmaresearchtrustnx |  | Previous PM Cockpit | Normal
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed | 617 | 94 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Goraksha Pawar | 270 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Metafab; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Goraksha Pawar. | Project Status Update - Metafab - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Goraksha Pawar | Prathamesh Mandavkar | Amarprit Kaur | NX | 270 |  |  |  |  | metafab |  | Previous PM Cockpit | Normal
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed | 615 | 92 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Santosh Yadav | 30 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Texple; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Santosh Yadav. | Project Status Update - Texple - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Santosh Yadav | Prathamesh Mandavkar | Aparna Santosh | NX | 30 |  |  |  |  | texple |  | Previous PM Cockpit | Normal
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed | 614 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Hardik Panchal | 55 | NX | Normal | Tracker/SCH Status | No manual PM note is available for ERMELLI PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Hardik Panchal. | Project Status Update - ERMELLI PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Hardik Panchal | Ganesh Jadhav | Pragnesh Panchal | NX | 55 |  |  |  |  | ermellipvtltd |  | Previous PM Cockpit | Normal
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed | 623 | 100 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [8 empty] | 80 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Helen Keller Institute for Deaf & Blind; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Helen Keller Institute for Deaf & Blind - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE |  | Hiren Bhimani | Manisha Paradia | NX | 80 |  |  |  |  | helenkellerinstitutefordeafblind |  | Previous PM Cockpit | Normal
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed | 607 | 84 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vikas Yadav | 500 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Cogencis; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Project Status Update - Cogencis - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vikas Yadav | Prathamesh Mandavkar | Pragnesh Panchal | NX | 500 |  |  |  |  | cogencis |  | Previous PM Cockpit | Normal
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed | 602 | 79 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Darshit Pithwa | 132 | NX | Normal | Tracker/SCH Status | No manual PM note is available for SEEBA INDUSTRIES PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Darshit Pithwa. | Project Status Update - SEEBA INDUSTRIES PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Darshit Pithwa | Hemanshu Wadia | Nikhil Solanki | NX | 132 |  |  |  |  | seebaindustriespvtltd |  | Previous PM Cockpit | Normal
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost | 595 | 258 | Watch | No approved SCH match | FALSE | [12 empty] | Rahul Ankush Dalvi | 70 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Sankalpan; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - Sankalpan | [5 empty] | No | No Match | 0 | 0 | TRUE | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | NX | 70 |  |  |  |  | sankalpan |  | Previous PM Cockpit | Normal
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed | 589 | 66 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Nandadeep Mhatre | 42 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Emmay Entertainment; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nandadeep Mhatre. | Project Status Update - Emmay Entertainment - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Nandadeep Mhatre | Prathamesh Mandavkar | Aparna Santosh | NX | 42 |  |  |  |  | emmayentertainment |  | Previous PM Cockpit | Normal
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed | 576 | 239 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vinay Kareliya | 125 | NG | Normal | Tracker/SCH Status | No manual PM note is available for ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vinay Kareliya. | Project Status Update - ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vinay Kareliya | Vinay Kareliya | Tejas Kareliya | NG | 125 |  |  |  |  | anmindustriespvtltdanmallianceanmgroupamketteanalyticsltd |  | Previous PM Cockpit | Normal
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed | 561 | 224 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Sahil Gadhave | 700 | NG | Normal | Tracker/SCH Status | No manual PM note is available for BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. | Project Status Update - BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Sahil Gadhave | Sahil Gadhave | Santosh Bhoja Shetty | NG | 700 |  |  |  |  | bijjargimotorspvtltdbijjargimotorsbijjargiexcavationsolutions |  | Previous PM Cockpit | Normal
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed | 554 | 68 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Sachin Thothawala | 1250 | NX | Normal | Tracker/SCH Status | No manual PM note is available for GUJARAT TEA PROCESSOR & PACKERS LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Sachin Thothawala. | Project Status Update - GUJARAT TEA PROCESSOR & PACKERS LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Sachin Thothawala | Sachin Thothawala | Tejas Kareliya | NX | 1250 |  |  |  |  | gujaratteaprocessorpackersltd |  | Previous PM Cockpit | Normal
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed | 562 | 76 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Kajal Inchanalkar | 850 | NX | Normal | Tracker/SCH Status | No manual PM note is available for INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Kajal Inchanalkar. | Project Status Update - INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Kajal Inchanalkar | Saurabh Pednekar | Mehul Patel | NX | 850 |  |  |  |  | industrialxrayalliedradiographersnx |  | Previous PM Cockpit | Normal
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed | 561 | 75 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Nagendra Poojary | 60 | NX | Normal | Tracker/SCH Status | No manual PM note is available for TATARIA HARDWARE INNOVATION; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Nagendra Poojary. | Project Status Update - TATARIA HARDWARE INNOVATION - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Nagendra Poojary | Viral Panchal | Manisha Paradia | NX | 60 |  |  |  |  | tatariahardwareinnovation |  | Previous PM Cockpit | Normal
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active | 560 |  | Critical | Ageing 560 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | NATIONAL SPORTS CLUB OF INDIA NX | 4859 | Account Activated | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. Due to biometric machine was not working due to which there were many employees who had not punched in the system. Because of which they have to do the salary as per the previous process. Were we told Mdm. Megha that as they have processed the September salary. So we will not regularize the September attendance. Will update the attendance from 25th September to 28th September. Sept salary processed by uploading atten. October sal is live target Need to discuss with client on monday with vasu for payment related. |  | 68 | Aug-26 | Mihir Navnath Mungekar | 450 | NX | Premium | Manual PM Note | Live Salary Processing Planned. | Project Status Update - THE NATIONAL SPORTS CLUB OF INDIA - Datafile Explanation | Live Salary Processing Planned. |  |  | Live Salary Processing Planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | Mihir Navnath Mungekar | Vinay Kareliya | Sanket Gosalia | NX | 450 | Mihir Navnath Mungekar | Vasu Mohan Dusa | Sanket Gosalia | 450 | thenationalsportsclubofindia | nationalsportsclubofindianx | Previous PM Cockpit | Premium | SPT107662232808 | Premium | B | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | On-Premises | 2023-09-02 | 2023-12-27 |  | Fresh | Spine HRMS | Onsite | 137 | Datafile Explanation
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed | 547 | 30 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Amol Takkar | 400 | NX | Premium | Tracker/SCH Status | No manual PM note is available for EROS ELEVATORS & ESCALATORS PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Project Status Update - EROS ELEVATORS & ESCALATORS PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Amol Takkar | Amol Takkar | Tejas Kareliya | NX | 400 |  |  |  |  | eroselevatorsescalatorspvtltd |  | Previous PM Cockpit | Premium
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed | 534 | 48 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Probian Biswas | 185 | NX | Normal | Tracker/SCH Status | No manual PM note is available for BRILLIANT POLYMERS PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Probian Biswas. | Project Status Update - BRILLIANT POLYMERS PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Probian Biswas | Viral Panchal | Tejas Kareliya | NX | 185 |  |  |  |  | brilliantpolymerspvtltd |  | Previous PM Cockpit | Normal
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed | 527 | 87 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Vikas Yadav | 205 | NX | Normal | Tracker/SCH Status | No manual PM note is available for AUTOTECH-SIRMAX INDIA PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Vikas Yadav. | Project Status Update - AUTOTECH-SIRMAX INDIA PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Vikas Yadav | Prathamesh Mandavkar | Nikhil Solanki | NX | 205 |  |  |  |  | autotechsirmaxindiapvtltd |  | Previous PM Cockpit | Normal
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed | 526 | 86 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Supriya Waghmare | 60 | NX | Normal | Tracker/SCH Status | No manual PM note is available for TAO AUTOMATION SERVICES PVT LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Supriya Waghmare. | Project Status Update - TAO AUTOMATION SERVICES PVT LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Supriya Waghmare | Hemanshu Wadia |  | NX | 60 |  |  |  |  | taoautomationservicespvtltd |  | Previous PM Cockpit | Normal
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost | 520 | 37 | Watch | No approved SCH match | FALSE | [12 empty] | Rahul Ankush Dalvi | 100 | NX | Normal | Tracker/SCH Status | No manual PM note is available for POONAM ROLLER FLOUR MILLS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Rahul Ankush Dalvi. | Project Status Update - POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | [5 empty] | No | No Match | 0 | 0 | TRUE | Rahul Ankush Dalvi | Viral Panchal | Aparna Santosh | NX | 100 |  |  |  |  | poonamrollerflourmillspvtltd |  | Previous PM Cockpit | Normal
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed | 494 | 60 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [8 empty] | 630 | NX | Normal | Tracker/SCH Status | No manual PM note is available for Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE |  | Hiren Bhimani | Rushabh Dinesh Shah | NX | 630 |  |  |  |  | royalchainspvtltdandroyalitalianjewelrypvtltd |  | Previous PM Cockpit | Normal
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed | 494 | 60 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Mayur Pendhari | 45 | NX | Normal | Tracker/SCH Status | No manual PM note is available for ARMITA INDIA SHIPPING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. | Project Status Update - ARMITA INDIA SHIPPING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Mayur Pendhari | Akshay Shinde | Manisha Singh | NX | 45 |  |  |  |  | armitaindiashippingpvtltd |  | Previous PM Cockpit | Normal
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed | 494 | 8 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Shreyas Karkera | 151 | NX | Normal | Tracker/SCH Status | No manual PM note is available for PRECIOUS ALLOYS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Shreyas Karkera. | Project Status Update - PRECIOUS ALLOYS PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Shreyas Karkera | Shreyas Karkera | Vaishali Ramniklal Puj | NX | 151 |  |  |  |  | preciousalloyspvtltd |  | Previous PM Cockpit | Normal
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost | 494 | 60 | Watch | No approved SCH match | FALSE | [13 empty] | 25 | NX | Normal | Tracker/SCH Status | No manual PM note is available for SUKHKARTA MULTISPECIALITY HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Lost. | Project Status Update - SUKHKARTA MULTISPECIALITY HOSPITAL | [5 empty] | No | No Match | 0 | 0 | TRUE |  |  | Sanket Gosalia | NX | 25 |  |  |  |  | sukhkartamultispecialityhospital |  | Previous PM Cockpit | Normal
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed | 486 | 59 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Amol Takkar | 495 | NX | Premium | Tracker/SCH Status | No manual PM note is available for GOLDSTAR ELITE JEWELS PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Amol Takkar. | Project Status Update - GOLDSTAR ELITE JEWELS PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Amol Takkar | Amol Takkar | Sanket Gosalia | NX | 495 |  |  |  |  | goldstarelitejewelspvtltd |  | Previous PM Cockpit | Premium
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed | 486 | 59 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [7 empty] | Mukeshkumar Shojiram kumavat | 300 | NX | Premium | Tracker/SCH Status | No manual PM note is available for SAINI ELECTRICAL & ENGINEERING WORKS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. Current owner/implementation contact: Mukeshkumar Shojiram kumavat. | Project Status Update - SAINI ELECTRICAL & ENGINEERING WORKS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | Mukeshkumar Shojiram kumavat | Nagesh Tiwari | Aparna Santosh | NX | 300 |  |  |  |  | sainielectricalengineeringworks |  | Previous PM Cockpit | Premium
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost | 486 | 52 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED FACTORY | 8831 | Account Activated | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | 100 |  | Shubham Gurav | 750 | NX | Normal | Manual PM Note | Review Meeting. | Project Status Update - GNG ELECTRONICS LIMITED FACTORY - Completed | Review Meeting |  |  | Review Meeting |  | Yes | Approved Alias | 1 | 3 | TRUE | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | NX | 750 | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 1600 | gngelectronicsltdfactory | gngelectronicsltdfactory | Previous PM Cockpit | Normal | SPG109937253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-01-29 | 2026-01-30 | 2026-02-10 | Fresh | Spine HRMS | Online | 47 | Completed
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost | 463 | 29 | Watch | No approved SCH match | FALSE | [12 empty] | Santosh Yadav | 200 | NG | Normal | Tracker/SCH Status | No manual PM note is available for Kuboz Arc Pvt Ltd; this update is generated from Tracker and SCH status. Tracker status is Lost. Current owner/implementation contact: Santosh Yadav. | Project Status Update - Kuboz Arc Pvt Ltd | [5 empty] | No | No Match | 0 | 0 | TRUE | Santosh Yadav | Vinay Kareliya | Giriraj Birendrasingh Tomar | NG | 200 |  |  |  |  | kubozarcpvtltd |  | Previous PM Cockpit | Normal
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed | 440 | 69 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | ILEAF RITZ BANQUETS | 8079 | Account DeActivated | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy | 110 | Jan-26 | Mayur Pendhari | 110 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - ILEAF RITZ BANQUETS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Anuj Kumar Ganga Prasad Tiwari | 110 | ileafritzbanquets | ileafritzbanquets | Previous PM Cockpit |  | SPI110558252806 | Normal | E | Mansi Singh | Probian Biswas | Viral Panchal | SAAS | 2025-06-28 | 2025-07-02 | 2026-06-18 | Fresh | Spine NG | Onsite | 75 | Completed
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost | 408 | 102 | Watch | No approved SCH match | FALSE | [16 empty] | Tracker/SCH Status | No manual PM note is available for PRASAD JEWELLERS; this update is generated from Tracker and SCH status. Tracker status is Lost. | Project Status Update - PRASAD JEWELLERS | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | prasadjewellers |  | Previous PM Cockpit
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed | 398 | 214 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | FUJIYAMA POWER SYSTEMS LIMITED | 8275 | Account DeActivated | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software | 110 | Feb-26 | Komal Kanadiya | 2400 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Another Software. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - FUJIYAMA POWER SYSTEM (UTL) - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 2400 | fujiyamapowersystemutl | fujiyamapowersystemsltd | Previous PM Cockpit |  | SPF110735252908 | Premium | E | Divya Bhide | Hiren Bhimani | Hiren Bhimani | SAAS | 2025-08-29 | 2025-09-23 | 2026-07-29 | Fresh | Spine NG | Online | 70 | Completed
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed | 404 | 67 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for KISHAN LAL PAWAN KUMAR JAIN; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - KISHAN LAL PAWAN KUMAR JAIN - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | kishanlalpawankumarjain |  | Previous PM Cockpit
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed | 403 | 66 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for TORQUE INSURANCE BROKING PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - TORQUE INSURANCE BROKING PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | torqueinsurancebrokingpvtltd |  | Previous PM Cockpit
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed | 391 | 146 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for POLMOR STEEL PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - POLMOR STEEL PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | polmorsteelpvtltd |  | Previous PM Cockpit
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed | 391 | 207 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ACEY ENGINEERING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ACEY ENGINEERING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | aceyengineeringpvtltd |  | Previous PM Cockpit
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed | 378 | 41 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ATHARVA FACILITY MANAGEMENT AND SECURITY; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ATHARVA FACILITY MANAGEMENT AND SECURITY - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | atharvafacilitymanagementandsecurity |  | Previous PM Cockpit
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 | 2026-09-30 | Low | Completed | 386 | 386 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | MEDIPULSE HOSPITAL | 8316 | Account Activated | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. August salary on monday | Using only the HRMS Module, payroll is now initiated | 98 | Aug-26 | Varun Rajbhar | 731 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - MEDIPULSE HOSPITAL - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Varun Rajbhar | Vasu Mohan Dusa | Manisha Singh | 731 | medipulsehospital | medipulsehospital | Previous PM Cockpit, Book1 |  | SPM110771250109 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-09-06 | 2025-10-09 |  | Fresh | Spine NG | Online | 69 | Completed
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active | 383 |  | Critical | Ageing 383 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | PARADISE GROUP | 8328 | Account Activated | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August |  | 97 |  | Pritesh Barot | 624 | Spine NG | SAAS | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Project Status Update - PARADISE GROUP - Datafile Explanation | Backend working is ongoing, training & implementation is planned. |  |  | Backend working is ongoing, training & implementation is planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Pritesh Barot | Vasu Mohan Dusa | Ankur Yewalekar | 624 | paradisegroup | paradisegroup | Previous PM Cockpit |  | SPP110783251209 | Premium | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2025-09-12 | 2025-09-23 |  | Fresh | Spine NG | Online | 68 | Completed
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost | 366 | 211 | High | Tracker status 'Lost' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | CENTRE FOR URBANIZATION BUILDINGS | 8381 | Account Activated | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on |  |  | 0 |  | 95 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on. Tracker status is Lost; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Active'. | Project Status Update - CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Roopa S | 95 | centreforurbanizationbuildingsandenvironmentcubeiitm | centreforurbanizationbuildings | Previous PM Cockpit |  | SPC110823252909 | Normal | E | Disha Kiran Kargutkar |  | Saurabh Thakur | SAAS | 2025-09-29 | 2025-10-02 |  | Fresh | Spine NG | Online | 67 | Datafile Explanation
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | 352 | 15 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for AUROUS JEWELS LLP; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - AUROUS JEWELS LLP - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | aurousjewelsllp |  | Previous PM Cockpit
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed | 337 | 92 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for RENMAKCH INDIA PVT. LTD.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - RENMAKCH INDIA PVT. LTD. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | renmakchindiapvtltd |  | Previous PM Cockpit
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active | 364 |  | Critical | No approved SCH match; Ageing 364 days from start date | FALSE |  |  |  |  | Datafile Explanation | [7 empty] | Nagendra Poojary |  |  |  | Manual PM Note | PMS Implementation Ongoing. | Project Status Update - WHISTLING WOODS INTERNATIONAL - Datafile Explanation | PMS Implementation Ongoing |  |  | PMS Implementation Ongoing |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | whistlingwoodsintl |  | Previous PM Cockpit, Book1
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS - RATNAGIRI LOC | 8547 | Account Activated | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also." | 98 | Aug-26 | Aditya Mazire | 180 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Aparna Santosh | 180 | naikmotorsnaikmahindraratnagiriloc | naikmotorsratnagiriloc | Previous PM Cockpit, Book1 |  | SPN110948251311 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-13 | 2025-12-22 |  | Fresh | Spine NG | Online | 60 | Completed
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed | 316 | 71 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ANUH PHARMA PVT. LTD NX; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ANUH PHARMA PVT. LTD NX - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | anuhpharmapvtltdnx |  | Previous PM Cockpit
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS -GOA LOC | 8531 | Account Activated | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn july done Aug sal done add module after 10th oct we will ask client. sept live sal will do. |  | 88 | Aug-26 | Aditya Mazire | 410 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS -GOA LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Sandeep Ashok Joundal | 410 | naikmotorsgoaloc | naikmotorsgoaloc | Previous PM Cockpit, Book1 |  | SPN110937250811 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-08 | 2025-12-17 |  | Fresh | Spine NG | Online | 61 | Completed
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed | 308 | 93 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for PPKG AND CO; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - PPKG AND CO - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | ppkgandco |  | Previous PM Cockpit
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed | 331 | 86 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for DOSHI MEDICARE PRIVATE LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - DOSHI MEDICARE PRIVATE LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | doshimedicarepvtltd |  | Previous PM Cockpit
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed | 305 | 121 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for COSMOS IMPEX INDIA PVT LTD NG; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - COSMOS IMPEX INDIA PVT LTD NG - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | cosmosimpexindiapvtltdng |  | Previous PM Cockpit
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed | 281 | 36 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for parvathyhospital; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - parvathyhospital - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | parvathyhospital |  | Previous PM Cockpit
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed | 260 | 76 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for Talib and Shamsi Constructions Pvt. Ltd.; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Talib and Shamsi Constructions Pvt. Ltd. - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | talibandshamsiconstructionspvtltd |  | Previous PM Cockpit
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active | 268 |  | Critical | No approved SCH match; Ageing 268 days from start date | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Manual PM Note | Implementation Demo fixed for 8th May. | Project Status Update - SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED - Datafile Explanation | Implementation Demo fixed for 8th May |  |  | Implementation Demo fixed for 8th May |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | suvarnadurgagroupsdgsuvarnadurgapaperboardspvtltd |  | Previous PM Cockpit, Book1
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed | 219 | 64 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for Procon RMC; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - Procon RMC - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | proconrmc |  | Previous PM Cockpit
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed | 215 | 60 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | 8713 | Account Activated | set up & training done, jan done, feb done later client is not responding to calls n mails |  | 100 | Feb-26 | Komal Kanadiya | 1400 | Spine NG | Hosting | SCH Project Remark | As per the latest SCH project remark: set up & training done, jan done, feb done later client is not responding to calls n mails. Tracker status is Completed; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Active'. | Project Status Update - EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 1400 | evergreenhousekeepingservicespvtevergreenfacilitysolutions | evergreenhousekeepingservicespvt | Previous PM Cockpit |  | SPE111097252312 | Escalated | C | Divya Bhide | Hiren Bhimani | Hiren Bhimani | Hosting | 2025-12-23 | 2026-01-07 |  | Fresh | Spine NG | Online | 54 | Datafile Explanation
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed | 217 | 62 | Critical | Held-up status needs management intervention | TRUE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Completed | SUNRISE FOODS BANGALORE | 8720 | Account Activated | Payroll Training completed July month salary processed and tallied. HRMS Training done. client were using hrms attendance for 2 months but after that they were not using are not taking interest for payroll module. after a multiple followup for aug salary aug sal done followup is going on for sept sal but no response. Not responding calledMr. Jeson he said will let us know in 2 days. afte 2-3 days we are calling and doing mail but no response. Held up- Payroll training has been completed. July salary was processed and successfully tallied. HRMS training has also been completed. The client was using HRMS attendance for around two months; however, they have not been actively using the system thereafter and are currently not showing much interest in the Payroll module. Follow-ups are currently ongoing for the September salary processing, but there has been no response from the client. We contacted Mr. Jeson, who informed us that he would provide an update within two days. However, even after 2–3 days, despite repeated calls and email follow-ups, we have not received any further response from the client. The client is currently not responding to our calls or follow-ups. | No Response - No Reason | 88 | Jul-26 | Tushar More | 50 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention. | Project Status Update - SUNRISE FOODS BANGALORE - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Tushar More | Vasu Mohan Dusa | Roopa S | 50 | sunrisefoodsbangalore | sunrisefoodsbangalore | Previous PM Cockpit |  | SPS111104252912 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-12-29 | 2026-01-17 | 2026-09-30 | Fresh | Spine NG | Online | 53 | Datafile Explanation
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed | 218 | 34 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for NOTCH INDIA PROJECTS; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - NOTCH INDIA PROJECTS - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | notchindiaprojects |  | Previous PM Cockpit
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed | 229 | 45 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for GUARDIAN CASTING PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - GUARDIAN CASTING PVT. LTD - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | guardiancastingpvtltd |  | Previous PM Cockpit
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active | 181 |  | Critical | Ageing 181 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | 9142 | Account Activated | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) target live sep live salary |  | 0 | Jun-26 | Riddhi Pramod Sutar | 650 | Spine NG | SAAS | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Project Status Update - SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) - Datafile Explanation | Confirm milestone progress and next client action. |  |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Riddhi Pramod Sutar | Vasu Mohan Dusa | Utsavi Setu | 650 | symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl | symbiosiscentrefordistancelearningsdcl | Previous PM Cockpit, Book1 |  | SPS111464263103 | Premium | E | Karuna Rajaram Sandim |  | Hiren Bhimani | SAAS | 2026-04-02 | 2026-05-20 |  | Fresh | Spine NG | Online | 37 | Datafile Explanation
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active | 177 |  | Critical | Held-up status needs management intervention | FALSE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Kick Off Meeting | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | 9121 | Account Activated | Basic payroll training has been completed. W26jul9046 Client is occupied in a full-day meeting today. T As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. not responding whatsapp group msg as their bal payment pending called Mr. Ganesh yesterday for issues and concern and recommend outsourcing options. they said will check and inform you. Held up-Basic Payroll training has been completed. Ticket reference: W26jul9046. The client was occupied in a full-day meeting today. The client is currently not responding to messages in the WhatsApp group, and the balance payment is also pending. We called Mr. Ganesh yesterday to understand the current issues and concerns and also discussed the option of outsourcing payroll processing. Mr. Ganesh informed us that they would check internally and get back to us. However, we have not received any further response from the client yet. The client currently does not have a dedicated resource for the software, and due to limited availability of the client/resource, they are unable to spend sufficient time on software utilisation and payroll activities. | Resource Problem | 10 | Mar-26 | Vikas Yadav | 300 | Spine NG | SAAS | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Project Status Update - SHRI JANARDAN SWAMI HOSPITAL (SJS) - Kick Off Meeting | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  |  | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Vikas Yadav | Vasu Mohan Dusa | Nandini Tiwari | 300 | shrijanardanswamihospitalsjs | rashtrasantjanardhanswamigroupofinstitutes | Previous PM Cockpit, Book1 |  | SPR111446263103 | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-04 | 2026-06-30 | 2026-09-30 | Fresh | Spine NG | Online | 38 | Datafile Explanation
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | 176 | 115 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | RUPA SOLUTIONS PRIVATE LIMITED | 9146 | Account Activated | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744 |  | 100 | Aug-26 | Ankush Rampyare Rajbhar | 300 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES - Completed | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  |  | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankush Rampyare Rajbhar | Vasu Mohan Dusa | Ankur Yewalekar | 300 | rupasolutionspvtltdrupagrouprupaproperties | rupasolutionspvtltd | Previous PM Cockpit, Book1 |  | SPR111468263103 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-07 | 2026-04-16 |  | Fresh | Spine NG | Onsite | 36 | Datafile Explanation
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active | 174 |  | High | Ageing 174 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | TRIO JEWELS PVT LTD | 9191 | Account Activated | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Aug-26 | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD - Datafile Explanation | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  |  | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mukeshkumar Shojiram kumavat | Vasu Mohan Dusa | Vaishali Ramniklal | 301 | triojewelspvtltd | triojewelspvtltd | Previous PM Cockpit, Book1 |  | SPT111502260904 | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-04-09 | 2026-04-24 |  | Fresh | Spine NG | Onsite | 34 | Completed
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active | 161 |  | High | No approved SCH match; Ageing 161 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Project Status Update - VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED - Kick Off Meeting | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | voguenhydepvtltdmodapellebagsaccessoriespvtltd |  | Previous PM Cockpit, Book1
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed | 160 | 33 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Manual PM Note | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Project Status Update - Navio Shipping - Completed | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  |  | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  | No | No Match | 0 | 0 | TRUE | [9 empty] | navioshipping |  | Previous PM Cockpit
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed | 152 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | Project Status Update - GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG - Kick Off Meeting | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  | 4th May | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | gngelectronicsltdelectronicsbazaarforstafflicenseconversiontong |  | Previous PM Cockpit, Book1
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active | 152 |  | High | Ageing 152 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | TRIO JEWELS PVT LTD | 9191 | Account Activated | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Aug-26 | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD Contractual - Kick Off Meeting | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | 8th May | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mukeshkumar Shojiram kumavat | Vasu Mohan Dusa | Vaishali Ramniklal | 301 | triojewelspvtltdcontractual | triojewelspvtltd | Previous PM Cockpit, Book1 |  | SPT111502260904 | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-04-09 | 2026-04-24 |  | Fresh | Spine NG | Onsite | 34 | Completed
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Ageing 135 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | EMPREO PREMIUM PVT LTD | 8919 | Account Activated | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 80 | Mar-26 | Goraksha Pawar | 105 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - EMPREO PREMIUM PVT LTD - Datafile Explanation | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | 8th May | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Tejas Kareliya | 105 | empreopremiumpvtltd | empreopremiumpvtltd | Previous PM Cockpit, Book1 |  | SPE111274261802 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-02-18 | 2026-03-25 |  | Fresh | Spine NG | Online | 43 | Datafile Explanation
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Ageing 135 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | EMPREO WHEEL PVT LIMITED (MG) | 8958 | Account Activated | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 65 | Apr-26 | Goraksha Pawar | 150 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - EMPREO WHEEL PVT LIMITED (MG) - Datafile Explanation | Same |  | 8th May | Same |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Swati Sangani | 150 | empreowheelpvtltdmg | empreowheelpvtltdmg | Previous PM Cockpit, Book1 |  | SPE111306262702 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-16 | 2026-05-28 |  | Fresh | Spine NG | Online | 41 | Datafile Explanation
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | SHREEKHETRA AUTOMOTIVE (TATA) | 8957 | Account DeActivated | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 4 | 0 | Goraksha Pawar | 200 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - SHREEKHETRA AUTOMOTIVE (TATA) - Kick Off Meeting | Same |  | 8th May | Same |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Tejas Kareliya | 200 | shreekhetraautomotivetata | shreekhetraautomotivetata | Previous PM Cockpit, Book1 |  | SPS111305262702 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-15 |  | 2026-10-02 | Fresh | Spine NG | Online | 42 | Completed
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active | 134 |  | High | Ageing 134 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | AMAL EMBROIDERIES PRIVATE LIMITED | 9304 | Account Activated | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. As per call accounts team is connected for payment with user Aparna. Only add mod pms left which will be done in the month of november directly. |  | 91 | Aug-26 | Vijay Bugde | 1200 | Spine NG | SAAS | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Project Status Update - AMAL EMBROIDERIES PVT. LTD - Datafile Explanation | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | 4th May | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Vijay Bugde | Vasu Mohan Dusa | Ankur Yewalekar | 1200 | amalembroideriespvtltd | amalembroideriespvtltd | Previous PM Cockpit, Book1 |  | SPA111591261305 | Premium | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-05-19 | 2026-06-04 |  | Fresh | Spine NG | Onsite | 25 | Completed
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active | 128 |  | High | Ageing 128 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MULTI ORGANICS PVT LTD | 9257 | Account Activated | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out |  | 95 | Jul-26 | Rajesh Ravindra Panchal | 350 | Spine NG | SAAS | Manual PM Note | KickOff & Datafile Explaination done. | Project Status Update - MULTI ORGANICS PVT LTD - Kick Off Meeting | KickOff & Datafile Explaination done |  | 5th May | KickOff & Datafile Explaination done |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mihir Navnath Mungekar | Vasu Mohan Dusa | Tejas Kareliya | 350 | multiorganicspvtltd | multiorganicspvtltd | Previous PM Cockpit, Book1 |  | SPM111555263004 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-05-23 | 2026-07-25 |  | Fresh | Spine NG | Onsite | 30 | Datafile Explanation
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost | 127 | 97 | Critical | Held-up status needs management intervention | FALSE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Datafile Explanation | BFMS FACILITY MANAGEMENT PVT LTD | 8728 | Account Activated | (E26aug6724) Project Held Up - Despite our continuous efforts to support and resolve queries and concerns, we have not received the required response from client Implementation and Training session aligned from 13th Jan E26jan1479 W26jan5503 Bfms Payroll Training and December Salary confirmation BFMS will not process with Attendance - W26mar1378 the salary of compliance section is not yet decided (in discussion) post that they will process march on monday team will update the company is shifting to pvt ltd hence they are bsy client not responding properly The client mentioned that they have employees such as delivery personnel working with platforms like Zomato, Swiggy, and Urban Company. These employees typically work for only 4–5 days and then leave the job after comparing their earnings with other platforms, stating that they are being paid less. Due to this high attrition and short working duration, salary processing becomes challenging. We also asked why they opted for the software despite this situation. The user responded that it was a management decision. as per vasu's meting client will be providing data post salary processing of june had a call with user to make her undertsand that all isue can be handled through spine which she is having but she seems not interested | FInds excel easy | 100 | Feb-26 | Amit Krishnakant Tiwari | 500 | Spine NG | SAAS | Manual PM Note | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Project Status Update - BFMS FACILITY MANAGEMENT PVT LTD - Datafile Explanation | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | 5th May | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Amit Krishnakant Tiwari | Vasu Mohan Dusa | Amarprit Kaur | 500 | bfmsfacilitymanagementpvtltd | bfmsfacilitymanagementpvtltd | Previous PM Cockpit, Book1 |  | SPB111113253112 | Normal | E | Ankita Bankar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-12-31 | 2026-01-13 | 2026-09-21 | Fresh | Spine NG | Onsite | 52 | Datafile Explanation
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active | 126 |  | High | Ageing 126 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MANJUSHREE INNOVATIONS PRIVATE LIMITED | 9354 | Account Activated | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. August sal processed by their own but not live- W26sep2587 sept will be target for live sal Attrition &amp; Absenteeism Report Query is going on client want automatic shifts. The September salary will be processed live through Spine for the staff with attendance, while the workers’ attendance will be uploaded manually for salary processing. |  | 76 | Aug-26 | Mayur Pendhari | 370 | Spine NG | SAAS | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Project Status Update - MANJUSHREE INNOVATIONS PVT. LTD - Kick Off Meeting | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | 5th May | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Manisha Singh | 370 | manjushreeinnovationspvtltd | manjushreeinnovationspvtltd | Previous PM Cockpit, Book1 |  | SPM111635262705 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-05-27 | 2026-06-15 |  | Fresh | Spine NG | Online | 24 | Datafile Explanation
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active | 121 |  | High | Ageing 121 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | 9374 | Account Activated | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NG & live target month for processing is August month August month live salary processed - W26aug7425 |  | 79 | Aug-26 | Varun Rajbhar | 550 | Spine NG | SAAS | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Project Status Update - CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Santosh Yadav | Vasu Mohan Dusa | Tejas Kareliya | 550 | cryogasequipmentpvtltdcryogasindia | cryogasequipmentpvtltdng | Previous PM Cockpit, Book1 |  | SPC111653263005 | Normal | E | Ankita Bankar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-06-02 | 2026-06-24 |  | Fresh | Spine NG | Online | 23 | Datafile Explanation
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active | 117 |  | High | Ageing 117 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | MANSHA AGENCIES PVT LTD | 9075 | Account Activated | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied june salary upload Aug salary processed integration done Logins roll out by next week. sept will be live sal | User is hospitalized so that’s why data files are received late & implementation is delayed | 80 | Aug-26 | Aditya Mazire | 260 | Spine NG | SAAS | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Project Status Update - Mansha Agencies - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Manisha Singh | 260 | manshaagencies | manshaagenciespvtltd | Previous PM Cockpit, Book1 |  | SPM111405262703 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2026-03-27 | 2026-06-22 |  | Fresh | Spine NG | Onsite | 40 | Datafile Explanation
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active | 117 |  | High | Ageing 117 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | MUKTANGAN EDUCATION TRUST. NX | 8778 | Account Activated | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly." | 93 |  | Aditya Mazire | 608 | Spine HRMS | SAAS | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Project Status Update - Muktangan Education Trust - Datafile Explanation | Confirm kickoff date, data readiness, and owner. |  |  | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. |  | Yes | Approved Alias | 1 | 2 | TRUE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Manisha Singh | 608 | muktanganeducationtrust | muktanganeducationtrustnx | Previous PM Cockpit, Book1 |  | SPM108453242903 | Normal | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2026-01-06 | 2026-04-18 |  | Fresh | Spine HRMS | Online | 50 | Datafile Explanation
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed | 118 | 57 | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Manual PM Note | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Project Status Update - Vivan Associate - Datafile Explanation | Confirm kickoff date, data readiness, and owner. |  |  | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vivanassociate |  | Previous PM Cockpit, Book1
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active | 114 |  | High | No approved SCH match; Ageing 114 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | Project Status Update - BSA CORPORATION LIMITED / BSA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | bsacorporationltdbsagroup |  | Previous PM Cockpit
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active | 113 |  | High | Ageing 113 days from start date | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | 9398 | Account Activated | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion |  | 48 | Aug-26 | Ankita Gupta | 500 | Spine NG | SAAS | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Project Status Update - INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankita Gupta | Vasu Mohan Dusa | Ankur Yewalekar | 500 | integratedpestmanagementsolutionsindiapvtltdipmsindia | integratedpestmanagementsolutionsindia | Previous PM Cockpit |  | SPI111677260206 | Normal | E | Ankita Bankar | Amey Telge | Viral Panchal | SAAS | 2026-06-09 | 2026-06-17 |  | Fresh | Spine NG | Online | 21 | Datafile Explanation
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active | 112 |  | High | Ageing 112 days from start date | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | SACRED HEART HOSPITAL JAL | 9392 | Account Activated | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul | 88 |  | Mayur Pendhari | 801 | Spine HRMS | On-Premises | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Project Status Update - SACRED HEART HOSPITAL JAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Jayesh Mojidra | 801 | sacredhearthospitaljal | sacredhearthospitaljal | Previous PM Cockpit |  | SPS111671263005 | Premium | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | On-Premises | 2026-06-10 | 2026-07-27 |  | Fresh | Spine HRMS | Online | 22 | Completed
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active | 105 |  | High | No approved SCH match; Ageing 105 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | Project Status Update - VED INDUSTRIES/ ROHIDA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vedindustriesrohidagroup |  | Previous PM Cockpit
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active | 104 |  | High | No approved SCH match; Ageing 104 days from start date | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | Project Status Update - ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | itcfortunehotelsiligurickimpromotersllpfortuneselectsiliguri |  | Previous PM Cockpit
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 | 2026-09-30 | High | Completed | 92 | 92 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | STERLING LIFESTYLE LLP | 8821 | Account Activated | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response |  | 100 | Aug-26 | Aarati Subhashchandra Yadav | 75 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'. | Project Status Update - STERLING LIFESTYLE LLP - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aarati Subhashchandra Yadav | Vasu Mohan Dusa | Amarprit Kaur | 75 | sterlinglifestylellp | sterlinglifestylellp | Previous PM Cockpit |  | SPS111195262301 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2026-01-23 | 2026-02-12 |  | Fresh | Spine NG | Onsite | 48 | Completed
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 | 2026-09-30 | High | Completed | 91 | 91 | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | acnhealthcarercmservicespvtltdacninfotech |  | Previous PM Cockpit
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active | 86 |  | High | SCH milestone 'AC' has not progressed for 86 days | FALSE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | HELL ENERGY PVT LTD | 9514 | Account Activated | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ) |  | 85 | Aug-26 |  | 550 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | Project Status Update - HELL ENERGY PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Sanket Gosalia | 550 | hellenergypvtltd | hellenergypvtltd | Previous PM Cockpit |  | SPH111773260307 | Normal | E | Karuna Rajaram Sandim |  | Hiren Bhimani | SAAS | 2026-07-03 | 2026-07-28 |  | Fresh | Spine NG | Onsite | 16 | Completed
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active | 85 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - VISHWAKARMA FOUNDERS (I) PVT. LTD - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | vishwakarmafoundersipvtltd |  | Previous PM Cockpit
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed | 58 | 8 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Manual PM Note | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Project Status Update - Navio Shipping - Completed | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  |  | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  | No | No Match | 0 | 0 | TRUE | [9 empty] | navioshipping |  | Previous PM Cockpit
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active | 58 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CREATIONS BY SHANAGAR - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | creationsbyshanagar |  | Previous PM Cockpit
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active | 58 |  | Watch | PM note missing for ageing open item | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | AKRITI PHARMACEUTICALS PVT LTD | 9512 | Account Activated | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance |  | 96 | Aug-26 | Ankush Rampyare Rajbhar | 310 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - AKRITI PHARMACEUTICALS PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankush Rampyare Rajbhar | Vasu Mohan Dusa | Bhavin Nitin Naik | 310 | akritipharmaceuticalspvtltd | akritipharmaceuticalspvtltd | Previous PM Cockpit |  | SPA111771260207 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-08-03 | 2026-08-20 |  | Fresh | Spine NG | Online | 17 | Datafile Explanation
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active | 48 |  | Watch | No approved SCH match; PM note missing for ageing open item | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | fabtechmultistatecooperativecreditsocietyfmsccs |  | Previous PM Cockpit
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active | 48 |  | Watch | PM note missing for ageing open item | FALSE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | JIET MEDICAL COLLEGE HOSPITAL | 9644 | Account Activated | we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935 |  | 0 |  | Varun Rajbhar | 800 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - JIET MEDICAL COLLEGE HOSPITAL - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Varun Rajbhar | Vasu Mohan Dusa | Manisha Singh | 800 | jietmedicalcollegehospital | jietmedicalcollegehospital | Previous PM Cockpit |  | SPJ111881261908 | Premium | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2026-08-19 | 2026-09-15 |  | Fresh | Spine NG | Online | 10 | Datafile Explanation
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Active | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Varun |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Varun | Vinay | [7 empty] | suranacharitabletrustsuranahospitalandresearchcentrempcthospitalsuranagroupofhospitalsuranahospital |  | Previous PM Cockpit
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Active | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Tejas |  |  |  | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Tejas | Vinay | [7 empty] | mahatmaphulecharitabletrustmpcthospitalsuranagroupofhospitalsuranahospitalsuranahospitalandresearchcentre |  | Previous PM Cockpit
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start | 25 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Santosh |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Santosh | Vinay | [7 empty] | suranagroupofhospitalsuranahospital |  | Previous PM Cockpit
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Active | 14 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [11 empty] | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | alshifamultispecialtyhospitalhumanwelfaretrust |  | Previous PM Cockpit
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start | 13 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Kick Off Meeting | [7 empty] | Yash |  |  |  | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - NAVKAR CORPORATION LIMITED - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Yash | Akshay Shinde | [7 empty] | navkarcorporationltd |  | Previous PM Cockpit
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active | 13 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - THE KANDIVALI EDUCATION SOCIETY - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | thekandivalieducationsociety |  | Previous PM Cockpit
5176 | Escalation | ARTSON LIMITED | Schedule | 2026-09-01 | 2026-09-30 | High | Completed | 29 | 29 | Watch | No approved SCH match | FALSE |  |  |  |  | Completed | [11 empty] | Tracker/SCH Status | No manual PM note is available for ARTSON LIMITED; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Completed. | Project Status Update - ARTSON LIMITED - Completed | [5 empty] | No | No Match | 0 | 0 | TRUE | [9 empty] | artsonltd
5177 | Escalation | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Schedule | 2026-09-28 |  | High | Active | 2 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [11 empty] | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - DIPESH ENGINEERING WORKS -STAFF LICENSE NG - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | [9 empty] | dipeshengineeringworksstafflicenseng
5179 | Allocation | CONTENDRE GREENERGY PVT. LTD | Schedule | 2026-09-21 |  | High | Active | 9 |  | Watch | No approved SCH match | FALSE |  |  |  |  | Datafile Explanation | [7 empty] | Tanwish |  |  |  | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CONTENDRE GREENERGY PVT. LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | No Match | 0 | 0 | TRUE | Tanwish | Akshay Shinde | [7 empty] | contendregreenergypvtltd

## Status_Mismatch
Project Code | Project Type | Project Name | Received From | Start Date | End Date | Tracker Priority | Tracker Status | Age Days | Cycle Days | Risk Level | Risk Reason | Status Mismatch | SCH Status | SCH Status Meaning | SCH Stage Group | SCH Milestone | Current Milestone | SCH Client Name | SCH Project Code | SCH Client Status | SCH Project Remark | SCH Project Update | SCH Achieved Percent | SCH Last Processed Year Month | Owner | Effective Employee Count | Effective Product | Effective Client Type | PM Note Source | Stakeholder PM Update | Stakeholder Update Subject | Next Action | Due Date | Action Date | PM Notes | Manual Risk Reason | Mail Include | Match Method | Match Score | SCH Match Count | Match Review Needed | Assigned Engineer | Team Leader | Marketing Executive | Product | Employee Count | SCH Implementation Engg | SCH Project Manager | SCH Project MKT | SCH No. Emp | Tracker Name Key | SCH Name Key | Notes Source | Tracker Client Type | SCH Client Code | SCH Priority | SCH Class | SCH Co-ordinator | SCH Team Leader | SCH Project Team Manager | SCH Client Type | SCH Project Start Date | SCH Project Implementation Date | SCH Project Close Date | SCH Product Type | SCH Project Product | SCH Project Mode | SCH Row Number | SCH Suggested Milestone
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost | 631 | 191 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | 7262 | Account DeActivated | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved |  | 66 |  | Sahil Gadhave | 1100 | NX | Normal | SCH Project Remark | As per the latest SCH project remark: Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved. Tracker status is Lost; SCH status is Go LIVE (Project is handed over from implementation team to support team.). Current milestone: Completed. Current owner/implementation contact: Sahil Gadhave. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Go LIVE'. | Project Status Update - TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | NX | 1100 | Sahil Gadhave | Vasu Mohan Dusa | Nirbhay Kumar | 1100 | tarasafeintlpvtlimitedworker | tarasafeintlpvtltdworkerlicense | Previous PM Cockpit | Normal | SPT109784243112 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2025-01-07 | 2025-02-13 | 2025-07-08 | Fresh | Spine HRMS | Online | 115 | Completed
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost | 486 | 52 | High | Tracker status 'Lost' conflicts with SCH status 'Go LIVE' | TRUE | Go LIVE | Project is handed over from implementation team to support team. | Go Live | Completed | Completed | GNG ELECTRONICS LIMITED FACTORY | 8831 | Account Activated | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  | 100 |  | Shubham Gurav | 750 | NX | Normal | Manual PM Note | Review Meeting. | Project Status Update - GNG ELECTRONICS LIMITED FACTORY - Completed | Review Meeting |  |  | Review Meeting |  | Yes | Approved Alias | 1 | 3 | TRUE | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | NX | 750 | Shubham Gurav | Vasu Mohan Dusa | Amarprit Kaur | 1600 | gngelectronicsltdfactory | gngelectronicsltdfactory | Previous PM Cockpit | Normal | SPG109937253101 | Normal | E | Ankita Bankar | Nagesh Tiwari | Ganesh Jadhav | SAAS | 2026-01-29 | 2026-01-30 | 2026-02-10 | Fresh | Spine HRMS | Online | 47 | Completed
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed | 440 | 69 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | ILEAF RITZ BANQUETS | 8079 | Account DeActivated | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy | 110 | Jan-26 | Mayur Pendhari | 110 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - ILEAF RITZ BANQUETS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Mayur Pendhari | Vasu Mohan Dusa | Anuj Kumar Ganga Prasad Tiwari | 110 | ileafritzbanquets | ileafritzbanquets | Previous PM Cockpit |  | SPI110558252806 | Normal | E | Mansi Singh | Probian Biswas | Viral Panchal | SAAS | 2025-06-28 | 2025-07-02 | 2026-06-18 | Fresh | Spine NG | Onsite | 75 | Completed
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed | 398 | 214 | High | Tracker status 'Completed' conflicts with SCH status 'Lost' | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Completed | FUJIYAMA POWER SYSTEMS LIMITED | 8275 | Account DeActivated | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software | 110 | Feb-26 | Komal Kanadiya | 2400 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: Another Software. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'. | Project Status Update - FUJIYAMA POWER SYSTEM (UTL) - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 2400 | fujiyamapowersystemutl | fujiyamapowersystemsltd | Previous PM Cockpit |  | SPF110735252908 | Premium | E | Divya Bhide | Hiren Bhimani | Hiren Bhimani | SAAS | 2025-08-29 | 2025-09-23 | 2026-07-29 | Fresh | Spine NG | Online | 70 | Completed
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 | 2026-09-30 | Low | Completed | 386 | 386 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | MEDIPULSE HOSPITAL | 8316 | Account Activated | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. August salary on monday | Using only the HRMS Module, payroll is now initiated | 98 | Aug-26 | Varun Rajbhar | 731 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - MEDIPULSE HOSPITAL - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Varun Rajbhar | Vasu Mohan Dusa | Manisha Singh | 731 | medipulsehospital | medipulsehospital | Previous PM Cockpit, Book1 |  | SPM110771250109 | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | Prathamesh Mandavkar | SAAS | 2025-09-06 | 2025-10-09 |  | Fresh | Spine NG | Online | 69 | Completed
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost | 366 | 211 | High | Tracker status 'Lost' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | CENTRE FOR URBANIZATION BUILDINGS | 8381 | Account Activated | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on |  |  | 0 |  | 95 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on. Tracker status is Lost; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Lost' conflicts with SCH status 'Active'. | Project Status Update - CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) - Datafile Explanation | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [6 empty] | Vasu Mohan Dusa | Roopa S | 95 | centreforurbanizationbuildingsandenvironmentcubeiitm | centreforurbanizationbuildings | Previous PM Cockpit |  | SPC110823252909 | Normal | E | Disha Kiran Kargutkar |  | Saurabh Thakur | SAAS | 2025-09-29 | 2025-10-02 |  | Fresh | Spine NG | Online | 67 | Datafile Explanation
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS - RATNAGIRI LOC | 8547 | Account Activated | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also." | 98 | Aug-26 | Aditya Mazire | 180 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Aparna Santosh | 180 | naikmotorsnaikmahindraratnagiriloc | naikmotorsratnagiriloc | Previous PM Cockpit, Book1 |  | SPN110948251311 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-13 | 2025-12-22 |  | Fresh | Spine NG | Online | 60 | Completed
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | 321 | 260 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | NAIK MOTORS -GOA LOC | 8531 | Account Activated | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn july done Aug sal done add module after 10th oct we will ask client. sept live sal will do. |  | 88 | Aug-26 | Aditya Mazire | 410 | Spine NG | SAAS | Manual PM Note | Live Salary Processing Planned for this Month. | Project Status Update - NAIK MOTORS -GOA LOC - Datafile Explanation | Live Salary Processing Planned for this Month |  |  | Live Salary Processing Planned for this Month |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aditya Mazire | Vasu Mohan Dusa | Sandeep Ashok Joundal | 410 | naikmotorsgoaloc | naikmotorsgoaloc | Previous PM Cockpit, Book1 |  | SPN110937250811 | Normal | E | Disha Kiran Kargutkar | Amey Telge | Viral Panchal | SAAS | 2025-11-08 | 2025-12-17 |  | Fresh | Spine NG | Online | 61 | Completed
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed | 215 | 60 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | 8713 | Account Activated | set up & training done, jan done, feb done later client is not responding to calls n mails |  | 100 | Feb-26 | Komal Kanadiya | 1400 | Spine NG | Hosting | SCH Project Remark | As per the latest SCH project remark: set up & training done, jan done, feb done later client is not responding to calls n mails. Tracker status is Completed; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Completed. Current owner/implementation contact: Komal Kanadiya. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Active'. | Project Status Update - EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No | Approved Alias | 1 | 1 | FALSE | [5 empty] | Komal Kanadiya | Vasu Mohan Dusa | Sumit Kumar | 1400 | evergreenhousekeepingservicespvtevergreenfacilitysolutions | evergreenhousekeepingservicespvt | Previous PM Cockpit |  | SPE111097252312 | Escalated | C | Divya Bhide | Hiren Bhimani | Hiren Bhimani | Hosting | 2025-12-23 | 2026-01-07 |  | Fresh | Spine NG | Online | 54 | Datafile Explanation
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed | 217 | 62 | Critical | Held-up status needs management intervention | TRUE | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Completed | SUNRISE FOODS BANGALORE | 8720 | Account Activated | Payroll Training completed July month salary processed and tallied. HRMS Training done. client were using hrms attendance for 2 months but after that they were not using are not taking interest for payroll module. after a multiple followup for aug salary aug sal done followup is going on for sept sal but no response. Not responding calledMr. Jeson he said will let us know in 2 days. afte 2-3 days we are calling and doing mail but no response. Held up- Payroll training has been completed. July salary was processed and successfully tallied. HRMS training has also been completed. The client was using HRMS attendance for around two months; however, they have not been actively using the system thereafter and are currently not showing much interest in the Payroll module. Follow-ups are currently ongoing for the September salary processing, but there has been no response from the client. We contacted Mr. Jeson, who informed us that he would provide an update within two days. However, even after 2–3 days, despite repeated calls and email follow-ups, we have not received any further response from the client. The client is currently not responding to our calls or follow-ups. | No Response - No Reason | 88 | Jul-26 | Tushar More | 50 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention. | Project Status Update - SUNRISE FOODS BANGALORE - Completed | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Tushar More | Vasu Mohan Dusa | Roopa S | 50 | sunrisefoodsbangalore | sunrisefoodsbangalore | Previous PM Cockpit |  | SPS111104252912 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2025-12-29 | 2026-01-17 | 2026-09-30 | Fresh | Spine NG | Online | 53 | Datafile Explanation
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | 176 | 115 | High | Tracker status 'Completed' conflicts with SCH status 'Active' | TRUE | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Completed | RUPA SOLUTIONS PRIVATE LIMITED | 9146 | Account Activated | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744 |  | 100 | Aug-26 | Ankush Rampyare Rajbhar | 300 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES - Completed | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  |  | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Ankush Rampyare Rajbhar | Vasu Mohan Dusa | Ankur Yewalekar | 300 | rupasolutionspvtltdrupagrouprupaproperties | rupasolutionspvtltd | Previous PM Cockpit, Book1 |  | SPR111468263103 | Normal | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-07 | 2026-04-16 |  | Fresh | Spine NG | Onsite | 36 | Datafile Explanation
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active | 135 |  | High | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date | TRUE | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | SHREEKHETRA AUTOMOTIVE (TATA) | 8957 | Account DeActivated | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 4 | 0 | Goraksha Pawar | 200 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - SHREEKHETRA AUTOMOTIVE (TATA) - Kick Off Meeting | Same |  | 8th May | Same |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Goraksha Pawar | Vasu Mohan Dusa | Tejas Kareliya | 200 | shreekhetraautomotivetata | shreekhetraautomotivetata | Previous PM Cockpit, Book1 |  | SPS111305262702 | Escalated | E | Ankita Bankar | Sahil Gadhave | Prathamesh Mandavkar | SAAS | 2026-04-15 |  | 2026-10-02 | Fresh | Spine NG | Online | 42 | Completed
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 | 2026-09-30 | High | Completed | 92 | 92 | High | Tracker status 'Completed' conflicts with SCH status 'AC' | TRUE | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | STERLING LIFESTYLE LLP | 8821 | Account Activated | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response |  | 100 | Aug-26 | Aarati Subhashchandra Yadav | 75 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'. | Project Status Update - STERLING LIFESTYLE LLP - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes | Approved Alias | 1 | 1 | FALSE | [5 empty] | Aarati Subhashchandra Yadav | Vasu Mohan Dusa | Amarprit Kaur | 75 | sterlinglifestylellp | sterlinglifestylellp | Previous PM Cockpit |  | SPS111195262301 | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | Ganesh Jadhav | SAAS | 2026-01-23 | 2026-02-12 |  | Fresh | Spine NG | Onsite | 48 | Completed

## Alias_Matching_Tracker
Tracker Project Code | Tracker Project Name | Tracker Status | Current Matched SCH Client | Suggested SCH Match 1 | Score 1 | Suggested SCH Match 2 | Score 2 | Suggested SCH Match 3 | Score 3 | Final SCH Client Name | Approved | Match Method | Review Notes
5001 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Completed | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | 0.807 | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | 0.655 | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | 0.6 | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5002 | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Lost | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | 0.814 | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | 0.655 | VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | 0.6 | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5003 | Maharashtra Book Manufacturing | Completed | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | 0.933 |  |  |  |  | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5004 | PLASMA RESEARCH TRUST NX | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5005 | Bengal Energy_Staff | Completed | BENGAL ENERGY LTD- STAFF | BENGAL ENERGY LTD- STAFF | 0.919 | BENGAL ENERGY LTD- CONTRACTUAL | 0.651 |  |  | BENGAL ENERGY LTD- STAFF | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5006 | Bengal Energy_Worker | Lost | BENGAL ENERGY LTD- CONTRACTUAL | BENGAL ENERGY LTD- CONTRACTUAL | 0.636 | BENGAL ENERGY LTD- STAFF | 0.632 |  |  | BENGAL ENERGY LTD- CONTRACTUAL | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5007 | Parbhani Medical College | Lost | PARBHANI MEDICAL COLLEGE (PMC) | PARBHANI MEDICAL COLLEGE (PMC) | 0.936 | JIET MEDICAL COLLEGE HOSPITAL | 0.625 |  |  | PARBHANI MEDICAL COLLEGE (PMC) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5008 | Aquaair International Frieght Services | Completed | AQUAAIR INTERNATIONAL FREIGHT SERVICES | AQUAAIR INTERNATIONAL FREIGHT SERVICES | 0.962 |  |  |  |  | AQUAAIR INTERNATIONAL FREIGHT SERVICES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5009 | Hardcarb Technologies Private Limited | Completed | HARDCARB TECHNOLOGIES PRIVATE LIMITED | HARDCARB TECHNOLOGIES PRIVATE LIMITED | 1 | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | 0.878 | KARVY TECHNOLOGIES PVT. LTD. | 0.727 | HARDCARB TECHNOLOGIES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5010 | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Completed | MADHUSUMAN ENTERPRISES | MADHUSUMAN ENTERPRISES | 0.677 |  |  |  |  | MADHUSUMAN ENTERPRISES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5011 | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Completed | KHERWADI SOCIAL WELFARE ASSOCIATION | KHERWADI SOCIAL WELFARE ASSOCIATION | 0.821 |  |  |  |  | KHERWADI SOCIAL WELFARE ASSOCIATION | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5012 | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Completed | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | 1 |  |  |  |  | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5013 | Metafab | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5014 | Texple | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5015 | ERMELLI PRIVATE LIMITED | Completed |  | PERFECT BELTS PVT. LTD | 0.645 | EMPREO WHEEL PVT LIMITED (MG) | 0.625 | EMPREO PREMIUM PVT LTD | 0.625 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5016 | Helen Keller Institute for Deaf & Blind | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5017 | Cartfire India | Completed | CARTFIRE INDIA | CARTFIRE INDIA | 1 |  |  |  |  | CARTFIRE INDIA | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5018 | Sky Prints | Completed | SKY PRINTS | SKY PRINTS | 1 |  |  |  |  | SKY PRINTS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5019 | Cogencis | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5020 | S K Traders | Completed | S K TRADERS NX | S K TRADERS NX | 0.9 |  |  |  |  | S K TRADERS NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Completed |  | ANM INDUSTRIES PVT LTD | 0.85 | ELIXRR INDUSTRIES PVT LTD. | 0.791 | SAI SANKET INDUSTRIES PVT. LTD. | 0.783 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5022 | Infexn Laboratories | Completed | INFEXN LABORATORIES PVT LTD | INFEXN LABORATORIES PVT LTD | 0.857 |  |  |  |  | INFEXN LABORATORIES PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5023 | Sankalpan | Lost | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5024 | Emmay Entertainment | Completed |  | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 0.612 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5025 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Completed | INDIANA GRATINGS PVT LTD | INDIANA GRATINGS PVT LTD | 0.778 |  |  |  |  | INDIANA GRATINGS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5026 | RADIX ELECTROSYSTEMS PVT LTD | Completed | RADIX ELECTROSYSTEMS PVT LTD | RADIX ELECTROSYSTEMS PVT LTD | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.619 | RADIX INNOVATIONS PRIVATE LIMITED | 0.596 | RADIX ELECTROSYSTEMS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5027 | MARU CONSULTANCY SERVICES | Lost | MARU CONSULTANCY SERVICES | MARU CONSULTANCY SERVICES | 1 | NAGRIK CONSULTANCY SERVICES | 0.875 |  |  | MARU CONSULTANCY SERVICES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5028 | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Completed | SHREE RAMDEV METALEX LLP | SHREE RAMDEV METALEX LLP | 0.792 |  |  |  |  | SHREE RAMDEV METALEX LLP | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5029 | APLAB LIMITED (FOR STAFF LICENSE) | Completed | APLAB LIMITED (FOR STAFF LICENSE) | APLAB LIMITED (FOR STAFF LICENSE) | 1 | APLAB LIMITED (FOR CONTRACT LICENSE) | 0.816 | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | 0.642 | APLAB LIMITED (FOR STAFF LICENSE) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5030 | APLAB LIMITED (FOR CONTRACT LICENSE) | Completed | APLAB LIMITED (FOR CONTRACT LICENSE) | APLAB LIMITED (FOR CONTRACT LICENSE) | 1 | APLAB LIMITED (FOR STAFF LICENSE) | 0.816 | TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | 0.633 | APLAB LIMITED (FOR CONTRACT LICENSE) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5031 | NPSE AUTOMATION PVT. LTD | Lost | NPSE AUTOMATION PVT. LTD. | NPSE AUTOMATION PVT. LTD. | 1 | RUPA SOLUTIONS PRIVATE LIMITED | 0.667 | MANJUSHREE INNOVATIONS PRIVATE LIMITED | 0.638 | NPSE AUTOMATION PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5033 | KARVY TECHNOLOGIES PVT LTD | Lost | KARVY TECHNOLOGIES PVT. LTD. | KARVY TECHNOLOGIES PVT. LTD. | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.75 | HARDCARB TECHNOLOGIES PRIVATE LIMITED | 0.727 | KARVY TECHNOLOGIES PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5034 | QUALIGENS PHARMA PVT. LTD | Completed | QUALIGENS PHARMA PVT. LTD. | QUALIGENS PHARMA PVT. LTD. | 1 | RUPA SOLUTIONS PRIVATE LIMITED | 0.6 | AKRITI PHARMACEUTICALS PVT LTD | 0.583 | QUALIGENS PHARMA PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5035 | MADURA INDUSTRIAL TEXTILES LIMITED | Completed | MADURA INDUSTRIAL TEXTILES LIMITED. | MADURA INDUSTRIAL TEXTILES LIMITED. | 1 | ANM INDUSTRIES PVT LTD | 0.609 |  |  | MADURA INDUSTRIAL TEXTILES LIMITED. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5037 | STEAM PULSE INDIA PVT LTD | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.708 | MESPACK INDIA PVT. LTD | 0.667 | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 0.625 | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5038 | STEAM HARBOUR LOGISTICS PVT LTD | Completed | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 1 | ISA LOGISTICS PRIVATE LIMITED | 0.756 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.704 | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5041 | TATARIA HARDWARE INNOVATION | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5042 | THE NATIONAL SPORTS CLUB OF INDIA | Active | NATIONAL SPORTS CLUB OF INDIA NX | NATIONAL SPORTS CLUB OF INDIA NX | 0.909 |  |  |  |  | NATIONAL SPORTS CLUB OF INDIA NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Completed |  | ESCON ELEVATORS PVT. LTD. | 0.694 | PROCON RMC PLANTS PRIVATE LIMITED | 0.6 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5044 | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Completed | ELECTROSTEEL CASTINGS LTD | ELECTROSTEEL CASTINGS LTD | 0.73 |  |  |  |  | ELECTROSTEEL CASTINGS LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5045 | SAI SANKET INDUSTRIES PVT.LTD | Completed | SAI SANKET INDUSTRIES PVT. LTD. | SAI SANKET INDUSTRIES PVT. LTD. | 1 | ANM INDUSTRIES PVT LTD | 0.818 | ELIXRR INDUSTRIES PVT LTD. | 0.723 | SAI SANKET INDUSTRIES PVT. LTD. | Yes | Exact Name | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5046 | LOTUS TEXCOM INDIA LLP | Lost | LOTUS TEXCOM INDIA LLP | LOTUS TEXCOM INDIA LLP | 1 |  |  |  |  | LOTUS TEXCOM INDIA LLP | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5047 | BRILLIANT POLYMERS PVT. LTD | Completed |  | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | 0.64 | BIJJARGI MOTORS PVT LTD | 0.605 | PRASHANT CORNER PRIVATE LIMITED | 0.605 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Completed |  | NPSE AUTOMATION PVT. LTD. | 0.622 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.615 | MESPACK INDIA PVT. LTD | 0.605 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5049 | TAO AUTOMATION SERVICES PVT LTD | Completed |  | NPSE AUTOMATION PVT. LTD. | 0.681 | FFSERVICES PRIVATE LIMITED | 0.651 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.63 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5050 | BASANT OVERSEAS | Lost | BASANT OVERSEAS | BASANT OVERSEAS | 1 | KAMAL ENTERPRISES | 0.6 |  |  | BASANT OVERSEAS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5051 | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | Lost | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5052 | SNAPWORK TECHNOLOGIES PVT LTD | Completed | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.743 | KARVY TECHNOLOGIES PVT. LTD. | 0.727 | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5054 | BRIGHT BROTHERS LTD. / BRITE | Completed | BRIGHT BROTHERS LTD | BRIGHT BROTHERS LTD | 0.872 |  |  |  |  | BRIGHT BROTHERS LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5055 | ARMITA INDIA SHIPPING PVT. LTD | Completed |  | INDIANA GRATINGS PVT LTD | 0.609 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 0.596 | PANKAJ FASHION PVT LTD | 0.591 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Completed |  | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | 0.636 | PERFECT BELTS PVT. LTD | 0.632 | ISA LOGISTICS PRIVATE LIMITED | 0.632 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5057 | SUKHKARTA MULTISPECIALITY HOSPITAL | Lost |  | ALSHIFA MULTISPECIALTY HOSPITAL | 0.82 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5058 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Completed | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 1 | ISA LOGISTICS PRIVATE LIMITED | 0.711 | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 0.704 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Completed |  | MASTER CHAINS N JEWELS PRIVATE LIMITED | 0.64 | TRIO JEWELS PVT LTD | 0.634 | ALLIED INSTRUMENTS PRIVATE LIMITED | 0.583 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5061 | GNG ELECTRONICS LIMITED STAFF | Completed | GNG ELECTRONICS LIMITED STAFF | GNG ELECTRONICS LIMITED STAFF | 1 | GNG ELECTRONICS LIMITED FACTORY | 0.783 | BENGAL ENERGY LTD- STAFF | 0.619 | GNG ELECTRONICS LIMITED STAFF | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5062 | GNG ELECTRONICS LIMITED FACTORY | Lost | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5063 | ALLIED INSTRUMENTS PRIVATE LIMITED | Completed | ALLIED INSTRUMENTS PRIVATE LIMITED | ALLIED INSTRUMENTS PRIVATE LIMITED | 1 | SAI SANKET INDUSTRIES PVT. LTD. | 0.667 | ANM INDUSTRIES PVT LTD | 0.667 | ALLIED INSTRUMENTS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5064 | MESPACK INDIA PVT. LTD | Completed | MESPACK INDIA PVT. LTD | MESPACK INDIA PVT. LTD | 1 | AEGIS PRECISION PVT LTD | 0.632 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.622 | MESPACK INDIA PVT. LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5065 | UNITED AIR EXPRESS | Completed | UNITED AIR EXPRESS | UNITED AIR EXPRESS | 1 |  |  |  |  | UNITED AIR EXPRESS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5066 | Kuboz Arc Pvt Ltd | Lost |  | KARVY TECHNOLOGIES PVT. LTD. | 0.69 | MULTI ORGANICS PVT LTD | 0.606 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5067 | ISA Logistics Private Limited | Completed | ISA LOGISTICS PRIVATE LIMITED | ISA LOGISTICS PRIVATE LIMITED | 1 | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | 0.756 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.711 | ISA LOGISTICS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5068 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 1 |  |  |  |  | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5069 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Completed | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 1 | FEATHERTOUCH LEARNING PRIVATE LIMITED | 0.586 |  |  | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5070 | CONTENDRE GREENERGY LIMITED | Completed | CONTENDRE GREENERGY LIMITED | CONTENDRE GREENERGY LIMITED | 1 | BENGAL ENERGY LTD- STAFF | 0.585 |  |  | CONTENDRE GREENERGY LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5071 | ILEAF RITZ BANQUETS | Completed | ILEAF RITZ BANQUETS | ILEAF RITZ BANQUETS | 1 |  |  |  |  | ILEAF RITZ BANQUETS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5072 | ROYAL EMBROIDERY THREADS PVT.LTD. | Completed | ROYAL EMBROIDERY THREADS PVT.LTD. | ROYAL EMBROIDERY THREADS PVT.LTD. | 1 | AMAL EMBROIDERIES PRIVATE LIMITED | 0.76 |  |  | ROYAL EMBROIDERY THREADS PVT.LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5073 | V ALLIANCE NX | Completed | V ALLIANCE NX | V ALLIANCE NX | 1 |  |  |  |  | V ALLIANCE NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5074 | UNITED AIR EXPRESS | Completed | UNITED AIR EXPRESS | UNITED AIR EXPRESS | 1 |  |  |  |  | UNITED AIR EXPRESS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5075 | ESCON ELEVATORS PVT. LTD. | Completed | ESCON ELEVATORS PVT. LTD. | ESCON ELEVATORS PVT. LTD. | 1 | PROCON RMC PLANTS PRIVATE LIMITED | 0.634 | PERFECT BELTS PVT. LTD | 0.632 | ESCON ELEVATORS PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5076 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Lost | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | 0.87 |  |  |  |  | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5077 | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Lost | RAMYASRI ELECTRICAL AUTOMATION | RAMYASRI ELECTRICAL AUTOMATION | 0.8 |  |  |  |  | RAMYASRI ELECTRICAL AUTOMATION | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5078 | FFSERVICES PRIVATE LIMITED | Completed | FFSERVICES PRIVATE LIMITED | FFSERVICES PRIVATE LIMITED | 1 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.698 | PERFECT BELTS PVT. LTD | 0.647 | FFSERVICES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5079 | PRASAD JEWELLERS | Lost | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5080 | SETHWALA FOODS LTD | Completed | SETHWALA FOODS LTD | SETHWALA FOODS LTD | 1 | SREE METALIKS LTD | 0.581 |  |  | SETHWALA FOODS LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5081 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Completed | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 1 |  |  |  |  | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Completed | MAHWS OILFIELD SERVICES PRIVATE LIMITED | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 1 | FFSERVICES PRIVATE LIMITED | 0.698 | AMAL EMBROIDERIES PRIVATE LIMITED | 0.653 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5083 | FUJIYAMA POWER SYSTEM (UTL) | Completed | FUJIYAMA POWER SYSTEMS LIMITED | FUJIYAMA POWER SYSTEMS LIMITED | 0.889 |  |  |  |  | FUJIYAMA POWER SYSTEMS LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5084 | VABA | Completed | VABA | VABA | 1 |  |  |  |  | VABA | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5085 | KISHAN LAL PAWAN KUMAR JAIN | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5086 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Completed | MICROPOINT COMPUTERS PRIVATE LIMITED NX | MICROPOINT COMPUTERS PRIVATE LIMITED NX | 1 | CHEMITO INFOTECH PVT.LTD. | 0.583 |  |  | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5088 | POLMOR STEEL PRIVATE LIMITED | Completed |  | APMOSYS TECHNOLOGIES PVT LTD | 0.706 | PERFECT BELTS PVT. LTD | 0.629 | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 0.629 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5089 | ACEY ENGINEERING PVT. LTD | Completed |  | HELL ENERGY PVT LTD | 0.649 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | 0.623 | ANM INDUSTRIES PVT LTD | 0.6 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Completed |  | BFMS FACILITY MANAGEMENT PVT LTD | 0.594 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5091 | MEDIPULSE HOSPITAL | Completed | MEDIPULSE HOSPITAL | MEDIPULSE HOSPITAL | 1 | JIET MEDICAL COLLEGE HOSPITAL | 0.651 |  |  | MEDIPULSE HOSPITAL | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5092 | PARADISE GROUP | Active | PARADISE GROUP | PARADISE GROUP | 1 | SUVARNA DURGA GROUP | 0.6 |  |  | PARADISE GROUP | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5093 | DRS EARTHWORK PRIVATE LIMITED | Completed | DRS EARTHWORK PRIVATE LIMITED | DRS EARTHWORK PRIVATE LIMITED | 1 | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 0.667 | PRASHANT CORNER PRIVATE LIMITED | 0.632 | DRS EARTHWORK PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5094 | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Lost | CENTRE FOR URBANIZATION BUILDINGS | CENTRE FOR URBANIZATION BUILDINGS | 0.732 |  |  |  |  | CENTRE FOR URBANIZATION BUILDINGS | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Completed | PISCES CONTAINER LINES INDIA PVT. LTD. | PISCES CONTAINER LINES INDIA PVT. LTD. | 1 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | 0.648 |  |  | PISCES CONTAINER LINES INDIA PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5096 | AUROUS JEWELS LLP | Completed |  | TRIO JEWELS PVT LTD | 0.581 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5097 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Completed | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | 0.597 |  |  |  |  | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5098 | RENMAKCH INDIA PVT. LTD. | Completed |  | MESPACK INDIA PVT. LTD | 0.757 | ANM INDUSTRIES PVT LTD | 0.632 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.609 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5099 | GNG ELECTRONICS LIMITED FACTORY | Completed | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5100 | WHISTLING WOODS INTERNATIONAL | Active | [7 empty] | WHISTLING WOODS INTERNATIONAL | Yes | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5101 | VIVID ELECTROMECH LTD. / VIVID GROUP | Completed | VIVID ELECTROMECH LIMITED | VIVID ELECTROMECH LIMITED | 0.792 |  |  |  |  | VIVID ELECTROMECH LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5102 | SREE METALIKS LTD | Completed | SREE METALIKS LTD | SREE METALIKS LTD | 1 | SETHWALA FOODS LTD | 0.581 |  |  | SREE METALIKS LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5103 | NAGRIK CONSULTANCY SERVICES | Completed | NAGRIK CONSULTANCY SERVICES | NAGRIK CONSULTANCY SERVICES | 1 | MARU CONSULTANCY SERVICES | 0.875 |  |  | NAGRIK CONSULTANCY SERVICES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5104 | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed | NAIK MOTORS - RATNAGIRI LOC | NAIK MOTORS - RATNAGIRI LOC | 0.786 |  |  |  |  | NAIK MOTORS - RATNAGIRI LOC | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5105 | ANUH PHARMA PVT. LTD NX | Completed |  | QUALIGENS PHARMA PVT. LTD. | 0.718 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5106 | NAIK MOTORS -GOA LOC | Completed | NAIK MOTORS -GOA LOC | NAIK MOTORS -GOA LOC | 1 | NAIK MOTORS - RATNAGIRI LOC | 0.737 |  |  | NAIK MOTORS -GOA LOC | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5107 | PPKG AND CO | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5108 | DOSHI MEDICARE PRIVATE LIMITED | Completed |  | FFSERVICES PRIVATE LIMITED | 0.629 | MESPACK INDIA PVT. LTD | 0.595 | DRS EARTHWORK PRIVATE LIMITED | 0.595 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5109 | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Completed | FEATHERTOUCH LEARNING PRIVATE LIMITED | FEATHERTOUCH LEARNING PRIVATE LIMITED | 0.743 |  |  |  |  | FEATHERTOUCH LEARNING PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5110 | COSMOS IMPEX INDIA PVT LTD NG | Completed |  | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | 0.583 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5111 | NIKIKA ENTERPRISES LLP | Completed | NIKIKA ENTERPRISES LLP | NIKIKA ENTERPRISES LLP | 1 | KAMAL ENTERPRISES | 0.722 | MADHUSUMAN ENTERPRISES | 0.585 | NIKIKA ENTERPRISES LLP | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5112 | PRIJAI HEAT EXCHANGERS PVT. LTD. | Completed | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | 0.963 | PRASHANT CORNER PRIVATE LIMITED | 0.609 | MASTER CHAINS N JEWELS PRIVATE LIMITED | 0.588 | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5113 | parvathyhospital | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5114 | PANKAJ FASHION PVT LTD | Lost | PANKAJ FASHION PVT LTD | PANKAJ FASHION PVT LTD | 1 | RUPA SOLUTIONS PRIVATE LIMITED | 0.632 | NPSE AUTOMATION PVT. LTD. | 0.615 | PANKAJ FASHION PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5115 | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Lost | RAJESHWARI INFOTEL PVT. LTD | RAJESHWARI INFOTEL PVT. LTD | 0.92 | PRASHANT CORNER PRIVATE LIMITED | 0.596 | CHEMITO INFOTECH PVT.LTD. | 0.583 | RAJESHWARI INFOTEL PVT. LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5116 | GNG ELECTRONICS LIMITED STAFF | Completed | GNG ELECTRONICS LIMITED STAFF | GNG ELECTRONICS LIMITED STAFF | 1 | GNG ELECTRONICS LIMITED FACTORY | 0.783 | BENGAL ENERGY LTD- STAFF | 0.619 | GNG ELECTRONICS LIMITED STAFF | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5117 | Talib and Shamsi Constructions Pvt. Ltd. | Completed |  | ALLIED INSTRUMENTS PRIVATE LIMITED | 0.643 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 0.585 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5118 | Seventy Seven Entertainment Pvt Ltd | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 1 |  |  |  |  | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5119 | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Completed | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | 0.857 |  |  |  |  | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5121 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Completed | VED INDUSTRIES POC | VED INDUSTRIES POC | 0.64 |  |  |  |  | VED INDUSTRIES POC | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5122 | Procon RMC | Completed |  | PROCON RMC PLANTS PRIVATE LIMITED | 0.6 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5123 | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Completed | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | 0.711 |  |  |  |  | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5124 | SUNRISE FOODS BANGALORE | Completed | SUNRISE FOODS BANGALORE | SUNRISE FOODS BANGALORE | 1 |  |  |  |  | SUNRISE FOODS BANGALORE | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5125 | NOTCH INDIA PROJECTS | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5126 | Elixrr Industries Pvt. Ltd. | Completed | ELIXRR INDUSTRIES PVT LTD. | ELIXRR INDUSTRIES PVT LTD. | 1 | ANM INDUSTRIES PVT LTD | 0.78 | CAM TOOLS INDUSTRIES PVT LTD | 0.739 | ELIXRR INDUSTRIES PVT LTD. | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5127 | GUARDIAN CASTING PVT. LTD | Completed |  | INDIANA GRATINGS PVT LTD | 0.714 | HARDCARB TECHNOLOGIES PRIVATE LIMITED | 0.615 | RADIX INNOVATIONS PRIVATE LIMITED | 0.605 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5128 | GNG ELECTRONICS LIMITED FACTORY | Completed | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5129 | STORM FINANCIAL SERVICES | Lost | STORM FINANCIAL SERVICES | STORM FINANCIAL SERVICES | 1 |  |  |  |  | STORM FINANCIAL SERVICES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5130 | CIRCLE RESOURCES PRIVATE LIMITED | Completed | CIRCLE RESOURCES PRIVATE LIMITED | CIRCLE RESOURCES PRIVATE LIMITED | 1 | PERFECT BELTS PVT. LTD | 0.615 | AMAL EMBROIDERIES PRIVATE LIMITED | 0.605 | CIRCLE RESOURCES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5131 | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Active | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | 0.724 |  |  |  |  | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5132 | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Active | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | 0.6 |  |  |  |  | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5133 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed | RUPA SOLUTIONS PRIVATE LIMITED | RUPA SOLUTIONS PRIVATE LIMITED | 0.623 |  |  |  |  | RUPA SOLUTIONS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5134 | TRIO JEWELS PVT LTD | Active | TRIO JEWELS PVT LTD | TRIO JEWELS PVT LTD | 1 | MASTER CHAINS N JEWELS PRIVATE LIMITED | 0.732 | TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | 0.64 | TRIO JEWELS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5135 | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5136 | Navio Shipping | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5137 | VIPUL ORGANICS LTD. - STAFF | Completed | VIPUL ORGANICS LTD. - STAFF | VIPUL ORGANICS LTD. - STAFF | 1 | GNG ELECTRONICS LIMITED STAFF | 0.651 | MULTI ORGANICS PVT LTD | 0.65 | VIPUL ORGANICS LTD. - STAFF | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5138 | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Lost | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | 0.73 |  |  |  |  | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5139 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Completed | CAM TOOLS INDUSTRIES PVT LTD | CAM TOOLS INDUSTRIES PVT LTD | 0.762 | ANM INDUSTRIES PVT LTD | 0.621 |  |  | CAM TOOLS INDUSTRIES PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5141 | TRIO JEWELS PVT LTD Contractual | Active | TRIO JEWELS PVT LTD | TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | 0.885 | TRIO JEWELS PVT LTD | 0.744 |  |  | TRIO JEWELS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5142 | EMPREO PREMIUM PVT LTD | Active | EMPREO PREMIUM PVT LTD | EMPREO PREMIUM PVT LTD | 1 | EMPREO WHEEL PVT LIMITED (MG) | 0.684 | CIRCLE RESOURCES PRIVATE LIMITED | 0.6 | EMPREO PREMIUM PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5143 | EMPREO WHEEL PVT LIMITED (MG) | Active | EMPREO WHEEL PVT LIMITED (MG) | EMPREO WHEEL PVT LIMITED (MG) | 1 | EMPREO PREMIUM PVT LTD | 0.684 | PERFECT BELTS PVT. LTD | 0.595 | EMPREO WHEEL PVT LIMITED (MG) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5144 | SHREEKHETRA AUTOMOTIVE (TATA) | Active | SHREEKHETRA AUTOMOTIVE (TATA) | SHREEKHETRA AUTOMOTIVE (TATA) | 1 |  |  |  |  | SHREEKHETRA AUTOMOTIVE (TATA) | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5145 | AMAL EMBROIDERIES PVT. LTD | Active | AMAL EMBROIDERIES PRIVATE LIMITED | AMAL EMBROIDERIES PRIVATE LIMITED | 1 | ROYAL EMBROIDERY THREADS PVT.LTD. | 0.76 | ANM INDUSTRIES PVT LTD | 0.683 | AMAL EMBROIDERIES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Completed | AEGIS PRECISION PVT LTD | AEGIS PRECISION PVT LTD | 0.69 |  |  |  |  | AEGIS PRECISION PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5147 | MULTI ORGANICS PVT LTD | Active | MULTI ORGANICS PVT LTD | MULTI ORGANICS PVT LTD | 1 | RUPA SOLUTIONS PRIVATE LIMITED | 0.684 | VIPUL ORGANICS LTD. - STAFF | 0.65 | MULTI ORGANICS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5148 | BFMS FACILITY MANAGEMENT PVT LTD | Lost | BFMS FACILITY MANAGEMENT PVT LTD | BFMS FACILITY MANAGEMENT PVT LTD | 1 |  |  |  |  | BFMS FACILITY MANAGEMENT PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5149 | MANJUSHREE INNOVATIONS PVT. LTD | Active | MANJUSHREE INNOVATIONS PRIVATE LIMITED | MANJUSHREE INNOVATIONS PRIVATE LIMITED | 1 | RADIX INNOVATIONS PRIVATE LIMITED | 0.735 | PANKAJ FASHION PVT LTD | 0.609 | MANJUSHREE INNOVATIONS PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5150 | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Active | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | 0.793 |  |  |  |  | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5151 | Mansha Agencies | Active | MANSHA AGENCIES PVT LTD | MANSHA AGENCIES PVT LTD | 0.824 |  |  |  |  | MANSHA AGENCIES PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5152 | Muktangan Education Trust | Active | MUKTANGAN EDUCATION TRUST. NX | MUKTANGAN EDUCATION TRUST. NX | 0.958 |  |  |  |  | MUKTANGAN EDUCATION TRUST. NX | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5153 | Vivan Associate | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5154 | BSA CORPORATION LIMITED / BSA GROUP | Active |  | BSA CORPORATION LIMITED | 0.81 | NAVKAR CORPORATION LIMITED NG | 0.681 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5155 | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Active | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | 0.835 |  |  |  |  | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5156 | SACRED HEART HOSPITAL JAL | Active | SACRED HEART HOSPITAL JAL | SACRED HEART HOSPITAL JAL | 1 |  |  |  |  | SACRED HEART HOSPITAL JAL | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5157 | VED INDUSTRIES/ ROHIDA GROUP | Active |  | VED INDUSTRIES | 0.703 | VED INDUSTRIES POC | 0.7 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5158 | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5159 | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Lost | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | 1 | SAI SANKET INDUSTRIES PVT. LTD. | 0.604 | MANJUSHREE INNOVATIONS PRIVATE LIMITED | 0.582 | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5160 | ANS NG | Completed | ANS NG | ANS NG | 1 |  |  |  |  | ANS NG | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5161 | STERLING LIFESTYLE LLP | Completed | STERLING LIFESTYLE LLP | STERLING LIFESTYLE LLP | 1 |  |  |  |  | STERLING LIFESTYLE LLP | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5162 | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5163 | HELL ENERGY PVT LTD | Active | HELL ENERGY PVT LTD | HELL ENERGY PVT LTD | 1 | BENGAL ENERGY LTD- STAFF | 0.611 |  |  | HELL ENERGY PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5164 | VISHWAKARMA FOUNDERS (I) PVT. LTD | Active |  | VISHWAKARMA FOUNDERS (I) PVT. LTD. - STAFF | 0.912 | VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | 0.897 | AMAL EMBROIDERIES PRIVATE LIMITED | 0.583 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5165 | Navio Shipping | Completed | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5166 | CREATIONS BY SHANAGAR | Active |  | CREATIONS BY SHANGAR | 0.973 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5167 | AKRITI PHARMACEUTICALS PVT LTD | Active | AKRITI PHARMACEUTICALS PVT LTD | AKRITI PHARMACEUTICALS PVT LTD | 1 | QUALIGENS PHARMA PVT. LTD. | 0.583 |  |  | AKRITI PHARMACEUTICALS PVT LTD | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5168 | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Active |  | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY | 0.932 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5169 | JIET MEDICAL COLLEGE HOSPITAL | Active | JIET MEDICAL COLLEGE HOSPITAL | JIET MEDICAL COLLEGE HOSPITAL | 1 | MEDIPULSE HOSPITAL | 0.651 | PARBHANI MEDICAL COLLEGE (PMC) | 0.627 | JIET MEDICAL COLLEGE HOSPITAL | Yes | Approved Alias | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5170 | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5171 | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5172 | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Yet To Start | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5173 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Active |  | ALSHIFA MULTISPECIALTY HOSPITAL | 0.773 | [5 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5174 | NAVKAR CORPORATION LIMITED | Yet To Start |  | NAVKAR CORPORATION LIMITED NG | 0.952 | BSA CORPORATION LIMITED | 0.811 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 0.632 |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5175 | THE KANDIVALI EDUCATION SOCIETY | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5176 | ARTSON LIMITED | Completed |  | MUKTA ARTS LTD | 0.667 | BSA CORPORATION LIMITED | 0.615 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5177 | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Active | [8 empty] | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5178 | APMOSYS TECHNOLOGIES PVT LTD | Active | APMOSYS TECHNOLOGIES PVT LTD | APMOSYS TECHNOLOGIES PVT LTD | 1 | KARVY TECHNOLOGIES PVT. LTD. | 0.75 | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 0.743 | APMOSYS TECHNOLOGIES PVT LTD | Yes | Exact Name | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5179 | CONTENDRE GREENERGY PVT. LTD | Active |  | CONTENDRE GREENERGY LIMITED | 0.933 | HELL ENERGY PVT LTD | 0.65 |  |  |  | No | No Match | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5180 | PERFECT BELTS PVT. LTD | Active | PERFECT BELTS PVT. LTD | PERFECT BELTS PVT. LTD | 1 | ESCON ELEVATORS PVT. LTD. | 0.632 | CIRCLE RESOURCES PRIVATE LIMITED | 0.615 | PERFECT BELTS PVT. LTD | Yes | Exact Name | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.
5181 | Saffron Speciality Papers Limited | Active | SAFFRON SPECIALITY PAPERS LIMITED | SAFFRON SPECIALITY PAPERS LIMITED | 1 |  |  |  |  | SAFFRON SPECIALITY PAPERS LIMITED | Yes | Exact Name | Update Final SCH Client Name and Approved=Yes if the suggested match is correct.

## Alias_Matching_SCH
SCH Client Name | SCH Status | Current Matched Tracker Project | Suggested Tracker Match 1 | Score 1 | Suggested Tracker Match 2 | Score 2 | Suggested Tracker Match 3 | Score 3 | Final Tracker Project Name | Approved | Review Notes
APMOSYS TECHNOLOGIES PVT LTD | Active | APMOSYS TECHNOLOGIES PVT LTD | APMOSYS TECHNOLOGIES PVT LTD | 1 | KARVY TECHNOLOGIES PVT LTD | 0.75 | SNAPWORK TECHNOLOGIES PVT LTD | 0.743 | APMOSYS TECHNOLOGIES PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CONTENDRE GREENERGY LIMITED | Active | CONTENDRE GREENERGY LIMITED | CONTENDRE GREENERGY LIMITED | 1 | CONTENDRE GREENERGY PVT. LTD | 0.933 |  |  | CONTENDRE GREENERGY LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PERFECT BELTS PVT. LTD | Active | PERFECT BELTS PVT. LTD | PERFECT BELTS PVT. LTD | 1 | ERMELLI PRIVATE LIMITED | 0.645 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.632 | PERFECT BELTS PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ALSHIFA MULTISPECIALTY HOSPITAL | Active |  | SUKHKARTA MULTISPECIALITY HOSPITAL | 0.787 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | 0.773 |  |  |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NAVKAR CORPORATION LIMITED NG | Pending For Milestone |  | NAVKAR CORPORATION LIMITED | 0.952 | BSA CORPORATION LIMITED / BSA GROUP | 0.681 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 0.61 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MAHATMA PHULE CHARITABLE TRUST | Active | [8 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SURANA CHARITABLE TRUST | Active | [8 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SAI SANKET INDUSTRIES PVT. LTD. | Pending For Milestone | SAI SANKET INDUSTRIES PVT.LTD | SAI SANKET INDUSTRIES PVT.LTD | 1 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.783 | Elixrr Industries Pvt. Ltd. | 0.723 | SAI SANKET INDUSTRIES PVT.LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
JIET MEDICAL COLLEGE HOSPITAL | Active | JIET MEDICAL COLLEGE HOSPITAL | JIET MEDICAL COLLEGE HOSPITAL | 1 | MEDIPULSE HOSPITAL | 0.651 | Parbhani Medical College | 0.625 | JIET MEDICAL COLLEGE HOSPITAL | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY | Active |  | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | 0.932 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CREATIONS BY SHANGAR | Active |  | CREATIONS BY SHANAGAR | 0.973 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VISHWAKARMA FOUNDERS (I) PVT. LTD. - STAFF | Active |  | VISHWAKARMA FOUNDERS (I) PVT. LTD | 0.912 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | Active |  | VISHWAKARMA FOUNDERS (I) PVT. LTD | 0.897 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Go LIVE | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | 0.857 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.636 | ERMELLI PRIVATE LIMITED | 0.595 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
HELL ENERGY PVT LTD | AC | HELL ENERGY PVT LTD | HELL ENERGY PVT LTD | 1 | CONTENDRE GREENERGY PVT. LTD | 0.65 | ACEY ENGINEERING PVT. LTD | 0.649 | HELL ENERGY PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AKRITI PHARMACEUTICALS PVT LTD | Active | AKRITI PHARMACEUTICALS PVT LTD | AKRITI PHARMACEUTICALS PVT LTD | 1 | QUALIGENS PHARMA PVT. LTD | 0.583 |  |  | AKRITI PHARMACEUTICALS PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Go LIVE | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | 0.857 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.636 | ERMELLI PRIVATE LIMITED | 0.595 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CKIM PROMOTERS LLP | Active | [8 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VED INDUSTRIES | Active |  | VED INDUSTRIES/ ROHIDA GROUP | 0.703 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.647 | Elixrr Industries Pvt. Ltd. | 0.629 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | Active | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | 0.835 |  |  |  |  | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SACRED HEART HOSPITAL JAL | AC | SACRED HEART HOSPITAL JAL | SACRED HEART HOSPITAL JAL | 1 |  |  |  |  | SACRED HEART HOSPITAL JAL | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CRYOGAS EQUIPMENT PRIVATE LIMITED NG | Active | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | 0.793 |  |  |  |  | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MANJUSHREE INNOVATIONS PRIVATE LIMITED | Active | MANJUSHREE INNOVATIONS PVT. LTD | MANJUSHREE INNOVATIONS PVT. LTD | 1 | PANKAJ FASHION PVT LTD | 0.609 | ESCON ELEVATORS PVT. LTD. | 0.596 | MANJUSHREE INNOVATIONS PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AMAL EMBROIDERIES PRIVATE LIMITED | AC | AMAL EMBROIDERIES PVT. LTD | AMAL EMBROIDERIES PVT. LTD | 1 | ROYAL EMBROIDERY THREADS PVT.LTD. | 0.76 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.653 | AMAL EMBROIDERIES PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ANS NG | AC | ANS NG | ANS NG | 1 |  |  |  |  | ANS NG | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | Lost | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | 0.73 | TAO AUTOMATION SERVICES PVT LTD | 0.593 |  |  | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BSA CORPORATION LIMITED | Active |  | NAVKAR CORPORATION LIMITED | 0.811 | BSA CORPORATION LIMITED / BSA GROUP | 0.81 | NPSE AUTOMATION PVT. LTD | 0.595 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CAM TOOLS INDUSTRIES PVT LTD | FC | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | 0.762 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.756 | Elixrr Industries Pvt. Ltd. | 0.739 | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MULTI ORGANICS PVT LTD | Active | MULTI ORGANICS PVT LTD | MULTI ORGANICS PVT LTD | 1 | VIPUL ORGANICS LTD. - STAFF | 0.65 | TAO AUTOMATION SERVICES PVT LTD | 0.609 | MULTI ORGANICS PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GNG ELECTRONICS LIMITED STAFF | FC | GNG ELECTRONICS LIMITED STAFF | GNG ELECTRONICS LIMITED STAFF | 1 | GNG ELECTRONICS LIMITED FACTORY | 0.783 | VIPUL ORGANICS LTD. - STAFF | 0.605 | GNG ELECTRONICS LIMITED STAFF | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VOGUE N HYDE PVT. LTD | Active |  | KARVY TECHNOLOGIES PVT LTD | 0.581 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | Active |  | TRIO JEWELS PVT LTD Contractual | 0.885 | TRIO JEWELS PVT LTD | 0.64 | APLAB LIMITED (FOR CONTRACT LICENSE) | 0.633 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
TRIO JEWELS PVT LTD | AC | TRIO JEWELS PVT LTD, TRIO JEWELS PVT LTD Contractual | TRIO JEWELS PVT LTD | 1 | TRIO JEWELS PVT LTD Contractual | 0.744 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | 0.732 | TRIO JEWELS PVT LTD Contractual | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Lost | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | 1 | SAI SANKET INDUSTRIES PVT.LTD | 0.604 | STEAM HARBOUR LOGISTICS PVT LTD | 0.582 | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RUPA SOLUTIONS PRIVATE LIMITED | Active | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | MULTI ORGANICS PVT LTD | 0.684 | PANKAJ FASHION PVT LTD | 0.632 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | 0.623 | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | Active | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | 0.724 |  |  |  |  | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | Held | SHRI JANARDAN SWAMI HOSPITAL (SJS) | SHRI JANARDAN SWAMI HOSPITAL (SJS) | 0.6 |  |  |  |  | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
STORM FINANCIAL SERVICES | Lost | STORM FINANCIAL SERVICES | STORM FINANCIAL SERVICES | 1 |  |  |  |  | STORM FINANCIAL SERVICES | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MANSHA AGENCIES PVT LTD | Active | Mansha Agencies | Mansha Agencies | 0.824 | FFSERVICES PRIVATE LIMITED | 0.611 | TAO AUTOMATION SERVICES PVT LTD | 0.596 | Mansha Agencies | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
EMPREO WHEEL PVT LIMITED (MG) | Active | EMPREO WHEEL PVT LIMITED (MG) | EMPREO WHEEL PVT LIMITED (MG) | 1 | EMPREO PREMIUM PVT LTD | 0.684 | ERMELLI PRIVATE LIMITED | 0.625 | EMPREO WHEEL PVT LIMITED (MG) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SHREEKHETRA AUTOMOTIVE (TATA) | Lost | SHREEKHETRA AUTOMOTIVE (TATA) | SHREEKHETRA AUTOMOTIVE (TATA) | 1 |  |  |  |  | SHREEKHETRA AUTOMOTIVE (TATA) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
EMPREO PREMIUM PVT LTD | Active | EMPREO PREMIUM PVT LTD | EMPREO PREMIUM PVT LTD | 1 | EMPREO WHEEL PVT LIMITED (MG) | 0.684 | ERMELLI PRIVATE LIMITED | 0.625 | EMPREO PREMIUM PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VED INDUSTRIES POC | Go LIVE | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | VED INDUSTRIES/ ROHIDA GROUP | 0.7 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.649 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | 0.64 | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FFSERVICES PRIVATE LIMITED | Go LIVE | FFSERVICES PRIVATE LIMITED | FFSERVICES PRIVATE LIMITED | 1 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.698 | TAO AUTOMATION SERVICES PVT LTD | 0.651 | FFSERVICES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Go LIVE | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | 0.857 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.636 | ERMELLI PRIVATE LIMITED | 0.595 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GNG ELECTRONICS LIMITED FACTORY | Go LIVE | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
STERLING LIFESTYLE LLP | AC | STERLING LIFESTYLE LLP | STERLING LIFESTYLE LLP | 1 |  |  |  |  | STERLING LIFESTYLE LLP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PANKAJ FASHION PVT LTD | Lost | PANKAJ FASHION PVT LTD | PANKAJ FASHION PVT LTD | 1 | NPSE AUTOMATION PVT. LTD | 0.615 | MANJUSHREE INNOVATIONS PVT. LTD | 0.609 | PANKAJ FASHION PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MUKTANGAN EDUCATION TRUST. NX | Active | Muktangan Education Trust | Muktangan Education Trust | 0.958 |  |  |  |  | Muktangan Education Trust | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SUVARNA DURGA GROUP | AC |  | PARADISE GROUP | 0.6 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BFMS FACILITY MANAGEMENT PVT LTD | Held | BFMS FACILITY MANAGEMENT PVT LTD | BFMS FACILITY MANAGEMENT PVT LTD | 1 | ATHARVA FACILITY MANAGEMENT AND SECURITY | 0.594 |  |  | BFMS FACILITY MANAGEMENT PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SUNRISE FOODS BANGALORE | Held | SUNRISE FOODS BANGALORE | SUNRISE FOODS BANGALORE | 1 |  |  |  |  | SUNRISE FOODS BANGALORE | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
EVERGREEN HOUSEKEEPING SERVICES PRIVATE | Active | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | 0.711 |  |  |  |  | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RAJESHWARI INFOTEL PVT. LTD | Lost | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | 0.92 | TRIO JEWELS PVT LTD | 0.615 | MANJUSHREE INNOVATIONS PVT. LTD | 0.6 | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NIKIKA ENTERPRISES LLP | Go LIVE | NIKIKA ENTERPRISES LLP | NIKIKA ENTERPRISES LLP | 1 |  |  |  |  | NIKIKA ENTERPRISES LLP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | FC | PRIJAI HEAT EXCHANGERS PVT. LTD. | PRIJAI HEAT EXCHANGERS PVT. LTD. | 0.963 |  |  |  |  | PRIJAI HEAT EXCHANGERS PVT. LTD. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FEATHERTOUCH LEARNING PRIVATE LIMITED | FC | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | 0.743 |  |  |  |  | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GNG ELECTRONICS LIMITED FACTORY | Go LIVE | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NAIK MOTORS - RATNAGIRI LOC | AC | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | 0.786 | NAIK MOTORS -GOA LOC | 0.737 |  |  | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NAIK MOTORS -GOA LOC | AC | NAIK MOTORS -GOA LOC | NAIK MOTORS -GOA LOC | 1 |  |  |  |  | NAIK MOTORS -GOA LOC | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SREE METALIKS LTD | Go LIVE | SREE METALIKS LTD | SREE METALIKS LTD | 1 | SETHWALA FOODS LTD | 0.581 |  |  | SREE METALIKS LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VIVID ELECTROMECH LIMITED | FC Lost | VIVID ELECTROMECH LTD. / VIVID GROUP | VIVID ELECTROMECH LTD. / VIVID GROUP | 0.792 |  |  |  |  | VIVID ELECTROMECH LTD. / VIVID GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NAGRIK CONSULTANCY SERVICES | FC | NAGRIK CONSULTANCY SERVICES | NAGRIK CONSULTANCY SERVICES | 1 | MARU CONSULTANCY SERVICES | 0.875 |  |  | NAGRIK CONSULTANCY SERVICES | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SAFFRON SPECIALITY PAPERS LIMITED | Active | Saffron Speciality Papers Limited | Saffron Speciality Papers Limited | 1 |  |  |  |  | Saffron Speciality Papers Limited | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
HARDCARB TECHNOLOGIES PVT. LTD - STAFF | FC | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Hardcarb Technologies Private Limited | 0.878 | KARVY TECHNOLOGIES PVT LTD | 0.632 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | 0.6 | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CENTRE FOR URBANIZATION BUILDINGS | Active | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | 0.732 |  |  |  |  | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PARADISE GROUP | AC | PARADISE GROUP | PARADISE GROUP | 1 |  |  |  |  | PARADISE GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MEDIPULSE HOSPITAL | AC | MEDIPULSE HOSPITAL | MEDIPULSE HOSPITAL | 1 | JIET MEDICAL COLLEGE HOSPITAL | 0.651 |  |  | MEDIPULSE HOSPITAL | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FUJIYAMA POWER SYSTEMS LIMITED | Lost | FUJIYAMA POWER SYSTEM (UTL) | FUJIYAMA POWER SYSTEM (UTL) | 0.889 |  |  |  |  | FUJIYAMA POWER SYSTEM (UTL) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SETHWALA FOODS LTD | FC | SETHWALA FOODS LTD | SETHWALA FOODS LTD | 1 | SREE METALIKS LTD | 0.581 |  |  | SETHWALA FOODS LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RAMYASRI ELECTRICAL AUTOMATION | Lost | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | 0.8 |  |  |  |  | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | Lost | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | 0.87 | PISCES CONTAINER LINES INDIA PVT. LTD. | 0.62 | ACEY ENGINEERING PVT. LTD | 0.59 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MUKTA ARTS LTD | Active |  | ARTSON LIMITED | 0.667 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ILEAF RITZ BANQUETS | Lost | ILEAF RITZ BANQUETS | ILEAF RITZ BANQUETS | 1 |  |  |  |  | ILEAF RITZ BANQUETS | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
UNITED AIR EXPRESS | FC | UNITED AIR EXPRESS | UNITED AIR EXPRESS | 1 |  |  |  |  | UNITED AIR EXPRESS | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MESPACK INDIA PVT. LTD | FC | MESPACK INDIA PVT. LTD | MESPACK INDIA PVT. LTD | 1 | RENMAKCH INDIA PVT. LTD. | 0.757 | STEAM PULSE INDIA PVT LTD | 0.667 | MESPACK INDIA PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CIRCLE RESOURCES PRIVATE LIMITED | FC | CIRCLE RESOURCES PRIVATE LIMITED | CIRCLE RESOURCES PRIVATE LIMITED | 1 | PERFECT BELTS PVT. LTD | 0.615 | Elixrr Industries Pvt. Ltd. | 0.605 | CIRCLE RESOURCES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BRIGHT BROTHERS LTD | FC | BRIGHT BROTHERS LTD. / BRITE | BRIGHT BROTHERS LTD. / BRITE | 0.872 |  |  |  |  | BRIGHT BROTHERS LTD. / BRITE | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Go LIVE | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 1 | NAVKAR CORPORATION LIMITED | 0.596 |  |  | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PROCON RMC PLANTS PRIVATE LIMITED | FC |  | PERFECT BELTS PVT. LTD | 0.615 | Procon RMC | 0.6 |  |  |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
DRS EARTHWORK PRIVATE LIMITED | FC | DRS EARTHWORK PRIVATE LIMITED | DRS EARTHWORK PRIVATE LIMITED | 1 | SNAPWORK TECHNOLOGIES PVT LTD | 0.667 | KARVY TECHNOLOGIES PVT LTD | 0.606 | DRS EARTHWORK PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SNAPWORK TECHNOLOGIES PRIVATE LIMITED | FC | SNAPWORK TECHNOLOGIES PVT LTD | SNAPWORK TECHNOLOGIES PVT LTD | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.743 | KARVY TECHNOLOGIES PVT LTD | 0.727 | SNAPWORK TECHNOLOGIES PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ASHWINI CONTAINER MOVERS LIMITED | Lost | [8 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ELECTROSTEEL CASTINGS LTD | FC | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | 0.73 | RADIX ELECTROSYSTEMS PVT LTD | 0.625 |  |  | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CONTENDRE GREENERGY LIMITED | FC | CONTENDRE GREENERGY LIMITED | CONTENDRE GREENERGY LIMITED | 1 | CONTENDRE GREENERGY PVT. LTD | 0.933 |  |  | CONTENDRE GREENERGY LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Go LIVE | STEAM HARBOUR LOGISTICS PVT LTD, STEAM PULSE INDIA PVT LTD | STEAM HARBOUR LOGISTICS PVT LTD | 1 | ISA Logistics Private Limited | 0.756 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.704 | STEAM PULSE INDIA PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VABA | Go LIVE | VABA | VABA | 1 |  |  |  |  | VABA | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ROYAL EMBROIDERY THREADS PVT.LTD. | FC | ROYAL EMBROIDERY THREADS PVT.LTD. | ROYAL EMBROIDERY THREADS PVT.LTD. | 1 | AMAL EMBROIDERIES PVT. LTD | 0.76 |  |  | ROYAL EMBROIDERY THREADS PVT.LTD. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BIJJARGI MOTORS PVT LTD | Go LIVE |  | ISA Logistics Private Limited | 0.632 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BASANT OVERSEAS | Lost | BASANT OVERSEAS | BASANT OVERSEAS | 1 |  |  |  |  | BASANT OVERSEAS | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MASTER CHAINS N JEWELS PRIVATE LIMITED | Go LIVE |  | TRIO JEWELS PVT LTD | 0.732 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | 0.64 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.609 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MADURA INDUSTRIAL TEXTILES LIMITED. | Go LIVE | MADURA INDUSTRIAL TEXTILES LIMITED | MADURA INDUSTRIAL TEXTILES LIMITED | 1 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.583 |  |  | MADURA INDUSTRIAL TEXTILES LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
QUALIGENS PHARMA PVT. LTD. | Go LIVE | QUALIGENS PHARMA PVT. LTD | QUALIGENS PHARMA PVT. LTD | 1 | ANUH PHARMA PVT. LTD NX | 0.667 | AKRITI PHARMACEUTICALS PVT LTD | 0.583 | QUALIGENS PHARMA PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ANM INDUSTRIES PVT LTD | Go LIVE |  | SEEBA INDUSTRIES PRIVATE LIMITED | 0.85 | SAI SANKET INDUSTRIES PVT.LTD | 0.818 | Elixrr Industries Pvt. Ltd. | 0.78 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
KARVY TECHNOLOGIES PVT. LTD. | Lost | KARVY TECHNOLOGIES PVT LTD | KARVY TECHNOLOGIES PVT LTD | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.75 | Hardcarb Technologies Private Limited | 0.727 | KARVY TECHNOLOGIES PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MAHWS OILFIELD SERVICES PRIVATE LIMITED | Go LIVE | MAHWS OILFIELD SERVICES PRIVATE LIMITED | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 1 | FFSERVICES PRIVATE LIMITED | 0.698 | AMAL EMBROIDERIES PVT. LTD | 0.653 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
APLAB LIMITED (FOR CONTRACT LICENSE) | Go LIVE | APLAB LIMITED (FOR CONTRACT LICENSE) | APLAB LIMITED (FOR CONTRACT LICENSE) | 1 | APLAB LIMITED (FOR STAFF LICENSE) | 0.816 |  |  | APLAB LIMITED (FOR CONTRACT LICENSE) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
APLAB LIMITED (FOR STAFF LICENSE) | Go LIVE | APLAB LIMITED (FOR STAFF LICENSE) | APLAB LIMITED (FOR STAFF LICENSE) | 1 | APLAB LIMITED (FOR CONTRACT LICENSE) | 0.816 |  |  | APLAB LIMITED (FOR STAFF LICENSE) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SHREE RAMDEV METALEX LLP | Go LIVE | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | 0.792 |  |  |  |  | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MARU CONSULTANCY SERVICES | Lost | MARU CONSULTANCY SERVICES | MARU CONSULTANCY SERVICES | 1 | NAGRIK CONSULTANCY SERVICES | 0.875 |  |  | MARU CONSULTANCY SERVICES | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RADIX ELECTROSYSTEMS PVT LTD | Go LIVE | RADIX ELECTROSYSTEMS PVT LTD | RADIX ELECTROSYSTEMS PVT LTD | 1 | APMOSYS TECHNOLOGIES PVT LTD | 0.619 |  |  | RADIX ELECTROSYSTEMS PVT LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
INDIANA GRATINGS PVT LTD | FC | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | 0.778 | GUARDIAN CASTING PVT. LTD | 0.714 | ARMITA INDIA SHIPPING PVT. LTD | 0.609 | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ISA LOGISTICS PRIVATE LIMITED | FC | ISA Logistics Private Limited | ISA Logistics Private Limited | 1 | STEAM HARBOUR LOGISTICS PVT LTD | 0.756 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.711 | ISA Logistics Private Limited | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GNG ELECTRONICS LIMITED FACTORY | Go LIVE | GNG ELECTRONICS LIMITED FACTORY | GNG ELECTRONICS LIMITED FACTORY | 1 | GNG ELECTRONICS LIMITED STAFF | 0.783 |  |  | GNG ELECTRONICS LIMITED FACTORY | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ALLIED INSTRUMENTS PRIVATE LIMITED | FC | ALLIED INSTRUMENTS PRIVATE LIMITED | ALLIED INSTRUMENTS PRIVATE LIMITED | 1 | SAI SANKET INDUSTRIES PVT.LTD | 0.667 | Elixrr Industries Pvt. Ltd. | 0.667 | ALLIED INSTRUMENTS PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GNG ELECTRONICS LIMITED STAFF | Go LIVE | GNG ELECTRONICS LIMITED STAFF | GNG ELECTRONICS LIMITED STAFF | 1 | GNG ELECTRONICS LIMITED FACTORY | 0.783 | VIPUL ORGANICS LTD. - STAFF | 0.605 | GNG ELECTRONICS LIMITED STAFF | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
S K TRADERS NX | Go LIVE | S K Traders | S K Traders | 0.9 |  |  |  |  | S K Traders | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
KHERWADI SOCIAL WELFARE ASSOCIATION | Go LIVE | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | 0.821 |  |  |  |  | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MADHUSUMAN ENTERPRISES | FC Lost | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | 0.677 | NIKIKA ENTERPRISES LLP | 0.585 |  |  | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PARBHANI MEDICAL COLLEGE (PMC) | Lost | Parbhani Medical College | Parbhani Medical College | 0.936 | JIET MEDICAL COLLEGE HOSPITAL | 0.627 |  |  | Parbhani Medical College | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BENGAL ENERGY LTD- CONTRACTUAL | Lost | Bengal Energy_Worker | Bengal Energy_Staff | 0.651 | Bengal Energy_Worker | 0.636 | TRIO JEWELS PVT LTD Contractual | 0.604 | Bengal Energy_Worker | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
BENGAL ENERGY LTD- STAFF | Go LIVE | Bengal Energy_Staff | Bengal Energy_Staff | 0.919 | Bengal Energy_Worker | 0.632 | GNG ELECTRONICS LIMITED STAFF | 0.619 | Bengal Energy_Staff | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | Go LIVE | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | 0.807 | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | 0.655 | APLAB LIMITED (FOR STAFF LICENSE) | 0.642 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | Go LIVE | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | 0.814 | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | 0.655 |  |  | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Go LIVE | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 1 | AUTOTECH-SIRMAX INDIA PVT LTD | 0.596 | ARMITA INDIA SHIPPING PVT. LTD | 0.596 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SKY PRINTS | Go LIVE | Sky Prints | Sky Prints | 1 |  |  |  |  | Sky Prints | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NPSE AUTOMATION PVT. LTD. | Lost | NPSE AUTOMATION PVT. LTD | NPSE AUTOMATION PVT. LTD | 1 | TAO AUTOMATION SERVICES PVT LTD | 0.681 | MANJUSHREE INNOVATIONS PVT. LTD | 0.638 | NPSE AUTOMATION PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
LOTUS TEXCOM INDIA LLP | Lost | LOTUS TEXCOM INDIA LLP | LOTUS TEXCOM INDIA LLP | 1 |  |  |  |  | LOTUS TEXCOM INDIA LLP | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | FC Lost | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | 1 |  |  |  |  | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
HARDCARB TECHNOLOGIES PRIVATE LIMITED | Go LIVE | Hardcarb Technologies Private Limited | Hardcarb Technologies Private Limited | 1 | KARVY TECHNOLOGIES PVT LTD | 0.727 | SNAPWORK TECHNOLOGIES PVT LTD | 0.667 | Hardcarb Technologies Private Limited | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MAHARASHTRA BOOK MANUFACTURING COMPANY NX | FC | Maharashtra Book Manufacturing | Maharashtra Book Manufacturing | 0.933 |  |  |  |  | Maharashtra Book Manufacturing | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CARTFIRE INDIA | Go LIVE | Cartfire India | Cartfire India | 1 |  |  |  |  | Cartfire India | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
V ALLIANCE NX | Go LIVE | V ALLIANCE NX | V ALLIANCE NX | 1 |  |  |  |  | V ALLIANCE NX | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AQUAAIR INTERNATIONAL FREIGHT SERVICES | Go LIVE | Aquaair International Frieght Services | Aquaair International Frieght Services | 0.962 |  |  |  |  | Aquaair International Frieght Services | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
RADIX INNOVATIONS PRIVATE LIMITED | Go LIVE |  | MANJUSHREE INNOVATIONS PVT. LTD | 0.735 | NPSE AUTOMATION PVT. LTD | 0.619 | RADIX ELECTROSYSTEMS PVT LTD | 0.596 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ONETEAM LOGISTICS INDIA PRIVATE LIMITED | FC Lost | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 1 | ISA Logistics Private Limited | 0.711 | STEAM PULSE INDIA PVT LTD | 0.708 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ANS NG | Go LIVE | ANS NG | ANS NG | 1 |  |  |  |  | ANS NG | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PVR CONTROLS -STAFF LICENSE | Go LIVE |  | APLAB LIMITED (FOR CONTRACT LICENSE) | 0.612 | APLAB LIMITED (FOR STAFF LICENSE) | 0.609 |  |  |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MUKTANGAN EDUCATION TRUST. NX | Go LIVE | Muktangan Education Trust | Muktangan Education Trust | 0.958 |  |  |  |  | Muktangan Education Trust | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
INFEXN LABORATORIES PVT LTD | Go LIVE | Infexn Laboratories | Infexn Laboratories | 0.857 | ESCON ELEVATORS PVT. LTD. | 0.636 | NPSE AUTOMATION PVT. LTD | 0.591 | Infexn Laboratories | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MICROPOINT COMPUTERS PRIVATE LIMITED NX | Go LIVE | MICROPOINT COMPUTERS PRIVATE LIMITED NX | MICROPOINT COMPUTERS PRIVATE LIMITED NX | 1 |  |  |  |  | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FFSERVICES PRIVATE LIMITED | Go LIVE | FFSERVICES PRIVATE LIMITED | FFSERVICES PRIVATE LIMITED | 1 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.698 | TAO AUTOMATION SERVICES PVT LTD | 0.651 | FFSERVICES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
LATHIA RUBBER MFG CO. PVT. LTD. | Go LIVE |  | Hardcarb Technologies Private Limited | 0.585 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PITAMBARI PRODUCTS PVT. LTD. | Go LIVE |  | CIRCLE RESOURCES PRIVATE LIMITED | 0.591 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SANKALPAN INFRASTRUCTURE PVT. LTD. | Go LIVE |  | SAI SANKET INDUSTRIES PVT.LTD | 0.593 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
NATIONAL SPORTS CLUB OF INDIA NX | Active | THE NATIONAL SPORTS CLUB OF INDIA | THE NATIONAL SPORTS CLUB OF INDIA | 0.909 |  |  |  |  | THE NATIONAL SPORTS CLUB OF INDIA | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AEGIS PRECISION PVT LTD | Go LIVE | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 0.69 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.65 | ACEY ENGINEERING PVT. LTD | 0.634 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SAI SANKET INDUSTRIES PVT. LTD. | Go LIVE | SAI SANKET INDUSTRIES PVT.LTD | SAI SANKET INDUSTRIES PVT.LTD | 1 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.783 | Elixrr Industries Pvt. Ltd. | 0.723 | SAI SANKET INDUSTRIES PVT.LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PRASHANT CORNER PRIVATE LIMITED | Go LIVE |  | PRIJAI HEAT EXCHANGERS PVT. LTD. | 0.609 | BRILLIANT POLYMERS PVT. LTD | 0.605 | ESCON ELEVATORS PVT. LTD. | 0.6 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MAHWS OILFIELD SERVICES PRIVATE LIMITED | Go LIVE | MAHWS OILFIELD SERVICES PRIVATE LIMITED | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 1 | FFSERVICES PRIVATE LIMITED | 0.698 | AMAL EMBROIDERIES PVT. LTD | 0.653 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MUMBAI CARGO SERVICE CENTER AIRPORT PVT. LTD NX | Go LIVE | [8 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ELIXRR INDUSTRIES PVT LTD. | Go LIVE | Elixrr Industries Pvt. Ltd. | Elixrr Industries Pvt. Ltd. | 1 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.791 | SAI SANKET INDUSTRIES PVT.LTD | 0.723 | Elixrr Industries Pvt. Ltd. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Go LIVE | SEVENTY SEVEN ENTERTAINMENT PVT. LTD, Seventy Seven Entertainment Pvt Ltd | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | 1 | Seventy Seven Entertainment Pvt Ltd | 1 | Emmay Entertainment | 0.612 | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
FFSERVICES PRIVATE LIMITED | Go LIVE | FFSERVICES PRIVATE LIMITED | FFSERVICES PRIVATE LIMITED | 1 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.698 | TAO AUTOMATION SERVICES PVT LTD | 0.651 | FFSERVICES PRIVATE LIMITED | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AEGIS PRECISION PVT LTD | Go LIVE | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 0.69 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.65 | ACEY ENGINEERING PVT. LTD | 0.634 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
AEGIS PRECISION PVT LTD | Go LIVE | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 0.69 | PRECIOUS ALLOYS PRIVATE LIMITED | 0.65 | ACEY ENGINEERING PVT. LTD | 0.634 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MASTER CHAINS N JEWELS PRIVATE LIMITED | Go LIVE |  | TRIO JEWELS PVT LTD | 0.732 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | 0.64 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.609 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
VIPUL ORGANICS LTD. - STAFF | Go LIVE | VIPUL ORGANICS LTD. - STAFF | VIPUL ORGANICS LTD. - STAFF | 1 | GNG ELECTRONICS LIMITED STAFF | 0.651 | MULTI ORGANICS PVT LTD | 0.65 | VIPUL ORGANICS LTD. - STAFF | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PISCES CONTAINER LINES INDIA PVT. LTD. | Go LIVE | PISCES CONTAINER LINES INDIA PVT. LTD. | PISCES CONTAINER LINES INDIA PVT. LTD. | 1 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 0.609 |  |  | PISCES CONTAINER LINES INDIA PVT. LTD. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
KAMAL ENTERPRISES | Go LIVE |  | NIKIKA ENTERPRISES LLP | 0.722 | BASANT OVERSEAS | 0.6 |  |  |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
ESCON ELEVATORS PVT. LTD. | Go LIVE | ESCON ELEVATORS PVT. LTD. | ESCON ELEVATORS PVT. LTD. | 1 | EROS ELEVATORS & ESCALATORS PVT LTD | 0.694 | PERFECT BELTS PVT. LTD | 0.632 | ESCON ELEVATORS PVT. LTD. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PISCES CONTAINER LINES INDIA PVT. LTD. | Go LIVE | PISCES CONTAINER LINES INDIA PVT. LTD. | PISCES CONTAINER LINES INDIA PVT. LTD. | 1 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | 0.609 |  |  | PISCES CONTAINER LINES INDIA PVT. LTD. | Yes | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
CHEMITO INFOTECH PVT.LTD. | Go LIVE |  | APMOSYS TECHNOLOGIES PVT LTD | 0.632 | MICROPOINT COMPUTERS PRIVATE LIMITED NX | 0.583 | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | 0.583 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
MASTER CHAINS N JEWELS PRIVATE LIMITED | Go LIVE |  | TRIO JEWELS PVT LTD | 0.732 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | 0.64 | SEEBA INDUSTRIES PRIVATE LIMITED | 0.609 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
PRASHANT CORNER PRIVATE LIMITED | Go LIVE |  | PRIJAI HEAT EXCHANGERS PVT. LTD. | 0.609 | BRILLIANT POLYMERS PVT. LTD | 0.605 | ESCON ELEVATORS PVT. LTD. | 0.6 |  | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.
LATHIA RUBBER MFG CO. PVT. LTD. | Go LIVE |  | Hardcarb Technologies Private Limited | 0.585 | [5 empty] | No | Use this reverse view when SCH has a client name that needs to be mapped back to Tracker.

## Unmatched_Clients
Tracker Project Code | Tracker Project Name | Tracker Status | Best SCH Candidate 1 | Score 1 | Best SCH Candidate 2 | Score 2 | Best SCH Candidate 3 | Score 3 | Recommended Action
5004 | PLASMA RESEARCH TRUST NX | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5013 | Metafab | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5014 | Texple | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5015 | ERMELLI PRIVATE LIMITED | Completed | PERFECT BELTS PVT. LTD | 0.645 | EMPREO WHEEL PVT LIMITED (MG) | 0.625 | EMPREO PREMIUM PVT LTD | 0.625 | Add approved alias if this project exists in SCH.
5016 | Helen Keller Institute for Deaf & Blind | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5019 | Cogencis | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5021 | SEEBA INDUSTRIES PRIVATE LIMITED | Completed | ANM INDUSTRIES PVT LTD | 0.85 | ELIXRR INDUSTRIES PVT LTD. | 0.791 | SAI SANKET INDUSTRIES PVT. LTD. | 0.783 | Add approved alias if this project exists in SCH.
5023 | Sankalpan | Lost | [6 empty] | Add approved alias if this project exists in SCH.
5024 | Emmay Entertainment | Completed | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | 0.612 |  |  |  |  | Add approved alias if this project exists in SCH.
5032 | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5036 | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5039 | GUJARAT TEA PROCESSOR & PACKERS LTD | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5040 | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5041 | TATARIA HARDWARE INNOVATION | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5043 | EROS ELEVATORS & ESCALATORS PVT LTD | Completed | ESCON ELEVATORS PVT. LTD. | 0.694 | PROCON RMC PLANTS PRIVATE LIMITED | 0.6 |  |  | Add approved alias if this project exists in SCH.
5047 | BRILLIANT POLYMERS PVT. LTD | Completed | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | 0.64 | BIJJARGI MOTORS PVT LTD | 0.605 | PRASHANT CORNER PRIVATE LIMITED | 0.605 | Add approved alias if this project exists in SCH.
5048 | AUTOTECH-SIRMAX INDIA PVT LTD | Completed | NPSE AUTOMATION PVT. LTD. | 0.622 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.615 | MESPACK INDIA PVT. LTD | 0.605 | Add approved alias if this project exists in SCH.
5049 | TAO AUTOMATION SERVICES PVT LTD | Completed | NPSE AUTOMATION PVT. LTD. | 0.681 | FFSERVICES PRIVATE LIMITED | 0.651 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | 0.63 | Add approved alias if this project exists in SCH.
5051 | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | Lost | [6 empty] | Add approved alias if this project exists in SCH.
5053 | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5055 | ARMITA INDIA SHIPPING PVT. LTD | Completed | INDIANA GRATINGS PVT LTD | 0.609 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 0.596 | PANKAJ FASHION PVT LTD | 0.591 | Add approved alias if this project exists in SCH.
5056 | PRECIOUS ALLOYS PRIVATE LIMITED | Completed | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | 0.636 | PERFECT BELTS PVT. LTD | 0.632 | ISA LOGISTICS PRIVATE LIMITED | 0.632 | Add approved alias if this project exists in SCH.
5057 | SUKHKARTA MULTISPECIALITY HOSPITAL | Lost | ALSHIFA MULTISPECIALTY HOSPITAL | 0.82 |  |  |  |  | Add approved alias if this project exists in SCH.
5059 | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Completed | MASTER CHAINS N JEWELS PRIVATE LIMITED | 0.64 | TRIO JEWELS PVT LTD | 0.634 | ALLIED INSTRUMENTS PRIVATE LIMITED | 0.583 | Add approved alias if this project exists in SCH.
5060 | SAINI ELECTRICAL & ENGINEERING WORKS | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5066 | Kuboz Arc Pvt Ltd | Lost | KARVY TECHNOLOGIES PVT. LTD. | 0.69 | MULTI ORGANICS PVT LTD | 0.606 |  |  | Add approved alias if this project exists in SCH.
5079 | PRASAD JEWELLERS | Lost | [6 empty] | Add approved alias if this project exists in SCH.
5085 | KISHAN LAL PAWAN KUMAR JAIN | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5087 | TORQUE INSURANCE BROKING PRIVATE LIMITED | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5088 | POLMOR STEEL PRIVATE LIMITED | Completed | APMOSYS TECHNOLOGIES PVT LTD | 0.706 | PERFECT BELTS PVT. LTD | 0.629 | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | 0.629 | Add approved alias if this project exists in SCH.
5089 | ACEY ENGINEERING PVT. LTD | Completed | HELL ENERGY PVT LTD | 0.649 | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | 0.623 | ANM INDUSTRIES PVT LTD | 0.6 | Add approved alias if this project exists in SCH.
5090 | ATHARVA FACILITY MANAGEMENT AND SECURITY | Completed | BFMS FACILITY MANAGEMENT PVT LTD | 0.594 |  |  |  |  | Add approved alias if this project exists in SCH.
5096 | AUROUS JEWELS LLP | Completed | TRIO JEWELS PVT LTD | 0.581 |  |  |  |  | Add approved alias if this project exists in SCH.
5098 | RENMAKCH INDIA PVT. LTD. | Completed | MESPACK INDIA PVT. LTD | 0.757 | ANM INDUSTRIES PVT LTD | 0.632 | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | 0.609 | Add approved alias if this project exists in SCH.
5100 | WHISTLING WOODS INTERNATIONAL | Active | [6 empty] | Add approved alias if this project exists in SCH.
5105 | ANUH PHARMA PVT. LTD NX | Completed | QUALIGENS PHARMA PVT. LTD. | 0.718 |  |  |  |  | Add approved alias if this project exists in SCH.
5107 | PPKG AND CO | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5108 | DOSHI MEDICARE PRIVATE LIMITED | Completed | FFSERVICES PRIVATE LIMITED | 0.629 | MESPACK INDIA PVT. LTD | 0.595 | DRS EARTHWORK PRIVATE LIMITED | 0.595 | Add approved alias if this project exists in SCH.
5110 | COSMOS IMPEX INDIA PVT LTD NG | Completed | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | 0.583 |  |  |  |  | Add approved alias if this project exists in SCH.
5113 | parvathyhospital | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5117 | Talib and Shamsi Constructions Pvt. Ltd. | Completed | ALLIED INSTRUMENTS PRIVATE LIMITED | 0.643 | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | 0.585 |  |  | Add approved alias if this project exists in SCH.
5119 | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Active | [6 empty] | Add approved alias if this project exists in SCH.
5122 | Procon RMC | Completed | PROCON RMC PLANTS PRIVATE LIMITED | 0.6 |  |  |  |  | Add approved alias if this project exists in SCH.
5125 | NOTCH INDIA PROJECTS | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5127 | GUARDIAN CASTING PVT. LTD | Completed | INDIANA GRATINGS PVT LTD | 0.714 | HARDCARB TECHNOLOGIES PRIVATE LIMITED | 0.615 | RADIX INNOVATIONS PRIVATE LIMITED | 0.605 | Add approved alias if this project exists in SCH.
5135 | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Active | [6 empty] | Add approved alias if this project exists in SCH.
5136 | Navio Shipping | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5140 | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5153 | Vivan Associate | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5154 | BSA CORPORATION LIMITED / BSA GROUP | Active | BSA CORPORATION LIMITED | 0.81 | NAVKAR CORPORATION LIMITED NG | 0.681 |  |  | Add approved alias if this project exists in SCH.
5157 | VED INDUSTRIES/ ROHIDA GROUP | Active | VED INDUSTRIES | 0.703 | VED INDUSTRIES POC | 0.7 |  |  | Add approved alias if this project exists in SCH.
5158 | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Active | [6 empty] | Add approved alias if this project exists in SCH.
5162 | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5164 | VISHWAKARMA FOUNDERS (I) PVT. LTD | Active | VISHWAKARMA FOUNDERS (I) PVT. LTD. - STAFF | 0.912 | VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | 0.897 | AMAL EMBROIDERIES PRIVATE LIMITED | 0.583 | Add approved alias if this project exists in SCH.
5165 | Navio Shipping | Completed | [6 empty] | Add approved alias if this project exists in SCH.
5166 | CREATIONS BY SHANAGAR | Active | CREATIONS BY SHANGAR | 0.973 |  |  |  |  | Add approved alias if this project exists in SCH.
5168 | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Active | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY | 0.932 |  |  |  |  | Add approved alias if this project exists in SCH.
5170 | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Active | [6 empty] | Add approved alias if this project exists in SCH.
5171 | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Active | [6 empty] | Add approved alias if this project exists in SCH.
5172 | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Yet To Start | [6 empty] | Add approved alias if this project exists in SCH.
5173 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Active | ALSHIFA MULTISPECIALTY HOSPITAL | 0.773 |  |  |  |  | Add approved alias if this project exists in SCH.
5174 | NAVKAR CORPORATION LIMITED | Yet To Start | NAVKAR CORPORATION LIMITED NG | 0.952 | BSA CORPORATION LIMITED | 0.811 | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | 0.632 | Add approved alias if this project exists in SCH.
5175 | THE KANDIVALI EDUCATION SOCIETY | Active | [6 empty] | Add approved alias if this project exists in SCH.
5176 | ARTSON LIMITED | Completed | MUKTA ARTS LTD | 0.667 | BSA CORPORATION LIMITED | 0.615 |  |  | Add approved alias if this project exists in SCH.
5177 | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Active | [6 empty] | Add approved alias if this project exists in SCH.
5179 | CONTENDRE GREENERGY PVT. LTD | Active | CONTENDRE GREENERGY LIMITED | 0.933 | HELL ENERGY PVT LTD | 0.65 |  |  | Add approved alias if this project exists in SCH.

## Match_Review
Tracker Project Code | Tracker Project Name | Tracker Status | Match Method | Candidate Count | Selected SCH Client | Selected SCH Status | Recommended Action
5045 | SAI SANKET INDUSTRIES PVT.LTD | Completed | Exact Name | 1900-01-01 | SAI SANKET INDUSTRIES PVT. LTD. | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5061 | GNG ELECTRONICS LIMITED STAFF | Completed | Approved Alias | 1900-01-01 | GNG ELECTRONICS LIMITED STAFF | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5062 | GNG ELECTRONICS LIMITED FACTORY | Lost | Approved Alias | 1900-01-02 | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5070 | CONTENDRE GREENERGY LIMITED | Completed | Approved Alias | 1900-01-01 | CONTENDRE GREENERGY LIMITED | FC | Review duplicate SCH candidates and add alias if selection is not correct.
5078 | FFSERVICES PRIVATE LIMITED | Completed | Approved Alias | 1900-01-02 | FFSERVICES PRIVATE LIMITED | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5082 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Completed | Approved Alias | 1900-01-01 | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5095 | PISCES CONTAINER LINES INDIA PVT. LTD. | Completed | Approved Alias | 1900-01-01 | PISCES CONTAINER LINES INDIA PVT. LTD. | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5099 | GNG ELECTRONICS LIMITED FACTORY | Completed | Approved Alias | 1900-01-02 | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5116 | GNG ELECTRONICS LIMITED STAFF | Completed | Approved Alias | 1900-01-01 | GNG ELECTRONICS LIMITED STAFF | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5120 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Completed | Approved Alias | 1900-01-02 | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5128 | GNG ELECTRONICS LIMITED FACTORY | Completed | Approved Alias | 1900-01-02 | GNG ELECTRONICS LIMITED FACTORY | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5146 | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Completed | Approved Alias | 1900-01-02 | AEGIS PRECISION PVT LTD | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.
5152 | Muktangan Education Trust | Active | Approved Alias | 1900-01-01 | MUKTANGAN EDUCATION TRUST. NX | Active | Review duplicate SCH candidates and add alias if selection is not correct.
5160 | ANS NG | Completed | Approved Alias | 1900-01-01 | ANS NG | Go LIVE | Review duplicate SCH candidates and add alias if selection is not correct.

## Alias_Map
Tracker Project Name | Tracker Name Key | SCH Client Name | SCH Name Key | Approved | Match Type | Last Reviewed | Notes
AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | aegisprecisionpvtltdshimnitindiapvtltd | AEGIS PRECISION PVT LTD | aegisprecisionpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
AKRITI PHARMACEUTICALS PVT LTD | akritipharmaceuticalspvtltd | AKRITI PHARMACEUTICALS PVT LTD | akritipharmaceuticalspvtltd | TRUE | Alias Review Tracker_to_SCH | 18-Sep-2026 | Approved from Alias_Matching_Review workbook.
ALLIED INSTRUMENTS PRIVATE LIMITED | alliedinstrumentspvtltd | ALLIED INSTRUMENTS PRIVATE LIMITED | alliedinstrumentspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
AMAL EMBROIDERIES PVT. LTD | amalembroideriespvtltd | AMAL EMBROIDERIES PRIVATE LIMITED | amalembroideriespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ANSHUTECH AIR CONDITIONING PVT. LTD. NX | anshutechairconditioningpvtltdnx | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | anshutechairconditioningpvtltdnx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ANS NG | ansng | ANS NG | ansng | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
APLAB LIMITED (FOR CONTRACT LICENSE) | aplabltdforcontractlicense | APLAB LIMITED (FOR CONTRACT LICENSE) | aplabltdforcontractlicense | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
APLAB LIMITED (FOR STAFF LICENSE) | aplabltdforstafflicense | APLAB LIMITED (FOR STAFF LICENSE) | aplabltdforstafflicense | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Aquaair International Frieght Services | aquaairintlfrieghtservices | AQUAAIR INTERNATIONAL FREIGHT SERVICES | aquaairintlfreightservices | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | arssteelsalloyintlpvtltdarsgroup | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | arssteelsalloyintlpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
BASANT OVERSEAS | basantoverseas | BASANT OVERSEAS | basantoverseas | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Bengal Energy_Staff | bengalenergystaff | BENGAL ENERGY LTD- STAFF | bengalenergyltdstaff | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Bengal Energy_Worker | bengalenergyworker | BENGAL ENERGY LTD- CONTRACTUAL | bengalenergyltdcontractual | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
BFMS FACILITY MANAGEMENT PVT LTD | bfmsfacilitymanagementpvtltd | BFMS FACILITY MANAGEMENT PVT LTD | bfmsfacilitymanagementpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
BRIGHT BROTHERS LTD. / BRITE | brightbrothersltdbrite | BRIGHT BROTHERS LTD | brightbrothersltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | camtoolsindustriespvtltddigitaltoolroom | CAM TOOLS INDUSTRIES PVT LTD | camtoolsindustriespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Cartfire India | cartfireindia | CARTFIRE INDIA | cartfireindia | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | centreforurbanizationbuildingsandenvironmentcubeiitm | CENTRE FOR URBANIZATION BUILDINGS | centreforurbanizationbuildings | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
CIRCLE RESOURCES PRIVATE LIMITED | circleresourcespvtltd | CIRCLE RESOURCES PRIVATE LIMITED | circleresourcespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
CONTENDRE GREENERGY LIMITED | contendregreenergyltd | CONTENDRE GREENERGY LIMITED | contendregreenergyltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | cryogasequipmentpvtltdcryogasindia | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | cryogasequipmentpvtltdng | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
DRS EARTHWORK PRIVATE LIMITED | drsearthworkpvtltd | DRS EARTHWORK PRIVATE LIMITED | drsearthworkpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | electrosteelcastingsltdelectrosteelgroup | ELECTROSTEEL CASTINGS LTD | electrosteelcastingsltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Elixrr Industries Pvt. Ltd. | elixrrindustriespvtltd | ELIXRR INDUSTRIES PVT LTD. | elixrrindustriespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
EMPREO PREMIUM PVT LTD | empreopremiumpvtltd | EMPREO PREMIUM PVT LTD | empreopremiumpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
EMPREO WHEEL PVT LIMITED (MG) | empreowheelpvtltdmg | EMPREO WHEEL PVT LIMITED (MG) | empreowheelpvtltdmg | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ESCON ELEVATORS PVT. LTD. | esconelevatorspvtltd | ESCON ELEVATORS PVT. LTD. | esconelevatorspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | evergreenhousekeepingservicespvtevergreenfacilitysolutions | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | evergreenhousekeepingservicespvt | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | feathertouchlearningpvtltdfeathertouhdaycare | FEATHERTOUCH LEARNING PRIVATE LIMITED | feathertouchlearningpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
FFSERVICES PRIVATE LIMITED | ffservicespvtltd | FFSERVICES PRIVATE LIMITED | ffservicespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
FUJIYAMA POWER SYSTEM (UTL) | fujiyamapowersystemutl | FUJIYAMA POWER SYSTEMS LIMITED | fujiyamapowersystemsltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | gcomsystemsandsolutionsourladyofsalvation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | gcomsystemsandsolutionsourladyofsalvation | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
GNG ELECTRONICS LIMITED FACTORY | gngelectronicsltdfactory | GNG ELECTRONICS LIMITED FACTORY | gngelectronicsltdfactory | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
GNG ELECTRONICS LIMITED STAFF | gngelectronicsltdstaff | GNG ELECTRONICS LIMITED STAFF | gngelectronicsltdstaff | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Hardcarb Technologies Private Limited | hardcarbtechpvtltd | HARDCARB TECHNOLOGIES PRIVATE LIMITED | hardcarbtechpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | hardcarbtechpvtltdvautidshahhardfacepvtltdstafflicense | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | hardcarbtechpvtltdstaff | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
HELL ENERGY PVT LTD | hellenergypvtltd | HELL ENERGY PVT LTD | hellenergypvtltd | TRUE | Alias Review Tracker_to_SCH | 18-Sep-2026 | Approved from Alias_Matching_Review workbook.
ILEAF RITZ BANQUETS | ileafritzbanquets | ILEAF RITZ BANQUETS | ileafritzbanquets | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | indianagroupindianagratingspvtltd | INDIANA GRATINGS PVT LTD | indianagratingspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Infexn Laboratories | infexnlaboratories | INFEXN LABORATORIES PVT LTD | infexnlaboratoriespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | integratedpestmanagementsolutionsindiapvtltdipmsindia | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | integratedpestmanagementsolutionsindia | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ISA Logistics Private Limited | isalogisticspvtltd | ISA LOGISTICS PRIVATE LIMITED | isalogisticspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
JIET MEDICAL COLLEGE HOSPITAL | jietmedicalcollegehospital | JIET MEDICAL COLLEGE HOSPITAL | jietmedicalcollegehospital | TRUE | Alias Review Tracker_to_SCH | 18-Sep-2026 | Approved from Alias_Matching_Review workbook.
KARVY TECHNOLOGIES PVT LTD | karvytechpvtltd | KARVY TECHNOLOGIES PVT. LTD. | karvytechpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
LOTUS TEXCOM INDIA LLP | lotustexcomindiallp | LOTUS TEXCOM INDIA LLP | lotustexcomindiallp | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | madhusumanenterprisesmsehvacservicesindia | MADHUSUMAN ENTERPRISES | madhusumanenterprises | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MADURA INDUSTRIAL TEXTILES LIMITED | maduraindustrialtextilesltd | MADURA INDUSTRIAL TEXTILES LIMITED. | maduraindustrialtextilesltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Maharashtra Book Manufacturing | maharashtrabookmanufacturing | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | maharashtrabookmanufacturingconx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MAHWS OILFIELD SERVICES PRIVATE LIMITED | mahwsoilfieldservicespvtltd | MAHWS OILFIELD SERVICES PRIVATE LIMITED | mahwsoilfieldservicespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MANJUSHREE INNOVATIONS PVT. LTD | manjushreeinnovationspvtltd | MANJUSHREE INNOVATIONS PRIVATE LIMITED | manjushreeinnovationspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Mansha Agencies | manshaagencies | MANSHA AGENCIES PVT LTD | manshaagenciespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MARU CONSULTANCY SERVICES | maruconsultancyservices | MARU CONSULTANCY SERVICES | maruconsultancyservices | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MEDIPULSE HOSPITAL | medipulsehospital | MEDIPULSE HOSPITAL | medipulsehospital | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MESPACK INDIA PVT. LTD | mespackindiapvtltd | MESPACK INDIA PVT. LTD | mespackindiapvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MICROPOINT COMPUTERS PRIVATE LIMITED NX | micropointcomputerspvtltdnx | MICROPOINT COMPUTERS PRIVATE LIMITED NX | micropointcomputerspvtltdnx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Muktangan Education Trust | muktanganeducationtrust | MUKTANGAN EDUCATION TRUST. NX | muktanganeducationtrustnx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
MULTI ORGANICS PVT LTD | multiorganicspvtltd | MULTI ORGANICS PVT LTD | multiorganicspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NAGRIK CONSULTANCY SERVICES | nagrikconsultancyservices | NAGRIK CONSULTANCY SERVICES | nagrikconsultancyservices | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NAIK MOTORS -GOA LOC | naikmotorsgoaloc | NAIK MOTORS -GOA LOC | naikmotorsgoaloc | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | naikmotorsnaikmahindraratnagiriloc | NAIK MOTORS - RATNAGIRI LOC | naikmotorsratnagiriloc | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | nationalbulkhandlingcorporationpvtltd | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | nationalbulkhandlingcorporationpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NIKIKA ENTERPRISES LLP | nikikaenterprisesllp | NIKIKA ENTERPRISES LLP | nikikaenterprisesllp | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | nivanbalajiautomoverspvtltdbalajikiacarshowroom | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | nivanbalajiautomoverspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
NPSE AUTOMATION PVT. LTD | npseautomationpvtltd | NPSE AUTOMATION PVT. LTD. | npseautomationpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ONETEAM LOGISTICS INDIA PRIVATE LIMITED | oneteamlogisticsindiapvtltd | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | oneteamlogisticsindiapvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
PANKAJ FASHION PVT LTD | pankajfashionpvtltd | PANKAJ FASHION PVT LTD | pankajfashionpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
PARADISE GROUP | paradisegroup | PARADISE GROUP | paradisegroup | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Parbhani Medical College | parbhanimedicalcollege | PARBHANI MEDICAL COLLEGE (PMC) | parbhanimedicalcollegepmc | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
PISCES CONTAINER LINES INDIA PVT. LTD. | piscescontainerlinesindiapvtltd | PISCES CONTAINER LINES INDIA PVT. LTD. | piscescontainerlinesindiapvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
PRIJAI HEAT EXCHANGERS PVT. LTD. | prijaiheatexchangerspvtltd | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | prijaiheatexchangerspvtltdng | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
QUALIGENS PHARMA PVT. LTD | qualigenspharmapvtltd | QUALIGENS PHARMA PVT. LTD. | qualigenspharmapvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
RADIX ELECTROSYSTEMS PVT LTD | radixelectrosystemspvtltd | RADIX ELECTROSYSTEMS PVT LTD | radixelectrosystemspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
RAJESHWARI INFOTEL PVT. LTD. (RIPL) | rajeshwariinfotelpvtltdripl | RAJESHWARI INFOTEL PVT. LTD | rajeshwariinfotelpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
ROYAL EMBROIDERY THREADS PVT.LTD. | royalembroiderythreadspvtltd | ROYAL EMBROIDERY THREADS PVT.LTD. | royalembroiderythreadspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | rupasolutionspvtltdrupagrouprupaproperties | RUPA SOLUTIONS PRIVATE LIMITED | rupasolutionspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SACRED HEART HOSPITAL JAL | sacredhearthospitaljal | SACRED HEART HOSPITAL JAL | sacredhearthospitaljal | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SETHWALA FOODS LTD | sethwalafoodsltd | SETHWALA FOODS LTD | sethwalafoodsltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SEVENTY SEVEN ENTERTAINMENT PVT. LTD | seventysevenentertainmentpvtltd | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | seventysevenentertainmentpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | shreedholisatitextilespvtltd | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | shreedholisatitextilespvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SHREEKHETRA AUTOMOTIVE (TATA) | shreekhetraautomotivetata | SHREEKHETRA AUTOMOTIVE (TATA) | shreekhetraautomotivetata | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SHREE RAMDEV METALEX LLP / RAMDEV GROUP | shreeramdevmetalexllpramdevgroup | SHREE RAMDEV METALEX LLP | shreeramdevmetalexllp | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SHRI JANARDAN SWAMI HOSPITAL (SJS) | shrijanardanswamihospitalsjs | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | rashtrasantjanardhanswamigroupofinstitutes | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
S K Traders | sktraders | S K TRADERS NX | sktradersnx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
Sky Prints | skyprints | SKY PRINTS | skyprints | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SNAPWORK TECHNOLOGIES PVT LTD | snapworktechpvtltd | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | snapworktechpvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SREE METALIKS LTD | sreemetaliksltd | SREE METALIKS LTD | sreemetaliksltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
STEAM HARBOUR LOGISTICS PVT LTD | steamharbourlogisticspvtltd | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | steamharbourlogisticspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
STEAM PULSE INDIA PVT LTD | steampulseindiapvtltd | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | steamharbourlogisticspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
STERLING LIFESTYLE LLP | sterlinglifestylellp | STERLING LIFESTYLE LLP | sterlinglifestylellp | TRUE | Alias Review Tracker_to_SCH | 18-Sep-2026 | Approved from Alias_Matching_Review workbook.
STORM FINANCIAL SERVICES | stormfinancialservices | STORM FINANCIAL SERVICES | stormfinancialservices | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SUNRISE FOODS BANGALORE | sunrisefoodsbangalore | SUNRISE FOODS BANGALORE | sunrisefoodsbangalore | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | svsengineeringramyasrielectricalautomation | RAMYASRI ELECTRICAL AUTOMATION | ramyasrielectricalautomation | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | symbiosiscentrefordistancelearningsdcl | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | tarasafeintlpvtlimitedstaff | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | tarasafeintlpvtltdstafflicense | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | tarasafeintlpvtlimitedworker | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | tarasafeintlpvtltdworkerlicense | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
THE NATIONAL SPORTS CLUB OF INDIA | thenationalsportsclubofindia | NATIONAL SPORTS CLUB OF INDIA NX | nationalsportsclubofindianx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
TRIO JEWELS PVT LTD | triojewelspvtltd | TRIO JEWELS PVT LTD | triojewelspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
TRIO JEWELS PVT LTD Contractual | triojewelspvtltdcontractual | TRIO JEWELS PVT LTD | triojewelspvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | trishulelectromechengineeringindiapvtltdtrishulgroup | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | trishulelectromechengineeringindiapvtltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
UNITED AIR EXPRESS | unitedairexpress | UNITED AIR EXPRESS | unitedairexpress | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
VABA | vaba | VABA | vaba | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
V ALLIANCE NX | valliancenx | V ALLIANCE NX | valliancenx | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | vedindustriesrohidagrouppoclicense | VED INDUSTRIES POC | vedindustriespoc | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
VIPUL ORGANICS LTD. - STAFF | vipulorganicsltdstaff | VIPUL ORGANICS LTD. - STAFF | vipulorganicsltdstaff | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
VIVID ELECTROMECH LTD. / VIVID GROUP | vividelectromechltdvividgroup | VIVID ELECTROMECH LIMITED | vividelectromechltd | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
WHISTLING WOODS INTERNATIONAL | whistlingwoodsintl | WHISTLING WOODS INTERNATIONAL | whistlingwoodsintl | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.
YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | yuvaparivartankherwadisocialwelfareassociation | KHERWADI SOCIAL WELFARE ASSOCIATION | kherwadisocialwelfareassociation | TRUE | Alias Review Tracker_to_SCH | 31-Jul-2026 | Approved from Alias_Matching_Review workbook.

## Theme_Config
Section | Item | Color
Base | primary | #1F4E78
Base | secondary | #305496
Base | background | #F7F9FC
Base | panel | #F3F6FA
Base | text | #1F1F1F
Base | muted | #606060
Base | border | #D7DEE8
Status | Active | #70AD47
Status | Completed | #D9EAF7
Status | Yet To Start | #FFC000
Status | Held Up | #ED7D31
Status | Lost | #C00000
Risk | Critical | #C00000
Risk | High | #ED7D31
Risk | Watch | #FFC000
Risk | Healthy | #70AD47
Risk | Closed | #D9EAF7

## Weekly_Mail_View
Project Name | Tracker Status | SCH Status | SCH Milestone | Current Milestone | Age Days | Risk Level | Owner | Next Action | PM Notes | PM Note Source | Stakeholder PM Update
THE NATIONAL SPORTS CLUB OF INDIA | Active | Active | Datafile Explanation | Datafile Explanation | 560 | Critical | Mihir Navnath Mungekar | Live Salary Processing Planned. | Live Salary Processing Planned. | Manual PM Note | Live Salary Processing Planned.
PARADISE GROUP | Active | AC | Completed | Datafile Explanation | 383 | Critical | Pritesh Barot | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Manual PM Note | Backend working is ongoing, training & implementation is planned.
WHISTLING WOODS INTERNATIONAL | Active |  |  | Datafile Explanation | 364 | Critical | Nagendra Poojary | PMS Implementation Ongoing | PMS Implementation Ongoing | Manual PM Note | PMS Implementation Ongoing.
SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Active |  |  | Datafile Explanation | 268 | Critical |  | Implementation Demo fixed for 8th May | Implementation Demo fixed for 8th May | Manual PM Note | Implementation Demo fixed for 8th May.
SUNRISE FOODS BANGALORE | Completed | Held | Datafile Explanation | Completed | 217 | Critical | Tushar More | Review blocker, confirm owner, and update next closure plan. |  | SCH Project Update | As per the latest SCH project update: No Response - No Reason. Tracker status is Completed; SCH status is Held (Project/license is running but implementation is on hold.). Current milestone: Completed. Current owner/implementation contact: Tushar More. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Held-up status needs management intervention.
SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Active | Active | Datafile Explanation | Datafile Explanation | 181 | Critical | Riddhi Pramod Sutar | Confirm milestone progress and next client action. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching.
SHRI JANARDAN SWAMI HOSPITAL (SJS) | Active | Held | Datafile Explanation | Kick Off Meeting | 177 | Critical | Vikas Yadav | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly.
BFMS FACILITY MANAGEMENT PVT LTD | Lost | Held | Datafile Explanation | Datafile Explanation | 127 | Critical | Amit Krishnakant Tiwari | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manual PM Note | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review.
GNG ELECTRONICS LIMITED FACTORY | Lost | Go LIVE | Completed | Completed | 486 | High | Shubham Gurav | Review Meeting | Review Meeting | Manual PM Note | Review Meeting.
ILEAF RITZ BANQUETS | Completed | Lost | Completed | Completed | 440 | High | Mayur Pendhari | Review blocker, confirm owner, and update next closure plan. |  | SCH Project Update | As per the latest SCH project update: Finds excel easy. Tracker status is Completed; SCH status is Lost (Client/project lost and license is deactivated.). Current milestone: Completed. Current owner/implementation contact: Mayur Pendhari. Next action: Review blocker, confirm owner, and update next closure plan. Attention required: Tracker status 'Completed' conflicts with SCH status 'Lost'.
MEDIPULSE HOSPITAL | Completed | AC | Completed | Datafile Explanation | 386 | High | Varun Rajbhar | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month.
NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Completed | AC | Completed | Datafile Explanation | 321 | High | Aditya Mazire | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month.
NAIK MOTORS -GOA LOC | Completed | AC | Completed | Datafile Explanation | 321 | High | Aditya Mazire | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Manual PM Note | Live Salary Processing Planned for this Month.
RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Completed | Active | Datafile Explanation | Completed | 176 | High | Ankush Rampyare Rajbhar | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned.
TRIO JEWELS PVT LTD | Active | AC | Completed | Datafile Explanation | 174 | High | Mukeshkumar Shojiram kumavat | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license.
VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Active |  |  | Kick Off Meeting | 161 | High |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration.
TRIO JEWELS PVT LTD Contractual | Active | AC | Completed | Kick Off Meeting | 152 | High | Mukeshkumar Shojiram kumavat | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license.
EMPREO PREMIUM PVT LTD | Active | Active | Datafile Explanation | Datafile Explanation | 135 | High | Goraksha Pawar | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned.
EMPREO WHEEL PVT LIMITED (MG) | Active | Active | Datafile Explanation | Datafile Explanation | 135 | High | Goraksha Pawar | Same | Same | Manual PM Note | Same.
SHREEKHETRA AUTOMOTIVE (TATA) | Active | Lost | Completed | Kick Off Meeting | 135 | High | Goraksha Pawar | Same | Same | Manual PM Note | Same.
AMAL EMBROIDERIES PVT. LTD | Active | AC | Completed | Datafile Explanation | 134 | High | Vijay Bugde | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free.
MULTI ORGANICS PVT LTD | Active | Active | Datafile Explanation | Kick Off Meeting | 128 | High | Rajesh Ravindra Panchal | KickOff & Datafile Explaination done | KickOff & Datafile Explaination done | Manual PM Note | KickOff & Datafile Explaination done.
MANJUSHREE INNOVATIONS PVT. LTD | Active | Active | Datafile Explanation | Kick Off Meeting | 126 | High | Mayur Pendhari | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th.
CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Active | Active | Datafile Explanation | Kick Off Meeting | 121 | High | Varun Rajbhar | Confirm kickoff date, data readiness, and owner. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday.
Mansha Agencies | Active | Active | Datafile Explanation | Kick Off Meeting | 117 | High | Aditya Mazire | Confirm kickoff date, data readiness, and owner. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week.
Muktangan Education Trust | Active | Active | Datafile Explanation | Datafile Explanation | 117 | High | Aditya Mazire | Confirm kickoff date, data readiness, and owner. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week.
BSA CORPORATION LIMITED / BSA GROUP | Active |  |  | Kick Off Meeting | 114 | High |  | Confirm kickoff date, data readiness, and owner. | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June.
INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Active | Active | Datafile Explanation | Kick Off Meeting | 113 | High | Ankita Gupta | Confirm kickoff date, data readiness, and owner. | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup.
SACRED HEART HOSPITAL JAL | Active | AC | Completed | Kick Off Meeting | 112 | High | Mayur Pendhari | Confirm kickoff date, data readiness, and owner. | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation.
VED INDUSTRIES/ ROHIDA GROUP | Active |  |  | Kick Off Meeting | 105 | High |  | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date.
ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Active |  |  | Kick Off Meeting | 104 | High |  | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date.
STERLING LIFESTYLE LLP | Completed | AC | Completed | Datafile Explanation | 92 | High | Aarati Subhashchandra Yadav | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response. Tracker status is Completed; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Current owner/implementation contact: Aarati Subhashchandra Yadav. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: Tracker status 'Completed' conflicts with SCH status 'AC'.
HELL ENERGY PVT LTD | Active | AC | Completed | Datafile Explanation | 86 | High |  | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days.
GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Completed |  |  | Kick Off Meeting | 152 | Watch |  | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | Manual PM Note | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th.
Vivan Associate | Completed |  |  | Datafile Explanation | 118 | Watch |  | Confirm kickoff date, data readiness, and owner. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Manual PM Note | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead.
ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Completed |  |  | Datafile Explanation | 91 | Watch |  | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH; this update is generated from Tracker and SCH status. Tracker status is Completed. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
VISHWAKARMA FOUNDERS (I) PVT. LTD | Active |  |  | Kick Off Meeting | 85 | Watch |  | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner.
CREATIONS BY SHANAGAR | Active |  |  | Datafile Explanation | 58 | Watch |  | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
AKRITI PHARMACEUTICALS PVT LTD | Active | Active | Datafile Explanation | Datafile Explanation | 58 | Watch | Ankush Rampyare Rajbhar | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation.
FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Active |  |  | Datafile Explanation | 48 | Watch |  | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
JIET MEDICAL COLLEGE HOSPITAL | Active | Active | Datafile Explanation | Datafile Explanation | 48 | Watch | Varun Rajbhar | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation.
SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Active |  |  | Kick Off Meeting | 25 | Watch | Varun | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner.
MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Active |  |  | Kick Off Meeting | 25 | Watch | Tejas | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner.
SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Yet To Start |  |  | Kick Off Meeting | 25 | Watch | Santosh | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner.
ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Active |  |  | Kick Off Meeting | 14 | Watch |  | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner.
NAVKAR CORPORATION LIMITED | Yet To Start |  |  | Kick Off Meeting | 13 | Watch | Yash | Confirm kickoff date, data readiness, and owner. |  | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner.
THE KANDIVALI EDUCATION SOCIETY | Active |  |  | Datafile Explanation | 13 | Watch |  | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
CONTENDRE GREENERGY PVT. LTD | Active |  |  | Datafile Explanation | 9 | Watch | Tanwish | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation.
DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Active |  |  | Datafile Explanation | 2 | Watch |  | Confirm progress for milestone: Datafile Explanation. |  | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
Saffron Speciality Papers Limited | Active | Active | Datafile Explanation | Datafile Explanation | 29 | Healthy | Yash Pankajkumar | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Update | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation.
PERFECT BELTS PVT. LTD | Active | Active | Datafile Explanation | Datafile Explanation | 12 | Healthy |  | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation.
APMOSYS TECHNOLOGIES PVT LTD | Active | Active | Datafile Explanation | Datafile Explanation | 8 | Healthy | Utkarsh | Confirm progress for milestone: Datafile Explanation. |  | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation.

## Project_Summary_View
Project Code | Project Name | Project Type | Tracker Status | SCH Status | SCH Status Meaning | SCH Stage Group | SCH Milestone | Current Milestone | SCH Suggested Milestone | Age Days | Risk Level | Risk Reason | Owner | Effective Employee Count | Effective Product | Effective Client Type | PM Note Source | Stakeholder PM Update | Stakeholder Update Subject | Next Action | Due Date | Action Date | PM Notes | SCH Project Remark | SCH Project Update | SCH Achieved Percent | Match Method | Match Review Needed | Tracker Name Key
5042 | THE NATIONAL SPORTS CLUB OF INDIA | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 560 | Critical | Ageing 560 days from start date | Mihir Navnath Mungekar | 450 | NX | Premium | Manual PM Note | Live Salary Processing Planned. | Project Status Update - THE NATIONAL SPORTS CLUB OF INDIA - Datafile Explanation | Live Salary Processing Planned. |  |  | Live Salary Processing Planned. | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. Due to biometric machine was not working due to which there were many employees who had not punched in the system. Because of which they have to do the salary as per the previous process. Were we told Mdm. Megha that as they have processed the September salary. So we will not regularize the September attendance. Will update the attendance from 25th September to 28th September. Sept salary processed by uploading atten. October sal is live target Need to discuss with client on monday with vasu for payment related. |  | 68 | Approved Alias | FALSE | thenationalsportsclubofindia
5092 | PARADISE GROUP | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | Completed | 383 | Critical | Ageing 383 days from start date | Pritesh Barot | 624 | Spine NG | SAAS | Manual PM Note | Backend working is ongoing, training & implementation is planned. | Project Status Update - PARADISE GROUP - Datafile Explanation | Backend working is ongoing, training & implementation is planned. |  |  | Backend working is ongoing, training & implementation is planned. | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August |  | 97 | Approved Alias | FALSE | paradisegroup
5100 | WHISTLING WOODS INTERNATIONAL | Allocation | Active |  |  |  |  | Datafile Explanation |  | 364 | Critical | No approved SCH match; Ageing 364 days from start date | Nagendra Poojary |  |  |  | Manual PM Note | PMS Implementation Ongoing. | Project Status Update - WHISTLING WOODS INTERNATIONAL - Datafile Explanation | PMS Implementation Ongoing |  |  | PMS Implementation Ongoing |  |  |  | No Match | TRUE | whistlingwoodsintl
5119 | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Allocation | Active |  |  |  |  | Datafile Explanation |  | 268 | Critical | No approved SCH match; Ageing 268 days from start date |  |  |  |  | Manual PM Note | Implementation Demo fixed for 8th May. | Project Status Update - SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED - Datafile Explanation | Implementation Demo fixed for 8th May |  |  | Implementation Demo fixed for 8th May |  |  |  | No Match | TRUE | suvarnadurgagroupsdgsuvarnadurgapaperboardspvtltd
5131 | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 181 | Critical | Ageing 181 days from start date | Riddhi Pramod Sutar | 650 | Spine NG | SAAS | Manual PM Note | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Project Status Update - SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) - Datafile Explanation | Confirm milestone progress and next client action. |  |  | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) target live sep live salary |  | 0 | Approved Alias | FALSE | symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl
5132 | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Allocation | Active | Held | Project/license is running but implementation is on hold. | Held | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 177 | Critical | Held-up status needs management intervention | Vikas Yadav | 300 | Spine NG | SAAS | Manual PM Note | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Project Status Update - SHRI JANARDAN SWAMI HOSPITAL (SJS) - Kick Off Meeting | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. |  |  | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Basic payroll training has been completed. W26jul9046 Client is occupied in a full-day meeting today. T As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. not responding whatsapp group msg as their bal payment pending called Mr. Ganesh yesterday for issues and concern and recommend outsourcing options. they said will check and inform you. Held up-Basic Payroll training has been completed. Ticket reference: W26jul9046. The client was occupied in a full-day meeting today. The client is currently not responding to messages in the WhatsApp group, and the balance payment is also pending. We called Mr. Ganesh yesterday to understand the current issues and concerns and also discussed the option of outsourcing payroll processing. Mr. Ganesh informed us that they would check internally and get back to us. However, we have not received any further response from the client yet. The client currently does not have a dedicated resource for the software, and due to limited availability of the client/resource, they are unable to spend sufficient time on software utilisation and payroll activities. | Resource Problem | 10 | Approved Alias | FALSE | shrijanardanswamihospitalsjs
5134 | TRIO JEWELS PVT LTD | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | Completed | 174 | High | Ageing 174 days from start date | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD - Datafile Explanation | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  |  | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Approved Alias | FALSE | triojewelspvtltd
5135 | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 161 | High | No approved SCH match; Ageing 161 days from start date |  |  |  |  | Manual PM Note | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Project Status Update - VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED - Kick Off Meeting | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  |  | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  |  |  | No Match | TRUE | voguenhydepvtltdmodapellebagsaccessoriespvtltd
5141 | TRIO JEWELS PVT LTD Contractual | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | Completed | 152 | High | Ageing 152 days from start date | Mukeshkumar Shojiram kumavat | 301 | Spine NG | SAAS | Manual PM Note | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Project Status Update - TRIO JEWELS PVT LTD Contractual - Kick Off Meeting | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. |  | 8th May | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  | 100 | Approved Alias | FALSE | triojewelspvtltdcontractual
5142 | EMPREO PREMIUM PVT LTD | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 135 | High | Ageing 135 days from start date | Goraksha Pawar | 105 | Spine NG | SAAS | Manual PM Note | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Project Status Update - EMPREO PREMIUM PVT LTD - Datafile Explanation | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. |  | 8th May | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 80 | Approved Alias | FALSE | empreopremiumpvtltd
5143 | EMPREO WHEEL PVT LIMITED (MG) | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 135 | High | Ageing 135 days from start date | Goraksha Pawar | 150 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - EMPREO WHEEL PVT LIMITED (MG) - Datafile Explanation | Same |  | 8th May | Same | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 65 | Approved Alias | FALSE | empreowheelpvtltdmg
5144 | SHREEKHETRA AUTOMOTIVE (TATA) | Escalation | Active | Lost | Client/project lost and license is deactivated. | Lost | Completed | Kick Off Meeting | Completed | 135 | High | Tracker status 'Active' conflicts with SCH status 'Lost'; Ageing 135 days from start date | Goraksha Pawar | 200 | Spine NG | SAAS | Manual PM Note | Same. | Project Status Update - SHREEKHETRA AUTOMOTIVE (TATA) - Kick Off Meeting | Same |  | 8th May | Same | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 4 | Approved Alias | FALSE | shreekhetraautomotivetata
5145 | AMAL EMBROIDERIES PVT. LTD | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | Completed | 134 | High | Ageing 134 days from start date | Vijay Bugde | 1200 | Spine NG | SAAS | Manual PM Note | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Project Status Update - AMAL EMBROIDERIES PVT. LTD - Datafile Explanation | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. |  | 4th May | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. As per call accounts team is connected for payment with user Aparna. Only add mod pms left which will be done in the month of november directly. |  | 91 | Approved Alias | FALSE | amalembroideriespvtltd
5147 | MULTI ORGANICS PVT LTD | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 128 | High | Ageing 128 days from start date | Rajesh Ravindra Panchal | 350 | Spine NG | SAAS | Manual PM Note | KickOff & Datafile Explaination done. | Project Status Update - MULTI ORGANICS PVT LTD - Kick Off Meeting | KickOff & Datafile Explaination done |  | 5th May | KickOff & Datafile Explaination done | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out |  | 95 | Approved Alias | FALSE | multiorganicspvtltd
5149 | MANJUSHREE INNOVATIONS PVT. LTD | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 126 | High | Ageing 126 days from start date | Mayur Pendhari | 370 | Spine NG | SAAS | Manual PM Note | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Project Status Update - MANJUSHREE INNOVATIONS PVT. LTD - Kick Off Meeting | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. |  | 5th May | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. August sal processed by their own but not live- W26sep2587 sept will be target for live sal Attrition &amp; Absenteeism Report Query is going on client want automatic shifts. The September salary will be processed live through Spine for the staff with attendance, while the workers’ attendance will be uploaded manually for salary processing. |  | 76 | Approved Alias | FALSE | manjushreeinnovationspvtltd
5150 | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 121 | High | Ageing 121 days from start date | Varun Rajbhar | 550 | Spine NG | SAAS | Manual PM Note | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Project Status Update - CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NG & live target month for processing is August month August month live salary processed - W26aug7425 |  | 79 | Approved Alias | FALSE | cryogasequipmentpvtltdcryogasindia
5151 | Mansha Agencies | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 117 | High | Ageing 117 days from start date | Aditya Mazire | 260 | Spine NG | SAAS | Manual PM Note | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Project Status Update - Mansha Agencies - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied june salary upload Aug salary processed integration done Logins roll out by next week. sept will be live sal | User is hospitalized so that’s why data files are received late & implementation is delayed | 80 | Approved Alias | FALSE | manshaagencies
5152 | Muktangan Education Trust | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 117 | High | Ageing 117 days from start date | Aditya Mazire | 608 | Spine HRMS | SAAS | Manual PM Note | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Project Status Update - Muktangan Education Trust - Datafile Explanation | Confirm kickoff date, data readiness, and owner. |  |  | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly." | 93 | Approved Alias | TRUE | muktanganeducationtrust
5154 | BSA CORPORATION LIMITED / BSA GROUP | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 114 | High | No approved SCH match; Ageing 114 days from start date |  |  |  |  | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June. | Project Status Update - BSA CORPORATION LIMITED / BSA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June |  |  |  | No Match | TRUE | bsacorporationltdbsagroup
5155 | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Kick Off Meeting | Datafile Explanation | 113 | High | Ageing 113 days from start date | Ankita Gupta | 500 | Spine NG | SAAS | Manual PM Note | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Project Status Update - INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion |  | 48 | Approved Alias | FALSE | integratedpestmanagementsolutionsindiapvtltdipmsindia
5156 | SACRED HEART HOSPITAL JAL | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Kick Off Meeting | Completed | 112 | High | Ageing 112 days from start date | Mayur Pendhari | 801 | Spine HRMS | On-Premises | Manual PM Note | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation. | Project Status Update - SACRED HEART HOSPITAL JAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. |  |  | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul | 88 | Approved Alias | FALSE | sacredhearthospitaljal
5157 | VED INDUSTRIES/ ROHIDA GROUP | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 105 | High | No approved SCH match; Ageing 105 days from start date |  |  |  |  | Tracker/SCH Status | No manual PM note is available for VED INDUSTRIES/ ROHIDA GROUP; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 105 days from start date. | Project Status Update - VED INDUSTRIES/ ROHIDA GROUP - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | vedindustriesrohidagroup
5158 | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 104 | High | No approved SCH match; Ageing 104 days from start date |  |  |  |  | Tracker/SCH Status | No manual PM note is available for ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. Attention required: No approved SCH match; Ageing 104 days from start date. | Project Status Update - ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | itcfortunehotelsiligurickimpromotersllpfortuneselectsiliguri
5163 | HELL ENERGY PVT LTD | Allocation | Active | AC | Everything is successfully completed and client is on watch list. | Active Complete | Completed | Datafile Explanation | Completed | 86 | High | SCH milestone 'AC' has not progressed for 86 days |  | 550 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ). Tracker status is Active; SCH status is AC (Everything is successfully completed and client is on watch list.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. Attention required: SCH milestone 'AC' has not progressed for 86 days. | Project Status Update - HELL ENERGY PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ) |  | 85 | Approved Alias | FALSE | hellenergypvtltd
5164 | VISHWAKARMA FOUNDERS (I) PVT. LTD | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 85 | Watch | No approved SCH match; PM note missing for ageing open item |  |  |  |  | Tracker/SCH Status | No manual PM note is available for VISHWAKARMA FOUNDERS (I) PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - VISHWAKARMA FOUNDERS (I) PVT. LTD - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | vishwakarmafoundersipvtltd
5167 | AKRITI PHARMACEUTICALS PVT LTD | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 58 | Watch | PM note missing for ageing open item | Ankush Rampyare Rajbhar | 310 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Ankush Rampyare Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - AKRITI PHARMACEUTICALS PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance |  | 96 | Approved Alias | FALSE | akritipharmaceuticalspvtltd
5166 | CREATIONS BY SHANAGAR | Allocation | Active |  |  |  |  | Datafile Explanation |  | 58 | Watch | No approved SCH match; PM note missing for ageing open item |  |  |  |  | Tracker/SCH Status | No manual PM note is available for CREATIONS BY SHANAGAR; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CREATIONS BY SHANAGAR - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. | [6 empty] | No Match | TRUE | creationsbyshanagar
5168 | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Allocation | Active |  |  |  |  | Datafile Explanation |  | 48 | Watch | No approved SCH match; PM note missing for ageing open item |  |  |  |  | Tracker/SCH Status | No manual PM note is available for FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS); this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. | [6 empty] | No Match | TRUE | fabtechmultistatecooperativecreditsocietyfmsccs
5169 | JIET MEDICAL COLLEGE HOSPITAL | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 48 | Watch | PM note missing for ageing open item | Varun Rajbhar | 800 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Varun Rajbhar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - JIET MEDICAL COLLEGE HOSPITAL - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935 |  | 0 | Approved Alias | FALSE | jietmedicalcollegehospital
5171 | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 25 | Watch | No approved SCH match | Tejas |  |  |  | Tracker/SCH Status | No manual PM note is available for MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Tejas. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | mahatmaphulecharitabletrustmpcthospitalsuranagroupofhospitalsuranahospitalsuranahospitalandresearchcentre
5170 | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 25 | Watch | No approved SCH match | Varun |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Current owner/implementation contact: Varun. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | suranacharitabletrustsuranahospitalandresearchcentrempcthospitalsuranagroupofhospitalsuranahospital
5172 | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Allocation | Yet To Start |  |  |  |  | Kick Off Meeting |  | 25 | Watch | No approved SCH match | Santosh |  |  |  | Tracker/SCH Status | No manual PM note is available for SURANA GROUP OF HOSPITAL / SURANA HOSPITAL; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Santosh. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - SURANA GROUP OF HOSPITAL / SURANA HOSPITAL - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | suranagroupofhospitalsuranahospital
5173 | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Allocation | Active |  |  |  |  | Kick Off Meeting |  | 14 | Watch | No approved SCH match |  |  |  |  | Tracker/SCH Status | No manual PM note is available for ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Kick Off Meeting. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | alshifamultispecialtyhospitalhumanwelfaretrust
5174 | NAVKAR CORPORATION LIMITED | Allocation | Yet To Start |  |  |  |  | Kick Off Meeting |  | 13 | Watch | No approved SCH match | Yash |  |  |  | Tracker/SCH Status | No manual PM note is available for NAVKAR CORPORATION LIMITED; this update is generated from Tracker and SCH status. Tracker status is Yet To Start. Current milestone: Kick Off Meeting. Current owner/implementation contact: Yash. Next action: Confirm kickoff date, data readiness, and owner. | Project Status Update - NAVKAR CORPORATION LIMITED - Kick Off Meeting | Confirm kickoff date, data readiness, and owner. | [6 empty] | No Match | TRUE | navkarcorporationltd
5175 | THE KANDIVALI EDUCATION SOCIETY | Escalation | Active |  |  |  |  | Datafile Explanation |  | 13 | Watch | No approved SCH match |  |  |  |  | Tracker/SCH Status | No manual PM note is available for THE KANDIVALI EDUCATION SOCIETY; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - THE KANDIVALI EDUCATION SOCIETY - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. | [6 empty] | No Match | TRUE | thekandivalieducationsociety
5179 | CONTENDRE GREENERGY PVT. LTD | Allocation | Active |  |  |  |  | Datafile Explanation |  | 9 | Watch | No approved SCH match | Tanwish |  |  |  | Tracker/SCH Status | No manual PM note is available for CONTENDRE GREENERGY PVT. LTD; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Current owner/implementation contact: Tanwish. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - CONTENDRE GREENERGY PVT. LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. | [6 empty] | No Match | TRUE | contendregreenergypvtltd
5177 | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Escalation | Active |  |  |  |  | Datafile Explanation |  | 2 | Watch | No approved SCH match |  |  |  |  | Tracker/SCH Status | No manual PM note is available for DIPESH ENGINEERING WORKS -STAFF LICENSE NG; this update is generated from Tracker and SCH status. Tracker status is Active. Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - DIPESH ENGINEERING WORKS -STAFF LICENSE NG - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. | [6 empty] | No Match | TRUE | dipeshengineeringworksstafflicenseng
5181 | Saffron Speciality Papers Limited | Escalation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 29 | Healthy | No immediate exception detected | Yash Pankajkumar | 440 | Spine NG | SAAS | SCH Project Update | As per the latest SCH project update: All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Yash Pankajkumar. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - Saffron Speciality Papers Limited - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | HRMS Training yet to start, for Dec 25 salary the attendance data yet to come YASH is in discussion salary processing session aligned post that user will release payment planning to proceed with one unit only user has conveyed that she will process march with attn from system in process The client is processing salary for her unit now. They process salary on a 45-day basis. Attendance integration is done. Logins won't be rolled out. The user has uploaded the roster; post manager's approval, she'll process salary with attendance from Spine. march processed for 114 employees logins rolled out they will be processing june live with attn- in process #30/07 - meeting planned for tomorrow. #5/08 - salary is delayed due to different salary cycle of 45 days, it is usually delayed because they receive data late from their site. #2/09 - eng - following up going on for attendance for august salary #8/09 - eng - As discussed, the current HR, Rupali, is serving her notice period, and this is her last working month. Since she is in the process of leaving, she is not showing much interest in the ongoing activities. For further communication, we are coordinating directly with Director Siddharth. However, he is currently occupied with a medical emergency involving a family member, so we will not be able to connect with him this week. We will follow up with him by 11th September based on his availability. Additionally, we are planning a surprise visit on Monday along with the PM and Engineer. We have also heard that the office may be relocating to Thane, so it would be important to discuss this with them at the earliest and understand the impact on the ongoing activities. #9/09 - As discussed with MD Siddharth, I asked him about the reason for the delay in salary processing and the pending salaries for July and August. He asked me to connect with Ms. Rupali regarding the same. He added her to the call and then left. During my discussion with Ms. Rupali, she explained that they have two units, and the employees there do not properly punch in and out for attendance. Due to this, attendance mismatches occur, which she has to regularize manually. This process takes a lot of time and is the main reason for the delay. I understood the issue and asked for her availability so that we could proceed with clearing the backlog and processing the July and August salaries. She requested us to give her a few minutes and said that she would try to clear the pending attendance backlogs herself. She also informed us that if she faces any issue, she will call us back. #26/09 - new user trng completed, awaiting for confirmation, user sunita is on leave, she will connect us for confirmation monday. #28/09 - Planned a onsite meeting for tomorrow. | All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay | 95 | Exact Name | FALSE | saffronspecialitypapersltd
5180 | PERFECT BELTS PVT. LTD | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 12 | Healthy | No immediate exception detected |  | 850 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Payroll- master uploaded, salary set up in process. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - PERFECT BELTS PVT. LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | Payroll- master uploaded, salary set up in process |  | 4 | Exact Name | FALSE | perfectbeltspvtltd
5178 | APMOSYS TECHNOLOGIES PVT LTD | Allocation | Active | Active | Project has started and is moving through implementation milestones. | Active | Datafile Explanation | Datafile Explanation | Datafile Explanation | 8 | Healthy | No immediate exception detected | Utkarsh | 1500 | Spine NG | SAAS | SCH Project Remark | As per the latest SCH project remark: Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data. Tracker status is Active; SCH status is Active (Project has started and is moving through implementation milestones.). Current milestone: Datafile Explanation. Current owner/implementation contact: Utkarsh. Next action: Confirm progress for milestone: Datafile Explanation. | Project Status Update - APMOSYS TECHNOLOGIES PVT LTD - Datafile Explanation | Confirm progress for milestone: Datafile Explanation. |  |  |  | Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data |  | 24 | Exact Name | FALSE | apmosystechpvtltd

## Monthly_Summary
Month | Opening | Add Alloc | Add Escal | Total Add | Completed | Lost | Held | Net Change | Closing
2025-01 | 0 | 8 | 12 | 20 | 0 | 0 | 0 | 20 | 20
2025-02 | 20 | 6 | 5 | 11 | 0 | 0 | 0 | 11 | 31
2025-03 | 31 | 7 | 4 | 11 | 0 | 0 | 0 | 11 | 42
2025-04 | 42 | 2 | 7 | 9 | 15 | 1 | 0 | -7 | 35
2025-05 | 35 | 2 | 4 | 6 | 2 | 0 | 0 | 4 | 39
2025-06 | 39 | 7 | 4 | 11 | 6 | 3 | 0 | 2 | 41
2025-07 | 41 | 0 | 7 | 7 | 9 | 5 | 0 | -7 | 34
2025-08 | 34 | 5 | 7 | 12 | 7 | 0 | 0 | 5 | 39
2025-09 | 39 | 4 | 3 | 7 | 3 | 0 | 0 | 4 | 43
2025-10 | 43 | 3 | 4 | 7 | 16 | 1 | 0 | -10 | 33
2025-11 | 33 | 5 | 5 | 10 | 2 | 1 | 0 | 7 | 40
2025-12 | 40 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 42
2026-01 | 42 | 4 | 3 | 7 | 9 | 1 | 0 | -3 | 39
2026-02 | 39 | 2 | 6 | 8 | 5 | 0 | 0 | 3 | 42
2026-03 | 42 | 1 | 1 | 2 | 12 | 2 | 0 | -12 | 30
2026-04 | 30 | 5 | 1 | 6 | 13 | 4 | 0 | -11 | 19
2026-05 | 19 | 7 | 6 | 13 | 5 | 0 | 0 | 8 | 27
2026-06 | 27 | 6 | 6 | 12 | 0 | 0 | 0 | 12 | 39
2026-07 | 39 | 3 | 0 | 3 | 7 | 2 | 0 | -6 | 33
2026-08 | 33 | 4 | 1 | 5 | 2 | 3 | 0 | 0 | 33
2026-09 | 33 | 8 | 4 | 12 | 5 | 0 | 0 | 7 | 40

## PM_Playbook
Section | Item | Description
Source Of Truth | Tracker | VASU's Tracker is the primary PM file for project list, allocation/escalation type, start/end date, PM-owned status, owner context, and notes.
Source Of Truth | SCH Project Master | SCH Project Master enriches missing details, official project remarks, implementation engineer, client information, and SCH status.
Project Type | Allocation | PM is involved from the start: kickoff, engineer assignment, datafile explanation, setup, training, integration, salary tally, handholding, then go-live.
Project Type | Escalation | PM enters midway or when stuck: understand current state, coordinate internally and with client/partner, resolve, track feedback for a month, then close.
Milestone Sequence | 01 | Kick Off Meeting
Milestone Sequence | 02 | Datafile Explanation
Milestone Sequence | 03 | Data & Policies Received
Milestone Sequence | 04 | Payroll Configuration & Training
Milestone Sequence | 05 | Salary Tallied
Milestone Sequence | 06 | Parallel Salary Processed
Milestone Sequence | 07 | Attendance Integration
Milestone Sequence | 08 | Leave & Attendance Configuration
Milestone Sequence | 09 | Employee Training & Login Roll Out
Milestone Sequence | 10 | Live Salary Processing
Milestone Sequence | 11 | Phase 2
Milestone Sequence | 12 | Completed
SCH Status Meaning | Pending For Milestone | Yet To Start: No progress or movement so far. Suggested milestone: Kick Off Meeting
SCH Status Meaning | Active | Active: Project has started and is moving through implementation milestones. Suggested milestone: Datafile Explanation
SCH Status Meaning | AC | Active Complete: Everything is successfully completed and client is on watch list. Suggested milestone: Completed
SCH Status Meaning | FC | Fully Complete: Live salary processing is complete and client is on watch list. Suggested milestone: Live Salary Processing
SCH Status Meaning | Go LIVE | Go Live: Project is handed over from implementation team to support team. Suggested milestone: Completed
SCH Status Meaning | Dropped | Dropped: Implementation dropped and client/license discontinued. Suggested milestone: Completed
SCH Status Meaning | Held | Held: Project/license is running but implementation is on hold. Suggested milestone: Datafile Explanation
SCH Status Meaning | Lost | Lost: Client/project lost and license is deactivated. Suggested milestone: Completed
SCH Status Meaning | FC Lost | FC Lost: Project was fully completed but later lost. Suggested milestone: Completed
Best PM Routine | Daily | Review Action_List for Critical/High items, update Current Milestone, PM Notes, Next Action, Owner, and Due Date.
Best PM Routine | Weekly | Refresh tracker and SCH export, run the cockpit, review project summaries, and send project-wise updates to mapped stakeholders.
Best PM Routine | Monthly | Generate the monthly dashboard workbook and executive PPT, then review trends, risks, completions, and next-month focus.

## Alias_Mapping_Guide
Section | Action | Details
Purpose | Why mapping exists | Tracker project codes and SCH project codes are different. Matching is done by project/client name.
Purpose | What alias means | An alias links one tracker Project Name to one SCH Client Name when the names differ but represent the same client/project.
Step 1 | Open Unmatched_Clients | Review rows where Match Method is No Match. Start with current Active, Yet To Start, and Held Up projects.
Step 2 | Check candidates | Compare Best SCH Candidate 1/2/3 with the tracker project name and SCH Project Remark/context.
Step 3 | Open client_alias_map.csv | File path: D:\Reports\PM Cockpit\config\client_alias_map.csv.
Step 4 | Add or edit row | Fill Tracker Project Name, SCH Client Name, Approved=True, Match Type=Manual Alias, Last Reviewed=today, Notes=reason.
Step 5 | Use exact names | Copy names exactly from Unmatched_Clients and SCH Project Master to avoid spelling mistakes.
Step 6 | Rerun cockpit | Run run_pm_cockpit.bat. The project should move from Unmatched_Clients into PM_Cockpit with Match Method Approved Alias.
Review Existing | Open Alias_Map | Review existing approved mappings. If a mapping is wrong, correct SCH Client Name or set Approved=False in client_alias_map.csv.
Review Existing | Open Match_Review | Rows with multiple SCH candidates need human confirmation. Add a manual alias for the correct SCH client.
Review Existing | Open Status_Mismatch | If tracker says Completed/Lost but SCH says Active/AC/etc., verify whether tracker or SCH needs updating.
Rule | Do not force uncertain matches | If not sure, leave unmapped. A wrong alias is worse than a missing alias because it can send the wrong project remark.

## TrackerData
Project Code | Project Type | Project Name | Received From | Start Date | End Date | Priority | Status | PM Note | Risk Identified | Employee Count | Product | Assigned Engineer | Team Leader | Marketing Executive | Client Type | Tracker Name Key | Tracker Row Number
5001 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Schedule | 2025-01-07 | 2025-10-28 | Low | Completed |  |  | 1270 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal | tarasafeintlpvtlimitedstaff | 2
5002 | Allocation | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Schedule | 2025-01-07 | 2025-07-17 | Low | Lost |  |  | 1100 | NX | Sahil Gadhave | Sahil Gadhave | Nirbhay Kumar | Normal | tarasafeintlpvtlimitedworker | 3
5003 | Escalation | Maharashtra Book Manufacturing | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Shubham Gurav | Nagesh Tiwari | Giriraj Birendrasingh Tomar | Normal | maharashtrabookmanufacturing | 4
5004 | Escalation | PLASMA RESEARCH TRUST NX | Schedule | 2025-01-07 | 2025-04-25 | Low | Completed |  |  | 35 | NX | Paras Mahesh Ladva | Viral Panchal | Anuj Kumar Ganga Prasad Tiwari | Normal | plasmaresearchtrustnx | 5
5005 | Allocation | Bengal Energy_Staff | Schedule | 2025-01-08 | 2026-03-30 | Low | Completed |  |  | 550 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium | bengalenergystaff | 6
5006 | Allocation | Bengal Energy_Worker | Schedule | 2025-01-08 | 2025-06-30 | Low | Lost |  |  | 1100 | NX | Mayur Pendhari | Probian Biswas | Nirbhay Kumar | Premium | bengalenergyworker | 7
5007 | Allocation | Parbhani Medical College | Schedule | 2025-01-13 | 2026-01-28 | Low | Lost |  |  | 500 | NG | Sushant Thombare | Shreyas Karkera | Jayesh Mojidra | Normal | parbhanimedicalcollege | 8
5008 | Escalation | Aquaair International Frieght Services | Schedule | 2025-01-13 | 2025-04-25 | Low | Completed |  |  | 45 | NX | Nagendra Poojary | Viral Panchal | Jigar Rupani | Normal | aquaairintlfrieghtservices | 9
5009 | Escalation | Hardcarb Technologies Private Limited | Maketing | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 250 | NX | Tejas Rajesh Baragade | Prathamesh Mandavkar | Amarprit Kaur | Normal | hardcarbtechpvtltd | 10
5010 | Allocation | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Schedule | 2025-01-14 | 2025-07-17 | Low | Completed |  |  | 125 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Ankur Yewalekar | Normal | madhusumanenterprisesmsehvacservicesindia | 11
5011 | Allocation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Schedule | 2025-01-14 | 2025-10-28 | Low | Completed |  |  | 350 | NX | Probian Biswas | Probian Biswas | Aparna Santosh | Premium | yuvaparivartankherwadisocialwelfareassociation | 12
5012 | Escalation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Schedule | 2025-01-14 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Amit Krishnakant Tiwari | Shreyas Karkera | Ankur Yewalekar | Normal | gcomsystemsandsolutionsourladyofsalvation | 13
5013 | Escalation | Metafab | Schedule | 2025-01-21 | 2025-04-25 | Low | Completed |  |  | 270 | NX | Goraksha Pawar | Prathamesh Mandavkar | Amarprit Kaur | Normal | metafab | 14
5014 | Escalation | Texple | Schedule | 2025-01-23 | 2025-04-25 | Low | Completed |  |  | 30 | NX | Santosh Yadav | Prathamesh Mandavkar | Aparna Santosh | Normal | texple | 15
5015 | Escalation | ERMELLI PRIVATE LIMITED | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 55 | NX | Hardik Panchal | Ganesh Jadhav | Pragnesh Panchal | Normal | ermellipvtltd | 16
5016 | Escalation | Helen Keller Institute for Deaf & Blind | Schedule | 2025-01-15 | 2025-04-25 | Low | Completed |  |  | 80 | NX |  | Hiren Bhimani | Manisha Paradia | Normal | helenkellerinstitutefordeafblind | 17
5017 | Escalation | Cartfire India | Schedule | 2025-01-24 | 2025-04-25 | Low | Completed |  |  | 26 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal | cartfireindia | 18
5018 | Escalation | Sky Prints | Schedule | 2025-01-25 | 2025-04-25 | Low | Completed |  |  | 100 | NX | Nagesh Tiwari | Viral Panchal | Manisha Singh | Normal | skyprints | 19
5019 | Escalation | Cogencis | Schedule | 2025-01-31 | 2025-04-25 | Low | Completed |  |  | 500 | NX | Vikas Yadav | Prathamesh Mandavkar | Pragnesh Panchal | Normal | cogencis | 20
5020 | Allocation | S K Traders | Schedule | 2025-01-31 | 2025-06-30 | Low | Completed |  |  | 25 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Premium | sktraders | 21
5021 | Escalation | SEEBA INDUSTRIES PRIVATE LIMITED | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 132 | NX | Darshit Pithwa | Hemanshu Wadia | Nikhil Solanki | Normal | seebaindustriespvtltd | 22
5022 | Escalation | Infexn Laboratories | Schedule | 2025-02-05 | 2025-04-25 | Low | Completed |  |  | 200 | NX | Shubham Gurav | Ganesh Jadhav | Nirbhay Kumar | Normal | infexnlaboratories | 23
5023 | Escalation | Sankalpan | Schedule | 2025-02-12 | 2025-10-28 | Low | Lost |  |  | 70 | NX | Rahul Ankush Dalvi | Viral Panchal | Nirbhay Kumar | Normal | sankalpan | 24
5024 | Escalation | Emmay Entertainment | Maketing | 2025-02-18 | 2025-04-25 | Low | Completed |  |  | 42 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Aparna Santosh | Normal | emmayentertainment | 25
5025 | Allocation | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Schedule | 2025-02-18 | 2026-02-27 | Low | Completed |  |  | 465 | NX | Rahul Ankush Dalvi | Akshay Shinde | Sanket Gosalia | Premium | indianagroupindianagratingspvtltd | 26
5026 | Allocation | RADIX ELECTROSYSTEMS PVT LTD | Schedule | 2025-02-18 | 2026-03-30 | Low | Completed |  |  | 630 | NX | Aditya Pathak | Probian Biswas | Pragnesh Panchal | Normal | radixelectrosystemspvtltd | 27
5027 | Allocation | MARU CONSULTANCY SERVICES | Schedule | 2025-02-19 | 2025-06-04 | Low | Lost |  |  | 150 | NG | Ruchit Shailesh Patel | Probian Biswas | Manisha Singh | Normal | maruconsultancyservices | 28
5028 | Allocation | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Schedule | 2025-02-24 | 2026-01-28 | Low | Completed |  |  | 300 | NX | Tejas Rajesh Baragade | Vinay Kareliya | Manisha Singh | Premium | shreeramdevmetalexllpramdevgroup | 29
5029 | Allocation | APLAB LIMITED (FOR STAFF LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 165 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal | aplabltdforstafflicense | 30
5030 | Allocation | APLAB LIMITED (FOR CONTRACT LICENSE) | Schedule | 2025-02-26 | 2025-10-28 | Low | Completed |  |  | 251 | NX | Varun Rajbhar | Vinay Kareliya | Tejas Kareliya | Normal | aplabltdforcontractlicense | 31
5031 | Escalation | NPSE AUTOMATION PVT. LTD | Schedule | 2025-02-12 | 2025-04-25 | Low | Lost |  |  | 55 | NX | Nandadeep Mhatre | Prathamesh Mandavkar | Amit Arjun Sawant | Normal | npseautomationpvtltd | 32
5032 | Allocation | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Schedule | 2025-03-03 | 2025-10-28 | Low | Completed |  |  | 125 | NG | Vinay Kareliya | Vinay Kareliya | Tejas Kareliya | Normal | anmindustriespvtltdanmallianceanmgroupamketteanalyticsltd | 33
5033 | Allocation | KARVY TECHNOLOGIES PVT LTD | Schedule | 2025-03-03 | 2026-03-30 | Low | Lost |  |  | 130 | NG | Tejas Rajesh Baragade | Vinay Kareliya | Vaishali Ramniklal Puj | Normal | karvytechpvtltd | 34
5034 | Allocation | QUALIGENS PHARMA PVT. LTD | Schedule | 2025-03-07 | 2025-10-28 | Low | Completed |  |  | 400 | NX | Ruchit Shailesh Patel | Probian Biswas | Giriraj Birendrasingh Tomar | Normal | qualigenspharmapvtltd | 35
5035 | Allocation | MADURA INDUSTRIAL TEXTILES LIMITED | Schedule | 2025-03-10 | 2026-04-28 | Low | Completed |  |  | 287 | NX | Varun Rajbhar | Vinay Kareliya | Jayesh Mojidra | Normal | maduraindustrialtextilesltd | 36
5036 | Allocation | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Schedule | 2025-03-18 | 2025-10-28 | Low | Completed |  |  | 700 | NG | Sahil Gadhave | Sahil Gadhave | Santosh Bhoja Shetty | Normal | bijjargimotorspvtltdbijjargimotorsbijjargiexcavationsolutions | 37
5037 | Allocation | STEAM PULSE INDIA PVT LTD | Schedule | 2025-03-25 | 2025-10-28 | Low | Completed |  |  | 140 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal | steampulseindiapvtltd | 38
5038 | Allocation | STEAM HARBOUR LOGISTICS PVT LTD | Schedule | 2025-03-25 | 2026-01-28 | Low | Completed |  |  | 60 | NG | Daksh Pawankumar | Akshay Shinde | Giriraj Birendrasingh Tomar | Normal | steamharbourlogisticspvtltd | 39
5039 | Escalation | GUJARAT TEA PROCESSOR & PACKERS LTD | Schedule | 2025-03-25 | 2025-06-01 | Low | Completed |  |  | 1250 | NX | Sachin Thothawala | Sachin Thothawala | Tejas Kareliya | Normal | gujaratteaprocessorpackersltd | 40
5040 | Escalation | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Schedule | 2025-03-17 | 2025-06-01 | Low | Completed |  |  | 850 | NX | Kajal Inchanalkar | Saurabh Pednekar | Mehul Patel | Normal | industrialxrayalliedradiographersnx | 41
5041 | Escalation | TATARIA HARDWARE INNOVATION | Schedule | 2025-03-18 | 2025-06-01 | Low | Completed |  |  | 60 | NX | Nagendra Poojary | Viral Panchal | Manisha Paradia | Normal | tatariahardwareinnovation | 42
5042 | Escalation | THE NATIONAL SPORTS CLUB OF INDIA | Schedule | 2025-03-19 |  | Low | Active | Monday Meeting scheduled with Payal for further plan of action and date for payment release |  | 450 | NX | Mihir Navnath Mungekar | Vinay Kareliya | Sanket Gosalia | Premium | thenationalsportsclubofindia | 43
5043 | Allocation | EROS ELEVATORS & ESCALATORS PVT LTD | Schedule | 2025-04-01 | 2025-05-01 | Low | Completed |  |  | 400 | NX | Amol Takkar | Amol Takkar | Tejas Kareliya | Premium | eroselevatorsescalatorspvtltd | 44
5044 | Allocation | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Schedule | 2025-04-01 | 2026-04-28 | Low | Completed |  |  | 1000 | NX | Kunal Joshi | Sahil Gadhave | Jayesh Mojidra | Premium | electrosteelcastingsltdelectrosteelgroup | 45
5045 | Escalation | SAI SANKET INDUSTRIES PVT.LTD | Schedule | 2025-04-01 | 2025-05-25 | Low | Completed |  |  | 410 | NX | Dakshesh D Nadkar | Viral Panchal | Nirbhay Kumar | Premium | saisanketindustriespvtltd | 46
5046 | Escalation | LOTUS TEXCOM INDIA LLP | Schedule | 2025-04-04 | 2025-07-23 | Low | Lost |  |  | 51 | NG | Prathamesh Mandavkar | Prathamesh Mandavkar | Sandeep Ashok Joundal | Normal | lotustexcomindiallp | 47
5047 | Escalation | BRILLIANT POLYMERS PVT. LTD | Schedule | 2025-04-14 | 2025-06-01 | Low | Completed |  |  | 185 | NX | Probian Biswas | Viral Panchal | Tejas Kareliya | Normal | brilliantpolymerspvtltd | 48
5048 | Escalation | AUTOTECH-SIRMAX INDIA PVT LTD | Schedule | 2025-04-21 | 2025-07-17 | Low | Completed |  |  | 205 | NX | Vikas Yadav | Prathamesh Mandavkar | Nikhil Solanki | Normal | autotechsirmaxindiapvtltd | 49
5049 | Escalation | TAO AUTOMATION SERVICES PVT LTD | Schedule | 2025-04-22 | 2025-07-17 | Low | Completed |  |  | 60 | NX | Supriya Waghmare | Hemanshu Wadia |  | Normal | taoautomationservicespvtltd | 50
5050 | Escalation | BASANT OVERSEAS | Schedule | 2025-04-25 | 2026-03-30 | Low | Lost |  |  | 1454 | NG | Yash Pankajkumar Shah | Akshay Shinde | Jayesh Mojidra | Normal | basantoverseas | 51
5051 | Escalation | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | CR | 2025-04-28 | 2025-06-04 | Low | Lost |  |  | 100 | NX | Rahul Ankush Dalvi | Viral Panchal | Aparna Santosh | Normal | poonamrollerflourmillspvtltd | 52
5052 | Allocation | SNAPWORK TECHNOLOGIES PVT LTD | Schedule | 2025-05-03 | 2026-02-27 | Low | Completed |  |  | 360 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Normal | snapworktechpvtltd | 53
5053 | Escalation | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | CR | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 630 | NX |  | Hiren Bhimani | Rushabh Dinesh Shah | Normal | royalchainspvtltdandroyalitalianjewelrypvtltd | 54
5054 | Allocation | BRIGHT BROTHERS LTD. / BRITE | Schedule | 2025-05-27 | 2026-02-27 | Low | Completed |  |  | 520 | NG | Rahul Ankush Dalvi | Akshay Shinde | Anuj Kumar Ganga Prasad Tiwari | Normal | brightbrothersltdbrite | 55
5055 | Escalation | ARMITA INDIA SHIPPING PVT. LTD | Schedule | 2025-05-24 | 2025-07-23 | Low | Completed |  |  | 45 | NX | Mayur Pendhari | Akshay Shinde | Manisha Singh | Normal | armitaindiashippingpvtltd | 56
5056 | Escalation | PRECIOUS ALLOYS PRIVATE LIMITED | Schedule | 2025-05-24 | 2025-06-01 | Low | Completed |  |  | 151 | NX | Shreyas Karkera | Shreyas Karkera | Vaishali Ramniklal Puj | Normal | preciousalloyspvtltd | 57
5057 | Escalation | SUKHKARTA MULTISPECIALITY HOSPITAL | Schedule | 2025-05-24 | 2025-07-23 | Low | Lost |  |  | 25 | NX |  |  | Sanket Gosalia | Normal | sukhkartamultispecialityhospital | 58
5058 | Escalation | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-08-30 | Low | Completed |  |  | 51 | NX |  |  | Nirbhay Kumar | Normal | oneteamlogisticsindiapvtltd | 59
5059 | Allocation | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 495 | NX | Amol Takkar | Amol Takkar | Sanket Gosalia | Premium | goldstarelitejewelspvtltd | 60
5060 | Allocation | SAINI ELECTRICAL & ENGINEERING WORKS | Schedule | 2025-06-01 | 2025-07-30 | Low | Completed |  |  | 300 | NX | Mukeshkumar Shojiram kumavat | Nagesh Tiwari | Aparna Santosh | Premium | sainielectricalengineeringworks | 61
5061 | Allocation | GNG ELECTRONICS LIMITED STAFF | Schedule | 2025-06-01 | 2025-10-28 | Low | Completed |  |  | 250 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal | gngelectronicsltdstaff | 62
5062 | Allocation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-06-01 | 2025-07-23 | Low | Lost |  |  | 750 | NX | Shubham Gurav | Nagesh Tiwari | Amarprit Kaur | Normal | gngelectronicsltdfactory | 63
5063 | Allocation | ALLIED INSTRUMENTS PRIVATE LIMITED | Schedule | 2025-06-01 | 2026-03-30 | Low | Completed |  |  | 500 | NX | Vijay Bugde | Amey Telge | Sanket Gosalia | Premium | alliedinstrumentspvtltd | 64
5064 | Allocation | MESPACK INDIA PVT. LTD | Schedule | 2025-06-09 | 2026-04-28 | Low | Completed |  |  | 50 | NG | Pooja Vikas Shinde | Akshay Shinde | Sandeep Ashok Joundal | Normal | mespackindiapvtltd | 65
5065 | Allocation | UNITED AIR EXPRESS | Schedule | 2025-06-20 | 2026-04-28 | Low | Completed |  |  | 2550 | NG | Shubham Gurav | Nagesh Tiwari | Nirbhay Kumar | Normal | unitedairexpress | 66
5066 | Escalation | Kuboz Arc Pvt Ltd | Schedule | 2025-06-24 | 2025-07-23 | Low | Lost |  |  | 200 | NG | Santosh Yadav | Vinay Kareliya | Giriraj Birendrasingh Tomar | Normal | kubozarcpvtltd | 67
5067 | Escalation | ISA Logistics Private Limited | Schedule | 2025-06-19 | 2025-07-23 | Low | Completed |  |  | 200 | NG | Mihir Navnath Mungekar | Vinay Kareliya | Ankur Yewalekar | Normal | isalogisticspvtltd | 68
5068 | Escalation | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Support | 2025-06-27 | 2025-07-23 | Low | Completed |  |  | 250 | NX | Pritesh Barot | Viral Panchal | Nikhil Solanki | Normal | seventysevenentertainmentpvtltd | 69
5069 | Escalation | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Schedule | 2025-07-12 | 2025-08-30 | Low | Completed | [8 empty] | anshutechairconditioningpvtltdnx | 70
5070 | Escalation | CONTENDRE GREENERGY LIMITED | Schedule | 2025-07-15 | 2025-08-30 | Low | Completed | [8 empty] | contendregreenergyltd | 71
5071 | Escalation | ILEAF RITZ BANQUETS | Schedule | 2025-07-17 | 2025-09-24 | Low | Completed | [8 empty] | ileafritzbanquets | 72
5072 | Escalation | ROYAL EMBROIDERY THREADS PVT.LTD. | Schedule | 2025-07-17 | 2025-08-30 | Low | Completed | [8 empty] | royalembroiderythreadspvtltd | 73
5073 | Escalation | V ALLIANCE NX | Schedule | 2025-07-18 | 2025-08-30 | Low | Completed | [8 empty] | valliancenx | 74
5074 | Escalation | UNITED AIR EXPRESS | Schedule | 2025-07-18 | 2025-08-21 | Low | Completed | [8 empty] | unitedairexpress | 75
5075 | Escalation | ESCON ELEVATORS PVT. LTD. | Schedule | 2025-07-23 | 2025-08-30 | Low | Completed | [8 empty] | esconelevatorspvtltd | 76
5076 | Allocation | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Schedule | 2025-08-02 | 2026-04-28 | Low | Lost | [8 empty] | trishulelectromechengineeringindiapvtltdtrishulgroup | 77
5077 | Allocation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Schedule | 2025-08-06 | 2026-04-28 | Low | Lost | [8 empty] | svsengineeringramyasrielectricalautomation | 78
5078 | Escalation | FFSERVICES PRIVATE LIMITED | CR | 2025-08-12 | 2025-11-28 | Low | Completed | [8 empty] | ffservicespvtltd | 79
5079 | Escalation | PRASAD JEWELLERS | Schedule | 2025-08-18 | 2025-11-28 | Low | Lost | [8 empty] | prasadjewellers | 80
5080 | Allocation | SETHWALA FOODS LTD | Schedule | 2025-08-21 | 2026-05-26 | Low | Completed | [8 empty] | sethwalafoodsltd | 81
5081 | Allocation | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Schedule | 2025-08-01 | 2026-01-28 | Low | Completed | [8 empty] | nationalbulkhandlingcorporationpvtltd | 82
5082 | Escalation | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Schedule | 2025-08-14 | 2025-09-24 | Low | Completed | [8 empty] | mahwsoilfieldservicespvtltd | 83
5083 | Allocation | FUJIYAMA POWER SYSTEM (UTL) | Schedule | 2025-08-28 | 2026-03-30 | Low | Completed | [8 empty] | fujiyamapowersystemutl | 84
5084 | Escalation | VABA | Schedule | 2025-08-04 | 2025-10-28 | Low | Completed | [8 empty] | vaba | 85
5085 | Escalation | KISHAN LAL PAWAN KUMAR JAIN | Schedule | 2025-08-22 | 2025-10-28 | Low | Completed | [8 empty] | kishanlalpawankumarjain | 86
5086 | Escalation | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Schedule | 2025-08-22 | 2025-09-24 | Low | Completed | [8 empty] | micropointcomputerspvtltdnx | 87
5087 | Escalation | TORQUE INSURANCE BROKING PRIVATE LIMITED | Schedule | 2025-08-23 | 2025-10-28 | Low | Completed | [8 empty] | torqueinsurancebrokingpvtltd | 88
5088 | Allocation | POLMOR STEEL PRIVATE LIMITED | Schedule | 2025-09-04 | 2026-01-28 | Low | Completed | [8 empty] | polmorsteelpvtltd | 89
5089 | Escalation | ACEY ENGINEERING PVT. LTD | Schedule | 2025-09-04 | 2026-03-30 | Low | Completed | [8 empty] | aceyengineeringpvtltd | 90
5090 | Escalation | ATHARVA FACILITY MANAGEMENT AND SECURITY | Schedule | 2025-09-17 | 2025-10-28 | Low | Completed | [8 empty] | atharvafacilitymanagementandsecurity | 91
5091 | Allocation | MEDIPULSE HOSPITAL | Schedule | 2025-09-09 | 2026-09-30 | Low | Completed | Renewal Done, payment confirmation received by Accounts team | [7 empty] | medipulsehospital | 92
5092 | Allocation | PARADISE GROUP | Schedule | 2025-09-12 |  | Low | Active | Query Resolution onsite Sessions ongoing | [7 empty] | paradisegroup | 93
5093 | Escalation | DRS EARTHWORK PRIVATE LIMITED | Schedule | 2025-09-24 | 2025-11-28 | Low | Completed | [8 empty] | drsearthworkpvtltd | 94
5094 | Allocation | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Schedule | 2025-09-29 | 2026-04-28 | Low | Lost | [8 empty] | centreforurbanizationbuildingsandenvironmentcubeiitm | 95
5095 | Escalation | PISCES CONTAINER LINES INDIA PVT. LTD. | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | [8 empty] | piscescontainerlinesindiapvtltd | 96
5096 | Escalation | AUROUS JEWELS LLP | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | [8 empty] | aurousjewelsllp | 97
5097 | Allocation | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Schedule | 2025-10-08 | 2026-04-28 | Low | Completed | [8 empty] | hardcarbtechpvtltdvautidshahhardfacepvtltdstafflicense | 98
5098 | Escalation | RENMAKCH INDIA PVT. LTD. | Schedule | 2025-10-28 | 2026-01-28 | Low | Completed | [8 empty] | renmakchindiapvtltd | 99
5099 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2025-10-13 | 2025-10-28 | Low | Completed | [8 empty] | gngelectronicsltdfactory | 100
5100 | Allocation | WHISTLING WOODS INTERNATIONAL | Schedule | 2025-10-01 |  | Low | Active | September Salary Processing scheduled | [7 empty] | whistlingwoodsintl | 101
5101 | Allocation | VIVID ELECTROMECH LTD. / VIVID GROUP | Schedule | 2025-10-30 | 2026-04-28 | Low | Completed | [8 empty] | vividelectromechltdvividgroup | 102
5102 | Allocation | SREE METALIKS LTD | Schedule | 2025-11-11 | 2026-04-28 | Low | Completed | [8 empty] | sreemetaliksltd | 103
5103 | Escalation | NAGRIK CONSULTANCY SERVICES | Schedule | 2025-11-10 | 2026-02-27 | Low | Completed | [8 empty] | nagrikconsultancyservices | 104
5104 | Allocation | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed | [7 empty] | naikmotorsnaikmahindraratnagiriloc | 105
5105 | Escalation | ANUH PHARMA PVT. LTD NX | Schedule | 2025-11-18 | 2026-01-28 | Low | Completed | [8 empty] | anuhpharmapvtltdnx | 106
5106 | Allocation | NAIK MOTORS -GOA LOC | Schedule | 2025-11-13 | 2026-07-31 | Low | Completed | May Salary Processed | [7 empty] | naikmotorsgoaloc | 107
5107 | Escalation | PPKG AND CO | Schedule | 2025-11-26 | 2026-02-27 | Low | Completed | [8 empty] | ppkgandco | 108
5108 | Escalation | DOSHI MEDICARE PRIVATE LIMITED | Schedule | 2025-11-03 | 2026-01-28 | Low | Completed | [8 empty] | doshimedicarepvtltd | 109
5109 | Allocation | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Schedule | 2025-11-26 | 2026-07-31 | Low | Completed | June 2026 Salary Completed with Attendance W26jul873. | [7 empty] | feathertouchlearningpvtltdfeathertouhdaycare | 110
5110 | Escalation | COSMOS IMPEX INDIA PVT LTD NG | Schedule | 2025-11-29 | 2026-03-30 | Low | Completed | [8 empty] | cosmosimpexindiapvtltdng | 111
5111 | Allocation | NIKIKA ENTERPRISES LLP | Schedule | 2025-11-29 | 2026-05-26 | Low | Completed | [8 empty] | nikikaenterprisesllp | 112
5112 | Allocation | PRIJAI HEAT EXCHANGERS PVT. LTD. | Schedule | 2025-12-10 | 2026-04-28 | Low | Completed | [8 empty] | prijaiheatexchangerspvtltd | 113
5113 | Escalation | parvathyhospital | Schedule | 2025-12-23 | 2026-01-28 | Low | Completed | [8 empty] | parvathyhospital | 114
5114 | Allocation | PANKAJ FASHION PVT LTD | Schedule | 2026-01-09 | 2026-08-11 | Low | Lost | Client is not interested and said won't be renewing | [7 empty] | pankajfashionpvtltd | 115
5115 | Allocation | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Schedule | 2026-01-16 | 2026-04-28 | Low | Lost | [8 empty] | rajeshwariinfotelpvtltdripl | 116
5116 | Escalation | GNG ELECTRONICS LIMITED STAFF | Maketing | 2026-01-19 | 2026-01-22 | Low | Completed | [8 empty] | gngelectronicsltdstaff | 117
5117 | Escalation | Talib and Shamsi Constructions Pvt. Ltd. | Maketing | 2026-01-13 | 2026-03-30 | Low | Completed | [8 empty] | talibandshamsiconstructionspvtltd | 118
5118 | Escalation | Seventy Seven Entertainment Pvt Ltd | Schedule | 2026-01-19 | 2026-03-30 | Low | Completed | [8 empty] | seventysevenentertainmentpvtltd | 119
5119 | Allocation | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Schedule | 2026-01-05 |  | Medium | Active | Discussion done with Probian, He would be sending a final mail with all the pointers with possible and not possible status remark | [7 empty] | suvarnadurgagroupsdgsuvarnadurgapaperboardspvtltd | 120
5120 | Allocation | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Schedule | 2026-01-31 | 2026-04-28 | Low | Completed | [8 empty] | arssteelsalloyintlpvtltdarsgroup | 121
5121 | Allocation | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Schedule | 2026-02-09 | 2026-05-26 | Low | Completed | [8 empty] | vedindustriesrohidagrouppoclicense | 122
5122 | Escalation | Procon RMC | Schedule | 2026-02-23 | 2026-04-28 | Low | Completed | [8 empty] | proconrmc | 123
5123 | Allocation | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Schedule | 2026-02-27 | 2026-04-28 | Low | Completed | [8 empty] | evergreenhousekeepingservicespvtevergreenfacilitysolutions | 124
5124 | Escalation | SUNRISE FOODS BANGALORE | Schedule | 2026-02-25 | 2026-04-28 | Low | Completed | [8 empty] | sunrisefoodsbangalore | 125
5125 | Escalation | NOTCH INDIA PROJECTS | Schedule | 2026-02-24 | 2026-03-30 | Low | Completed | [8 empty] | notchindiaprojects | 126
5126 | Escalation | Elixrr Industries Pvt. Ltd. | Maketing | 2026-02-10 | 2026-04-28 | Low | Completed | [8 empty] | elixrrindustriespvtltd | 127
5127 | Escalation | GUARDIAN CASTING PVT. LTD | CR | 2026-02-13 | 2026-03-30 | Low | Completed | [8 empty] | guardiancastingpvtltd | 128
5128 | Escalation | GNG ELECTRONICS LIMITED FACTORY | Schedule | 2026-02-25 | 2026-03-30 | Low | Completed | [8 empty] | gngelectronicsltdfactory | 129
5129 | Allocation | STORM FINANCIAL SERVICES | Schedule | 2026-03-28 | 2026-07-31 | Low | Lost | Client is not responding and is not interested, mail has been shared and an Onsite visit scheduled along with Mukesh | [7 empty] | stormfinancialservices | 130
5130 | Escalation | CIRCLE RESOURCES PRIVATE LIMITED | Schedule | 2026-03-12 | 2026-03-30 | Low | Completed | [8 empty] | circleresourcespvtltd | 131
5131 | Allocation | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Schedule | 2026-04-02 |  | High | Active | Discussion done with Sheetal Ji, she said everything is aligned and progressing properly, she is coordinating with Atul Ji for further plan of action. | [7 empty] | symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl | 132
5132 | Allocation | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Schedule | 2026-04-06 |  | High | Active | Review Call done with Sadhana, she said sorry and due to internal work processes she does not get time for spine. Tired to understand her processes, salary processing involved Accounts team, so informed her to let us have a common meeting to discuss the roles and accordingly segregate and start the training and implementation. Sadhana to discuss the same internally and arrange for a review meeting. | [7 empty] | shrijanardanswamihospitalsjs | 133
5133 | Allocation | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Schedule | 2026-04-07 | 2026-07-31 | High | Completed | Review Call done with Siddhi, she said everything is streamlined, she highlighted mobile app related login issues informed her basic pratices like clearing the cache and app data etc and if it still doesnt work to raise a ticket, about the payment part she said she has already submitted it to the team for approval, and it will be cleared by the next week. | [7 empty] | rupasolutionspvtltdrupagrouprupaproperties | 134
5134 | Allocation | TRIO JEWELS PVT LTD | Schedule | 2026-04-09 |  | High | Active | PMS Training Completed, September Live Planned | [7 empty] | triojewelspvtltd | 135
5135 | Allocation | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Schedule | 2026-04-22 |  | High | Active | #26/09 - new user payroll trng and HRMS trng completed, awaiting for confirmation, will do salary with attendance by 11th. | [7 empty] | voguenhydepvtltdmodapellebagsaccessoriespvtltd | 136
5136 | Escalation | Navio Shipping | Schedule | 2026-04-23 | 2026-05-26 | Low | Completed | [8 empty] | navioshipping | 137
5137 | Escalation | VIPUL ORGANICS LTD. - STAFF | Schedule | 2026-05-01 | 2026-05-26 | Low | Completed | [8 empty] | vipulorganicsltdstaff | 138
5138 | Allocation | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Schedule | 2026-05-04 | 2026-08-31 | High | Lost | Live Salary Processing planned | [7 empty] | nivanbalajiautomoverspvtltdbalajikiacarshowroom | 139
5139 | Allocation | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Schedule | 2026-05-06 | 2026-08-31 | High | Completed | Everything is aligned and leave configuration and live salary processing on going | [7 empty] | camtoolsindustriespvtltddigitaltoolroom | 140
5140 | Allocation | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Schedule | 2026-05-01 | 2026-07-31 | High | Completed | Live Salary Processing aligned | [7 empty] | gngelectronicsltdelectronicsbazaarforstafflicenseconversiontong | 141
5141 | Allocation | TRIO JEWELS PVT LTD Contractual | Schedule | 2026-05-01 |  | High | Active | Payroll training completed-E26apr9978 Hrms training completed-E26apr11242 April salary processed and tallied-E26may4682 May salary done-E26jun6874 contrctual attendance will be by uploading June salary processed. july salary processed The user is now looking for the shortest possible solution for uploading attendance to save time and effort. mail done from outlook that they will upload attendance and do salary . As discussed with client they confirmed us that Till August 2026 we update contractor attendance & salary for report purpose only. We will try to update salary till 7th Oct 2026.-E26sep6547 | [7 empty] | triojewelspvtltdcontractual | 142
5142 | Escalation | EMPREO PREMIUM PVT LTD | Schedule | 2026-05-18 |  | High | Active | Review Meeting done along with Partner Team, New HR has joined in, highlighted all the challenges and progress of all the 3 licenses, He said he will discuss and review the same internally and revert on the same. | [7 empty] | empreopremiumpvtltd | 143
5143 | Escalation | EMPREO WHEEL PVT LIMITED (MG) | Schedule | 2026-05-18 |  | High | Active | [8 empty] | empreowheelpvtltdmg | 144
5144 | Escalation | SHREEKHETRA AUTOMOTIVE (TATA) | Schedule | 2026-05-18 |  | High | Active | [8 empty] | shreekhetraautomotivetata | 145
5145 | Allocation | AMAL EMBROIDERIES PVT. LTD | Schedule | 2026-05-19 |  | High | Active | Discussion done with Pradeep, payment has been sent to their accounts team for processing, he will update tom | [7 empty] | amalembroideriespvtltd | 146
5146 | Escalation | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Schedule | 2026-05-19 | 2026-07-31 | High | Completed | Live Salary Processing | [7 empty] | aegisprecisionpvtltdshimnitindiapvtltd | 147
5147 | Allocation | MULTI ORGANICS PVT LTD | Schedule | 2026-05-25 |  | High | Active | C Shift issue done, verification pending | [7 empty] | multiorganicspvtltd | 148
5148 | Escalation | BFMS FACILITY MANAGEMENT PVT LTD | Schedule | 2026-05-26 | 2026-08-31 | High | Lost | Reminder sent to the user for data and further plan of action | [7 empty] | bfmsfacilitymanagementpvtltd | 149
5149 | Allocation | MANJUSHREE INNOVATIONS PVT. LTD | Schedule | 2026-05-27 |  | High | Active | Live Salary Processing planned for September | [7 empty] | manjushreeinnovationspvtltd | 150
5150 | Allocation | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Schedule | 2026-06-01 |  | High | Active | Live Salary Processing Done | [7 empty] | cryogasequipmentpvtltdcryogasindia | 151
5151 | Escalation | Mansha Agencies | Schedule | 2026-06-05 |  | High | Active | Live Salary Planned for September | [7 empty] | manshaagencies | 152
5152 | Escalation | Muktangan Education Trust | Schedule | 2026-06-05 |  | High | Active | Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | [7 empty] | muktanganeducationtrust | 153
5153 | Escalation | Vivan Associate | Schedule | 2026-06-04 | 2026-07-31 | Low | Completed | The management has decided not to proceed further and is not willing to continue. | [7 empty] | vivanassociate | 154
5154 | Allocation | BSA CORPORATION LIMITED / BSA GROUP | Schedule | 2026-06-08 |  | High | Active | September Salary Processing is being planned | [7 empty] | bsacorporationltdbsagroup | 155
5155 | Allocation | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Schedule | 2026-06-09 |  | High | Active | Ongoing Queries session planned | [7 empty] | integratedpestmanagementsolutionsindiapvtltdipmsindia | 156
5156 | Allocation | SACRED HEART HOSPITAL JAL | Schedule | 2026-06-10 |  | High | Active | Live Salary processing done, Additional Modules planned for October | [7 empty] | sacredhearthospitaljal | 157
5157 | Allocation | VED INDUSTRIES/ ROHIDA GROUP | Schedule | 2026-06-17 |  | High | Active | #5/10 - as per last sch, salary process was completed, including batch creation, Paytime Basket upload, validation, salary slip generation, and salary register export. The user will check the salary register and confirm the results. | [7 empty] | vedindustriesrohidagroup | 158
5158 | Allocation | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Schedule | 2026-06-18 |  | High | Active | Live Salary Processing Ongoing | [7 empty] | itcfortunehotelsiligurickimpromotersllpfortuneselectsiliguri | 159
5159 | Escalation | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Schedule | 2026-06-23 | 2026-07-31 | High | Lost | Discussion done with Amit (Director), explained the current situation, he said Rajesh will coordinate and close the same. Discussion done with Probian, he said coodinated with Rajesh and resolved pending items and processed salary as well and about the payment they would be processing the same in a day or two. | [7 empty] | shreedholisatitextilespvtltd | 160
5160 | Escalation | ANS NG | Schedule | 2026-06-24 | 2026-09-30 | High | Completed | Live Salary Processing Done | [7 empty] | ansng | 161
5161 | Escalation | STERLING LIFESTYLE LLP | Schedule | 2026-06-30 | 2026-09-30 | High | Completed | Salary Processing Session planned | [7 empty] | sterlinglifestylellp | 162
5162 | Allocation | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Schedule | 2026-07-01 | 2026-09-30 | High | Completed | Transfered to Amit Sir | [7 empty] | acnhealthcarercmservicespvtltdacninfotech | 163
5163 | Allocation | HELL ENERGY PVT LTD | Schedule | 2026-07-06 |  | High | Active | Review Call done with Roshni, everything is now aligned, Pranali is connected for ongoing quries | [7 empty] | hellenergypvtltd | 164
5164 | Allocation | VISHWAKARMA FOUNDERS (I) PVT. LTD | Schedule | 2026-07-07 |  | High | Active | Review call done with Rahul, he said everything is proper, he was busy in payroll and Archana is connecting properly. He said initial training is done, he will now verify everything and again connect with Archana and plan for login roll out as well. | [7 empty] | vishwakarmafoundersipvtltd | 165
5165 | Escalation | Navio Shipping | Schedule | 2026-08-03 | 2026-08-11 | Low | Completed | [8 empty] | navioshipping | 166
5166 | Allocation | CREATIONS BY SHANAGAR | Schedule | 2026-08-03 |  | High | Active | Training & Implementation of Payroll is compelted along with August month tallied - #E26sep2251 Training & Impelmentation of ESSM, LV & TAM is completed along with Mobile HR - #E26sep2251 | [7 empty] | creationsbyshanagar | 167
5167 | Allocation | AKRITI PHARMACEUTICALS PVT LTD | Schedule | 2026-08-03 |  | High | Active | September month live target with attendance | [7 empty] | akritipharmaceuticalspvtltd | 168
5168 | Allocation | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Schedule | 2026-08-13 |  | High | Active | processed salary for the month of August 2026 and tallied - W26sep2575 | [7 empty] | fabtechmultistatecooperativecreditsocietyfmsccs | 169
5169 | Allocation | JIET MEDICAL COLLEGE HOSPITAL | Schedule | 2026-08-13 |  | High | Active | Implementation & Training Planned for Oct | [7 empty] | jietmedicalcollegehospital | 170
5170 | Allocation | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Active | processed the August 2026 salary and tallied the processed salary data to verify the calculations and ensure the salary processing was completed correctly. |  |  |  | Varun | Vinay |  |  | suranacharitabletrustsuranahospitalandresearchcentrempcthospitalsuranagroupofhospitalsuranahospital | 171
5171 | Allocation | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Schedule | 2026-09-05 |  | High | Active | Backend Working done, Onsite Training Sessions Ongoing |  |  |  | Tejas | Vinay |  |  | mahatmaphulecharitabletrustmpcthospitalsuranagroupofhospitalsuranahospitalsuranahospitalandresearchcentre | 172
5172 | Allocation | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Schedule | 2026-09-05 |  | High | Yet To Start |  |  |  |  | Santosh | Vinay |  |  | suranagroupofhospitalsuranahospital | 173
5173 | Allocation | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Schedule | 2026-09-16 |  | High | Active | #29/09 - today sch aligned for emp. trng #E26sep7598 - Payroll-NG Conf. till Loan Mod. #E26sep8088 - payroll confirmation #E26sep9506 - HRMS & Mob App confirmation | [7 empty] | alshifamultispecialtyhospitalhumanwelfaretrust | 174
5174 | Allocation | NAVKAR CORPORATION LIMITED | Schedule | 2026-09-17 |  | High | Yet To Start | Conversion activity - company realted discuss is going on with user Mr. Mukesh & waiting for thier revert - E26sep5977 |  |  |  | Yash | Akshay Shinde |  |  | navkarcorporationltd | 175
5175 | Escalation | THE KANDIVALI EDUCATION SOCIETY | Schedule | 2026-09-17 |  | High | Active | Meeting done, Vinay will conclude the 2 pending queries of sandwitch leave policy | [7 empty] | thekandivalieducationsociety | 176
5176 | Escalation | ARTSON LIMITED | Schedule | 2026-09-01 | 2026-09-30 | High | Completed | [8 empty] | artsonltd | 177
5177 | Escalation | DIPESH ENGINEERING WORKS -STAFF LICENSE NG | Schedule | 2026-09-28 |  | High | Active | No Response from Even Director | [7 empty] | dipeshengineeringworksstafflicenseng | 178
5178 | Allocation | APMOSYS TECHNOLOGIES PVT LTD | Schedule | 2026-09-22 |  | High | Active | Implementation & Training Ongoing |  |  |  | Utkarsh | Nagesh |  |  | apmosystechpvtltd | 179
5179 | Allocation | CONTENDRE GREENERGY PVT. LTD | Schedule | 2026-09-21 |  | High | Active | Conversion Activity done, training ongoing, |  |  |  | Tanwish | Akshay Shinde |  |  | contendregreenergypvtltd | 180
5180 | Allocation | PERFECT BELTS PVT. LTD | Schedule | 2026-09-18 |  | High | Active | Payroll- master uploaded, salary set up in process | [7 empty] | perfectbeltspvtltd | 181
5181 | Escalation | Saffron Speciality Papers Limited | Schedule | 2026-09-01 |  | High | Active | Implementation & Training Planned for Oct | [7 empty] | saffronspecialitypapersltd | 182

## SCH_Project_Master
Client Code | Project Code | Type | Client Status | Client Name | Priority | Class | Co-ordinator | Team Leader | Project AC Date | Implementation Engg | DI/CH | Support Partner Type | Support Partner | Project MKT | Project Team Manager | Project Manager | Client Type | No. Emp | Amc Date | Project Start Date | Project Installation Date | Project Implementation Date | Project Managed By | Project Close Date | Title | Type of Product | Balance Flag | Achived Percent | Project Product | Status | Project Mode | Project Remark | Project Update | Project Balance Payment | Bal Pay Month | Last Processed Year Month | SCH Name Key | SCH Freshness Date | SCH Row Number
SPA111975262209 | 9756 | New | Account Activated | APMOSYS TECHNOLOGIES PVT LTD | Normal | E | Ankita Bankar | Nagesh Tiwari |  | Utkarsh Sanjay Chavan | Channel |  |  | Jayesh Mojidra | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1500 | 2026-12-31 | 2026-09-22 | 2026-09-23 | 2026-09-29 | ENGG |  | NG,ESSM | Fresh | 1 | 24 | Spine NG | Active | Online | Welcome mail done - 22nd sep Data files expalanation session done - 23rd sep data followup - #W26sep9147 Working started from 29th Sep for rcvd data |  | 80% of the total cost and its GST received The balance amount of the first 80% and the remaining 20% and its GST will be received after implementation, along with imp cost | 0 | 0 | apmosystechpvtltd | 2026-12-31 | 2
SPC110185252803 | 9748 | Conv | Account Activated | CONTENDRE GREENERGY LIMITED | Normal | E | Ritika Dilip Singh | Akshay Shinde |  | Tanwish Ramnath Naik | Channel |  |  | Rushabh Dinesh Shah | Viral Panchal | Vasu Mohan Dusa | SAAS | 160 | 2027-03-31 | 2026-09-21 | 2026-09-25 | 2026-09-30 | ENGG |  | Conv NG, RCT | Conversion | 0 | 63 | Spine NG | Active | Online | #5/10 – RCT training completed. However, the user requires offline training as they are finding it difficult to implement the process through online training. In the meantime, we have shared the SOPs as requested, and based on the user’s availability, we will confirm the onsite availability of the engineer as well. |  | 100% Advanced payment received | 0 | 0 | contendregreenergyltd | 2027-03-31 | 3
SPP111961261709 | 9739 | New | Account Activated | PERFECT BELTS PVT. LTD | Normal | E | Divya Bhide |  |  |  | Channel |  | VUNIFY TECHNOLOGY PVT. LTD | Manish Sikarwar | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 850 | 2026-12-31 | 2026-09-17 | 2026-09-17 | 2026-09-19 | PARTNER |  | NG,ESS,LV,TAM | Fresh | 0 | 4 | Spine NG | Active | Online | Payroll- master uploaded, salary set up in process |  |  | 0 | 0 | perfectbeltspvtltd | 2026-12-31 | 4
SPA111958261609 | 9736 | New | Account Activated | ALSHIFA MULTISPECIALTY HOSPITAL | Premium | E | Ritika Dilip Singh | Shreyas Karkera |  | Gaurav Karmokar | Channel |  |  | Jayesh Mojidra | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 330 | 2026-12-31 | 2026-09-16 | 2026-09-16 | 2026-09-23 | ENGG |  | NG, ESSM, TAM, LV | Fresh | 1 | 96 | Spine NG | Active | Online | # 1/10 - Sep Regularisation Will run parallel by 5th / 6th With Attendance #E26sep7598 - Payroll-NG Conf. till Loan Mod. #E26sep8088 - payroll confirmation #E26sep9506 - HRMS & Mob App confirmation |  | #excess amount to be adjusted while client pays the implementation amount. | Aug-26 | Aug-26 | alshifamultispecialtyhospital | 2026-12-31 | 5
SPN111933260109 | 9705 | Conv | Account Activated | NAVKAR CORPORATION LIMITED NG | Normal | E | Ankita Bankar | Akshay Shinde |  | Yash Pankajkumar | Direct |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 1000 | 2027-02-28 | 2026-09-17 |  |  | ENGG |  | Con NG,LV,TAM,ESSM | Fresh | 0 |  | Spine NG | Pending For Milestone | Online | Welcome mail done - 17th Sep for Conversion activity - company realted discuss is going on with user Mr. Mukesh & waiting for thier revert - E26sep5977 |  | #Received total module cost +18%GST on that cost deducting 10%TDS on that amount #remaining DMC +server setup cost Payable within 10 days from the date is installation (Received) | 0 | 0 | navkarcorporationltdng | 2027-02-28 | 6
SPM111927263108 | 9702 | New | Account Activated | MAHATMA PHULE CHARITABLE TRUST | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 325 | 2026-12-31 | 2026-09-05 | 2026-09-21 | 2026-09-26 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 1 | 0 | Spine NG | Active | Online | working done processed the August 2026 salary and tallied the processed salary data to verify the calculations and ensure the salary processing was completed correctly. |  | 50% of total cost and its GSTreceived The balance 50% and its GST will be received after 60 days of implementation or 3 months of live payroll, whichever is earlier | 0 | 0 | mahatmaphulecharitabletrust | 2026-12-31 | 7
SPS111926263108 | 9698 | New | Account Activated | SURANA CHARITABLE TRUST | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Kajal Inchanalkar | Direct |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 117 | 2026-11-30 | 2026-08-31 | 2026-09-22 | 2026-09-29 | ENGG |  | NG,ESSM,TAM,LV | Fresh | 1 | 44 | Spine NG | Active | Onsite | We proceed and tallied Aug 2026 for staff employees.-W26oct442 Payroll training completed, Leave application will not be used, All leaves will get encashed Quaterly, Further implementation in process.-W26oct407 SMTP done W26oct411 |  | 50% of total cost and its GST received Balance 50% and its GST will bewill be received after 60 days of implementation or 3 months live payroll whichever is earlier | Aug-26 | Aug-26 | suranacharitabletrust | 2026-11-30 | 8
SPS107604233107 | 9669 | Conv | Account Activated | SAI SANKET INDUSTRIES PVT. LTD. | Normal | E | Ankita Bankar | Amey Telge |  | Vijay Bugde | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 251 | 2027-07-31 | 2026-08-27 |  |  | ENGG |  | CONVNG, EXP | Conversion | 0 |  | Spine NG | Pending For Milestone | Online | Welcome mail done - 28th August User is processing salary internally of August month & will share us downtime tent. @ 7-8 sep for conversion user is busy in processing & will let us know the dates for conversion - 8th Sep As per discussed with user, we have started pre-conversion working from 16th sep Pre-conversion working is going on - W26sep6506 conversion started from 2nd Oct |  |  | 0 | 0 | saisanketindustriespvtltd | 2027-07-31 | 9
SPJ111881261908 | 9644 | New | Account Activated | JIET MEDICAL COLLEGE HOSPITAL | Premium | E | Disha Kiran Kargutkar | Vinay Kareliya |  | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 800 | 2026-11-30 | 2026-08-19 | 2026-09-15 | 2026-09-15 | ENGG |  | NG,ESSM,LV,TAM,ONBO,OFFBOR,EXP | Fresh | 1 | 0 | Spine NG | Active | Online | we have successfully activated attendance API Key and completed integration, kindly check the same-E26sep5869 Client mentioned that training for the Leave and Time Attendance module in the SPINE HRMS software is currently not required, as we will manage the training internally. and they will plan the training for the Payroll and Expense modules starting towards the end of October.-E26sep9921 client told that JMCH, attendance policy is the same as Medipulse Hospital. we can copy the same settings and configuration in the SPINE HRMS Software.-E26sep5935 |  | 100% subcription cost against the commercial and its GST - received 100% server setup and its GST will be paid after installation |  |  | jietmedicalcollegehospital | 2026-11-30 | 10
SPF111878261308 | 9636 | New | Account Activated | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY | Normal | E | Ankita Bankar | Shreyas Karkera |  | Tushar More | Direct |  |  | Ankur Yewalekar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 300 | 2027-08-31 | 2026-08-13 | 2026-08-17 | 2026-08-24 | ENGG |  | NG,ESSM,LV,TAM,EXP | Fresh | 1 | 88 | Spine NG | Active | Online | Welcome mail done - 13th August Datafiles expalantion done on 14th Aug Datafiles rcvd & checking is going on - #E26aug4289 Online traning started from 24th August We have completed spineNG payroll HRMS & mobile Application training. July month processed & tallied SMTP configuration done. - W26aug9351 we have processed salary for the month of August 2026 and tallied - W26sep2575 |  | 50% of total cost and 50% implement charges and full GST receivd Balance 50% of the total cost and implement charges will be received after 2 salary processes. | 0 | Aug-26 | fabtechmultistatecooperativecreditsociety | 2027-08-31 | 11
SPC111844263107 | 9596 | New | Account Activated | CREATIONS BY SHANGAR | Premium | E | Ankita Bankar | Akshay Shinde |  | Yash Pankajkumar | Direct |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2026-10-31 | 2026-07-31 | 2026-07-31 | 2026-08-21 | ENGG |  | NG,ESSM,LV,TAM,OB | Fresh | 0 | 96 | Spine NG | Active | Onsite | Welcome mail done - 31st onsite kick-off done - 3rd August Installation done As per dis done with user, will share us data by 10th August tent. user will share us data after 15th August Datafiles followup - W26aug5008 Employee master rcvd & checking is going on Working started from 21st August Training & Implementation of Payroll is compelted along with August month tallied - #E26sep2251 Training & Impelmentation of ESSM, LV & TAM is completed along with Mobile HR - #E26sep2251 |  |  | 0 | Aug-26 | creationsbyshangar | 2026-10-31 | 12
SPV111792261307 | 9538 | New | Account Activated | VISHWAKARMA FOUNDERS (I) PVT. LTD. - STAFF | Normal | E | Ankita Bankar | Shreyas Karkera |  | Archana Ramesh Pawar | Direct |  |  | Manisha Singh | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 101 | 2027-08-31 | 2026-07-13 | 2026-07-21 | 2026-07-28 | ENGG |  | NG,ESSM,LV,TAM,PMS,TS | Fresh | 1 | 79 | Spine NG | Active | Online | Welcome mail don - 13th July Kick-off done on 14th July EMP master file rcvd Working started from 28th July Online meeting started from 4th august Traning & Implementation of Payroll is completed along with June month tallied - E26aug1816 training for the Staff HRMS & Employee Individual Login module. Training for the Worker module will continue next week. - 20th August July month salary processed - E26aug4362 August month attendance regulatization is going on & will conclude till 10th Sep September month live salary target |  | NEFT Received as on 10/07/2026 Full GST received, 35% payment received, remaining 65% will be paid in August after salary is processed | 0 | Aug-26 | vishwakarmafoundersipvtltdstaff | 2027-08-31 | 13
SPV111791261307 | 9537 | New | Account Activated | VISHWAKARMA FOUNDERS (I) PVT. LTD- WORKER | Normal | E | Ankita Bankar | Shreyas Karkera |  | Archana Ramesh Pawar | Channel |  |  | Manisha Singh | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 100 | 2027-07-31 | 2026-07-13 | 2026-07-21 | 2026-07-28 | ENGG |  | NG,TAM | Fresh | 0 | 76 | Spine NG | Active | Online | Welcome mail on - 13th July Kick-off done on 14th July Working started from 28th July Online meeting started from 4th august Traning & Implementation of Payroll is completed along with June month tallied - E26aug1816 training for the Staff HRMS & Employee Individual Login module. Training for the Worker module will continue next week. - 20th August August month attendance regulatization is going on & will conclude till 10th Sep September month live salary target |  |  | 0 | Aug-26 | vishwakarmafoundersipvtltdworker | 2027-07-31 | 14
SPA111227263101 | 9521 | Add Mod | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Disha Kiran Kargutkar |  | 2026-08-07 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 710 | 2027-02-28 | 2026-07-07 | 2026-07-07 | 2026-07-07 | OS | 2026-08-07 | TS | Fresh | 0 | 0 | Spine NG | Go LIVE | Online | Training done Client is live processing. Time sheet module also live. |  | RECEIVED |  | 0 | arssteelsalloyintlpvtltd | 2027-02-28 | 15
SPH111773260307 | 9514 | New | Account Activated | HELL ENERGY PVT LTD | Normal | E | Karuna Rajaram Sandim |  | 2026-09-02 |  | Channel |  | MIRACLE TECHNOLOGIES | Sanket Gosalia | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 550 | 2027-06-30 | 2026-07-03 | 2026-07-10 | 2026-07-28 | PARTNER |  | NG, ESSM, LV, TAM, EXP,PMS, ON-OFF BOARD | Fresh | 0 | 85 | Spine NG | AC | Onsite | 5th of every month, Payroll setup training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration done, login rolled out ( further module - PMS, ELC pending ) ( note - they are only going to process contract emp ) |  | 100% payment rcvd to partner | Jun-26,Jul-26,Aug-26 | Aug-26 | hellenergypvtltd | 2027-06-30 | 16
SPA111771260207 | 9512 | New | Account Activated | AKRITI PHARMACEUTICALS PVT LTD | Normal | E | Ankita Bankar | Sahil Gadhave |  | Ankush Rampyare Rajbhar | Channel |  |  | Bhavin Nitin Naik | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 310 | 2027-07-31 | 2026-08-03 | 2026-08-17 | 2026-08-20 | ENGG |  | NG,ESSM,LV,TAM,off-boarding | Fresh | 1 | 96 | Spine NG | Active | Online | Welcome mail done - 3rd August WC call done & data files explanation sch on 5th August Data files shared by client & checking is going on - W26aug5072 Working done on 20th August onsite training started from 24th August Payroll training & Impelmentation is done along with july month salary processed & tallied - W26aug7965 HRMS modules training & Implementation is done & attendance integration is completed - W26aug8903 Mobile HR training & setup is done Logins rolled out to all the emps - W26sep466 August month Live salary processed & tallied - W26sep2960 September month live target with attendance |  | 55% received with full GST extra amount received to be adjusted with the pending 45% of the balance, which will bereceived after implementation or 60 days, whichever is earlier | 0 | Aug-26 | akritipharmaceuticalspvtltd | 2027-07-31 | 17
SPA111227263101 | 9465 | Add Mod | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Disha Kiran Kargutkar |  | 2026-09-12 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 710 | 2027-02-28 | 2026-06-25 | 2026-06-25 | 2026-06-30 | OS | 2026-09-12 | exp | Fresh | 0 | 0 | Spine NG | Go LIVE | Onsite | training done expense explaination also given |  | Billing to vincible, 50% of yearly subscription + 50% gst pending to be paid whithin 90 days from the date of purchase (Note - Pending with client Client paid 40% oftotal cost which is 40% of subscription + 40% of SS + 40% of IMPL + 40% gst)(received) |  | 0 | arssteelsalloyintlpvtltd | 2027-02-28 | 18
SPC111708261806 | 9442 | New | Account Activated | CKIM PROMOTERS LLP | Normal | E | Disha Kiran Kargutkar | Amey Telge |  | Ankita Gupta | Channel |  |  | Swati Sangani | Viral Panchal | Vasu Mohan Dusa | SAAS | 120 | 2026-12-31 | 2026-06-18 | 2026-07-03 | 2026-07-07 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 92 | Spine NG | Active | Online | PayrollNx trainig completed.-E26sep1136 HRMS Training completed-E26sep1141 Attendance Integration completed-E26aug1380 Employee trng done Aug-26 salary & Sep-26 dummy salary process has done today.-E26sep6366 We guided the user to complete salary processing for September 2026 on a dummy basis and reviewed the leave data. We generated the Leave Report and asked the user to review the same. today sept sal and leave reports will do live sept sal salary processing started queries and requirement we are checking user will check the salary register and let us know. |  | Full payment receive | May-26,Jun-26,Jul-26,Aug-26,Sep-26 | Sep-26 | ckimpromotersllp | 2026-12-31 | 19
SPV111703261706 | 9436 | Add Mod | Account Activated | VED INDUSTRIES | Normal | E | Ritika Dilip Singh | Sahil Gadhave |  | Dhanashree Dalvi | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 300 | 2027-06-30 | 2026-06-17 | 2026-06-19 | 2026-06-19 | ENGG |  | NG, TAM, HR | Fresh | 1 | 42 | Spine HRMS | Active | Online | handholding done queries are getting handled #3/08 - eng - everything is sorted, awaiting for salary calculation, today she is on off, will connect her tomorrow. #4/08 - eng - today calculation configure done, trng for payroll processing will be provided as per user's availability. #19/08 - user is out of town, will connect only after monday. #25/08 - eng - user will connect on thursday #17/09 - As discussed, there office is closed today, we asked for his avaialbility he disconnected the call. later i tried again, but no response, so i dropped a msg in our whatsapp.. #23/09 - he is working on salary sheet,and will share sheet with engineer by tomorrow, and regarding salary processing he is available after friday. #1/10 - awaiting for Salary Structure details and Paytime Basket data from user end, dropped mail for the same. #5/10 - as per last sch, salary process was completed, including batch creation, Paytime Basket upload, validation, salary slip generation, and salary register export. The user will check the salary register and confirm the results. |  | Extra amount of first 70% balance to be adjusted with the balance 30% + full GST, which will be received by next month. | 0 | 0 | vedindustries | 2027-06-30 | 20
SPI111677260206 | 9398 | New | Account Activated | INTEGRATED PEST MANAGEMENT SOLUTIONS INDIA | Normal | E | Ankita Bankar | Amey Telge |  | Ankita Gupta | Channel |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2026-09-30 | 2026-06-09 | 2026-06-15 | 2026-06-17 | ENGG |  | NG, ESSM, LV, TAM, EXP,ELC | Fresh | 0 | 48 | Spine NG | Active | Online | Welcome mail & datafile explanation done on 9th June Working done Online Traning started from 17th June Training & Implementation of payroll is completed along with may month tallied - E26jul1514 & E26jun6944 for HRMS mod data gathering is going on - 23rd July Attendance Policy rcvd - #E26jul9482 July month processed with new user Ms. Taniya August month salary processed - E26sep3127 Renewal is quite positve & is in disucssion |  |  |  | Aug-26 | integratedpestmanagementsolutionsindia | 2026-09-30 | 21
SPS111671263005 | 9392 | New | Account Activated | SACRED HEART HOSPITAL JAL | Premium | E | Disha Kiran Kargutkar | Amey Telge | 2026-09-11 | Mayur Pendhari | Channel |  |  | Jayesh Mojidra | Viral Panchal | Vasu Mohan Dusa | On-Premises | 801 | 2027-05-31 | 2026-06-10 | 2026-07-02 | 2026-07-27 | ENGG |  | NG,ESSM,LV,TAM,ELC,MOBHR | Fresh | 1 | 88 | Spine HRMS | AC | Online | we have activated the key and installation procedure has been completed-E26jun9985. Payroll NX Training completed- W26jul10950 The client is currently using only the HRMS module in Spine.- E26jul11993 Atten Integration done. logins done for some staff As per probian they will do payroll to internal discussion going on. only one unit salary for july with attendance done. try for one unit salary with attendance for aug too. As per feedback user Narendra said no queries and concern as of now we are busy in inspections so add mod we are planning for oct or next week evern we are planning for payroll module too. we will let you know. | Onsite vist from 27th Jul | #50% Payment along with full gst received #30% payment will be released once the implementation will start, till tan welcome email will be on hold till 10th June. #20% Payment will be done after completion of implementation and salary processing( full payment received ) |  |  | sacredhearthospitaljal | 2027-05-31 | 22
SPC111653263005 | 9374 | New | Account Activated | CRYOGAS EQUIPMENT PRIVATE LIMITED NG | Normal | E | Ankita Bankar | Vinay Kareliya |  | Santosh Yadav | Channel |  | SOFTCORE SOLUTIONS PVT. LTD. | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 550 | 2027-05-31 | 2026-06-02 | 2026-06-10 | 2026-06-24 | ENGG |  | NG,ESSM,LV,TAM,PMS, Help Desk, Off-Boarding, & On- | Fresh | 1 | 79 | Spine NG | Active | Online | Welcome mail on 2nd June 2026 & data files explanation is done Project delivery rcvd Working started from 24th june Training & Implementation of Payroll is completed along with may month salary tallied - W26jun11157 & W26jun11801 Training & Implementation of ESSM, LV & TAM module is done Attendance integration is done & logins rolled out ELC, PMS & HD training - once July salary is done will proceed to further module impl due to attendance quries, July processed from NG & live target month for processing is August month August month live salary processed - W26aug7425 |  | 80% payment rcvd to spine with full GST remaining 20% rcvd after second salary process. | 0 | Aug-26 | cryogasequipmentpvtltdng | 2027-05-31 | 23
SPM111635262705 | 9354 | New | Account Activated | MANJUSHREE INNOVATIONS PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Amey Telge |  | Mayur Pendhari | Channel | SA | Data Crown Computer Consultancy. - SA | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 370 | 2027-05-31 | 2026-05-27 | 2026-06-02 | 2026-06-15 | ENGG |  | NG,ESSM,LV,TAM,ELC,PMS,RCT | Fresh | 0 | 76 | Spine NG | Active | Online | The payroll process has been successfully completed based on the May attendance.-W26jun10571 HRMS Leave and TAM Training and configuration done integration is pending from client side. pms training is going on July salary processed Integration done. August sal processed by their own but not live- W26sep2587 sept will be target for live sal Attrition &amp; Absenteeism Report Query is going on client want automatic shifts. The September salary will be processed live through Spine for the staff with attendance, while the workers’ attendance will be uploaded manually for salary processing. |  |  | May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | manjushreeinnovationspvtltd | 2027-05-31 | 24
SPA111591261305 | 9304 | New | Account Activated | AMAL EMBROIDERIES PRIVATE LIMITED | Premium | E | Disha Kiran Kargutkar | Amey Telge | 2026-08-04 | Vijay Bugde | Direct |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1200 | 2027-04-30 | 2026-05-19 | 2026-06-02 | 2026-06-04 | ENGG |  | NG,ESSM,LV,TAM,PMS,Off-Boarding & OnBoarding,RCT | Fresh | 0 | 91 | Spine NG | AC | Onsite | Payroll training and salary processing completed for the month of April, May and June 2026. HRMS training attendance module completed. Recruitment training completed-W26jul4175 training for Spine employees was successfully conducted -E26jul7000 today session regarding recruitment, queries resolving and elc July salary processed with attendance. and ELC mod completed.-W26aug2135 pms pending but client said we have some time will not start as of now. called Mr.pradeep for feedback he said there are few query and requirement as gave the task for the same August payroll processed with attendance- W26sep296 called for feedback to Mr. Pradeep but not responded the call. As per call accounts team is connected for payment with user Aparna. Only add mod pms left which will be done in the month of november directly. |  | #we received the 75% of product cost + Full server setup + Full gst on whole amount #the excess amount of first 75% balance needs to be adjusted with the balance pending #Balance 25% of License cost Payable after 30 days or 1 month payroll live whichever is earlier. (full payment received) | July-25,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | amalembroideriespvtltd | 2027-04-30 | 25
SPA108616242604 | 9283 | Conv | Account Activated | ANS NG | Normal | E | Ankita Bankar | Amey Telge | 2026-09-07 | Aditya Mazire | Direct |  |  | Vaishali Ramniklal | Viral Panchal | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2026-05-04 | 2026-05-14 | 2026-05-20 | ENGG |  | Conv NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | AC | Onsite | Welcome mail on - 4th May Installation done & conversion done Onsite training aligned on 25th May Database Handholding confirmation - E26may9526 Traninig of Payroll is completed - E26may10825 HRMS training & Impementation is done - E26jul3101 | salary based on attendance from August 2026 onwards. |  | 0 | Aug-26 | ansng | 2027-04-30 | 26
SPN111575260205 | 9280 | New | Account DeActivated | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED | Normal | E | Ankita Bankar | Vinay Kareliya |  | Mihir Navnath Mungekar | Channel |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 400 | 2026-07-31 | 2026-05-04 | 2026-05-11 | 2026-05-26 | ENGG | 2026-08-05 | NG,LV,TAM | Fresh | 0 | 85 | Spine NG | Lost | Online | Project Lost -Mr. Ravi informed us that they will not be renewing the software due to low utilization by their staff & a lack of acceptance of automation within the organization. He appreciated our software and support; however, management has decided not to continue with the renewal. Welcome maild on 4th May Project delivery rcvd Training & Implementation of Payorll is completed along with April month tallied - HRMS modules Training & Implementation is done Attendance integration is done Logins rolled out to employees - E26may6183 Live salary with attednace proceed of June month for some employees | July wth attendance | # full advance payment received |  | Jun-26 | nivanbalajiautomoverspvtltd | 2026-08-05 | 27
SPB111573263004 | 9276 | New | Account Activated | BSA CORPORATION LIMITED | Premium | E | Divya Bhide | Amey Telge |  | Nagendra Poojary | Channel | SP | SHRADDHA INFOSYSTEMS | Rushabh Dinesh Shah | Viral Panchal | Vasu Mohan Dusa | SAAS | 1563 | 2027-05-31 | 2026-06-08 | 2026-07-22 | 2026-06-19 | ENGG |  | NG,ESS,LV,TAM,ON,OFF | Fresh | 1 | 20 | Spine NG | Active | Online | onboard training done- additional field req-E26jul9751, payroll set up done, salary processed parellel, training not ready july tallied, bio int done 1 plant, sql not in our format, payment pending - add emp whatsapp int pending - token key pending from vendor end, bio int done- need to add fields- pending from client end, pushing for sept salary but less response. | Icici integration discusson ongoing | 20% payment received. ---- 40% upon the processing of the second salary 40% upon the processing of the third salary | Jul-26,Aug-26 | Aug-26 | bsacorporationltd | 2027-05-31 | 28
SPC111560263004 | 9261 | New | Account Activated | CAM TOOLS INDUSTRIES PVT LTD | Normal | E | Ankita Bankar | Shreyas Karkera | 2026-08-13 | Harsh Dilip Ashar | Direct |  |  | Tejas Kareliya | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 315 | 2026-10-31 | 2026-05-05 | 2026-05-06 | 2026-05-20 | ENGG | 2026-09-11 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Project Live- Training & Implementation is done along with April month tallied - W26may10013 Attendance inetgration is done Logins rolled out June month with attednace done & July month processed with attedance Leave policy is pending from client's end, they will share as per their convience- E26sep4961 processed Live salary for the month of August- E26sep3629 |  |  |  | Aug-26 | camtoolsindustriespvtltd | 2026-10-31 | 29
SPM111555263004 | 9257 | New | Account Activated | MULTI ORGANICS PVT LTD | Normal | E | Ankita Bankar | Vinay Kareliya |  | Mihir Navnath Mungekar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 350 | 2027-04-30 | 2026-05-23 | 2026-07-17 | 2026-07-25 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 1 | 95 | Spine NG | Active | Onsite | Welcome mail done on 23rd May Welcome call done, data files expalnation session is done -E26jun840 NDA Pending from Spine accounts once cleared client will share Corp ID - NDA shared on 16th June Emp master rcvd - 20th July we have rcvd the complete data & wil plan working & training in last week of july - 24th July Attendance Policy rcvd #E26jul9367 -27th July Working done on 25th July Onsite training started from 28th july We have scheduled onsite training from 4th August to 10 August Payroll training & Impelmentation is done along with June month tallied - W26aug1721 Essm, LV & TAM module training & Implementation is done along with attednance integration - E26aug3507 Mihir is visitig at their chandrapur location from 25th August for training & roll out |  | 80% of the total cost and Full GST received Balance 20% will be received after successful implementation | 0 | Jul-26 | multiorganicspvtltd | 2027-04-30 | 30
SPG109930253101 | 9242 | Conv | Account Activated | GNG ELECTRONICS LIMITED STAFF | Normal | E | Ankita Bankar | Nagesh Tiwari | 2026-07-15 | Nagesh Tiwari | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 400 | 2027-04-30 | 2026-04-28 | 2026-06-11 | 2026-06-12 | ENGG | 2026-08-14 | Conv NG | Fresh | 0 | 100 | Spine NG | FC | Online | Project Live - Conversion to NG is done & Handholding confirmation - E26jun4559 Online Training is completed - E26jun6574 JUN (E26jul1005) & JUL (E26aug3785) Month salary processed from system |  |  |  | Aug-26 | gngelectronicsltdstaff | 2027-04-30 | 31
SPV111527262204 | 9224 | New | Account Activated | VOGUE N HYDE PVT. LTD | Premium | E | Ritika Dilip Singh | Vinay Kareliya |  | Akshaya Patil | Channel |  |  | Aparna Santosh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1000 | 2027-04-30 | 2026-04-22 | 2026-04-27 | 2026-05-25 | ENGG |  | NG, TAM | Fresh | 0 | 100 | Spine NG | Active | Online | training and impl confirmation- W26may10964 E26may10665 they process salary on weekly basis client is opting 500 employee count post implementation if the same they will process may integration done logins not going to roll out july targetted as salary with attn #29/07 - eng - worker salary register is pending from user end. else everything is done. #30/07 - regarding his few queries, he tried connecting akshaya today, but she was quite allocated on another call, user told, he is available tomorrow we can connevct him. #3/08 - ENG - we're working on staff salary, once it is completed then will proceed with worker too. #6/08 - eng - will do with attendance salary for the first time with july, they are working on attendance regularisation and then will connect for salary processing by 10th. today we'll create and share the attendance report to user. #27/08 - eng - as user is on leave today, they will connect tomorrow for dummy salary #3/09 - as discussed with user surojit, salary configuration is done, they will recheck and update us, will process salary with attendance by 10th sept. #10/09 - eng - attendance regularizing is going on, but not completed bcoz of MD's unavailability, once he approve, they will proceed with the same, by tomorrow. #21/09 - new user trng from tomorrow i.e. 22nd sept. (engineer is'nt aware about name and me too, will take user detail tomorrow) #26/09 - new user payroll trng and HRMS trng completed, awaiting for confirmation, will do salary with attendance by 11th. | July with attendance |  | 0 | Aug-26 | voguenhydepvtltd | 2027-04-30 | 32
SPT111503260904 | 9192 | New | Account Activated | TRIO JEWELS PRIVATE LIMITED-CONTRACTUAL LICENSE | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-05-21 | Mukeshkumar Shojiram kumavat | Direct |  |  | Vaishali Ramniklal | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 151 | 2027-04-30 | 2026-04-09 | 2026-04-13 | 2026-05-13 | ENGG |  | NG,TAM | Fresh | 0 | 100 | Spine NG | Active | Onsite | Payroll training completed-E26apr9978 Hrms training completed-E26apr11242 April salary processed and tallied-E26may4682 May salary done-E26jun6874 contrctual attendance will be by uploading June salary processed. july salary processed The user is now looking for the shortest possible solution for uploading attendance to save time and effort. mail done from outlook that they will upload attendance and do salary . As discussed with client they confirmed us that Till August 2026 we update contractor attendance & salary for report purpose only. We will try to update salary till 7th Oct 2026.-E26sep6547 |  |  | Apr-25,May-26,Jun-26,Jul-26 | Jul-26 | triojewelspvtltdcontractuallicense | 2027-04-30 | 33
SPT111502260904 | 9191 | New | Account Activated | TRIO JEWELS PVT LTD | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-07-17 | Mukeshkumar Shojiram kumavat | Direct |  |  | Vaishali Ramniklal | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 301 | 2027-04-30 | 2026-04-09 | 2026-04-13 | 2026-04-24 | ENGG |  | NG,ESSMLV,TAM,PMS,RCT | Fresh | 0 | 100 | Spine NG | AC | Onsite | Training of payroll module done-E26apr9978 Training of HRMS module done-E26apr11242 April salary processed-E26may6288 logins roll out done may salary with attendance parallely done-E26jun6874 june salary done with attendance.-E26jul3491 july salary processed-W26aug2701 user is connected with team for recruitment and exp module. As per feedback call user said we have queries as we asked she said I am out of office will call you later. client have completed the implementation of the Recruitment Module and would now like to proceed with the PMS Module. PMS Training compleyed -W26sep8011 fc after sept live sak |  |  | Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | triojewelspvtltd | 2027-04-30 | 34
SPS111486260104 | 9164 | New | Account DeActivated | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Premium | E | Disha Kiran Kargutkar | Probian Biswas |  | Bhavika Gite | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 251 | 2026-06-30 | 2026-04-04 | 2026-04-13 | 2026-04-29 | ENGG | 2026-08-06 | NG,ESSM,LV,TAM | Fresh | 0 | 50 | Spine NG | Lost | Online | Payroll training done hrms training done april tallied may salary process june salary process integration is pending As per the user's update, due to heavy rainfall, our Director is not present for renewal discussion and therefore the vendor has also not visited. We will update you on mail. Lost- Payroll & HRMS training completed, and June salary was processed. Only biometric integration remained pending. Earlier as informed by Director Amit to Swati Ji that already their existing biometric device did not support integration and a new device was required. Despite multiple follow-ups and discussions, the client did not respond and later informed us they would coordinate with another vendor. Due to delays from client side the integration remained pending and the client ultimately decided to discontinue the software. | Attendance Integration issue | Full payment received | Apr-26,May-26,Jun-26 | Jun-26 | shreedholisatitextilespvtltd | 2026-08-06 | 35
SPR111468263103 | 9146 | New | Account Activated | RUPA SOLUTIONS PRIVATE LIMITED | Normal | E | Ankita Bankar | Sahil Gadhave |  | Ankush Rampyare Rajbhar | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-09-30 | 2026-04-07 | 2026-04-08 | 2026-04-16 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | Active | Onsite | Training & Implementation of Payroll NG is completed & April month processed & tallied - W26apr7935 Training & implementation completed for all the opted modules - W26apr9950 & W26apr8893 mobile HR application login rollout for employees has been successfully completed - W26apr12704 half renewal payment is rcvd & user said will release rest soon also she updated wil process june month soon & followup on outlook is going on from outlook 3rd August session is aligned for July month processing before 15th August will process as user is occupied with internal work salary processing for August 2026, along with Spine attendance, has been successfully completed - #E26sep744 |  |  |  | Aug-26 | rupasolutionspvtltd | 2026-09-30 | 36
SPS111464263103 | 9142 | New | Account Activated | SYMBIOSIS CENTRE FOR DISTANCE LEARNING (SDCL) | Premium | E | Karuna Rajaram Sandim |  |  | Riddhi Pramod Sutar | Channel |  | AMALAN TECHNOLOGIES - PUNE-SP | Utsavi Setu | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 650 | 2027-04-30 | 2026-04-02 | 2026-04-03 | 2026-05-20 | PARTNER |  | NG,ESSM,LV,TAM,ELC,PMS,RCT | Fresh | 1 | 0 | Spine NG | Active | Online | 15th of every month, Payroll setup and training Done. Salary processed and tallied for May 26 month. Hrms: Ess leave time setup Done, Integration pending ( punching code mismatch client shall re-share the data again and after that they shall login rolled out ) ( in second phase RCT is complted ) ( for Aug salary asked partner, as per update client is saying that they are busy internally told them to understand reason ) target live sep live salary |  | Payment will be received in 1-2 days ----- 93% PAYMENT & Its GST WILL BE RECEIVED IN ADVANCE, 7% & Its GST WILL BE RECEIVED WITHIN 90 DAYS. ( 85% of the total cost with GST already rcvd) 15% of the total cost with GST will be paid within 90 days | Apr-26,May-26 | Jun-26 | symbiosiscentrefordistancelearningsdcl | 2027-04-30 | 37
SPR111446263103 | 9121 | New | Account Activated | RASHTRASANT JANARDHAN SWAMI GROUP OF INSTITUTES | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave |  | Vikas Yadav | Channel |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-09-30 | 2026-04-04 | 2026-04-08 | 2026-06-30 | ENGG | 2026-09-30 | NG,ESSM,LV,TAM | Fresh | 1 | 10 | Spine NG | Held | Online | Basic payroll training has been completed. W26jul9046 Client is occupied in a full-day meeting today. T As per the message from NSS Sir. The first payment needs to be cleared before we proceed further with the training and implementation activities. not responding whatsapp group msg as their bal payment pending called Mr. Ganesh yesterday for issues and concern and recommend outsourcing options. they said will check and inform you. Held up-Basic Payroll training has been completed. Ticket reference: W26jul9046. The client was occupied in a full-day meeting today. The client is currently not responding to messages in the WhatsApp group, and the balance payment is also pending. We called Mr. Ganesh yesterday to understand the current issues and concerns and also discussed the option of outsourcing payroll processing. Mr. Ganesh informed us that they would check internally and get back to us. However, we have not received any further response from the client yet. The client currently does not have a dedicated resource for the software, and due to limited availability of the client/resource, they are unable to spend sufficient time on software utilisation and payroll activities. | Resource Problem | 55% payment received | Mar-26 | Mar-26 | rashtrasantjanardhanswamigroupofinstitutes | 2026-09-30 | 38
SPS111411262803 | 9081 | New | Account DeActivated | STORM FINANCIAL SERVICES | Normal | E | Disha Kiran Kargutkar | Nagesh Tiwari | 2026-05-15 | Mukeshkumar Shojiram kumavat | Channel |  |  | Utsavi Setu | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 410 | 2026-06-30 | 2026-03-28 | 2026-03-30 | 2026-04-01 | ENGG | 2026-07-10 | NG,ESSM,TAM | Fresh | 0 | 100 | Spine NG | Lost | Onsite | Completed Payroll training and also processed February 26 payroll and matched.-E26apr3050 completed all the training, also provided login access to employee-E26apr3347. completed with March Salary process for 391 employees.-E26apr4776. April month payroll has been processed, and payslip has been published for the employees. -E26may5873. Held up-As per the discussion with the client during the onsite visit by engineer mukesh the client is not ready to continue with the Spine. They have decided to develop and implement their own in-house software. | Another Software | Full payment received | Feb-26,Mar-26,Apr-26 | Apr-26 | stormfinancialservices | 2026-07-10 | 39
SPM111405262703 | 9075 | New | Account Activated | MANSHA AGENCIES PVT LTD | Normal | E | Disha Kiran Kargutkar | Amey Telge |  | Aditya Mazire | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 260 | 2027-03-31 | 2026-03-27 | 2026-04-30 | 2026-06-22 | ENGG |  | NG,LV,TAM | Fresh | 0 | 80 | Spine NG | Active | Onsite | completed with Payroll NG training.-E26jun5179 HRMS Training completed-E26jul4041 may salary tallied june salary upload Aug salary processed integration done Logins roll out by next week. sept will be live sal | User is hospitalized so that’s why data files are received late & implementation is delayed | 60% received along with full GST 40% of total payment pending will receive after implementation( FULL PAYMENT RECEIVED) | May-26,Jul-26,Aug-26 | Aug-26 | manshaagenciespvtltd | 2027-03-31 | 40
SPE111306262702 | 8958 | New | Account Activated | EMPREO WHEEL PVT LIMITED (MG) | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  |  | Swati Sangani | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 150 | 2027-02-28 | 2026-04-16 | 2026-05-25 | 2026-05-28 | ENGG |  | NG, ESSM, LV, TAM | Fresh | 0 | 65 | Spine NG | Active | Online | Welcome mail done - 16th April Training completed for Payroll Software. Training completed for Employee Portal Software. Training completed for Mobile-HR. - W26may11024 Payroll and HRMS implementation completed. User training completed. April-26 salary successfully processed. Pending: May-26 salary processing. Attendance integration. Employee login rollout. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 25% after 3 month payroll processed 25% after 4th month payroll processed (Received) | 0 | Apr-26 | empreowheelpvtltdmg | 2027-02-28 | 41
SPS111305262702 | 8957 | New | Account DeActivated | SHREEKHETRA AUTOMOTIVE (TATA) | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  | TRISTAR SOFTWARE & SOLUTIONS PVT. LTD | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2026-08-31 | 2026-04-15 | 2026-06-09 |  | ENGG | 2026-10-02 | NG,ESSMLV,TAM | Fresh | 1 | 4 | Spine NG | Lost | Online | Project Held - Required data was not shared by the user despite multiple follow-ups, resulting in the project being marked as Held-up Welcome mail on 15th April Corporate ID has been created. Pending : Submission of required data files to initiate the implementation process. user Mr. Das keep saying us will share us data but unable to share as he said will do reamaninig licneses imp first then will focus on this licnese User will share the data till 10th sep Mr. Jagat mentioned that the employees currently covered under the SHREEKHETRA AUTOMOTIVE (TATA) license will be shifted to the following two licenses: 1.EMPREO PREMIUM PVT. LTD. (KIA) 2.EMPREO WHEEL PVT. LTD. (MG) The proposed license restructuring is currently under discussion, and Mr. Jagat will share an email confirming the same once finalized. | Data files not received, esc to Swati & Partner Tristar, they are in follow up | 50% payment pending to partner after 1st payroll process | 0 | 0 | shreekhetraautomotivetata | 2026-10-02 | 42
SPE111274261802 | 8919 | New | Account Activated | EMPREO PREMIUM PVT LTD | Escalated | E | Ankita Bankar | Sahil Gadhave |  | Goraksha Pawar | Channel |  | TRISTAR SOFTWARE & SOLUTIONS PVT. LTD | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 105 | 2027-02-28 | 2026-02-18 | 2026-03-25 | 2026-03-25 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 80 | Spine NG | Active | Online | WELCOME MAIL DONE training and impl in done W26mar9808- employees training done attendance integration done Payroll and HRMS implementation completed. Training and Mobile-HR login rollout completed. April-26 salary successfully processed. Employee login rollout completed. (Employees are actively using Mobile Clock In/Out.) Pending : May-26 salary processing. Discussed the usage of the 3 opted licenses with Mr. Jagat. He informed us that the core HR team has left, and a new HR user has been appointed to handle Spine. However, the joining is currently on hold as the CEO is on leave. Once the new HR user joins, Mr. Jagat will share the contact details for further discussion. | 3 license single user, will take time to Go Live, as user is unable to process | 50% received 25% after 3rd month payroll processed 25% after 4th month payroll processed (Received) | 0 | Mar-26 | empreopremiumpvtltd | 2027-02-28 | 43
SPV111249260602 | 8886 | New | Account DeActivated | VED INDUSTRIES POC | Premium | E | Mansi Singh | Sahil Gadhave | 2026-06-24 | Dhanashree Dalvi | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 300 | 2026-04-30 | 2026-02-06 | 2026-02-11 | 2026-03-06 | ENGG | 2026-06-24 | NX, TAM, HR | Fresh | 0 | 58 | Spine HRMS | Go LIVE | Onsite | employee master uploaded attn was there priority attn integration done currently their main focus in only on attendance mail lic follow up ongoing ankur and vasu will co-ordinate with client opted on premises lic |  |  | 0 |  | vedindustriespoc | 2026-06-24 | 44
SPF107062230902 | 8880 | Add Mod | Account Activated | FFSERVICES PRIVATE LIMITED | Normal | E | Ankita Bankar | Shreyas Karkera | 2026-02-12 | Harsh Dilip Ashar | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 220 | 2026-12-31 | 2026-02-05 | 2026-02-05 | 2026-02-10 | ENGG | 2026-02-14 | PMS NX | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - PMS CONF (E26feb3272) Training & Implementation is done of PMS module |  | Full GST pending (Received) | 0 |  | ffservicespvtltd | 2026-12-31 | 45
SPA111227263101 | 8860 | New | Account Activated | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD | Normal | E | Mansi Singh |  | 2026-03-15 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 710 | 2027-02-28 | 2026-01-31 | 2026-02-02 | 2026-02-03 | OS | 2026-03-31 | NG, ESSM, LV,TAM,ELC,CLAIMS,PMS,RCT,Add On | Fresh | 0 | 0 | Spine NG | Go LIVE | Onsite | live- training and impl done feb processed from spine |  | Billing to vincible, 50% of yearly subscription + 50% gst pending to be paid whithin 90 days from the date of purchase (Note - Pending with client Client paid 40% of total cost which is 40% of subscription + 40% of SS + 40% of IMPL + 40% gst) (Received) | 0 | Feb-26 | arssteelsalloyintlpvtltd | 2027-02-28 | 46
SPG109937253101 | 8831 | Add Mod | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2026-02-05 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2026-01-29 | 2026-01-29 | 2026-01-30 | ENGG | 2026-02-10 | RCT NX | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - Training & Implementation of RCT Module is done - E26jan11064 |  |  |  |  | gngelectronicsltdfactory | 2026-10-31 | 47
SPS111195262301 | 8821 | New | Account Activated | STERLING LIFESTYLE LLP | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | 2026-05-15 | Aarati Subhashchandra Yadav | Channel | SA | KESHAV COMPUTER PVT LTD - SA | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 75 | 2027-01-31 | 2026-01-23 | 2026-01-27 | 2026-02-12 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | AC | Onsite | hrms and empl trng done-E26feb9421 payroll training done and feb salary processed W26mar276 IT Team is not available today after integration mobile logins will be roll out. march salary till 10th april Explained how to check shift allocated report and attendance group report, exported the same, user will check march salary done april salary done new user Mr. Sagar has taken training payroll and hrms August salary processed called for feedback but no response |  | No data | Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | sterlinglifestylellp | 2027-01-31 | 48
SPP111159260801 | 8782 | New | Account DeActivated | PANKAJ FASHION PVT LTD | Premium | E | Divya Bhide | Amey Telge |  | Aditya Mazire | Channel |  | SA-LANSAR | Deepak Choubisia | Viral Panchal | Vasu Mohan Dusa | SAAS | 1001 | 2026-06-30 | 2026-01-08 | 2026-01-13 | 2026-01-28 | ENGG | 2026-08-20 | NG,TAM | Fresh | 1 | 88 | Spine NG | Lost | Online | "10th, 15th, 25th" 110 emp- E26jan8973, payroll hr set up done, training done, int done, logins done, meeting done- workers not stable hence unable to share accurate data, meeting done may target, later will share data ot policy pending W26jun7203, contractual basic- change- card assign Director has not confidence on his user, Client LOST- Director dont have confidence on his user, meeting done onsite but not productive. Director has stopped receiving calls, client deactivated | Resource Problem | Remaining 50% will be paid in 90 days or after implementation, whichever is earlier | Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26 | May-26 | pankajfashionpvtltd | 2026-08-20 | 49
SPM108453242903 | 8778 | Add Mod | Account Activated | MUKTANGAN EDUCATION TRUST. NX | Normal | E | Ankita Bankar | Amey Telge |  | Aditya Mazire | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 608 | 2027-03-31 | 2026-01-06 | 2026-01-06 | 2026-04-18 | ENGG |  | LV,ESSM,ELC,TS,RCT,PMS | Fresh | 0 | 93 | Spine HRMS | Active | Online | imp & traning completed of add ESSM & ELC Module - E26may5936 Training of Time Sheet, Recruitment and PMS module is completed - E26may5512 required the data from Team Muktangan, 1. The Policy of PMS and the Time Sheet module. 2. Approver file for all employees. Leave traning session on 16th & 17th July Leave mod training - user was on leave & will let us know next training dates - 22nd July Leave Mod training is done - W26jul7942 Leave Policy implementation is done for TS mod training user will share us the dates | "As per the user's requirement, they needed the Leave module under their license. However, the Leave module was not included in the initial license. The user coordinated with the Marketing team to add the required module, and the Leave module has now been successfully included in their license. In the meantime, we successfully completed the training for all other modules. The Leave module training will commence shortly." |  | 0 |  | muktanganeducationtrustnx | 2027-03-31 | 50
SPS111112253012 | 8729 | New | Account Activated | SUVARNA DURGA GROUP | Normal | E | Divya Bhide | Amey Telge | 2026-06-12 | Ankita Gupta | Channel | SP | BRILLIANT TECHNOLOGIES_Silver - SP | Roopa S | Viral Panchal | Vasu Mohan Dusa | SAAS | 500 | 2027-01-31 | 2026-01-05 | 2026-01-12 | 2026-02-06 | ENGG |  | NG,ESS,LV,TAM,ON,OFF,RCT | Fresh | 1 | 100 | Spine NG | AC | Online | payroll set up & training done, hr set up & training done, bio int done, rct,on,off std training done, logins done, meeting 2/6 for balance payment n pending points, new user of rct has requirement july done, client specifically wants to meet Roopa, impl details shared with her, meeting done, PM meeting done, rct requirement, aug co wise will be processed, |  | remaining 50% of product cost +server setup + implementation cost +full GST yet to be payable after the implementation or 45 days whichever is earlier . | Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26,Sep-26 | Sep-26 | suvarnadurgagroup | 2027-01-31 | 51
SPB111113253112 | 8728 | New | Account Activated | BFMS FACILITY MANAGEMENT PVT LTD | Normal | E | Ankita Bankar | Shreyas Karkera |  | Amit Krishnakant Tiwari | Channel | SA | KESHAV COMPUTER PVT LTD - SA | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 500 | 2026-12-31 | 2025-12-31 | 2026-01-05 | 2026-01-13 | ENGG | 2026-09-21 | NG, TAM | Fresh | 0 | 100 | Spine NG | Held | Onsite | (E26aug6724) Project Held Up - Despite our continuous efforts to support and resolve queries and concerns, we have not received the required response from client Implementation and Training session aligned from 13th Jan E26jan1479 W26jan5503 Bfms Payroll Training and December Salary confirmation BFMS will not process with Attendance - W26mar1378 the salary of compliance section is not yet decided (in discussion) post that they will process march on monday team will update the company is shifting to pvt ltd hence they are bsy client not responding properly The client mentioned that they have employees such as delivery personnel working with platforms like Zomato, Swiggy, and Urban Company. These employees typically work for only 4–5 days and then leave the job after comparing their earnings with other platforms, stating that they are being paid less. Due to this high attrition and short working duration, salary processing becomes challenging. We also asked why they opted for the software despite this situation. The user responded that it was a management decision. as per vasu's meting client will be providing data post salary processing of june had a call with user to make her undertsand that all isue can be handled through spine which she is having but she seems not interested | FInds excel easy | na |  | Feb-26 | bfmsfacilitymanagementpvtltd | 2026-12-31 | 52
SPS111104252912 | 8720 | New | Account Activated | SUNRISE FOODS BANGALORE | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera |  | Tushar More | Channel |  |  | Roopa S | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 50 | 2026-12-31 | 2025-12-29 | 2026-01-14 | 2026-01-17 | ENGG | 2026-09-30 | NG,TAM | Fresh | 0 | 88 | Spine NG | Held | Online | Payroll Training completed July month salary processed and tallied. HRMS Training done. client were using hrms attendance for 2 months but after that they were not using are not taking interest for payroll module. after a multiple followup for aug salary aug sal done followup is going on for sept sal but no response. Not responding calledMr. Jeson he said will let us know in 2 days. afte 2-3 days we are calling and doing mail but no response. Held up- Payroll training has been completed. July salary was processed and successfully tallied. HRMS training has also been completed. The client was using HRMS attendance for around two months; however, they have not been actively using the system thereafter and are currently not showing much interest in the Payroll module. Follow-ups are currently ongoing for the September salary processing, but there has been no response from the client. We contacted Mr. Jeson, who informed us that he would provide an update within two days. However, even after 2–3 days, despite repeated calls and email follow-ups, we have not received any further response from the client. The client is currently not responding to our calls or follow-ups. | No Response - No Reason | No data | Jul-26 | Jul-26 | sunrisefoodsbangalore | 2026-12-31 | 53
SPE111097252312 | 8713 | New | Account Activated | EVERGREEN HOUSEKEEPING SERVICES PRIVATE | Escalated | C | Divya Bhide | Hiren Bhimani |  | Komal Kanadiya | Channel |  | TAPASH SOFTWARE-SP | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | Hosting | 1400 | 2026-12-31 | 2025-12-23 | 2026-01-05 | 2026-01-07 | PARTNER |  | NG | Fresh | 0 | 100 | Spine NG | Active | Online | set up & training done, jan done, feb done later client is not responding to calls n mails |  | Received | Jan-26,Feb-26 | Feb-26 | evergreenhousekeepingservicespvt | 2026-12-31 | 54
SPR111093252212 | 8709 | New | Account DeActivated | RAJESHWARI INFOTEL PVT. LTD | Normal | E | Karuna Rajaram Sandim |  |  | Riddhi Pramod Sutar | Channel |  | ACQUIRO BUSINESS | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 1200 | 2026-03-31 | 2025-12-22 | 2025-12-31 | 2026-01-08 | PARTNER | 2026-05-12 | NG,ESSM,LV,TAM,ELC,EXP | Fresh | 0 | 56 | Spine NG | Lost | Online | payroll hr set up done, jan tallied, payroll hr training done, onboard impl going on- client lost report as per their req not possible, had taken on trail basis, they will continue with TCS | Another Software |  | Dec-25,Jan-26,Feb-26 | Feb-26 | rajeshwariinfotelpvtltd | 2026-05-12 | 55
SPN111014252911 | 8623 | New | Account Activated | NIKIKA ENTERPRISES LLP | Normal | E | Mansi Singh |  | 2026-05-14 |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 175 | 2026-12-31 | 2025-11-29 | 2025-12-04 | 2025-12-03 | OS | 2026-05-19 | NG,ESSM,LV,TAM,EXP | Fresh | 0 |  | Spine NG | Go LIVE | Onsite | go live - training and impl done april processed |  | FULL PAYMENT RECVD | 0 | Apr-26 | nikikaenterprisesllp | 2026-12-31 | 56
SPP111012252911 | 8619 | New | Account Activated | PRIJAI HEAT EXCHANGERS PRIVATE LIMITED NG | Normal | E | Ankita Bankar | Sahil Gadhave | 2026-02-12 | Goraksha Pawar | Direct |  |  | Amarprit Kaur | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 400 | 2026-11-30 | 2025-12-10 | 2025-12-15 | 2026-01-02 | ENGG | 2026-03-11 | NG,ESSM,LV,TAM,HD,PMS,RCT,ON,OFF | Fresh | 0 | 100 | Spine NG | FC | Onsite | Project Live - Training & Implementation of Payroll is completed along with December month processing & tallied - W26jan4616 We have completed training for Spine Employee Portal (ESSM,HR-Leave,HR-Time,Time,Leave and Mobile-HR). - W26jan2535 Spine HR training has been successfully completed for employees and HODs, and login rollout has also been successfully completed across the organization. - W26jan6293 We have completed Training for Onboard, Confirmation and Offboard Module, - W26jan5538 Training & Implementation completed for PMS Module - W26jan2536 Training and implementation completed for Recruitment Module - W26jan5505 February month salary processed live with attendance from system |  | Received |  | Aug-26 | prijaiheatexchangerspvtltdng | 2026-11-30 | 57
SPF110994252511 | 8600 | New | Account Activated | FEATHERTOUCH LEARNING PRIVATE LIMITED | Normal | E | Ritika Dilip Singh | Saurabh Pednekar | 2026-07-14 | Sunita Yadav | Channel | SA | KALYA TECHNOLOGY INNOVATION PRIVATE LIMITED-SA | Roopa S | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 500 | 2026-11-30 | 2025-11-25 | 2025-12-03 | 2025-12-30 | ENGG | 2026-07-15 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Online | welcome mail done #3/12 - eng - Corp ID done, datafiles awaiting #22/12 - no response Non Payroll Master Data received and uploaded. Salary Calculation received and configured. #19/01 - eng - salary processed, shared register to client for verification, waiting for reply Payroll Training and Implementation Completed W26jan4046. Mobile HR Training Completed W26jan5841. 19/01 - User is on leave and will connect on 21/01 for salary processing. SMTP Configuration Completed #W26jan7987. Location Configuration Completed #W26jan7983. HRMS Training Completed #W26jan8122. December 2025 Salary Completed #E26jan11453. January 2026 Salary Completed #W26feb6498. 08/04 - February processed and tallied, awaiting confirmation. User is too busy in internal work. Attendance Policy changes done. User will process salary by 15/04. #10/4 - busy February 2026 Salary Completed E26apr9176. Roll Out Completed E26apr9176. 24/04 - As per discussion, user not able to process March salary due to license count exhausted. In April as well count is exceeded. User is in discussion with management to increase the license count. User will discuss internally and will update. March salary will be processed post license update. #14/05 - eng - Non payroll employees april processed. Payroll employees configuration is completed and client will process salary in few days #1/06 - eng - in last schedule, they processed may salary with attendance. #W26may11974 - may salary conf. #25/06 - eng -All configuration done and training completed. Till May salary done but May confirmation not received as the Payroll user left the organization so coordinating with another user for all the processes. Now user have shared some changes in the calculation for Payroll category employees so we are finding a way to configure this. From June month user will process the salary with attendance data as they have some internal issues with the attendance. June 2026 Salary Completed with Attendance W26jul873. #10/08 - feedback good and positive #24/09 - regarding renewal as discussed with our accounts team, partner has rcvd the payment from user end, however, payment from partner is still pending. #5/10 - as discussed with our accounts team, partner has released the payment to spine. |  | FULL PAYMENT RECEIVED | Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26,Sep-26 | Sep-26 | feathertouchlearningpvtltd | 2026-11-30 | 58
SPG109937253101 | 8572 | Add Mod | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-11-22 | Utkarsh Sanjay Chavan | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2025-11-19 | 2025-11-19 | 2025-11-21 | ENGG | 2025-12-10 | ELC (NX) | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training & Implementation of ELC Module is completed - E25nov7072 Logins rolled out for ELC module |  |  | Dec-25 |  | gngelectronicsltdfactory | 2026-10-31 | 59
SPN110948251311 | 8547 | New | Account Activated | NAIK MOTORS - RATNAGIRI LOC | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2026-08-10 | Aditya Mazire | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 180 | 2026-10-31 | 2025-11-13 | 2025-11-25 | 2025-12-22 | ENGG |  | NG, ESSM, LV,TAM, ELC | Fresh | 0 | 98 | Spine NG | AC | Online | completed the payroll & HRMS training and have process the salary of Dec.2025. we have updated the leave policy, attendance policy. MAY PROCESSED June processed July processed with attendance. August salary processed As per feedback user sultana said salary has been processed and disbursed but not with attendance as 10--15 employees attendance card no got mismatched by goa loc thats why we unable to process and done atten manually. but salary has been disbursed on 7th yesterday. | "The user did not provide the data files initially. After a delay of two months, the required data files were shared. We will begin the implementation based on the received data. During this interim period, we conducted multiple follow-ups with the Naik Motors team to obtain the required information. Additionally, the attendance integration issue continues to persist then we will resolved that isuue also." | The balance amount of first 70% and pending 30% will be paid after 1 month salary process Also full GST pending which will be received by 1 month salary process (Received) | Jul-26,Aug-26 | Aug-26 | naikmotorsratnagiriloc | 2026-10-31 | 60
SPN110937250811 | 8531 | New | Account Activated | NAIK MOTORS -GOA LOC | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2026-07-14 | Aditya Mazire | Channel |  |  | Sandeep Ashok Joundal | Viral Panchal | Vasu Mohan Dusa | SAAS | 410 | 2026-10-31 | 2025-11-08 | 2025-11-20 | 2025-12-17 | ENGG |  | NG, ESSM, LV,TAM,ELC | Fresh | 0 | 88 | Spine NG | AC | Online | following has been completed in the training: Payroll & HRMS Salary of Dec 2025 Shift creation Leave policy Leave opening balance upto Dec 2025- W26jan7547 MAY PROCESSED june processed with attn july done Aug sal done add module after 10th oct we will ask client. sept live sal will do. |  | The sum amount of first 60% and pending 40% will be paid after 1st salary process. ( Received) | Jul-26,Aug-26 | Aug-26 | naikmotorsgoaloc | 2026-10-31 | 61
SPS110901253110 | 8487 | New | Account Activated | SREE METALIKS LTD | Premium | E | Divya Bhide | Sahil Gadhave | 2025-12-22 | Nandadeep Mhatre | Channel |  | TAPASH SOFTWARE-SP | Sumit Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 700 | 2026-10-31 | 2025-10-31 | 2025-11-04 | 2025-11-17 | ENGG | 2026-03-10 | NG,ESS,LV,TAM | Fresh | 0 | 110 | Spine NG | Go LIVE | Online | "7th "payroll hr set up done, oct tallied,bio int done, logins done, training done, dec done W26jan10986 client FC |  |  | Mar-26 | Mar-26 | sreemetaliksltd | 2026-10-31 | 62
SPV110891253010 | 8476 | New | Account Activated | VIVID ELECTROMECH LIMITED | Normal | E | Ritika Dilip Singh | Vinay Kareliya | 2026-03-06 | Mihir Navnath Mungekar | Direct |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 250 | 2026-10-31 | 2025-10-30 | 2025-11-18 | 2025-11-19 | ENGG | 2026-09-30 | NG,ESSM,LV,TAM | Fresh | 0 | 96 | Spine NG | FC Lost | Onsite | #payroll training and impl done- E25nov7138, E25nov8316 E25nov9114 #hrms training and configuration done- E25dec416 #geo tagging and integration done #E25dec4143 November salary also tallied, #dec done- E26jan2964 #feb done with attn have few requirements they were not willing to proceed because of that somehow we are convincing them team is in discussion we are following up for salary #28/09 - no response #FC LOST - As discussed with User Akash, Vivid Electro has decided not to continue using our software. They require certain modifications to the dashboard, along with changes to the hierarchy structure. These requirements are currently not feasible within our software. | Requirement | Received | 0 | Jun-26 | vividelectromechltd | 2026-10-31 | 63
SPN110876251610 | 8434 | New | Account Activated | NAGRIK CONSULTANCY SERVICES | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2025-12-03 | Aditya Mazire | Direct |  |  | Nandini Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 205 | 2027-04-30 | 2025-10-18 | 2025-10-24 | 2025-10-25 | ENGG | 2026-06-15 | NG,ESSM,LV,TAM,ON/OFF,HD | Fresh | 0 | 100 | Spine NG | FC | Onsite | completed Payroll training .-W25oct5654 completed with HRMS training on 1st Phase with Add on service. processed and tally the salary of Sep 2025 month for all 3 grades for126 employees. processed the salary of Oct 2025 month.- W25nov634 Employee training and logins roll out processed Salary for Nov 2025, for Midas touct MT, NHO, with attendance and tallied the same November salary processed December salary processed Jan salary done. Feb salary done. March salary done. april salary done may salary processed june salary processed As per feedback user Ms. Suvarna said No queries as such we are getting support which we required. June salary is in process. user said no queries and concern if we have we raised the mail as we asked mansi ji has escalated the attendance queries it has been resolved | Suggestion ID: 3709 Requirement: Leave Year Selection in Mobile Application Suggestion ID: 3536 Requirement: Add-On Service Request and Approval Option in Mobile Application | 70% payment to be made in advance to initiate the implementation process. Remaining 30% payment to be made after completion of implementation, i.e., within 30 days. (Received) | Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | nagrikconsultancyservices | 2027-04-30 | 64
SPS110851253009 | 8410 | New | Account Activated | SAFFRON SPECIALITY PAPERS LIMITED | Normal | E | Ritika Dilip Singh | Akshay Shinde |  | Yash Pankajkumar | Direct |  |  | Amarprit Kaur | Viral Panchal | Vasu Mohan Dusa | SAAS | 440 | 2026-09-30 | 2025-10-08 | 2025-10-09 | 2025-10-28 | ENGG |  | NG,ESSM,LV,TAM | Fresh | 0 | 95 | Spine NG | Active | Onsite | HRMS Training yet to start, for Dec 25 salary the attendance data yet to come YASH is in discussion salary processing session aligned post that user will release payment planning to proceed with one unit only user has conveyed that she will process march with attn from system in process The client is processing salary for her unit now. They process salary on a 45-day basis. Attendance integration is done. Logins won't be rolled out. The user has uploaded the roster; post manager's approval, she'll process salary with attendance from Spine. march processed for 114 employees logins rolled out they will be processing june live with attn- in process #30/07 - meeting planned for tomorrow. #5/08 - salary is delayed due to different salary cycle of 45 days, it is usually delayed because they receive data late from their site. #2/09 - eng - following up going on for attendance for august salary #8/09 - eng - As discussed, the current HR, Rupali, is serving her notice period, and this is her last working month. Since she is in the process of leaving, she is not showing much interest in the ongoing activities. For further communication, we are coordinating directly with Director Siddharth. However, he is currently occupied with a medical emergency involving a family member, so we will not be able to connect with him this week. We will follow up with him by 11th September based on his availability. Additionally, we are planning a surprise visit on Monday along with the PM and Engineer. We have also heard that the office may be relocating to Thane, so it would be important to discuss this with them at the earliest and understand the impact on the ongoing activities. #9/09 - As discussed with MD Siddharth, I asked him about the reason for the delay in salary processing and the pending salaries for July and August. He asked me to connect with Ms. Rupali regarding the same. He added her to the call and then left. During my discussion with Ms. Rupali, she explained that they have two units, and the employees there do not properly punch in and out for attendance. Due to this, attendance mismatches occur, which she has to regularize manually. This process takes a lot of time and is the main reason for the delay. I understood the issue and asked for her availability so that we could proceed with clearing the backlog and processing the July and August salaries. She requested us to give her a few minutes and said that she would try to clear the pending attendance backlogs herself. She also informed us that if she faces any issue, she will call us back. #26/09 - new user trng completed, awaiting for confirmation, user sunita is on leave, she will connect us for confirmation monday. #28/09 - Planned a onsite meeting for tomorrow. | All setup and training done, integration also done, due to internal activity always the data get delay due to the project is delay | Received | 0 | Jun-26 | saffronspecialitypapersltd | 2026-09-30 | 65
SPH110833253009 | 8409 | New | Account Activated | HARDCARB TECHNOLOGIES PVT. LTD - STAFF | Normal | E | Ankita Bankar | Vinay Kareliya | 2026-04-08 | Mihir Navnath Mungekar | Direct |  |  | Amarprit Kaur | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 135 | 2027-03-31 | 2025-10-08 | 2025-10-16 | 2025-10-17 | ENGG | 2026-05-11 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | Project Live - Payroll NX training completed & HRMS training done Regular month wise salary processing is going on |  | 50% of the product cost +full GST will be receivable after implementation or 45 days whichever is earlier (Received) | 0 | Sep-26 | hardcarbtechpvtltdstaff | 2027-03-31 | 66
SPC110823252909 | 8381 | New | Account Activated | CENTRE FOR URBANIZATION BUILDINGS | Normal | E | Disha Kiran Kargutkar |  |  |  | Channel |  | VINCIBLE SOLUTION-SP | Roopa S | Saurabh Thakur | Vasu Mohan Dusa | SAAS | 95 | 2027-08-31 | 2025-09-29 | 2025-09-30 | 2025-10-02 | OS |  | NG,ESSM,LV,TAM,EXP,ELC,RCT,TS,HD | Fresh | 0 |  | Spine NG | Active | Online | training and Implementation done from January they will process payroll from our system, currently using existing system Implementation in process/ PMS module training going. Time Sheet only live processing. Remaining module implementation is going on. Training is going on |  | Extra amount received need to adjust with future billing | 0 | 0 | centreforurbanizationbuildings | 2027-08-31 | 67
SPP110783251209 | 8328 | New | Account Activated | PARADISE GROUP | Premium | E | Ankita Bankar | Amey Telge | 2026-06-26 | Pritesh Barot | Channel |  |  | Ankur Yewalekar | Viral Panchal | Vasu Mohan Dusa | SAAS | 624 | 2026-09-30 | 2025-09-12 | 2025-09-16 | 2025-09-23 | ENGG |  | NG,ESSM,LV,TAM,PMS,RCT,ELC | Fresh | 0 | 97 | Spine NG | AC | Online | Training & Implementation of Payroll is completed along with August month processed & tallied - E25oct1359 Training & Implementation of ESSM, Leave & Tam module is completed & attendance integration is done - E25oct1359 RCT module training & Implementation is done PMS Training & Implementation is done for Payroll processing our team is doing followup but user is not giving proper response onsite engineer visit for daily queries dicussion is going on with user - 20th August |  | Received | 0 |  | paradisegroup | 2026-09-30 | 68
SPM110771250109 | 8316 | New | Account Activated | MEDIPULSE HOSPITAL | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2026-07-31 | Varun Rajbhar | Channel |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 731 | 2026-12-31 | 2025-09-06 | 2025-09-09 | 2025-10-09 | ENGG |  | NG,ESSM,LV,TAM,ELC,RCT,EXP | Fresh | 0 | 98 | Spine NG | AC | Online | Today, we completed the HRIS module of payroll. We aim to roll out the employee login before continuing the training from HR. We have finished the self-service module. Discussions regarding the remaining modules (leave, attendance, time, and mobile) and configuration will continue tomorrow at 10:30 AM-E25oct4617 * Employee Self Service = Training completed * Leave & Time Management = Partial * Recruitment = Training completed, feedback forwarded * Onboarding = Training completed, feedback forwarded April salary processed with attendance. June salary processed. Using only hrms module-E26jul2760 As per client first we want clear the payroll and basic regular issue Then we move to expense module we are connected with medipulse to tally remaining employees salary of june after that other queries will be resolve. As per feedback Payroll: No major queries as such. However, the client reported a salary mismatch for 10 employees and is currently unable to identify the reason for the difference. Attendance is being used but is not fully live, as some entries are still managed manually. They also mentioned delays in receiving proper support. One ticket, E26AUG4427, is ongoing regarding the reimbursement policy queries are on going. August salary on monday | Using only the HRMS Module, payroll is now initiated | Received | Dec-25,Mar-26,Apr-26,Jun-26,Jul-26,Aug-26 | Aug-26 | medipulsehospital | 2026-12-31 | 69
SPF110735252908 | 8275 | New | Account DeActivated | FUJIYAMA POWER SYSTEMS LIMITED | Premium | E | Divya Bhide | Hiren Bhimani | 2026-01-12 | Komal Kanadiya | Channel |  | PARAMHANS COMPUTERS-SP | Sumit Kumar | Hiren Bhimani | Vasu Mohan Dusa | SAAS | 2400 | 2026-02-28 | 2025-08-29 | 2025-09-08 | 2025-09-23 | PARTNER | 2026-07-29 | NG,ESS,LV,TAM | Fresh | 0 | 110 | Spine NG | Lost | Online | cut off- 8th of every month payroll- set up & training done, aug 25 salary processed & tallied hrms- ess, lv ,tam modules set up & training done, bio int done, logins done attendance queries, not showing interest meeting done of RM Manish Lost- opted GreytHR, support-integration related concerns. | Another Software | The remaining 50% + Implementation cost will be payable after 90 days.(Lost) | July-25,Aug-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26 | Feb-26 | fujiyamapowersystemsltd | 2026-07-29 | 70
SPS110711252008 | 8245 | New | Account Activated | SETHWALA FOODS LTD | Normal | E | Disha Kiran Kargutkar | Sahil Gadhave | 2026-03-12 | Kunal Joshi | Direct |  |  | Nandini Tiwari | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 600 | 2027-08-31 | 2025-08-20 | 2025-08-22 | 2025-08-28 | ENGG | 2026-05-14 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | GO FC- Client have completed training session of Payroll & HRMS . Also SMTP setup & locationAPI setting has been done successfully.-E25sep1207 september salary of ho done October salary done The training has been completed in talasari-E25nov8643 client have processed SFLD unit salary for the month of Dec'25 with attendance muster from the software successfully. With Login was provided to employees -E26jan2962 client inform us, for this month, HO salary will be run through Spine, while Talasari salary will be processed via Excel uploading.-E26feb1695 feb salary done march salary processed April salary processed-E26may3191 May salary processed Jun salary processed july salary done August salary processed. Called for feedback user vidhya user said queries are coming but it is getting resolved first only mumbai loc we were doing live but now talasari loc we are doing for aug but lie with attendance. sept will be fully live for both loc. will do sept live by 10th | user will directly do august salary but they will do in excel first and then in software for one month after attendance integration will do with aug and next sept month live salary. for integration discussion is going on with vendor. 9/9 | Received | Apr-25,May-25,Aug-25,Sept-25,Oct-25,Nov-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26 | Aug-26 | sethwalafoodsltd | 2027-08-31 | 71
SPR110686250108 | 8212 | New | Account DeActivated | RAMYASRI ELECTRICAL AUTOMATION | Normal | E | Divya Bhide | Probian Biswas |  | Ankita Gupta | Channel | SP | BRILLIANT TECHNOLOGIES_Silver - SP | Roopa S | Viral Panchal | Vasu Mohan Dusa | SAAS | 250 | 2026-02-28 | 2025-08-06 | 2025-08-28 | 2025-09-17 | ENGG | 2026-03-31 | NG,TAM | Fresh | 0 | 36 | Spine NG | Lost | Online | 47 emp data recd, tallied, payroll set up done, training pending not responding,esc to PM, partner team, ignoring calls, 5/2 structure recd of 36 recd, uploaded, rest data follow up going on 10/3 meeting done- datafiles will share 12/3 client not showing interest, amc not renewed, no response from client,client deactivated, | No Reponse - No Reason |  | Sept-25,Oct-25 | Oct-25 | ramyasrielectricalautomation | 2026-03-31 | 72
SPT110669253107 | 8204 | New | Account DeActivated | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. | Normal | E | Mansi Singh | Amey Telge |  | Vijay Bugde | Direct |  |  | Amarprit Kaur | Viral Panchal | Vasu Mohan Dusa | SAAS | 1500 | 2026-07-31 | 2025-08-02 | 2025-08-22 | 2025-09-02 | ENGG | 2026-05-13 | NG | Fresh | 0 | 100 | Spine NG | Lost | Onsite | corp id creation done trng and impl in process Toyota and Hyudai branch employee data uploaded sucessfully also we processed Toyota branch sept month salary Employees work across multiple sites/companies and salary processing happens there. The director is using our software only to verify if the salary tallies with attendance data User is not responding, we are trying to reach user multiple times. vasu is looking into it (planning visit) director is not available, nor he is responding calls vasu went for onsite visit but they are not interested to proceed escalated the concern to amrprit through email client not interested | No Reponse - No Reason |  | Oct-25 | Oct-25 | trishulelectromechengineeringindiapvtltd | 2026-07-31 | 73
SPW110622251807 | 8143 | New | Account Activated | MUKTA ARTS LTD | Normal | E | Ankita Bankar | Amey Telge |  | Nagendra Poojary | Direct |  |  | Mehul Patel | Viral Panchal | Vasu Mohan Dusa | SAAS | 350 | 2027-07-31 | 2025-07-18 | 2025-07-24 | 2025-08-06 | ENGG |  | NG,ESSM,LV,TAM,MOB, PMS,EXP,ELC | Fresh | 0 | 82 | Spine NG | Active | Onsite | Working done on 6th August for training user will let us know the dates attendance integration done as per users request W25aug2358 Payroll Training done & August month processed & tallied September month salary processed January 2026 month salary processed Apr month salary processed June month live with attednace salary processed User is busy interanally in PMS & after July month processing will plan add mod training - 22nd july renewal will be done before 10th august as user convyed at vasu's visit Tech ID - 4192 Currently, the PMS system allows ratings in decimal values. However, as per the client's requirement, there should be a configuration/setting available to disable decimal ratings and allow only whole-number ratings during the performance evaluation process. - This req is yet to delivered user & after that only they are ready to renew - renewal is done | Initially, the user was not using the Spine software, as they felt that performing tasks in the system was time-consuming. To address their concerns, we arranged a meeting with the Project Manager and the client to discuss the issues and provide clarification. Following the meeting, the user agreed to adopt the software and has started using the system. | Received | 0 | Aug-26 | muktaartsltd | 2027-07-31 | 74
SPI110558252806 | 8079 | New | Account DeActivated | ILEAF RITZ BANQUETS | Normal | E | Mansi Singh | Probian Biswas |  | Mayur Pendhari | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 110 | 2026-06-30 | 2025-06-28 | 2025-07-01 | 2025-07-02 | ENGG | 2026-06-18 | NG,ESSM,LV,TAM | Fresh | 0 | 110 | Spine NG | Lost | Onsite | Welcome mail done Implementation and training starts from 2nd Jul 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. Proper data wasnt received, earlier , received proper data on 21st aug, and we have aligned working schedule from 22nd aug 25. payroll training done, hrms in process schedule aligned for pending training. Payroll training done HRMS started Jul salary tallied client has not disbursed aug salary yet, there is no fix date. Balance payment received and user shall process the salary in this week. Vasu had a meeting with client , as per discussion in meeting there are lot of queries and user shall mail us the same. Jan salary done. As per recent Meeting, as mentioned by Vasu the user was busy in her activities, did not interacted much, New user has joined i leaf, Need to give training for new user, however the user is busy in salary processing apr not much interested user find steps too lengthy not interested in using the software | Finds excel easy | Received | July-25,Aug-25,Oct-25,Nov-25,Dec-25,Jan-26 | Jan-26 | ileafritzbanquets | 2026-06-30 | 75
SPU110473253105 | 8042 | New | Account Activated | UNITED AIR EXPRESS | Premium | E | Ankita Bankar | Nagesh Tiwari | 2026-02-13 | Shubham Gurav | Channel |  |  | Nirbhay Kumar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 3050 | 2027-05-31 | 2025-06-19 | 2025-06-24 | 2025-07-21 | ENGG | 2026-03-11 | NG,TAM | Fresh | 0 | 100 | Spine NG | FC | Online | Project Live - Training & Implementation of Payroll is completed & June month tallied - #E25jul9421 Training & Implementation for Tam & Mobile HR module is completed - #E25jul11682 Mangers are using logins & As of now user will not rolled out logins to employee- #E25jul11682 July month salary processed August and September month processing done January & February month live salary with attendance is done through system |  | Receeived | 0 | Aug-26 | unitedairexpress | 2027-05-31 | 76
SPM110480253105 | 8009 | New | Account Activated | MESPACK INDIA PVT. LTD | Normal | E | Disha Kiran Kargutkar | Akshay Shinde | 2026-06-19 | Pooja Vikas Shinde | Channel |  |  | Sandeep Ashok Joundal | Viral Panchal | Vasu Mohan Dusa | SAAS | 60 | 2027-05-31 | 2025-06-09 | 2025-06-12 | 2025-07-02 | ENGG | 2026-06-19 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Payroll training done successfully completed the attendance integration activity at the client’s location. W25oct6232 , E25nov1863 october salary has been processed. nov salary done successfully processed the December 2025 salary. - E26jan4924. Expense module training done Jan salary processed February salary done March salary has been processed-E26apr8430 April done may salary done parallelly GO FC- As all activities related to training and implementation have been completed successfully, and the system is now fully ready for use. Due to an internal gap, the attendance has not been regularized so salary processing will be carried out in parallel. August salary has been processed with attendance. Called for feedback to user Ms. Usha not responded the call. sept live sal target As per akshay sept sal followup is going on |  | Received | June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jul-26,Aug-26 | Aug-26 | mespackindiapvtltd | 2027-05-31 | 77
SPC110448252805 | 7954 | Add Mod | Account Activated | CIRCLE RESOURCES PRIVATE LIMITED | Premium | E | Disha Kiran Kargutkar | Amey Telge | 2025-11-13 | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1700 | 2026-10-09 | 2025-05-28 | 2025-06-17 | 2025-06-17 | ENGG | 2026-06-15 | NX,ESSM,LV,TAM,ELC,EXP,HR | Fresh | 0 | 91 | Spine HRMS | FC | Online | WELCOME MAIL DONE WILL PROCEED WITH THIS BY 10TH JUNE - E25jun3240 SPLITTING DONE training and impl done Oct 2025 salary processed - E25nov2426 from spine Disbursement date - 11th of every month. processing salaries parallely additional rule techical given by hemant sir on friday Engineer mayur has restored the database after that we will check and update the client as viral sir said till thursday we will connect client as mayur is onsite. One month extension is given by accounts team. As discussed with Mayur, some policies and shifts were removed as per the client’s requirements. A solution was provided for attendance recalculation, regularisation, and lock/unlock of attendance for 7 days at a time. The client will check and monitor the solution for one month. The salary disbursement date is the 7th of every month. After September salary processing and one month of observation, the client will decide on renewal. | Disbursement date by 15th |  | May-25,June-25,July-25,Aug-25,Sept-25,Oct-25 | Jun-26 | circleresourcespvtltd | 2026-10-09 | 78
SPB110442252705 | 7947 | New | Account Activated | BRIGHT BROTHERS LTD | Normal | E | Ankita Bankar | Akshay Shinde | 2026-02-24 | Yash Pankajkumar | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Viral Panchal | Vasu Mohan Dusa | SAAS | 330 | 2026-11-30 | 2025-05-27 | 2025-05-27 | 2025-06-07 | ENGG | 2026-08-14 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Project Live - training and impl done logins rolled out HO AND FARIDABAD attn issues resolved. they will be processing the salary with attn. DEC SALARY done Pondy Branch they wont be processing salary- W26jan10247 salary processing in process(loc wise) July month live salary processed from system |  | Received | June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25 | Sep-26 | brightbrothersltd | 2026-11-30 | 79
SPN110379253004 | 7880 | New | Account Activated | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Premium | E | Ankita Bankar | Amey Telge | 2025-08-18 | Aditya Mazire | Channel | SP | RISHIKESH CONSULTANCY- SP | Tejas Kareliya | Viral Panchal | Vasu Mohan Dusa | On-Premises | 2500 | 2027-04-30 | 2025-05-07 | 2025-05-08 | 2025-05-21 | ENGG | 2025-11-11 | NX,ESSM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Installation done & Project delivery rcvd Training & Impelmentiaon of Payroll NG done & April month salary processed. HRMS training done June 2025 and July 2025 processed and tallied the same. - E25aug6925 August month salary processed live - E25aug6925 September month salary processed Live from system October month salary processed live |  |  | Mar-26 | Mar-26 | nationalbulkhandlingcorporationpvtltd | 2027-04-30 | 80
SPP110398250605 | 7876 | New | Account Activated | PROCON RMC PLANTS PRIVATE LIMITED | Escalated | E | Disha Kiran Kargutkar | Shreyas Karkera | 2025-08-11 | Sushant Thombare | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2025-05-06 | 2025-05-12 | 2025-05-13 | ENGG | 2025-08-15 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | E25jun699 Payroll training confirmation Training confirmation till leave module #E25jun1063 E25jul1122Hrms training and May 25 Salary confirmation till aug salary has been uploaded client said an audit is currently underway at our office, and I am occupied with the auditors to address their issues and resolve their queries. Kindly allow some time to complete the audit-related work. will get back to us as soon as he will be available. |  |  | Apr-25,May-25,June-25,July-25,Aug-26 | Aug-26 | proconrmcplantspvtltd | 2027-04-30 | 81
SPD110360252904 | 7872 | New | Account Activated | DRS EARTHWORK PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2026-05-15 | Mihir Navnath Mungekar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2026-10-31 | 2025-05-05 | 2025-05-06 | 2025-06-16 | ENGG | 2026-05-15 | NX,ESSM,LV,TAM,EXP | Fresh | 0 | 97 | Spine HRMS | FC | Online | payrollnx training has been done.-E25jun5999 Admin, attendance, leave module training is done.-E25jun6439 processed the salary for the month of June 25 in Payroll NX.-E25jul6312 July 25 salary has been processed. August salary has been donebut not with attendance. August salary processed. September salary processed Oct salary done Nov salary done December salary processed. Jan salary done Feb salary done March salary done April salary done GO FC- As discussed with client, the current issue is internal from client side and is not related to our software or engineer support. We are glad to know that the support provided by our team has been satisfactory. Since HRMS and Mobile HR are functioning as discussed, we are considering the project as Fully Completed (FC). Salary-related activities will continue in parallel as agreed. connected with client Last week as per user requirement we have deleted salary for Apr-25 to Mar-26, and uploaded past salary data for all emps, Now user will process Apr & May this week and will get back to us incase of any query by 27-Jun. client will do june salary by own which will be parallel. As per feedback user said no queries if it is will let you know as I am on leave connected today for july salary As per the discussion done with Shital ji, major emps are in the field, and are not willing to mark attendance through mobile. HRMS is utilitised by approx 100 emps but live disbursement is done through excel and they will process salary in Spine for record keeping purpose only As per the feedback received from user Ms. Shital, the client is currently using the HRMS, but the process is partially manual and partially system-based. For employees who work outside the office, proper in/out punches are not recorded, so their attendance is managed manually. For employees working in the office, attendance is recorded through the system. The client uses the system for attendance summary reports and collect leave data; however, salary processing is still done manually based on these reports. Currently she has a few minor query. We told her to share the queries on the support ticket ID for further assistance. |  |  | May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Jul-26 |  | drsearthworkpvtltd | 2026-10-31 | 82
SPS110245253103 | 7866 | New | Account Activated | SNAPWORK TECHNOLOGIES PRIVATE LIMITED | Normal | E | Ritika Dilip Singh | Amey Telge | 2025-11-12 | Vijay Bugde | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | SAAS | 470 | 2027-05-31 | 2025-05-03 | 2025-05-08 | 2025-05-20 | ENGG | 2026-04-15 | NX,ESSM,LV,TAM,ELC,EXP,PMS,RCT,TS,RD | Fresh | 0 | 98 | Spine HRMS | FC | Onsite | welcome call done payroll done april tallied hrms basic module done geo tagging done logins rolled out integration/smtp done MAY DONE E25jun8292 june salary conf- E25jul5746 LDAP and maker checker. provided processing live salary from system pms and time sheet pending- if session required client will reach out to us.W26apr5969 #10/08 - rcvd a ticket from user regarding issue in approver. #18/08 - feedback was not good at all, she told she would give zero rating, her main issue was about resource allocation charges, which i was explaining her, then she told, she is quite allocated today, we can connect tomorrow. #28/08 - E26aug9070 - user requested for user manual for sharing with their employees. | Not responding to accounts team, Vasu has asked Sejal to speak with Prashant ji, Vasu also to speak and update 30/10 | Received | Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Jul-26,Aug-26,Sep-26 | Sep-26 | snapworktechpvtltd | 2027-05-31 | 83
SPA110196252903 | 7773 | New | Account DeActivated | ASHWINI CONTAINER MOVERS LIMITED | Normal | E | Disha Kiran Kargutkar | Amey Telge | 2025-09-08 | Amey Telge | Direct |  |  | Tejas Kareliya | Viral Panchal | Vasu Mohan Dusa | SAAS | 300 | 2025-10-31 | 2025-04-17 | 2025-04-21 | 2025-05-02 | ENGG | 2025-11-25 | NG,ESSM,LV,TAM,PMS | Fresh | 0 | 89 | Spine NG | Lost | Onsite | Client completed the training for Payroll and HRMS.-E25may4794 May salary done for both companies-E25jun3160 June salary Processed july salary has been processed. August salary processed. sept salary processed As per feedback client inform us that the AMC renewal has been kept on hold, as their management has decided not to proceed with the renewal at this time, due to the implementation of a new software solution. | Requirement |  | Mar-25,Apr-25,May-25,June-25,July-25,Sept-25 | Sept-25 | ashwinicontainermoversltd | 2025-11-25 | 84
SPE110247253103 | 7706 | New | Account Activated | ELECTROSTEEL CASTINGS LTD | Premium | A | Ankita Bankar | Sahil Gadhave | 2026-05-12 | Kunal Joshi | Channel |  |  | Jayesh Mojidra | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 1000 | 2027-03-31 | 2025-03-31 | 2025-04-25 | 2025-07-09 | ENGG | 2026-05-13 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Online | training and impl conf- E25jul10921 logins rolled out not going to process salary from spine, using hrms. renewal done | SAP directly integration requirement for attendance muster, To check with Avaniko parner for the same, Roopa has denied to approach avaniko No proper response from Roopa | 1.25% of Software Cost payable on Installation of software duly certified by concerned in-charge. 2. 50% of Software Cost + Implementation charges along with GST bills to be submit in accounts duly certified by concerned in-charge. 3. GST amount will be paid against proof of uploading of bills in GSTR1A and GSTR3B. (Received) | 0 |  | electrosteelcastingsltd | 2027-03-31 | 85
SPC110185252803 | 7668 | New | Account Activated | CONTENDRE GREENERGY LIMITED | Normal | E | Ritika Dilip Singh | Akshay Shinde | 2025-07-17 | Daksh Pawankumar | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 160 | 2027-03-31 | 2025-03-27 | 2025-03-28 | 2025-04-21 | ENGG | 2026-05-14 | NX, ESSM,LV,TAM,MOB-HR, ELC,Travel exp | Fresh | 0 | 100 | Spine NG | FC | Onsite | #Trng and impl from 21st April #E25apr9485 - complete upto loan processing module #E25apr10010 - Payroll nx training is completed Location IQ set up has been done #E25apr11264 - have completed HRMS and SMTP training #W26may1493 - update ESIC rules in Payroll #E25jul1135 - june salary conf. #W25aug3365 - PAYROLL HRMS CONF. #W25sep4179 - august salary done. #07/05 - feedback was good, processed april month salary. #18/08 - overall feedback was good, they’ve been facing an issue while transferring employee from one company to another.she require a proper solution for the same. | No open queries as of now, Vasu to connect with the director for review meet 5/9 |  | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26,Sep-26 | Sep-26 | contendregreenergyltd | 2027-03-31 | 86
SPS110155252403 | 7631 | New | Account Activated | STEAM HARBOUR LOGISTICS PRIVATE LIMITED | Normal | E | Mansi Singh | Akshay Shinde | 2025-12-08 | Daksh Pawankumar | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | SAAS | 65 | 2027-03-31 | 2025-03-24 | 2025-03-25 | 2025-04-07 | ENGG | 2025-12-12 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | client want impl of this license first and post this license they will proceed with steam pulse- E25mar8257 Payroll and HRMS training has been completed. SMTP setting has been configured. Salary has been processed for March 2025 and same was tallied properly. E25apr4714 MAY SALARY done salary done till july with attn from spine. nov processed | HRMS using properly, for salary procesing to be done from Spine, user will discuss internally and get back to us | Received | Mar-26 | Mar-26 | steamharbourlogisticspvtltd | 2027-03-31 | 87
SPV110114251303 | 7577 | New | Account Activated | VABA | Normal | E | Disha Kiran Kargutkar | Shreyas Karkera | 2025-06-17 | Karan Rajesh Tiwari | Channel |  |  | Anuj Kumar Ganga Prasad Tiwari | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 430 | 2027-03-31 | 2025-03-13 | 2025-03-17 | 2025-03-26 | ENGG | 2025-10-09 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have successfully completed the PayrollNX training Client have processed the one company Bishan Steel Industries March 2025 month salary and tally with register matches to our salary register. 1. salary attendance days demo done and queries solved Client inform that our executive Mr. Karan Has Done Following works :- 1. smtp work done 2. Leave Workflow & Attendance work flow Done 3. Tally Integration work done as demo basis and it is ok -E25apr4753 As per telecon attendance integration has been done. user is processing the may salary by its own. We have completed our Salary Process for the Month of May 2025-E25jun5684 Client have completed our Salary Process for the Month of June 2025-E25jul5468 July month salary processed August salary processed August salary processed September salary processed Oct salary processed Nov salary processed January Salary processed feb salary is in process as client want to extend the employee count. | Partner billing, User Santoshji requires invoices to clear payment from his director, but he is unable to receive from Partner, escalated to Viral to close the loop | received | Dec-25 | Mar-26 | vaba | 2027-03-31 | 88
SPR110105251203 | 7568 | New | Account Activated | ROYAL EMBROIDERY THREADS PVT.LTD. | Normal | E | Ritika Dilip Singh | Akshay Shinde | 2026-05-14 | Bhavika Gite | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | SAAS | 370 | 2027-04-30 | 2025-03-12 | 2025-03-13 | 2025-04-03 | ENGG | 2026-05-14 | NG,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | #trng and impl from 3rd april #E25mar4404 - completed training of Payroll & HRMS #W25apr6337 - added all shift schedules, and attendace logics have been added & also training & login rollouts of Mobile HR #W25may504 - Attendace integration has been done #W25may7421 - processed the april salary #W25aug449 - june salary done #W25aug772 - july salary done ##W25sep5963 - conf. of total hours calculation calculation #11/09 - processed wages of 191 employee of pune for Aug_2025, During the verification some discrepancies identified, awaitng for final confirmation. #W25DEC1871 - nov salary done #08/05 - feedback was good no issue as of now, processed april month salary. #18/08 - feedback was neutral as always, right now there is nothing to escalate.. | client conveyed that within this week end will do payment 22/9 | Received | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26,May-26,Jun-26,Jul-26,Aug-26,Sep-26 | Sep-26 | royalembroiderythreadspvtltd | 2027-04-30 | 89
SPB110087250303 | 7567 | New | Account Activated | BIJJARGI MOTORS PVT LTD | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-06-16 | Sahil Gadhave | Channel |  |  | Santosh Bhoja Shetty | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 650 | 2027-03-31 | 2025-03-11 | 2025-03-13 | 2025-03-19 | ENGG | 2025-08-21 | NG,ESSM,LV,TAM,ELC | Fresh | 0 | 100 | Spine NG | Go LIVE | Online | Project Live - Project delivery rcvd Working done 1) Spine NG Training Confirmation Ticket ID : W25mar8629 2) Spine HRMS Training Confirmation Phase I Ticket ID : W25mar9709 (Admin, Self Service, Leave, Time) 3) Spine HRMS Training Confirmation Phase II Ticket ID : W25mar10339 (Mobile HR,ELC Module (Onboarding & Offboarding)) 4) Mar'25 salary processing completed in PayrollNX and tallied for all the employees Ticket ID : #W25apr1467. 5) Login are rollout for all the employees Ticket ID : #W25apr1467. 6) Employee Training Confirmation Ticket ID : #W25apr1467. We have Scheduled the onsite session dated 10th and 11th June onsite. Reference Ticket ID : E25jun1574 Confirmation Ticket ID : W25jun5440 July month live salary with attendance from system is processed |  | Received | Jun-26 | Jun-26 | bijjargimotorspvtltd | 2027-03-31 | 90
SPB110104251103 | 7566 | New | Account DeActivated | BASANT OVERSEAS | Premium | E | Mansi Singh | Akshay Shinde |  | Yash Pankajkumar | Channel |  |  | Jayesh Mojidra | Viral Panchal | Vasu Mohan Dusa | SAAS | 1454 | 2025-09-30 | 2025-03-11 | 2025-04-23 | 2025-06-19 | ENGG | 2025-11-11 | NX,ESSM,LV,TAM | Fresh | 0 | 13 | Spine NG | Lost | Online | Till date, all the requirements received have been delivered to Team Basant. Mr. Deep has also confirmed that he is satisfied with the updates—reference ticket number W25AUG5167. The delay occurred due to the day-to-day new requirements received from the team, based on which our team made the necessary changes and obtained confirmation accordingly. We are now ready to proceed with the further training and implementation activities. However, the client’s AMC has expired. Requesting your guidance on how we should proceed further. yash is working on the same with hemant sir | Resoure Problem |  | 0 | 0 | basantoverseas | 2025-11-11 | 91
SPA104424190108 | 7557 | Add Mod | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Usha Gupta | Viral Panchal | 2025-03-25 | Pritesh Barot | Direct |  |  | Sanket Gosalia |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2025-03-10 | 2025-03-10 | 2025-03-18 | ENGG | 2025-03-25 | PMS | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Files awaiting, training from 18th, training done #W25mar6022 |  | na | 0 | 0 | masterchainsnjewelspvtltd | 2026-01-31 | 92
SPM110039252802 | 7556 | New | Account Activated | MADURA INDUSTRIAL TEXTILES LIMITED. | Normal | E | Mansi Singh | Vinay Kareliya | 2025-09-18 | Varun Rajbhar | Channel |  |  | Jayesh Mojidra | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 327 | 2027-03-31 | 2025-03-10 | 2025-03-13 | 2025-04-21 | ENGG | 2025-12-12 | NX,ESSM,LV,TAM,ELC,EXP,TD,VM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | first focus on the HRMS module, as they wil be revising the salary structure after the appraisal so want to proceed with hrms- E25apr8632 we have Completed the HRMS Training for Admin, Self Service, Leave and Time (till Shift) Module.- E25apr8632 they are processing salary live with attn additional module done VM confirmation- E25dec2755 |  | Received | Mar-26 | Mar-26 | maduraindustrialtextilesltd | 2027-03-31 | 93
SPQ109952253101 | 7549 | New | Account Activated | QUALIGENS PHARMA PVT. LTD. | Normal | B | Disha Kiran Kargutkar | Probian Biswas | 2025-08-12 | Ruchit Shailesh Patel | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | On-Premises | 400 | 2027-02-28 | 2025-03-06 | 2025-04-02 | 2025-04-09 | ENGG | 2025-08-12 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have completed Payroll Nx,Spine HRMS & Mobile HR training we processed the salary for March_2025. Client have successfully installed & configured attendance module in Spine HRMS software.-E25apr7956 completed the process of Leave Policy ,we have checked & it is ok. Client was facing issues to process the month of May salary due to new TAX regime,this query has resolved now we are processing the May month salary.-W25jun5512 June salary processed and MLWF Query has resolved -Connected by Ms. Ankita.- W25jul1673 July salary in process.-W25aug2373 |  | Received | Dec-25,Jan-26,Feb-26 | Feb-26 | qualigenspharmapvtltd | 2027-02-28 | 94
SPA110034252702 | 7521 | New | Account Activated | ANM INDUSTRIES PVT LTD | Normal | E | Ankita Bankar | Vinay Kareliya | 2025-05-13 | Vinay Kareliya | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 135 | 2027-02-28 | 2025-03-03 | 2025-03-04 | 2025-03-15 | ENGG | 2025-06-03 | NG,ESSM,LV,TAM,ELC,EXP | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | Project Live - Training & Implementation of Payroll is completed & February month salary processed - #W25mar6029 completed training for Self Service, Leave & Time modules - W25mar6166 March Month live salary processed & tallied - #W25mar11238 May month live salary processed with attendance & tallied- E25may11820 |  | Received | Mar-26 | Mar-26 | anmindustriespvtltd | 2027-02-28 | 95
SPK110049252802 | 7518 | New | Account DeActivated | KARVY TECHNOLOGIES PVT. LTD. | Normal | E | Mansi Singh | Vinay Kareliya |  | Tejas Rajesh Baragade | Direct |  |  | Vaishali Ramniklal | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 130 | 2026-02-28 | 2025-03-03 | 2025-03-03 | 2025-03-24 | ENGG | 2025-12-24 | NG,ESSM,LV,TAM | Fresh | 0 | 87 | Spine NG | Lost | Onsite | Payroll training confirmation: E25mar9331 HRMS, Mobile HR, and geotagging confirmation: E25mar9330 may processed as ashwini ji left the organisation nikhil from accounts team will take trng post that will proceed with payment but he is not respondng, so vasu is planning to meet phani ji cfo. new user training session done now for salary processing user is not responding positively. geo location, fencing done attendance is coming proper as of now user have few queries, impl team in discussion QUERIES RESOLVED PAYMENT FOLLOW UP ONGOING Few concerns with regards to geo fencing was there, we resolved it too, user not ready to release the pending payment. | Not happy with service | 50% of product cost + Full GST pending | Feb-25,Mar-25,Apr-25,May-25 | May-25 | karvytechpvtltd | 2026-02-28 | 96
SPM107218233003 | 7491 | Add Mod | Account Activated | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Premium | C | Disha Kiran Kargutkar | Probian Biswas | 2025-09-12 | Ruchit Shailesh Patel | Channel |  |  | Giriraj Birendrasingh Tomar | Viral Panchal | Vasu Mohan Dusa | On-Premises | 1410 | 2027-03-31 | 2025-02-26 | 2025-02-26 | 2025-03-17 | ENGG | 2025-09-15 | ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Training done #E25mar4260, as per discussion with team leader user is in testing period for this month and will start implementing with salary and attendance from june month. called user Ms. Sushama about update as they said it working properly and we have check the may salary too and attendance queries has been solved. As per our discussion over the call, client will be processing the salary from your end. In case any assistance is required during the process.-W25jul4028. July salary processeed August salary processed- E25sep4242, E25sep4197. | Employees are not punching properly, so due to internal issue they are unable to process with attendance from Spine 4/9 | Received | May-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26 |  | mahwsoilfieldservicespvtltd | 2027-03-31 | 97
SPA109915253101 | 7490 | New | Account Activated | APLAB LIMITED (FOR CONTRACT LICENSE) | Normal | D | Mansi Singh | Vinay Kareliya | 2025-09-04 | Varun Rajbhar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 251 | 2027-03-31 | 2025-02-25 | 2025-04-09 | 2025-05-15 | ENGG | 2025-09-11 | NX,ESSM,TAM | Fresh | 0 |  | Spine HRMS | Go LIVE | Onsite | contractual conv not required user will share fresh data-E25mar2250 TRAINING DONE - They will be using spine for tracking attendance only E25jun5035 - confirmation using only for attendance, will not use for payroll E25jul10109 |  | Received | Dec-25 |  | aplabltdforcontractlicense | 2027-03-31 | 98
SPA109903253001 | 7489 | Conv+New | Account Activated | APLAB LIMITED (FOR STAFF LICENSE) | Normal | C | Mansi Singh | Vinay Kareliya | 2025-09-04 | Varun Rajbhar | Direct |  |  | Tejas Kareliya | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 200 | 2027-03-31 | 2025-02-25 | 2025-04-09 | 2025-04-11 | ENGG | 2025-09-11 | NX,ESSM,LV,TAM | Conversion | 0 | 84 | Spine HRMS | Go LIVE | Onsite | conversion done user want separate db- E25mar2449 installation done handholding done today - W25apr4191 confirmation feb & march salay procssed from spine Aplab PayrollNX Training completion Ticket I'd W25apr4191 attendance integration done implementation confirmation- W25jun5948 they will not process payroll live, they process salary for 2 3 months together for statutory reports E25jul10109 - confirmation |  | Received | Dec-25 |  | aplabltdforstafflicense | 2027-03-31 | 99
SPS110019252102 | 7477 | New | Account Activated | SHREE RAMDEV METALEX LLP | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2025-08-21 | Tejas Rajesh Baragade | Direct |  |  | Manisha Singh | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 325 | 2027-02-28 | 2025-02-21 | 2025-02-25 | 2025-03-12 | ENGG | 2025-11-14 | NX,ESSM,LV,TAM,MOB HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Client have completed the Spine Payroll Software training on 19/03/2025 -E25mar6215 Spine payroll training for Day-2 has been completed. We covered the HRMS module (Admin, Self-Service, and Leave), as well as the February 2025 salary process and Tally.-E25mar6704 Client have successfully completed the Spine HRMS and Mobile HR training on 21st March 2025.-E25mar7156 March month salary processed The salary of month May-2025 has been successfully processed in spine. -E25jun1773 July has been successfully processed and tallied-W25aug6270 August salary done This is to notify you that currently our employees are not regularizing attendance before payroll, So we are in the process of streaming line our attendance regularization on time. For next few months (3-4) Month we shall process salary in Spine parallel. Currently we have processed salary till Sep-25 and we shall get back to team Spine support in future whenever required-E25oct4126 Oct-25 processed with Spine attendance parallel November salary processing is completed for 179 employees. |  | Received | Dec-25,Jan-26,Feb-26 | Feb-26 | shreeramdevmetalexllp | 2027-02-28 | 100
SPM110010251902 | 7465 | New | Account DeActivated | MARU CONSULTANCY SERVICES | Normal | E | Usha Gupta | Probian Biswas |  | Ruchit Shailesh Patel | Channel |  |  | Manisha Singh | Viral Panchal | Vasu Mohan Dusa | SAAS | 150 | 2025-05-31 | 2025-02-19 | 2025-02-19 | 2025-03-24 | ENGG | 2025-06-13 | NG,TAM | Fresh | 0 | 83 | Spine NG | Lost | Onsite | URL & files awaiting, payroll files expected on 22nd, master file will be share on 27th, master file received, kick off meeting on 4th Waiting for revised & Register file #E25mar2864, files received, training date waiting, imple from 24th, training done #E25mar8603, #E25mar9860 Geo fencing #E25mar10496 Geo fencing #E25apr105, session arranged on 3rd #E25apr105 fencing done mobile login given to half employees #E25apr1678, logins given, march salary will be complete in 3rd week April salary expected live March done user will get back to us for April salary, probably complete by 7th S/w not in use, outsourcing, attendance is priority, blue collar employees unable to use attendance, for meeting user will get back to us. Onsite meeting on 29th RECENT UPDATE - MARU CONSULTANCY SERVICES use to process salary for their client, however they have left, if any new cliient onboards then they shall renew it for salary processing. | Funds issue | na | Feb-25,Mar-25 | Mar-25 | maruconsultancyservices | 2025-06-13 | 101
SPR109998251802 | 7453 | New | Account Activated | RADIX ELECTROSYSTEMS PVT LTD | Premium | E | Ankita Bankar | Probian Biswas | 2025-07-24 | Aditya Pathak | Direct |  |  | Pragnesh Panchal | Viral Panchal | Vasu Mohan Dusa | SAAS | 630 | 2027-02-28 | 2025-02-18 | 2025-02-19 | 2025-03-18 | ENGG | 2026-03-11 | NX,ESSM,LV,TAM,ELC,EXP,PMS,TD | Fresh | 0 | 76 | Spine HRMS | Go LIVE | Onsite | Project Live - PMS mod overviwe is done & for same module training user will get back to us with policies Training & Implementation of Payroll Nx is completed - #E25mar11411 & #E25mar6281 February month salary processed & tallied - #E25mar10450 March month live processing done April month salary processed & tallied June & july month tallied ELC module training & Implementation done PMS & request desk will are doing followup with user but they are not giving us data to do training & Implementation |  | Recevied | Mar-26 | Mar-26 | radixelectrosystemspvtltd | 2027-02-28 | 102
SPI109902253001 | 7449 | New | Account Activated | INDIANA GRATINGS PVT LTD | Premium | E | Disha Kiran Kargutkar | Akshay Shinde | 2025-07-14 | Akshay Joshi | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | SAAS | 440 | 2026-10-31 | 2025-02-17 | 2025-03-26 | 2025-03-31 | ENGG | 2026-05-13 | NX,ESSM,LV,TAM,REIMB,ELC,EXP,PMS,TRNG,RCT | Fresh | 0 | 79 | Spine HRMS | FC | Onsite | payroll conf- E25apr503 leave module conf- E25apr1089 june processed. july salary processed. August salary processed Called client for feedback to user saloni and payal but no response sept sal will be live processing |  | Received | Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Oct-25,Jul-26,Aug-26 | Aug-26 | indianagratingspvtltd | 2026-10-31 | 103
SPI109996251402 | 7445 | New | Account Activated | ISA LOGISTICS PRIVATE LIMITED | Normal | E | Disha Kiran Kargutkar | Vinay Kareliya | 2025-12-05 | Mihir Navnath Mungekar | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 200 | 2027-02-28 | 2025-02-14 | 2025-03-03 | 2025-03-24 | ENGG | 2026-03-12 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | FC | Onsite | Completed the training of Payroll, Mobile and HRMS -E25mar9861 payroll process for the month of April 2025 has been processed successfully-E25may7360 May-2025 Salary Processed- E25may12012 June salary processed-W25jul6461 July salary processed August salary processed October month salary done Nov salary processed-E25dec1872 Dec salary processed- Processed the salary for Jan 26 got tallied for all employees-E26feb4932. PMS done- E26feb33. Feb salary processed-E26mar1563. march salary done April salary only 43 employees done new hr manager training completed Client has processed salary from excel. Currently client's priority is to process PMS from Spine, Once done they will process salary for May26 using only hrms module- E26jul2753. New user Mr. Rahul has shared HRMS Scope of Work for Review and Feasibility Confirmation and requirements has mentioned we are still working on it last working in 14th aug has been done by mihir and still we are working and need clarification by client and need to discuss with them. hrms queries are ongoing user has shared attached KRA and KPI document for reference sch to be aligned | Only HRMS |  | Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Oct-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26,Apr-26 |  | isalogisticspvtltd | 2027-02-28 | 104
SPG109937253101 | 7424 | New | Account Activated | GNG ELECTRONICS LIMITED FACTORY | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-07-09 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 1600 | 2026-10-31 | 2025-02-12 | 2025-03-06 | 2025-03-07 | ENGG | 2025-08-14 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training & Implementation of Payroll NX is completed - #E25mar6319 February month salary processed & tallied - #E25mar6319 Training & Implementation of HRMS- Self service, Leave & Admin Module is completed - #E25mar6319 Attendance integration done & HRMS training done - #E25mar9245 logins rolled done to employees March month live salary processed Processing done from system months: FEB (E25MAR6319) JUL (E25aug1663) |  |  | Dec-25 | Mar-26 | gngelectronicsltdfactory | 2026-10-31 | 105
SPA109926253101 | 7403 | New | Account Activated | ALLIED INSTRUMENTS PRIVATE LIMITED | Premium | E | Ankita Bankar | Amey Telge | 2026-05-25 | Vijay Bugde | Direct |  |  | Sanket Gosalia | Viral Panchal | Vasu Mohan Dusa | On-Premises | 500 | 2027-01-31 | 2025-02-05 | 2025-02-08 | 2025-04-01 | ENGG | 2026-05-25 | NX,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | training and impl confirmation - E25apr6298 training provided on 28th july attendance centralization ongoing daman silvasa khar integration in process. ------------------------------------------ STUCK- july pending new user training provided queries resolving going on Manish ji said from spine we are getting good support, but its my team we are not on track lot many things are going -audits etc & they are hands on tally so getting out of comfort zone for them is the thing. will try to start processing for oct month. E25sep1678- aug processed by importing attendance they use spine for audit purpose only for jan salary we scheduled a session, we have added all the employees they have conveyed that they will start doing live salary within few months client only use our system when they have audit not going to process live salary go live mail sent to client- E26may9307 |  | Received | Apr-25,May-25,July-25,Aug-25,Sept-25,Oct-25 |  | alliedinstrumentspvtltd | 2027-01-31 | 106
SPG109930253101 | 7377 | New | Account Activated | GNG ELECTRONICS LIMITED STAFF | Normal | E | Ankita Bankar | Nagesh Tiwari | 2025-06-10 | Shubham Gurav | Direct |  |  | Amarprit Kaur | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 400 | 2027-04-30 | 2025-01-31 | 2025-02-12 | 2025-02-17 | ENGG | 2025-06-10 | NX, ESSM, LEAVE, TAM, Mobile HR, ELC | Fresh | 0 | 100 | Spine NG | Go LIVE | Onsite | Project Live - Payroll NX training & Implementation is done & January Month salary processed & tallied - E25feb7532 ESSM & Leave done / Hrms Training with ELC Module , Mobile app and attendance integration - E25feb7965 February month salary processed - E25mar899 logins rolled done to employees May Month salary processed with attendance live - E25jun3535 |  |  | Dec-25 | Mar-26 | gngelectronicsltdstaff | 2027-04-30 | 107
SPS109898253001 | 7359 | New | Account DeActivated | S K TRADERS NX | Premium | E | Usha Gupta | Viral Panchal | 2025-02-27 | Rahul Ankush Dalvi | Channel |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 25 | 2026-01-31 | 2025-01-30 | 2025-01-31 | 2025-02-12 | ENGG | 2025-04-08 | NX, ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | URL & Files awaiting, files received, imple from 12th, client will not use payroll #E25feb5774 HRMS training #E25feb5780 training done login will be share on 18th #E25feb6379, logins given Client live- #E25feb6379, training & imple done, client will not use payroll, using only HRMS, logins given. |  | received server setup amount pending (Write Off) | 0 | 0 | sktradersnx | 2026-01-31 | 108
SPK109842251001 | 7288 | New | Account Activated | KHERWADI SOCIAL WELFARE ASSOCIATION | Premium | E | Ankita Bankar | Probian Biswas | 2025-06-05 | Probian Biswas | Channel |  |  | Aparna Santosh | Viral Panchal | Vasu Mohan Dusa | SAAS | 650 | 2026-12-31 | 2025-01-14 | 2025-01-14 | 2025-01-24 | ENGG | 2025-07-08 | NX,ESSM, Leave, Time, Mobile HR, ELC, Claim & Reim | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Payroll Till Tax done/ HRMS & mobile app logins rolled out to employees - E25feb5562 HRMS training done & RCT module training & implementation done - E25feb5562 HRMS training done-E25jan12873 February month salary processed ELC, RCT, RD & PMS Module training & implementation is done April month salary processed May & June month salary processed live from system with attendance | Processing will be done till 13th March for Feb month as client rcvd Funds late to disburse salary |  | Mar-26 | Mar-26 | kherwadisocialwelfareassociation | 2026-12-31 | 109
SPM109810243112 | 7286 | New | Account DeActivated | MADHUSUMAN ENTERPRISES | Normal | E | Karuna Rajaram Sandim | Vinay Kareliya | 2025-05-07 | Tejas Rajesh Baragade | Channel |  |  | Ankur Yewalekar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 125 | 2025-12-31 | 2025-01-13 | 2025-01-15 | 2025-01-29 | ENGG | 2025-12-08 | NX,TAM | Fresh | 0 | 83 | Spine HRMS | FC Lost | Onsite | Welcome call done URL created #trng and impl from 29 th jan payroll training done - W25jan12818 HRMS on 12th feb We have completed the training on attendance module also december & January month salary process and tally. - W25feb5072 they are going to use mark in mark out, only for few empl if location is proper then logins logins done march salary 26 emp done, pending emp they will complete in this week In Madhusuman as there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | there are multiple locations, sites they are not ready for integration , and for mob in /out they do not allow mobile for workers, and she was doing salary by importing data , but now she is finding it difficult as mostly she has do all manual work and time consuming, they are not going to process salary from spine. | Received | Dec-24,Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25 | Aug-25 | madhusumanenterprises | 2025-12-31 | 110
SPP109843251301 | 7282 | New | Account DeActivated | PARBHANI MEDICAL COLLEGE (PMC) | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera |  | Sushant Thombare | Channel |  |  | Jayesh Mojidra | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 500 | 2025-12-31 | 2025-01-13 | 2025-01-13 | 2025-02-14 | ENGG | 2026-01-31 | NG,ESSM,LV,TAM | Fresh | 0 | 100 | Spine NG | Lost | Onsite | Welcome call done data file expl done Implementation starts from 14th feb 25 HRMS and Mobile HR Training Completed and All modules Explained and Showed by Engineer -W25feb8024 PayrollNg Training Completed and All modules Explained and Showed by Engineer and Jan 2025 salary Processed -W25feb6982 was following up the user since last week, however call was not received , Today had a call with him , he mentioned he was on leave past 8 to 10 days and now he is working on March salary and will reach out to me i assistance required, and for feb salary he will upload the past salary data. salary processed till march aprl salary mostly till next week, New biometric machine is installed, again we need to integrate data again, and now the user is admitted in hospital and currently there is no other user in his absence. April 25 Salary Process complete - E25may10890 In Parbhani , Half employees do not receive salary yet of april, they shall receive in May or june , told shreyas to take this on mail. May salary he shall process till 10th june. This email is to inform you that we have not been able to process the salaries for our remaining employees through your software. This is due to a temporary issue that we are actively working to resolve. We will resume full salary processing via your platform as soon as possible. We appreciate your understanding in this matter and will keep you updated on our progress. E25jun2237 They have fund issues that is the reason salary is delayed Salary processing is delayed every month as there is funds issue at client end, hence closing as lost | Funds issue | Received | Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Sept-25,Oct-25 | Oct-25 | parbhanimedicalcollegepmc | 2026-01-31 | 111
SPB109807243112 | 7268 | New | Account DeActivated | BENGAL ENERGY LTD- CONTRACTUAL | Premium | E | Mansi Singh | Probian Biswas |  | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 1100 | 2025-03-31 | 2025-01-08 | 2025-01-15 | 2025-01-18 | ENGG | 2025-06-27 | NX,TAM | Fresh | 0 |  | Spine HRMS | Lost | Online | they clarified that there are no concerns or issues from Spine’s end. The current process is a business decision on their part. For contractual employees, the contractors submit attendance via Excel sheets, which the internal team simply verifies before processing payments. They also mentioned that they are in the process of streamlining their work process system. Once that is properly aligned, they will reconnect with Spine to proceed with the contractual employee license. | Finds excel easy |  | 0 | 0 | bengalenergyltdcontractual | 2025-06-27 | 112
SPB109806243112 | 7267 | New | Account Activated | BENGAL ENERGY LTD- STAFF | Premium | E | Mansi Singh | Probian Biswas | 2025-05-26 | Mayur Pendhari | Channel |  |  | Nirbhay Kumar | Viral Panchal | Vasu Mohan Dusa | SAAS | 550 | 2026-10-31 | 2025-01-08 | 2025-01-15 | 2025-01-18 | ENGG | 2025-11-06 | NX,ESSM,LV,TAM,ELC,EXP,PMS | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | welcome mail & url done hrms done confirmation - E25feb5676 june done they process salary with attn processed sept month as well. oct salary processed from spine live-W25nov2189 |  | na | Dec-25 | Mar-26 | bengalenergyltdstaff | 2026-10-31 | 113
SPT109788243112 | 7263 | New | Account Activated | TARASAFE INTERNATIONAL PVT LTD. STAFF LICENSE | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-03-05 | Sahil Gadhave | Channel |  |  | Nirbhay Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1400 | 2026-12-31 | 2025-01-07 | 2025-01-10 | 2025-01-23 | ENGG | 2025-07-10 | NX, ESSM, LEAVE, TAM, Mobile HR, ELC | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | Project Live - 1) Ahemdabad Location PayrollNX Training and Dec'24 Salary Confirmation : W25jan10514 2) Kolkata Location PayrollNX Training and Dec'24 Salary Confirmation : E25jan12587 3) Ahemdabad Location Jan'25 live salary confirmation : W25feb1205 4) Ahemdabad Location Login rollout confirmation : W25feb2040 5) Spine HRMS - (Admin, ESSM. Leave module) training Confirmation : W25feb2040 6) Spine HRMS -Spine HRMS_Phase 1 Training Confirmation : W25feb2365 7) Kolkata Location Jan'25 live salary confirmation : W25feb3068 8) Kolkatta Location Login rollout confirmation : W25feb4649 9) Ahemdabad Attendance Integration Confirmation : E25feb7343 10) ELC module Training Confirmation : W25feb8518 11) Ahemdabad location Feb'25 Live salary confirmation along with Attendance : W25mar1674 12) Kolkatta location Feb'25 live Salary confirmation : W25mar1677 May month live salary processed from system June month live salary from with attendance from system is done |  | Received | Mar-26 | Mar-26 | tarasafeintlpvtltdstafflicense | 2026-12-31 | 114
SPT109784243112 | 7262 | New | Account DeActivated | TARASAFE INTERNATIONAL PVT LTD WORKER LICENSE | Normal | E | Ankita Bankar | Sahil Gadhave | 2025-07-03 | Sahil Gadhave | Channel |  |  | Nirbhay Kumar | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 1100 | 2025-05-31 | 2025-01-07 | 2025-01-10 | 2025-02-13 | ENGG | 2025-07-08 | NX, TAM, Mobile HR | Fresh | 0 | 66 | Spine HRMS | Go LIVE | Online | Project Live- Worker's license is merged into staff as per client's request W25jun4377 AHD location workers configuration is done / Training & Impelmentiaon of Payroll & HRMS is done/ live salary processing milestone is achieved |  | Received | Apr-25,May-25 |  | tarasafeintlpvtltdworkerlicense | 2025-07-08 | 115
SPA109790243112 | 7258 | New | Account Activated | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Normal | E | Karuna Rajaram Sandim | Ganesh Jadhav | 2025-03-10 | Hardik Panchal | Direct |  |  | Tejas Kareliya |  | Vasu Mohan Dusa | SAAS | 145 | 2026-12-31 | 2025-01-07 | 2025-01-08 | 2025-01-30 | ENGG | 2025-03-11 | HRIS /Payroll NX,ESSM, Leave, Time Attendance, Mob | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Welcome call done data expl done Training starts from 30th 2025 #completed the Payroll Training and Also Employee rollout has been done and Also december salary has been matched with our records - E25feb974 employees training and all the queries have been resolved.-E25feb7093 salary for the month of February 2025 has been confirmed and tally. - E25mar1995 | Karuna in follow up for balance payment | Received | Dec-24,Jan-25,Feb-25 | Feb-25 | anshutechairconditioningpvtltdnx | 2026-12-31 | 116
SPS109684240612 | 7098 | New | Account DeActivated | SKY PRINTS | Normal | E | Disha Kiran Kargutkar | Viral Panchal | 2025-03-03 | Nagesh Tiwari | Channel |  | AVI DEALER | Manisha Singh |  | Vasu Mohan Dusa | SAAS | 100 | 2025-11-30 | 2024-12-06 | 2024-12-10 | 2024-12-20 | ENGG | 2025-03-11 | HRIS /Payroll NX, Workflow, Time Attendance, Mobil | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Direct Training & Implementation from 20th Dec We have completed and implementation and Training of spine HR and payroll NX We will discussed internally and will update and regarding roll out- W24dec7076 Need session for attendance integration and salary processing query on 28th Jan 2025 December salary done, we will process Jan salary till 03.02.2025 i will let u know if any issue happens, we have not decided to give the logins employees-E25jan8659 February Salary completed with attendance.-E25mar499 February Salary completed |  |  | Nov-24,Dec-24,Jan-25,Feb-25 | Feb-25 | skyprints | 2025-11-30 | 117
SPN109637243011 | 7053 | New | Account DeActivated | NPSE AUTOMATION PVT. LTD. | Normal | E | Disha Kiran Kargutkar | Prathamesh Mandavkar |  | Nandadeep Mhatre | Channel | SA | Telly Soft Service Private Limited | Amit Arjun Sawant |  | Vasu Mohan Dusa | SAAS | 55 | 2025-02-28 | 2024-11-30 | 2024-11-30 | 2024-12-11 | ENGG | 2025-03-26 | HRIS /Payroll NX, Workflow, Leave, Time Attendance | Fresh | 0 | 56 | Spine HRMS | Lost | Online | Training & Implementation from 16th December 2024 We attend training of payroll nx & we have process salary of nov24 in payroll NX- E24dec3116 we have completed the Training of HRMS and its modules Admin,Leave and Time and MobileHR.-E24dec5532 Attendance integration issue not sorted as we have provided multiple solutions but they are not gave any response and also as cost barer regarding attendance integartions, solutions were provided: We have proposed the following solutions to retrieve attendance data in HRMS: Provide us with the attendance data in a SQL table in the format specified by Spine. Allow us to add the necessary extra fields to the SQL attendance table maintained by the biometric vendor. For daily attendance, use MobileHR, which will be reflected directly in HRMS and does not require a biometric machine. Based on your request, we have also suggested other biometric vendor recommendations. npse partner binu mathew is taking charge of attendance issue we need to wait for 2 days User and Owner not responding call and even mails. | Attendance Integration issue, vendor providing data only through API | SALES RETURN | Nov-24 | Nov-24 | npseautomationpvtltd | 2025-03-26 | 118
SPR109402242809 | 6837 | New | Account DeActivated | LOTUS TEXCOM INDIA LLP | Normal | E | Karuna Rajaram Sandim | Prathamesh Mandavkar |  | Prathamesh Mandavkar | Channel |  | SUN HEIGHTS - SA | Sandeep Ashok Joundal | Prathamesh Mandavkar | Vasu Mohan Dusa | SAAS | 51 | 2025-09-30 | 2024-10-08 | 2024-10-09 | 2024-12-27 | ENGG | 2025-07-28 | NG,TAM | Fresh | 0 |  | Spine NG | Lost | Online | mail done- call done, URL done, data file expln done Impelementation and trng starts from 27th dec 24 biometric data is not proper in atten sql problem from their side suggested vendor As my recent call with user for follow up, Mr. Vaibhav user told that as per their senior, they want unsubscribe the services, told him, whatever your concerns are kindly mail and let me know we can arrange meeting with PM and your senior awaiting mail from his end. user not responding, same is informed to PM and partner, partner team shall do visit at client placed as mentioned by them. Meeting arranged tomorrow for discussion with PM and Lotus Texcom Director. Spoke to Mr. Harshal , he mentioned there are issues going on and on , there were biometric issues, data was not not getting pushed in sql table its not syncing and Mr. Harshal does not want to invest in New Biometric Machine, he mentioned he has informed the same to Sun heights parther Mr. Liayakt too. | Attendance integration issue | WAIVE OFF | 0 | 0 | lotustexcomindiallp | 2025-09-30 | 119
SPG109421243009 | 6799 | New | Account DeActivated | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Normal | E | Ritika Dilip Singh | Shreyas Karkera | 2025-05-12 | Amit Krishnakant Tiwari | Direct |  |  | Ankur Yewalekar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 30 | 2025-09-30 | 2024-09-30 | 2024-10-07 | 2025-01-27 | ENGG | 2025-07-15 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC Lost | Onsite | #Payroll training has been completed, jan salary processing also done and salary tallied, further training and policy setup of hrms will be done next week - W25jan11630 W25mar3684 - HRMS Training is completed #W25apr9497 - march done with attendance #April'2025 Salary processed and Tally with attendance. #W25jul4405 - june salary done & live confirmation #FC LOST : The client was expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. | expecting 10% of the renewal cost, which is not feasible. He also mentioned that their management has rejected the approval of our software. |  | Jan-25,Feb-25,Mar-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25 | Sept-25 | gcomsystemsandsolutionsourladyofsalvation | 2025-09-30 | 120
SPH109257242608 | 6620 | New | Account Activated | HARDCARB TECHNOLOGIES PRIVATE LIMITED | Normal | E | Ankita Bankar | Prathamesh Mandavkar | 2025-04-09 | Tejas Rajesh Baragade | Direct |  |  | Amarprit Kaur |  | Vasu Mohan Dusa | SAAS | 250 | 2027-03-31 | 2024-08-26 | 2024-08-26 | 2024-09-16 | ENGG | 2025-04-09 | NX, TAM, Mobile HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Project Live - Training of payroll done - #E24oct8342 August month tallied HRMS training done - #E24oct8342 October month salary processed November month salary processed integration done February month salary processed March month live salary processing done with attendance from NX |  | Received | Feb-25 | Mar-25 | hardcarbtechpvtltd | 2027-03-31 | 121
SPM109213241208 | 6555 | New | Account Activated | MAHARASHTRA BOOK MANUFACTURING COMPANY NX | Normal | E | Karuna Rajaram Sandim | Nagesh Tiwari | 2025-05-19 | Shubham Gurav | Direct |  |  | Giriraj Birendrasingh Tomar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 100 | 2027-07-31 | 2024-08-12 | 2024-08-13 | 2024-08-29 | ENGG | 2025-07-15 | NX,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC | Onsite | Welcome call done data file explanation friday-16 /08 training starts from 29th August 24 payroll nx training and processed salary for the month of July 2024.-E24aug7750 we have processed salary for the month of August 24 for Mumbai branch by fetching attendance from HRMS.-E24aug7750 We have completed training of spine HRMS and mobile HR-E24sep1058 salary processed till sep and remaining will be done on friday 20th dec followig with user for nov salary 24 , user not responding following up with user, no response. Meeting aligned with PM on 28th jan 25 following up with user constantly, however no response. As mentioned by Amit Sir, not to follow up with user. Salary processed till feb following up with user, he cut the call , he mentions he will call back, however no call received. We have done Mar 25 and April 25 salary of Mumbai Branch with Attendance And we will upload Wada Salary till Mar 25 and Process from April 25 -E25may5783 May salary done. after june we can do live. We have processed May 25 and June 25 salary with attendance for MUMBAI branch employees. We will get back for Wada branch salary processing -E25jul1557 aug salary shall be done till friday. |  | Received | Dec-25,Aug-26 | Aug-26 | maharashtrabookmanufacturingconx | 2027-07-31 | 122
SPC109142243107 | 6511 | New | Account DeActivated | CARTFIRE INDIA | Normal | E | Ankita Bankar | Viral Panchal | 2024-12-19 | Nagendra Poojary | Channel |  |  | Manisha Paradia |  | Vasu Mohan Dusa | SAAS | 26 | 2025-07-31 | 2024-08-03 | 2024-08-28 | 2024-10-09 | ENGG | 2025-02-11 | NX,ESSM, Leave, Time Attendance, Mobile HR | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Payroll, HRMS and mobile HR training completed - #E24sep6995 Integration is done # processed Oct & Nov. Salary with Attendance from HRMS - E24dec5935 December month salary processed January month salary processed |  | Received |  | Jan-25 | cartfireindia | 2025-07-31 | 123
SPV109057241607 | 6373 | Conv+New | Account Activated | V ALLIANCE NX | Normal | E | Usha Gupta | Viral Panchal | 2024-11-13 | Rahul Ankush Dalvi | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 1000 | 2027-06-30 | 2024-07-16 | 2024-07-17 | 2024-08-23 | ENGG | 2024-11-13 | Conv nx,TAM | Conversion | 0 | 100 | Spine HRMS | Go LIVE | Onsite | URL, DB & Files awaiting, DB received, DB after 10th #403279, DB received, DB hand holding & training from 23rd #E24aug2900, training done #E24aug3773, payroll done #E24aug4052, session on 30th for salary, Aug salary #E24aug7376 & #E24sep468, HRMS pending, User will not use attendance module #E24oct7985, oct done #W24nov513 Client live - training & imple done, Client will not use HRMS E24oct7985(Worker Grade Employees), Oct done - #W24nov513 |  |  | 0 | Oct-24 | valliancenx | 2027-06-30 | 124
SPA108965242906 | 6265 | New | Account DeActivated | AQUAAIR INTERNATIONAL FREIGHT SERVICES | Normal | E | Karuna Rajaram Sandim | Viral Panchal | 2025-02-24 | Nagendra Poojary | Direct |  |  | Jigar Rupani |  | Vasu Mohan Dusa | SAAS | 45 | 2025-06-30 | 2024-06-29 | 2024-07-25 | 2024-09-16 | ENGG | 2025-04-09 | Payroll NX ,ESSM,Leave,Attendance, Mobile HR,,ELC | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | Welcome call done data file explanation on 11th july 24 awaiting files training starts from 16 th sep 24 successfully completed the Payroll training and processed and verified the salary for the month of August using the Payroll system they have successfully logged into the app.-402035 HRMS training was successfully completed today.-402035 Salary processed till nov and dec salary they will process with attendance. queries resolved New user training has started. payroll training done , HRMS Training is done.W25mar9197 We have successfully processed salary of March 2025 with attendance from HRMS-W25mar9197 | Karuna in follow up, user waiting for management approval 24/2 | Received | Nov-24,Dec-24,Jan-25,Feb-25,Mar-25 | Mar-25 | aquaairintlfreightservices | 2025-06-30 | 125
SPR108865241406 | 6151 | New | Account Activated | RADIX INNOVATIONS PRIVATE LIMITED | Normal | E | Karuna Rajaram Sandim | Arpit Patel | 2024-11-14 | Jay Jatinbhai Kansara | Channel | SA | KGSOFT TECHNOLOGIES | Deepak Choubisia |  | Vasu Mohan Dusa | SAAS | 55 | 2026-12-31 | 2024-06-14 | 2024-06-17 | 2024-06-24 | ENGG | 2024-11-30 | Payroll NX, TVL EXP, LVE, TAM, Mob | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Online | URL Done / Employee master done / Salar structure done / PayrollNX & HRMS Training done /Waiting for confirmation We have successfully completed the > Installation, Implementation & Training and Team RADIX INNOVATIONS > PRIVATE LIMITED is utilizing SPINE Payroll NX.-E24oct7557 October Salary processed -W24nov4114 | Need to visit onsite for suprise meet Renewal positive update by Arpit |  |  | Oct-24 | radixinnovationspvtltd | 2026-12-31 | 126
SPO108695241605 | 5973 | New | Account DeActivated | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Normal | E | Karuna Rajaram Sandim | Shreyas Karkera | 2025-05-13 | Tushar More | Direct |  |  | Nirbhay Kumar | Ganesh Jadhav | Vasu Mohan Dusa | SAAS | 51 | 2026-05-31 | 2024-05-16 | 2024-06-06 | 2024-07-04 | ENGG | 2026-06-11 | NX,ESSM,LV,TAM | Fresh | 0 | 100 | Spine HRMS | FC Lost | Onsite | Welcome Call done URL sent for creation training and Implementation from 4th july 24 We proceed july and august salary.-E24aug7741 ONETEAM LOGISTICS INDIA PRIVATE LIMITED- held up-22nd oct 24 we have completed the training of Payroll NX and HRMS till Self services. -E25feb8341 Add module welcome call done. following up with user for workflow and policies, however still files are not received Leave and TAM module impl and training aligned 4th april 2025 LEave tam training done and Integration done, following up with user he mentioned that still there are lot of queries , told him to mail and we can schedule the same, Schedule aligned for past salary and queries. tomorrow. 09th may. 25 We processed the salary april_2025 with attendance -W25may486 May salary has been processed, No response from user- project is stuck. user was busy in audit, and shall process aug sep in 1st week of oct. oct salary processed Nov will be done till 15th dec 25. user is not responding, we tried reaching out to user many times, no response hence closing as lost | Not responding no reason |  | Nov-24,Dec-24,Jan-25,Feb-25,Apr-25,May-25,June-25,July-25,Aug-25,Sept-25,Nov-25,Dec-25,Jan-26,Feb-26,Mar-26 | Mar-26 | oneteamlogisticsindiapvtltd | 2026-06-11 | 127
SPA108616242604 | 5883 | Conv | Account Activated | ANS NG | Normal | E | Ankita Bankar | Viral Panchal | 2024-05-16 | Aditya Mazire | Direct |  |  | Vaishali Ramniklal |  | Vasu Mohan Dusa | SAAS | 200 | 2027-04-30 | 2024-04-27 | 2024-04-27 | 2024-05-15 | ENGG | 2024-06-07 | Con NX | Conversion | 0 | 100 | Spine NG | Go LIVE | Onsite | Training of Payroll NX is completed - #371589 March, April & May month salary processed. |  |  | 0 | May-24 | ansng | 2027-04-30 | 128
SPP108596242204 | 5850 | New | Account Activated | PVR CONTROLS -STAFF LICENSE | Normal | E | Usha Gupta | Ganesh Jadhav | 2025-02-07 | Shreyas Karkera | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 250 | 2027-04-30 | 2024-04-22 | 2024-04-27 | 2024-06-12 | ENGG | 2025-02-07 | HRIS /Payroll NX, ESSM, Lve, Tam, Mob, Travel exp, | Fresh | 0 | 88 | Spine HRMS | Go LIVE | Onsite | #Training completed #Attn Training integration and mobile training pending, salary processing parallel from dec they will process live, sep will be complete by 10th, session arranged on 10th for salary with attendance. No proper response for salary, sep done, oct done #E24nov2868, New biometric Machin installed, Nov done #E24dec4456, mail follow up for dec salary #E25jan4941, project live #E25feb2274 Client live - #E25feb2274, Trang & imple done, logins given, processing payroll parallelly, For PMS training client will get back |  |  | 0 | Jan-25 | pvrcontrolsstafflicense | 2027-04-30 | 129
SPM108453242903 | 5694 | Conv+New | Account Activated | MUKTANGAN EDUCATION TRUST. NX | Normal | E | Ankita Bankar | Viral Panchal | 2024-06-26 | Pritesh Barot | Channel |  |  | Sanket Gosalia |  | Vasu Mohan Dusa | SAAS | 608 | 2027-03-31 | 2024-03-29 | 2024-04-10 | 2024-04-26 | ENGG | 2024-06-26 | Conversion to NX, TAM, MOB HR | Conversion | 0 | 80 | Spine HRMS | Go LIVE | Onsite | Training & Implementation done April month salary processed May Month salary processed - #388257 Attendance module training done Ticket #393358: Project Live |  |  | 0 | May-24 | muktanganeducationtrustnx | 2027-03-31 | 130
SPI108350242902 | 5579 | New | Account DeActivated | INFEXN LABORATORIES PVT LTD | Normal | E | Shivani Girish Dhonde | Ganesh Jadhav | 2024-05-09 | Shubham Gurav | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 200 | 2026-03-31 | 2024-03-06 | 2024-03-12 | 2024-03-21 | ENGG | 2024-06-07 | NX,ESSM, Lea, Tam, Mob HR, ELC, Rct, Trng, PMS, Re | Fresh | 0 | 100 | Spine HRMS | Go LIVE | Onsite | #Ticket #354264: URL prefix. #Ticket #358227: Payroll NX training confirmation -363683. #Participation certificate. #Ticket #364150: March Salary processed. #Ticket #375239: April salary processed. # Ticket #386874: May Salary processed. |  | Testimonial Received |  | May-24 | infexnlaboratoriespvtltd | 2026-03-31 | 131
SPM108327242902 | 5551 | Conv+New | Account Activated | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Normal | E | Mansi Singh | Prathamesh Mandavkar | 2024-07-10 | Mayur Pendhari | Direct |  |  | Jatin Thakkar |  | Vasu Mohan Dusa | SAAS | 700 | 2027-02-28 | 2024-02-29 | 2024-03-18 | 2024-03-22 | ENGG | 2024-07-15 | CONVNX, ESSM, Leave, Time Attendance, Mobile HR, | Conversion |  | 78 | Spine HRMS | Go LIVE | Onsite | go live- they want to keep the database separate and conversion will be done for both the companies Micropoint Computers Pvt Ltd. Goanfest Food & Beverages Pvt Ltd-#354379 Database Handholding Both Company Databases Confirmation. # 356675 PAYROLL NX TRAINING COMPLETED #358872 successfully processed month of March 2024 of both company from payroll NX System -363500 April- salary Process #375292 2nd Entity Salary For the month of April- 375286 rct mod they will get back to us when required. few employees are using mobile app for marking attendance disbursing salary live from spine |  |  | 0 | Jun-24 | micropointcomputerspvtltdnx | 2027-02-28 | 132
SPF107062230902 | 5312 | Add Mod | Account Activated | FFSERVICES PRIVATE LIMITED | Normal | E | Ankita Bankar | Ganesh Jadhav | 2024-01-29 | Gaurav Karmokar | Direct |  |  | Bhumika Yogesh Arsania |  | Vasu Mohan Dusa | SAAS | 220 | 2026-12-31 | 2024-01-03 | 2024-01-03 | 2024-01-09 | ENGG | 2024-01-29 | Claim & Reimbursement, Travel Expense | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Training done. Expense Module Training to the Employees and Implementation Confirmation - # 335312 |  |  | 0 | Dec-23 | ffservicespvtltd | 2026-12-31 | 133
SPL103086181602 | 5165 | Conv | Account Activated | LATHIA RUBBER MFG CO. PVT. LTD. | Normal | B | Usha Gupta | Viral Panchal | 2024-03-15 | Yash Pankajkumar | Direct |  |  | Pragnesh Panchal |  | Vasu Mohan Dusa | On-Premises | 750 | 2026-10-31 | 2023-11-30 | 2024-01-11 | 2024-01-25 | ENGG | 2024-03-15 | Conv nx | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Pre-requisites & DB awaiting, DB will shared by 2nd, Upasana coordinating with user for amc payment, DB received, installation pending, DB hand holding done #329264, training date awaiting, Training from 25th. Training completed #337791, session arranged on 5th for salary Jan salary #341460, Feb Done #352253 |  |  | Jan-24 | Feb-24 | lathiarubbermfgcopvtltd | 2026-10-31 | 134
SPP100297152606 | 4978 | Conv | Account Activated | PITAMBARI PRODUCTS PVT. LTD. | Normal | A | Usha Gupta | Prathamesh Mandavkar | 2024-01-10 | Santosh Yadav | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | On-Premises | 1500 | 2027-03-31 | 2023-10-04 | 2023-11-21 | 2023-11-23 | ENGG | 2024-02-13 | Conv nx | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Pre-requisites & DB awaiting, busy in salary will share DB by 20th #303229, DB back up will be shared by 10th Nov #307079, DB backup received, DB Hand Holding done #316236, training from 23rd, Nov Salary #320399, #320827, Dec salary #330763, jan done #344213 |  |  | Nov-23,Dec-23,Jan-24 | Jan-24 | pitambariproductspvtltd | 2027-03-31 | 135
SPS107683233108 | 4861 | Conv+New | Account DeActivated | SANKALPAN INFRASTRUCTURE PVT. LTD. | Normal | E | Ankita Bankar | Viral Panchal | 2024-04-25 | Rahul Ankush Dalvi | Direct |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 70 | 2025-09-30 | 2023-09-04 | 2023-09-13 | 2023-10-09 | ENGG | 2024-04-25 | ConvNX, ESSM, Leave, TAM, MOB, ELC, PMS | Conversion |  | 78 | Spine HRMS | Go LIVE | Onsite | Training of Payroll NX & HRMS is completed - #305568 August, October & November month salary processed - #321444 December month salary processed - #335184 Logins rolled out - #338967 January month salary processed - #346574 February month salary processed - 358372 March month salary processed - #362620 Project live - 370783 |  | Testimonial Received | March-24 | March-24 | sankalpaninfrastructurepvtltd | 2025-09-30 | 136
SPT107662232808 | 4859 | New | Account Activated | NATIONAL SPORTS CLUB OF INDIA NX | Premium | B | Disha Kiran Kargutkar | Vinay Kareliya |  | Mihir Navnath Mungekar | Channel |  |  | Sanket Gosalia | Prathamesh Mandavkar | Vasu Mohan Dusa | On-Premises | 450 | 2026-07-31 | 2023-09-02 | 2023-10-04 | 2023-12-27 | ENGG |  | NX,LV,TAM | Fresh | 0 | 68 | Spine HRMS | Active | Onsite | hrms conf- 331169 Training done 05/06 onsite schedule done with new CFO and IT Manager, salary cycle issue discussed and team NSCI will discuss internally and get back to us. No internally co- ordination with their team members AMC EXPIRED NO RENEWAL DONE W24nov2773 - confirmation on leave and admin ------------------------------------------------ 12/11- conf- W24nov2773 leave and admin tam conf-W24nov2773 they want training again awaiting for mihir 's availability post rcvng the visit charges will proceed with training ----------------------------------------------------------- not reachable/since the payment is rcvd we have to discuss with user the next plan of action. --------------------------------------------------------- PM.Vasu in discussion with Client policies and files not rcvd --------------------------------------------------------- Payroll HRMS data received Onsite on monday for queries resolving and trng& impl engineer is onsite employee master update leave policy configured. Due to biometric machine was not working due to which there were many employees who had not punched in the system. Because of which they have to do the salary as per the previous process. Were we told Mdm. Megha that as they have processed the September salary. So we will not regularize the September attendance. Will update the attendance from 25th September to 28th September. Sept salary processed by uploading atten. October sal is live target Need to discuss with client on monday with vasu for payment related. |  | Received | Aug-26 | Aug-26 | nationalsportsclubofindianx | 2026-07-31 | 137
SPA106322220704 | 4763 | Add Mod | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Prathamesh Mandavkar | 2023-10-09 | Goraksha Pawar | Channel |  | AVI DEALER | Jayesh Mojidra |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2023-08-08 | 2023-08-09 | 2023-08-18 | ENGG | 2023-10-09 | Travel exp, Travel Desk | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite | Files & Policy awaiting, training from 18th. training completed #287080, logins will be shared by 1st week of sep, logins will be shared by 16th sep Training completed, Logins will share as per their convenient. #302271 |  |  | 0 | 0 | aegisprecisionpvtltd | 2027-03-31 | 138
SPS107604233107 | 4749 | Conv+New | Account Activated | SAI SANKET INDUSTRIES PVT. LTD. | Normal | E | Mayuri Thackrey | Viral Panchal | 2023-11-02 | Dakshesh D Nadkar | Channel |  |  | Nirbhay Kumar |  | Vasu Mohan Dusa | SAAS | 251 | 2027-07-31 | 2023-08-02 | 2023-08-07 | 2023-08-21 | ENGG | 2023-12-14 | ConvNX,ESSM, LV,TAM,EXP,MOB | Conversion |  | 86 | Spine NG | Go LIVE | Onsite | Database conversion confirmation Ticket ID: #287747(required reconversions) # Training done for Payroll Nx and LVE and TAM module. # Clam module training pending bio matric pending for both company # Clint will process the salary in month of September #Login been given to employee # Pending query done 310479 #Salary has been processed for month of september Ticket #310479 # salary has been processed for oct moth |  |  | 0 | Nov-23 | saisanketindustriespvtltd | 2027-07-31 | 139
SPP102671182910 | 4620 | Conv | Account Activated | PRASHANT CORNER PRIVATE LIMITED | Normal | A | Nilima Karmokar | Prathamesh Mandavkar | 2023-09-26 | Akshay Joshi | Direct |  |  | Jatin Thakkar |  | Vasu Mohan Dusa | On-Premises | 1500 | 2026-11-30 | 2023-06-28 | 2023-07-21 | 2023-07-31 | ENGG | 2023-09-26 | conv to NX | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Training completed: #283586 Aug Slary done Live from NX: #296319 live mail shred by us : 299979 |  |  | Aug-23 | Aug-23 | prashantcornerpvtltd | 2026-11-30 | 140
SPM107218233003 | 4259 | Conv+New | Account Activated | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Premium | C | Usha Gupta | Ganesh Jadhav | 2023-05-12 | Aditya Pathak | Channel |  |  | Jayesh Mojidra |  | Vasu Mohan Dusa | On-Premises | 1410 | 2027-03-31 | 2023-03-30 | 2023-04-13 | 2023-04-25 | ENGG | 2023-06-09 | Conv NX | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Database back up after 15th april, Busy in tds work. installation done, Database in conversion, DB Hand holding done #241335, training from 25th, Training done #247004, april salary will be processed by 10th, april done #253524, may done #263924 |  | Testimonial Received | March-23,April-23,May-23 | May-23 | mahwsoilfieldservicespvtltd | 2027-03-31 | 141
SPM107089232402 | 4244 | Conv+New | Account Activated | MUMBAI CARGO SERVICE CENTER AIRPORT PVT. LTD NX | Normal | E | Aisha Patel | Ganesh Jadhav | 2023-10-09 | Gaurav Karmokar | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 695 | 2027-02-28 | 2023-03-24 | 2023-03-29 | 2023-04-19 | ENGG | 2023-10-09 | Conv to NX, ESSM,LV,TAM,MOB | Conversion |  | 42 | Spine HRMS | Go LIVE | Onsite | Conv conf 243113. Training done on all module. March salary processed and tallied 245031. April Live done 252891. May done 263687. June done. Logins pending. July done. Aug & Sept processed. For Attend module client will get back later. Integration done |  |  | 0 | Sept-23 | mumbaicargoservicecenterairportpvtltdnx | 2027-02-28 | 142
SPE107169232103 | 4199 | New | Account Activated | ELIXRR INDUSTRIES PVT LTD. | Normal | E | Nilima Karmokar | Ganesh Jadhav | 2023-06-06 | Krishna Yadav | Direct |  |  | Kishan Joshi |  | Vasu Mohan Dusa | SAAS | 1078 | 2027-03-31 | 2023-03-21 | 2023-03-23 | 2023-04-19 | ENGG | 2023-07-14 | HRIS /Payroll NX, WF, ESSM, LV, TAM, ELC, Mobile H | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Implementation & training completed : #247750 Integration done Logins Given April processed : #248183 May Live with atten : 261615 June Salary Live Done with atten : #274817 |  |  | April-23,May-23,Jun-23 | Jun-23 | elixrrindustriespvtltd | 2027-03-31 | 143
SPS101600122310 | 4067 | Conv | Account Activated | SEVENTY SEVEN ENTERTAINMENT PVT. LTD. | Normal | C | Usha Gupta | Viral Panchal | 2023-03-25 | Pritesh Barot | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | On-Premises | 250 | 2027-03-31 | 2023-02-09 | 2023-02-22 | 2023-02-28 | ENGG | 2023-06-06 | Conv,ELC | Conversion |  | 100 | Spine HRMS | Go LIVE | Onsite | Database in conversion & ELC file awaiting, DB hand holding & installation done #223067 ,Training completed #223067, ELC completed #231686, march salary will be done by 7th, april salary is done, need to do some chnages in shift timing, for that they will get back to us. |  |  | Feb-23,April-23 | April-23 | seventysevenentertainmentpvtltd | 2027-03-31 | 144
SPF107062230902 | 4066 | New | Account Activated | FFSERVICES PRIVATE LIMITED | Premium | E | Aisha Patel | Prathamesh Mandavkar | 2023-04-27 | Mayur Pendhari | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | SAAS | 220 | 2026-12-31 | 2023-02-09 | 2023-02-13 | 2023-02-27 | ENGG | 2023-07-11 | NX,ESSM,LV,TAM,MOB,ELC,RCT,PMS,RD | Fresh |  | 63 | Spine HRMS | Go LIVE | Onsite | Payroll NX Training done 221803 HRMS Done. Logins given. Feb done. March & April done. May Live done 263263 For Phase 2 client will get back - 275285 |  | Testimonial Received | 0 | Jun-23 | ffservicespvtltd | 2026-12-31 | 145
SPA106322220704 | 3920 | Add Mod | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Hemanshu Wadia | 2023-05-08 | Vinay Kareliya | Channel |  | AVI DEALER | Jayesh Mojidra |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2023-01-13 | 2023-01-13 | 2023-05-05 | ENGG | 2023-05-09 | PMS | Fresh |  | 100 | Spine HRMS | Go LIVE | Onsite | Files & policy awaiting, training probably on 20th. client will get back for pms training #215285, no response for standard training & files. Pms Standard training probably by 20th. April., required training on 5th May, Training completed logins will be share in july month #251187 |  |  | 0 | 0 | aegisprecisionpvtltd | 2027-03-31 | 146
SPA106322220704 | 3053 | New | Account Activated | AEGIS PRECISION PVT LTD | Normal | E | Usha Gupta | Prathamesh Mandavkar | 2022-08-13 | Nayan Choudhary | Channel |  | AVI DEALER | Jigar Rupani |  | Vasu Mohan Dusa | SAAS | 172 | 2027-03-31 | 2022-04-07 | 2022-04-11 | 2022-05-05 | ENGG | 2022-08-13 | NX,ESSM,LV,TAM | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite | July done #168845 |  |  | May-22,Jun-22,Jul-22 | Jul-22 | aegisprecisionpvtltd | 2027-03-31 | 147
SPA104424190108 | 2980 | Add Mod | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Aisha Patel | Prathamesh Mandavkar | 2022-04-12 | Nayan Choudhary | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2022-01-29 | 2022-01-29 | 2022-02-09 | ENGG | 2022-04-12 | LV | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | masterchainsnjewelspvtltd | 2026-01-31 | 148
SPV106083220301 | 2919 | Conv+New | Account Activated | VIPUL ORGANICS LTD. - STAFF | Premium | E | Aisha Patel | Hemanshu Wadia | 2022-06-15 | Santosh Yadav | Direct |  |  | Nikhil Solanki |  | Vasu Mohan Dusa | SAAS | 145 | 2026-12-31 | 2022-01-06 | 2022-01-06 | 2022-01-17 | ENGG | 2022-06-15 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite | Impl & Training done. Attendance Integration done but still some errors. Jan and Feb processed. Logins Rolled out. Ticket 123279. Mar & April Live done - 142745 |  |  | 0 | 0 | vipulorganicsltdstaff | 2026-12-31 | 149
SPP105402212702 | 2522 | Add Mod | Account Activated | PISCES CONTAINER LINES INDIA PVT. LTD. | Normal | E | Jyoti Mishra | Viral Panchal | 2021-11-11 | Pritesh Barot | Channel |  |  | Kunal Joshi |  | Vasu Mohan Dusa | SAAS | 100 | 2027-02-28 | 2021-08-10 | 2021-08-10 | 2021-08-19 | ENGG | 2021-11-11 | TAM | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | piscescontainerlinesindiapvtltd | 2027-02-28 | 150
SPK100839081706 | 2324 | Conv | Account Activated | KAMAL ENTERPRISES | Normal | A | Nilima Karmokar | Hemanshu Wadia | 2021-11-02 | Santosh Yadav | Direct |  |  | Kishan Joshi |  | Vasu Mohan Dusa | Hosting | 2500 | 2026-12-31 | 2021-04-22 | 2021-04-22 | 2021-05-13 | ENGG | 2021-11-02 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | kamalenterprises | 2026-12-31 | 151
SPE105433211303 | 2203 | New | Account Activated | ESCON ELEVATORS PVT. LTD. | Normal | A | Riya Jindam | Viral Panchal | 2022-02-07 | Probian Biswas | Channel |  | SOFTCORE SOLUTIONS PVT. LTD. | Jigar Rupani |  | Vasu Mohan Dusa | On-Premises | 805 | 2027-03-31 | 2021-03-11 |  | 2021-04-12 | ENGG | 2022-02-07 |  | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | esconelevatorspvtltd | 2027-03-31 | 152
SPP105402212702 | 2164 | New | Account Activated | PISCES CONTAINER LINES INDIA PVT. LTD. | Normal | E | Jyoti Mishra | Viral Panchal | 2021-08-14 | Krunal Pandya | Channel |  |  | Kunal Joshi |  | Vasu Mohan Dusa | SAAS | 100 | 2027-02-28 | 2021-03-01 |  | 2021-03-08 | ENGG | 2021-08-14 |  | Fresh |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | piscescontainerlinesindiapvtltd | 2027-02-28 | 153
SPC104730192512 | 1387 | New | Account DeActivated | CHEMITO INFOTECH PVT.LTD. |  | D | Riya Jindam | Prathamesh Mandavkar |  | Sonali Shejaval | Direct |  |  |  |  | Vasu Mohan Dusa | SAAS | 310 | 2026-09-30 | 2019-12-25 |  | 2019-12-25 | ENGG | 2020-05-09 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | chemitoinfotechpvtltd | 2026-09-30 | 154
SPA104424190108 | 1042 | Conv+New | Account DeActivated | MASTER CHAINS N JEWELS PRIVATE LIMITED | Normal | E | Riya Jindam | Prathamesh Mandavkar |  | Akshay Halankar | Direct |  |  | Mehul Patel |  | Vasu Mohan Dusa | SAAS | 240 | 2026-01-31 | 2019-07-31 |  | 2019-07-31 | ENGG | 2019-10-07 |  | Conversion |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | masterchainsnjewelspvtltd | 2026-01-31 | 155
SPP102671182910 | 298 | New | Account Activated | PRASHANT CORNER PRIVATE LIMITED |  | A |  | Hemanshu Wadia |  | Darshit Pithwa | Direct |  |  |  |  | Vasu Mohan Dusa | On-Premises | 1500 | 2026-11-30 | 2018-09-26 |  | 2018-09-26 | ENGG | 2019-05-25 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | prashantcornerpvtltd | 2026-11-30 | 156
SPL103086181602 | 29 | New | Account Activated | LATHIA RUBBER MFG CO. PVT. LTD. |  | B | Riya Jindam | Prathamesh Mandavkar |  | Prathamesh Mandavkar | Direct |  |  |  |  | Vasu Mohan Dusa | On-Premises | 750 | 2026-10-31 | 2018-10-13 |  | 2018-10-13 | ENGG | 2019-01-19 |  |  |  | 0 | Spine HRMS | Go LIVE | Onsite |  |  |  | 0 | 0 | lathiarubbermfgcopvtltd | 2026-10-31 | 157

## Preserved_Notes
Notes Key | Project Name | Source | Priority | Current Milestone | PM Notes | Next Action | Owner | Due Date | Action Date | Manual Risk Reason | Mail Include
aceyengineeringpvtltd | ACEY ENGINEERING PVT. LTD | Previous PM Cockpit | 30 | Completed | [6 empty] | No
acnhealthcarercmservicespvtltdacninfotech | ACN HEALTHCARE RCM SERVICES PRIVATE LIMITED / ACN INFOTECH | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes
aegisprecisionpvtltdshimnitindiapvtltd | AEGIS PRECISION PVT LTD // SHIMNIT INDIA PVT. LTD | Previous PM Cockpit, Book1 | 30 | Completed | Review Meeting pending. | Review Meeting pending. | Goraksha Pawar |  | 4th May |  | No
akritipharmaceuticalspvtltd | AKRITI PHARMACEUTICALS PVT LTD | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. | Ankush Rampyare Rajbhar |  |  |  | Yes
alliedinstrumentspvtltd | ALLIED INSTRUMENTS PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Vijay Bugde |  |  |  | No
alshifamultispecialtyhospitalhumanwelfaretrust | ALSHIFA MULTI SPECIALTY HOSPITAL / HUMAN WELFARE TRUST | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
amalembroideriespvtltd | AMAL EMBROIDERIES PVT. LTD | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Coordinated with Aparna, she said the delay is from their end as she is busy in payroll activities and she will coordinate with the team once she gets free. | Vijay Bugde |  | 4th May |  | Yes
anmindustriespvtltdanmallianceanmgroupamketteanalyticsltd | ANM INDUSTRIES PVT LTD / ANM ALLIANCE / ANM GROUP/ AMKETTE ANALYTICS LTD. | Previous PM Cockpit | 30 | Completed |  |  | Vinay Kareliya |  |  |  | No
anshutechairconditioningpvtltdnx | ANSHUTECH AIR CONDITIONING PVT. LTD. NX | Previous PM Cockpit | 30 | Completed | Need to plan Review Meeting | Need to plan Review Meeting | Hardik Panchal |  |  |  | No
ansng | ANS NG | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. | Aditya Mazire |  |  |  | Yes
anuhpharmapvtltdnx | ANUH PHARMA PVT. LTD NX | Previous PM Cockpit | 30 | Completed | [6 empty] | No
aplabltdforcontractlicense | APLAB LIMITED (FOR CONTRACT LICENSE) | Previous PM Cockpit | 30 | Completed | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Discussion done with Aparna for Amal Embroideries, She said due to their internal processing there was a delay, but now they are aligned fully. Discussion done for further milestones, and their target is to close the implementation this month and proceed with live salary processing. She said everything is aligned for now just would be needing help for some reports as they would be needing the same for management purposes. Informed the same to coordinate with Vijay and if anything is needed to inform me for the same. | Varun Rajbhar |  |  |  | No
aplabltdforstafflicense | APLAB LIMITED (FOR STAFF LICENSE) | Previous PM Cockpit | 30 | Completed | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Discussion done with Sunil & Team for Multi Organics, discussed everything in detailed, cleared all the communication gap which happened during the initial implementation call. He said he would prefer all session in this manner only at their onsite office. Informed that we would be needing Master Data, Payroll Structure and Salary Register of all employees, Leave Records, Leave and Attendance Policies for all locations. Once this is done we can proceed with implementation & Training. They would be needing Google API integration as well for some of the employees. They said they will prepare and share the data by 15th. Told them to try and share the data by 12 so the engineer can do the backend setup in the office and from 15th onwards we can start the implementation and training with the team. | Varun Rajbhar |  |  |  | No
aquaairintlfrieghtservices | Aquaair International Frieght Services | Previous PM Cockpit | 30 | Completed |  |  | Nagendra Poojary |  |  |  | No
armitaindiashippingpvtltd | ARMITA INDIA SHIPPING PVT. LTD | Previous PM Cockpit | 30 | Completed |  |  | Mayur Pendhari |  |  |  | No
arssteelsalloyintlpvtltdarsgroup | ARS STEELS & ALLOY INTERNATIONAL PVT. LTD / ARS GROUP | Previous PM Cockpit | 30 | Completed | Informed Vinay to Send a status mail | Informed Vinay to Send a status mail |  |  |  |  | No
atharvafacilitymanagementandsecurity | ATHARVA FACILITY MANAGEMENT AND SECURITY | Previous PM Cockpit | 30 | Completed | [6 empty] | No
aurousjewelsllp | AUROUS JEWELS LLP | Previous PM Cockpit | 30 | Completed | [6 empty] | No
autotechsirmaxindiapvtltd | AUTOTECH-SIRMAX INDIA PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Vikas Yadav |  |  |  | No
basantoverseas | BASANT OVERSEAS | Previous PM Cockpit | 30 | Datafile Explanation | Live Salary Processing Planned. | Review blocker, confirm owner, and update next closure plan. | Yash Pankajkumar Shah |  |  |  | No
bengalenergystaff | Bengal Energy_Staff | Previous PM Cockpit | 30 | Completed |  |  | Mayur Pendhari |  |  |  | No
bengalenergyworker | Bengal Energy_Worker | Previous PM Cockpit | 30 | Datafile Explanation |  | Review blocker, confirm owner, and update next closure plan. | Mayur Pendhari |  |  |  | No
bfmsfacilitymanagementpvtltd | BFMS FACILITY MANAGEMENT PVT LTD | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Amit Krishnakant Tiwari |  | 5th May |  | Yes
bijjargimotorspvtltdbijjargimotorsbijjargiexcavationsolutions | BIJJARGI MOTORS PVT LTD / BIJJARGI MOTORS / BIJJARGI EXCAVATION SOLUTIONS | Previous PM Cockpit | 30 | Completed |  |  | Sahil Gadhave |  |  |  | No
brightbrothersltdbrite | BRIGHT BROTHERS LTD. / BRITE | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Rahul Ankush Dalvi |  |  |  | No
brilliantpolymerspvtltd | BRILLIANT POLYMERS PVT. LTD | Previous PM Cockpit | 30 | Completed |  |  | Probian Biswas |  |  |  | No
bsacorporationltdbsagroup | BSA CORPORATION LIMITED / BSA GROUP | Previous PM Cockpit | 30 | Kick Off Meeting | KickOff Meeting & Datafiles Explaination done, client to share datafiles by 17th June | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
camtoolsindustriespvtltddigitaltoolroom | CAM TOOLS INDUSTRIES PVT LTD / DIGITAL TOOL ROOM | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Discussion was conducted with Sintu and team regarding attendance challenges due to continuous shift operations and hourly-based workforce management. Harsh is currently working on salary tally verification. Client highlighted delays caused by inadequate support from the existing biometric vendor. Coordination was done with Divya and Yogendra from Technowin to address the concerns. Technowin has agreed to provide a 7-day trial period against 20% advance payment. Client management is reviewing the proposal and is expected to take a decision on priority. | Harsh Dilip Ashar |  | 8th May |  | No
cartfireindia | Cartfire India | Previous PM Cockpit | 30 | Completed | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Nagendra Poojary |  |  |  | No
centreforurbanizationbuildingsandenvironmentcubeiitm | CENTRE FOR URBANIZATION BUILDINGS AND ENVIRONMENT (CUBE IITM) | Previous PM Cockpit | 30 | Datafile Explanation |  | Review blocker, confirm owner, and update next closure plan. |  |  |  |  | No
circleresourcespvtltd | CIRCLE RESOURCES PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | Progress & Review Call | Progress & Review Call | Mayur Pendhari |  |  |  | No
cogencis | Cogencis | Previous PM Cockpit | 30 | Completed |  |  | Vikas Yadav |  |  |  | No
contendregreenergyltd | CONTENDRE GREENERGY LIMITED | Previous PM Cockpit | 30 | Completed | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Internal infrastructure changes happening, hence salary is delayed, Team is following up for May salary process. | Daksh Pawankumar |  |  |  | No
cosmosimpexindiapvtltdng | COSMOS IMPEX INDIA PVT LTD NG | Previous PM Cockpit | 30 | Completed | [6 empty] | No
creationsbyshanagar | CREATIONS BY SHANAGAR | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes
cryogasequipmentpvtltdcryogasindia | CRYOGAS EQUIPMENT PRIVATE LIMITED/CRYOGAS INDIA | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Confirm kickoff date, data readiness, and owner. | Varun Rajbhar |  |  |  | Yes
doshimedicarepvtltd | DOSHI MEDICARE PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | [6 empty] | No
drsearthworkpvtltd | DRS EARTHWORK PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Mihir Navnath Mungekar |  |  |  | No
electrosteelcastingsltdelectrosteelgroup | ELECTROSTEEL CASTINGS LTD / ELECTROSTEEL GROUP | Previous PM Cockpit | 30 | Completed |  |  | Kunal Joshi |  |  |  | No
elixrrindustriespvtltd | Elixrr Industries Pvt. Ltd. | Previous PM Cockpit | 30 | Completed |  |  | Krishna Yadav |  |  |  | No
emmayentertainment | Emmay Entertainment | Previous PM Cockpit | 30 | Completed |  |  | Nandadeep Mhatre |  |  |  | No
empreopremiumpvtltd | EMPREO PREMIUM PVT LTD | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Goraksha Pawar |  | 8th May |  | Yes
empreowheelpvtltdmg | EMPREO WHEEL PVT LIMITED (MG) | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Same | Same | Goraksha Pawar |  | 8th May |  | Yes
ermellipvtltd | ERMELLI PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Hardik Panchal |  |  |  | No
eroselevatorsescalatorspvtltd | EROS ELEVATORS & ESCALATORS PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Amol Takkar |  |  |  | No
esconelevatorspvtltd | ESCON ELEVATORS PVT. LTD. | Previous PM Cockpit | 30 | Completed |  |  | Probian Biswas |  |  |  | No
evergreenhousekeepingservicespvtevergreenfacilitysolutions | EVERGREEN HOUSEKEEPING SERVICES PRIVATE / EVERGREEN FACILITY SOLUTIONS | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Komal Kanadiya |  |  |  | No
fabtechmultistatecooperativecreditsocietyfmsccs | FABTECH MULTI STATE COOPERATIVE CREDIT SOCIETY (FMSCCS) | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes
feathertouchlearningpvtltdfeathertouhdaycare | FEATHERTOUCH LEARNING PRIVATE LIMITED / FEATHER TOUH DAY CARE | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Need to discuss internally for live processing | Need to discuss internally for live processing | Sunita Yadav |  |  |  | No
ffservicespvtltd | FFSERVICES PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | April Salary Processed, Review Meeting & Closure Note | April Salary Processed, Review Meeting & Closure Note | Harsh Dilip Ashar |  |  |  | No
fujiyamapowersystemutl | FUJIYAMA POWER SYSTEM (UTL) | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Komal Kanadiya |  |  |  | No
gcomsystemsandsolutionsourladyofsalvation | GCOM SYSTEMS AND SOLUTIONS (OUR LADY OF SALVATION) | Previous PM Cockpit | 30 | Completed | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Amit Krishnakant Tiwari |  |  |  | No
gngelectronicsltdelectronicsbazaarforstafflicenseconversiontong | GNG ELECTRONICS LIMITED / ELECTRONICS BAZAAR - FOR STAFF LICENSE CONVERSION TO NG | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. | User was not available as he was on leave, he said their VP was also not available, hence it was pending. He would be joining back on 4th. He said he will discuss the same and get the confirmation and close it on 4th. |  |  | 4th May |  | Yes
gngelectronicsltdfactory | GNG ELECTRONICS LIMITED FACTORY | Previous PM Cockpit | 30 | Completed | Review Meeting | Review Meeting | Shubham Gurav |  |  |  | Yes
gngelectronicsltdstaff | GNG ELECTRONICS LIMITED STAFF | Previous PM Cockpit | 30 | Completed | plan activities in 2days. | plan activities in 2days. | Shubham Gurav |  |  |  | No
goldstarelitejewelspvtltd | GOLDSTAR ELITE JEWELS PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Amol Takkar |  |  |  | No
guardiancastingpvtltd | GUARDIAN CASTING PVT. LTD | Previous PM Cockpit | 30 | Completed | [6 empty] | No
gujaratteaprocessorpackersltd | GUJARAT TEA PROCESSOR & PACKERS LTD | Previous PM Cockpit | 30 | Completed |  |  | Sachin Thothawala |  |  |  | No
hardcarbtechpvtltd | Hardcarb Technologies Private Limited | Previous PM Cockpit | 30 | Completed | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Tejas Rajesh Baragade |  |  |  | No
hardcarbtechpvtltdvautidshahhardfacepvtltdstafflicense | HARDCARB TECHNOLOGIES PVT. LTD. / VAUTID-SHAH HARDFACE PVT. LTD. - STAFF LICENSE | Previous PM Cockpit | 30 | Completed |  |  | Mihir Navnath Mungekar |  |  |  | No
helenkellerinstitutefordeafblind | Helen Keller Institute for Deaf & Blind | Previous PM Cockpit | 30 | Completed | [6 empty] | No
hellenergypvtltd | HELL ENERGY PVT LTD | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes
ileafritzbanquets | ILEAF RITZ BANQUETS | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Mayur Pendhari |  |  |  | Yes
indianagroupindianagratingspvtltd | INDIANA GROUP / INDIANA GRATINGS PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Rahul Ankush Dalvi |  |  |  | No
industrialxrayalliedradiographersnx | INDUSTRIAL X-RAY & ALLIED RADIOGRAPHERS NX | Previous PM Cockpit | 30 | Completed |  |  | Kajal Inchanalkar |  |  |  | No
infexnlaboratories | Infexn Laboratories | Previous PM Cockpit | 30 | Completed |  |  | Shubham Gurav |  |  |  | No
integratedpestmanagementsolutionsindiapvtltdipmsindia | INTEGRATED PEST MANAGEMENT SOLUTIONS (INDIA) PVT. LTD. (IPMS INDIA) | Previous PM Cockpit | 30 | Kick Off Meeting | Corp ID has been Generated, Client has shared the datafiles and team is working on backend setup. | Confirm kickoff date, data readiness, and owner. | Ankita Gupta |  |  |  | Yes
isalogisticspvtltd | ISA Logistics Private Limited | Previous PM Cockpit | 30 | Completed | April Salary Processed, Review Meeting | April Salary Processed, Review Meeting | Mihir Navnath Mungekar |  |  |  | No
itcfortunehotelsiligurickimpromotersllpfortuneselectsiliguri | ITC FORTUNE HOTEL-SILIGURI / CKIM PROMOTERS LLP / FORTUNE SELECT SILIGURI | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
jietmedicalcollegehospital | JIET MEDICAL COLLEGE HOSPITAL | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. | Varun Rajbhar |  |  |  | Yes
karvytechpvtltd | KARVY TECHNOLOGIES PVT LTD | Previous PM Cockpit | 30 | Datafile Explanation | Live Salary Processing Planned for this Month | Review blocker, confirm owner, and update next closure plan. | Tejas Rajesh Baragade |  |  |  | No
kishanlalpawankumarjain | KISHAN LAL PAWAN KUMAR JAIN | Previous PM Cockpit | 30 | Completed | [6 empty] | No
kubozarcpvtltd | Kuboz Arc Pvt Ltd | Previous PM Cockpit | 30 |  |  |  | Santosh Yadav |  |  |  | No
lotustexcomindiallp | LOTUS TEXCOM INDIA LLP | Previous PM Cockpit | 30 | Datafile Explanation | Discussion done with Sintu and Team for Cam Tools, Introduction done and discussed in details about their issues and expectations. They were using excel. And Major pain area is attendance as their workers work in contineous shifts and working is done in hours. Harsh in working for talling the salary. Training has been completed successfully. Their Biometric vendor is not giving them proper support. They are causing the delays. They said team has suggested for biometric vendor. Upon asking he said he is in discussion with Technowin Team. Coordinated with Divya and Yogendra from Technowin team and cleared all the gaps and reassured them. Yogendra ji agreed to give them a trial of 7 days period with a 20% payment. Sintu Ji said that he will discussed the same with his director and close the same on priority. | Review blocker, confirm owner, and update next closure plan. | Prathamesh Mandavkar |  |  |  | No
madhusumanenterprisesmsehvacservicesindia | MADHUSUMAN ENTERPRISES (MSE) HVAC SERVICES INDIA | Previous PM Cockpit | 30 | Completed |  |  | Tejas Rajesh Baragade |  |  |  | No
maduraindustrialtextilesltd | MADURA INDUSTRIAL TEXTILES LIMITED | Previous PM Cockpit | 30 | Completed | Closed | Closed | Varun Rajbhar |  |  |  | No
maharashtrabookmanufacturing | Maharashtra Book Manufacturing | Previous PM Cockpit | 30 | Completed |  |  | Shubham Gurav |  |  |  | No
mahatmaphulecharitabletrustmpcthospitalsuranagroupofhospitalsuranahospitalsuranahospitalandresearchcentre | MAHATMA PHULE CHARITABLE TRUST/MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL / SURANA HOSPITAL AND RESEARCH CENTRE | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
mahwsoilfieldservicespvtltd | MAHWS OILFIELD SERVICES PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Ruchit Shailesh Patel |  |  |  | No
manjushreeinnovationspvtltd | MANJUSHREE INNOVATIONS PVT. LTD | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training to be started from 8th May. Team to followup for the same on 5th. | Mayur Pendhari |  | 5th May |  | Yes
manshaagencies | Mansha Agencies | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Coordinated with Aditya Mazire, he said the delay is from User end, and they are taking followups for the same. Informed Disha to Align a review meeting for this week. | Confirm kickoff date, data readiness, and owner. | Aditya Mazire |  |  |  | Yes
maruconsultancyservices | MARU CONSULTANCY SERVICES | Previous PM Cockpit | 30 | Datafile Explanation | Manoj has left the organisation, Dhanashree is not involved, Vinantee looks into Spine, Guided user related to payroll structure and compliance, she said she their director is out of town, she will coordinate and confirm the structure and move ahead with Spine Implementation and Processing. Need to plan a visit for review. | Review blocker, confirm owner, and update next closure plan. | Ruchit Shailesh Patel |  |  |  | No
medipulsehospital | MEDIPULSE HOSPITAL | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Varun Rajbhar |  |  |  | Yes
mespackindiapvtltd | MESPACK INDIA PVT. LTD | Previous PM Cockpit | 30 | Completed | Pranit to coordinate internally and align the implementation, team to coordinate for further activities | Review blocker, confirm owner, and update next closure plan. | Pooja Vikas Shinde |  |  |  | No
metafab | Metafab | Previous PM Cockpit | 30 | Completed |  |  | Goraksha Pawar |  |  |  | No
micropointcomputerspvtltdnx | MICROPOINT COMPUTERS PRIVATE LIMITED NX | Previous PM Cockpit | 30 | Completed | Progress & Review Call | Progress & Review Call | Mayur Pendhari |  |  |  | No
muktanganeducationtrust | Muktangan Education Trust | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Discussion done with Sarita from Muktangan, introduction done, she said everything is aligned and about the new modules the other team is coordinating, Then coordinated with Mayuri she sits in Wadala branch and she said to coordinate with Samir, and she will let me know her availability for discussion. Coordinated with Samir, he was heading for a meeting, he said there was a communication gap from partner team, earlier during the sales they said that ESSM Module has leave feature and post that now they said that leave module needs to be procured, explained him how it works, he then said ok. Asked that should i coordinate further with the partner, he said no and he will coordinate internally and then coordinate with partner and close this. Informed Ankita to align a review meeting for next week. | Confirm kickoff date, data readiness, and owner. | Aditya Mazire |  |  |  | Yes
multiorganicspvtltd | MULTI ORGANICS PVT LTD | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | KickOff & Datafile Explaination done | KickOff & Datafile Explaination done | Rajesh Ravindra Panchal |  | 5th May |  | Yes
nagrikconsultancyservices | NAGRIK CONSULTANCY SERVICES | Previous PM Cockpit | 30 | Completed | Progress & Review Call | Progress & Review Call | Aditya Mazire |  |  |  | No
naikmotorsgoaloc | NAIK MOTORS -GOA LOC | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Aditya Mazire |  |  |  | Yes
naikmotorsnaikmahindraratnagiriloc | NAIK MOTORS / NAIK MAHINDRA - RATNAGIRI LOC | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Aditya Mazire |  |  |  | Yes
nationalbulkhandlingcorporationpvtltd | NATIONAL BULK HANDLING CORPORATION PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Aditya Mazire |  |  |  | No
navioshipping | Navio Shipping | Previous PM Cockpit | 30 | Completed | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. | Awaiting Response from User, Msg dropped to user to connect with Nagesh for further plan of action. |  |  |  |  | No
navkarcorporationltd | NAVKAR CORPORATION LIMITED | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
nikikaenterprisesllp | NIKIKA ENTERPRISES LLP | Previous PM Cockpit | 30 | Completed | Arpit informed that Partner team was not available, informed him to push and | Arpit informed that Partner team was not available, informed him to push and |  |  |  |  | No
nivanbalajiautomoverspvtltdbalajikiacarshowroom | NIVAN BALAJI AUTOMOVERS PRIVATE LIMITED / BALAJI KIA - CAR SHOWROOM | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Implementation & Training has been completed. Vinay is aligning a review meeting. | Implementation & Training has been completed. Vinay is aligning a review meeting. | Mihir Navnath Mungekar |  | 8th May |  | No
notchindiaprojects | NOTCH INDIA PROJECTS | Previous PM Cockpit | 30 | Completed | [6 empty] | No
npseautomationpvtltd | NPSE AUTOMATION PVT. LTD | Previous PM Cockpit | 30 | Completed | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Discussion done with Pankaj for Aegis Precision, everything is aligned and the feedback was also positive. He said the training was also done properly. Only 1 or 2 issues are there and they are coordinating with the team for the same. Asked about the Director's availability for feedback. He checked but the director was not available, he said he will inform the same to the management and let me know. | Nandadeep Mhatre |  |  |  | No
oneteamlogisticsindiapvtltd | ONETEAM LOGISTICS INDIA PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | Review Meeting | Review Meeting | Tushar More |  |  |  | No
pankajfashionpvtltd | PANKAJ FASHION PVT LTD | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Onsite Visit planned for 15th June | Review blocker, confirm owner, and update next closure plan. | Arpit Patel |  |  |  | No
paradisegroup | PARADISE GROUP | Previous PM Cockpit | 30 | Datafile Explanation | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Pritesh Barot |  |  |  | Yes
parbhanimedicalcollege | Parbhani Medical College | Previous PM Cockpit | 30 | Completed |  |  | Sushant Thombare |  |  |  | No
parvathyhospital | parvathyhospital | Previous PM Cockpit | 30 | Completed | [6 empty] | No
piscescontainerlinesindiapvtltd | PISCES CONTAINER LINES INDIA PVT. LTD. | Previous PM Cockpit | 30 | Completed | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated | 25 Staff & 84 Worker Salary Processed, 584 Employee data updated | Pritesh Barot |  |  |  | No
plasmaresearchtrustnx | PLASMA RESEARCH TRUST NX | Previous PM Cockpit | 30 | Completed |  |  | Paras Mahesh Ladva |  |  |  | No
polmorsteelpvtltd | POLMOR STEEL PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | [6 empty] | No
poonamrollerflourmillspvtltd | POONAM ROLLER FLOUR MILLS PRIVATE LIMITED | Previous PM Cockpit | 30 |  |  |  | Rahul Ankush Dalvi |  |  |  | No
ppkgandco | PPKG AND CO | Previous PM Cockpit | 30 | Completed | [6 empty] | No
prasadjewellers | PRASAD JEWELLERS | Previous PM Cockpit | 30 | [7 empty] | No
preciousalloyspvtltd | PRECIOUS ALLOYS PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Shreyas Karkera |  |  |  | No
prijaiheatexchangerspvtltd | PRIJAI HEAT EXCHANGERS PVT. LTD. | Previous PM Cockpit | 30 | Completed |  |  | Goraksha Pawar |  |  |  | No
proconrmc | Procon RMC | Previous PM Cockpit | 30 | Completed | [6 empty] | No
qualigenspharmapvtltd | QUALIGENS PHARMA PVT. LTD | Previous PM Cockpit | 30 | Completed | Backend working is ongoing, training & implementation is planned. | Backend working is ongoing, training & implementation is planned. | Ruchit Shailesh Patel |  |  |  | No
radixelectrosystemspvtltd | RADIX ELECTROSYSTEMS PVT LTD | Previous PM Cockpit | 30 | Completed | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | KickOff Done, Datafiles to be shared by 6th May and Implementation & Training was planned to started from 8th May. Probian to take a followup call and align the same. Post which Probian informed data will be send on 10th and aligning the same for implementation as well. | Aditya Pathak |  |  |  | No
rajeshwariinfotelpvtltdripl | RAJESHWARI INFOTEL PVT. LTD. (RIPL) | Previous PM Cockpit | 30 | Completed |  |  | Riddhi Pramod Sutar |  |  |  | No
renmakchindiapvtltd | RENMAKCH INDIA PVT. LTD. | Previous PM Cockpit | 30 | Completed | [6 empty] | No
royalchainspvtltdandroyalitalianjewelrypvtltd | Royal Chains Pvt. Ltd. and Royal Italian Jewelry Pvt. Ltd. | Previous PM Cockpit | 30 | Completed | [6 empty] | No
royalembroiderythreadspvtltd | ROYAL EMBROIDERY THREADS PVT.LTD. | Previous PM Cockpit | 30 | Completed |  |  | Bhavika Gite |  |  |  | No
rupasolutionspvtltdrupagrouprupaproperties | RUPA SOLUTIONS PRIVATE LIMITED / RUPA GROUP / RUPA PROPERTIES | Previous PM Cockpit, Book1 | 30 | Completed | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | April Salary Process and Tally done, Attendance Integration done, May Live processing planned. | Ankush Rampyare Rajbhar |  |  |  | Yes
sacredhearthospitaljal | SACRED HEART HOSPITAL JAL | Previous PM Cockpit | 30 | Kick Off Meeting | KickOff Meeting & Datafiles Explaination done, client requires 2 to 3 days time for data preparation | Confirm kickoff date, data readiness, and owner. | Mayur Pendhari |  |  |  | Yes
sainielectricalengineeringworks | SAINI ELECTRICAL & ENGINEERING WORKS | Previous PM Cockpit | 30 | Completed |  |  | Mukeshkumar Shojiram kumavat |  |  |  | No
saisanketindustriespvtltd | SAI SANKET INDUSTRIES PVT.LTD | Previous PM Cockpit | 30 | Completed |  |  | Dakshesh D Nadkar |  |  |  | No
sankalpan | Sankalpan | Previous PM Cockpit | 30 |  |  |  | Rahul Ankush Dalvi |  |  |  | No
seebaindustriespvtltd | SEEBA INDUSTRIES PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed |  |  | Darshit Pithwa |  |  |  | No
sethwalafoodsltd | SETHWALA FOODS LTD | Previous PM Cockpit | 30 | Completed |  |  | Kunal Joshi |  |  |  | No
seventysevenentertainmentpvtltd | SEVENTY SEVEN ENTERTAINMENT PVT. LTD | Previous PM Cockpit | 30 | Completed | Datafiles Received, Implementation planned, Team to followup | Datafiles Received, Implementation planned, Team to followup | Pritesh Barot |  |  |  | No
shreedholisatitextilespvtltd | SHREE DHOLI SATI TEXTILES PRIVATE LIMITED | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. | Bhavika Gite |  |  |  | No
shreekhetraautomotivetata | SHREEKHETRA AUTOMOTIVE (TATA) | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Same | Same | Goraksha Pawar |  | 8th May |  | Yes
shreeramdevmetalexllpramdevgroup | SHREE RAMDEV METALEX LLP / RAMDEV GROUP | Previous PM Cockpit | 30 | Completed | Progress & Review Call | Progress & Review Call | Tejas Rajesh Baragade |  |  |  | No
shrijanardanswamihospitalsjs | SHRI JANARDAN SWAMI HOSPITAL (SJS) | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Coordinated with Vikas, Client would be sending March data on 4th May. Informed Vikas to coordinate and take their accounts team on Concall and ask them the disbursement data directly. | Vikas Yadav |  |  |  | Yes
sktraders | S K Traders | Previous PM Cockpit | 30 | Completed | Progress & Review Call | Progress & Review Call | Rahul Ankush Dalvi |  |  |  | No
skyprints | Sky Prints | Previous PM Cockpit | 30 | Completed | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | KickOff And Datafile explaination done, Session attended by Mdm. Stuthi Work Done Mobile HR Payroll Nx Others Discussed regarding Planners and informed the user about the share Corp Id. Explained the process of create Spine Implementation required files and informed the user to share below mentioned details. Employee Master Leave Opening Leave Policy Leave Workflow Attendance Policy Attendance Workflow CTC Salary Register And discussed regarding the planner and for Implementation. Informed Vinay to discuss and followup with client for datafiles and ticket booking for onsite implementation visit from Monday or Tuesday. | Nagesh Tiwari |  |  |  | No
snapworktechpvtltd | SNAPWORK TECHNOLOGIES PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Vijay Bugde |  |  |  | No
sreemetaliksltd | SREE METALIKS LTD | Previous PM Cockpit | 30 | Completed | Live Salary Processing Planned for this Month | Live Salary Processing Planned for this Month | Nandadeep Mhatre |  |  |  | No
steamharbourlogisticspvtltd | STEAM HARBOUR LOGISTICS PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Daksh Pawankumar |  |  |  | No
steampulseindiapvtltd | STEAM PULSE INDIA PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Daksh Pawankumar |  |  |  | No
sterlinglifestylellp | STERLING LIFESTYLE LLP | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. | Aarati Subhashchandra Yadav |  |  |  | Yes
stormfinancialservices | STORM FINANCIAL SERVICES | Previous PM Cockpit, Book1 | 30 | Completed | April Salary Process and Tally done, Attendance Integration is planned. | April Salary Process and Tally done, Attendance Integration is planned. | Mukeshkumar Shojiram kumavat |  |  |  | No
sukhkartamultispecialityhospital | SUKHKARTA MULTISPECIALITY HOSPITAL | Previous PM Cockpit | 30 | [7 empty] | No
sunrisefoodsbangalore | SUNRISE FOODS BANGALORE | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Tushar More |  |  |  | Yes
suranacharitabletrustsuranahospitalandresearchcentrempcthospitalsuranagroupofhospitalsuranahospital | SURANA CHARITABLE TRUST / SURANA HOSPITAL AND RESEARCH CENTRE / MPCT HOSPITAL / SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
suranagroupofhospitalsuranahospital | SURANA GROUP OF HOSPITAL / SURANA HOSPITAL | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
suvarnadurgagroupsdgsuvarnadurgapaperboardspvtltd | SUVARNA DURGA GROUP (SDG) / SUVARNA DURGA PAPER BOARDS PRIVATE LIMITED | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Implementation Demo fixed for 8th May | Implementation Demo fixed for 8th May |  |  |  |  | Yes
svsengineeringramyasrielectricalautomation | SVS ENGINEERING / RAMYASRI ELECTRICAL AUTOMATION | Previous PM Cockpit | 30 | Datafile Explanation |  | Review blocker, confirm owner, and update next closure plan. | Ankita Gupta |  |  |  | No
symbiosiscentrefordistancelearningsymbiosisopeneducationsocietysdcl | SYMBIOSIS CENTRE FOR DISTANCE LEARNING/SYMBIOSIS OPEN EDUCATION SOCIETY (SDCL) | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Confirm milestone progress and next client action. | Riddhi Pramod Sutar |  |  |  | Yes
talibandshamsiconstructionspvtltd | Talib and Shamsi Constructions Pvt. Ltd. | Previous PM Cockpit | 30 | Completed | [6 empty] | No
taoautomationservicespvtltd | TAO AUTOMATION SERVICES PVT LTD | Previous PM Cockpit | 30 | Completed |  |  | Supriya Waghmare |  |  |  | No
tarasafeintlpvtlimitedstaff | TARASAFE INTERNATIONAL PRIVATE LIMITED_STAFF | Previous PM Cockpit | 30 | Completed | plan for further activities scheduled for 10th. | plan for further activities scheduled for 10th. | Sahil Gadhave |  |  |  | No
tarasafeintlpvtlimitedworker | TARASAFE INTERNATIONAL PRIVATE LIMITED_WORKER | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Sahil Gadhave |  |  |  | No
tatariahardwareinnovation | TATARIA HARDWARE INNOVATION | Previous PM Cockpit | 30 | Completed |  |  | Nagendra Poojary |  |  |  | No
texple | Texple | Previous PM Cockpit | 30 | Completed |  |  | Santosh Yadav |  |  |  | No
thekandivalieducationsociety | THE KANDIVALI EDUCATION SOCIETY | Previous PM Cockpit | 30 | Datafile Explanation |  | Confirm progress for milestone: Datafile Explanation. |  |  |  |  | Yes
thenationalsportsclubofindia | THE NATIONAL SPORTS CLUB OF INDIA | Previous PM Cockpit | 30 | Datafile Explanation | Live Salary Processing Planned. | Live Salary Processing Planned. | Mihir Navnath Mungekar |  |  |  | Yes
torqueinsurancebrokingpvtltd | TORQUE INSURANCE BROKING PRIVATE LIMITED | Previous PM Cockpit | 30 | Completed | [6 empty] | No
triojewelspvtltd | TRIO JEWELS PVT LTD | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Mukeshkumar Shojiram kumavat |  |  |  | Yes
triojewelspvtltdcontractual | TRIO JEWELS PVT LTD Contractual | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Suprio confirmed validation of April payroll with the internal team. May salary processing has been planned. Discussion was done regarding salary component restructuring and planning for a June parallel run. PMS configuration activities are progressing simultaneously. Contractual license implementation will be taken up after successful confirmation and stabilization of the staff license. | Mukeshkumar Shojiram kumavat |  | 8th May |  | Yes
trishulelectromechengineeringindiapvtltdtrishulgroup | TRISHUL ELECTROMECH ENGINEERING INDIA PVT.LTD. / TRISHUL GROUP | Previous PM Cockpit | 30 | Completed |  | Review blocker, confirm owner, and update next closure plan. | Vijay Bugde |  |  |  | No
unitedairexpress | UNITED AIR EXPRESS | Previous PM Cockpit | 30 | Completed | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | 5 days schedule completed at Symbiosis. Core HRIS and payroll module data is imported, salary processed and most of data is matching. | Shubham Gurav |  |  |  | No
vaba | VABA | Previous PM Cockpit | 30 | Completed |  |  | Karan Rajesh Tiwari |  |  |  | No
valliancenx | V ALLIANCE NX | Previous PM Cockpit | 30 | Completed |  |  | Rahul Ankush Dalvi |  |  |  | No
vedindustriesrohidagroup | VED INDUSTRIES/ ROHIDA GROUP | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
vedindustriesrohidagrouppoclicense | VED INDUSTRIES/ ROHIDA GROUP - POC LICENSE | Previous PM Cockpit | 30 | Completed | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Feedback is positive, User to resolve internal issues and plan for live processing from June. | Dhanashree Dalvi |  |  |  | No
vipulorganicsltdstaff | VIPUL ORGANICS LTD. - STAFF | Previous PM Cockpit | 30 | Completed |  |  | Santosh Yadav |  |  |  | No
vishwakarmafoundersipvtltd | VISHWAKARMA FOUNDERS (I) PVT. LTD | Previous PM Cockpit | 30 | Kick Off Meeting |  | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
vivanassociate | Vivan Associate | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | Discussion done with Rohit, he is the HR Manager, they are into real estate, hence they have a dependancy on Mobile Application for Location Tracking for attendance. And they were trying since long to coordinate and rectify but nothing worked, hence the management has decided to stop the services and they have put a mail for refund as well. Explained and informed everything about location IQ and other 3rd party integrations and not spine issue. And alternatively, we can go ahead with Google API for better accuracy and to give me a chance to try as the subscription is ongoing. Also about the refund, informed that spine does not have a refund policy. He said he will talk to the management about this and let me know the way ahead. | Confirm kickoff date, data readiness, and owner. |  |  |  |  | Yes
vividelectromechltdvividgroup | VIVID ELECTROMECH LTD. / VIVID GROUP | Previous PM Cockpit | 30 | Completed |  |  | Mihir Navnath Mungekar |  |  |  | No
voguenhydepvtltdmodapellebagsaccessoriespvtltd | VOGUE N HYDE PRIVATE LIMITED/ MODAPELLE BAGS & ACCESSORIES PRIVATE LIMITED | Previous PM Cockpit, Book1 | 30 | Kick Off Meeting | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. | Training has been completed. Vinay informed that team is currently working on daily wages calculation tally. Surojit ji gave good feedback about akshay's training. He said the team is now working on rest of the implementation, and then focus on live salary processing post attendance integration. |  |  |  |  | Yes
whistlingwoodsintl | WHISTLING WOODS INTERNATIONAL | Previous PM Cockpit, Book1 | 30 | Datafile Explanation | PMS Implementation Ongoing | PMS Implementation Ongoing | Nagendra Poojary |  |  |  | Yes
yuvaparivartankherwadisocialwelfareassociation | YUVA PARIVARTAN KHERWADI SOCIAL WELFARE ASSOCIATION | Previous PM Cockpit | 30 | Completed |  |  | Probian Biswas |  |  |  | No

## Run_Log
Metric | Value
Run Timestamp | 06-Oct-2026 12:25:27
Tracker Rows Used | 181
SCH Rows Used | 156
Merged Cockpit Rows | 181
Unmatched Tracker Rows | 66
Rows Needing Match Review | 80
Preserved Note Keys | 169
Critical Risks | 8
High Risks | 29
Open Pipeline | 40